## Structure_Type
| Items | Initial | Code | Payment_30_06_2020 | DPP_Item
0 | Construction of Irrigation Inlet | IRRI_C | 1 | 291.81 | Inlet
1 | Rehab Regulator Rehab Haor | REG_R_REHAB | 2 | 0 | Reg_Rehab_Rehab
2 | Regulator | REG_C | 3 | 6503.97 | Reg_CW_Box
3 | Box Drainage Outlet | DROU_C | 4 | 0 | Reg_CW_Box
4 | Causeway | CW_C | 5 | 0 | Reg_CW_Box
5 | Bridge | BRI_C | 6 | 0 | Reg_CW_Box
6 | Khal_River Reexcavation(New Haor) | REX_KH_RIV_NEW | 7 | 2546.54 | Khal_Riv_New
7 | Khal_River Reexcavation(Rehab Haor) | REX_KH_RIV_REHAB | 8 | 51.09 | Khal_Riv_Rehab
8 | Embankment Rehablitation | EMB_R | 9 | 0 | Full_Emb_Rehab
9 | Submersible Embankment Rehabilitation | SEMB_R | 10 | 0 | Sub_Emb_Rehab
10 | Submersible Embankment Construction | SEMB_C | 11 | 5833.04 | Sub_Emb_Const
11 | Rehab Regulator New Haor | REG_R_NEW | 12 | 0 | Reg_Rehab_New
12 | Thrashing Floor Construction | THF_CONS | 14 | 0 | Thr_Fl_Cost
13 | Construction of WMG | WMG_OFF | 15 | 0 | Wmg_Office
14 | M&E GATE Repair | GATE_REP | 16 | 0 | Gate_Repair

## Projection_Info
| Package Name | Component | Unit | Qnty | Cost | Present_Progress | Projected_progress | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code
0 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Submersible Embankment between km10.600 to 49.426 total 33.849km | km | 33.849 | 867.33 | 0.58 | 1 | SUNM/PW-01 | New | 11 | 0 | N-14 | SUNM
1 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Re-Excavation of Dariabaz Khal | km | 1.48 | 18.8287 | 0.84 | 1 | SUNM/PW-01 | New | 7 | 0 | N-14 | SUNM
2 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Re-Excavation of Juriganga Khal | km | 1.438 | 32.0288 | 0.84 | 1 | SUNM/PW-01 | New | 7 | 0 | N-14 | SUNM
3 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Re-Excavation of Purukania Khal | km | 1.56 | 41.0489 | 0.84 | 1 | SUNM/PW-01 | New | 7 | 0 | N-14 | SUNM
4 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Re-Excavation of Muktakhai River | Km | 3.2 | 176.4745 | 0.84 | 1 | SUNM/PW-01 | New | 7 | 0 | N-14 | SUNM
5 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-1 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
6 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-2 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
7 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-3 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
8 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-4 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
9 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-5 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
10 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-6 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
11 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-7 | Nos | 1 | 45.09 | 0.54 | 1 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
12 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Irrigation Inlet | Nos | 9 | 10.66 | 0 | 1 | SUNM/PW-01 | New | 1 | 0 | 0 | SUNM
13 | BWDB/Sunam/HFMLIP/PW-02 Dhakua Haor (Division-2) | Re-excavation of Piyan River from km 19.000 to km 55.575 total 36.575km | Km | 36.575 | 1193.75 | 0.8 | 1 | SUNM/PW-02 | New | 7 | 0 | N-14 | SUNM
14 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | 1 vent (1.50m X 1.80m)-1 | Nos | 1 | 183.3461 | 0.6 | 1 | SUNM/PW-03 | New | 3 | 0 | N-14 | SUNM
15 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | 2 vent (1.50m X 1.80m)-1 | Nos | 1 | 308.0018 | 0.6 | 1 | SUNM/PW-03 | New | 3 | 0 | N-14 | SUNM
16 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-1 | Nos | 1 | 182.286 | 0.27 | 0.67 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
17 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-2 | Nos | 1 | 182.286 | 0.27 | 0.67 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
18 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-3 | Nos | 1 | 182.286 | 0.27 | 0.67 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
19 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-4 | Nos | 1 | 182.286 | 0.27 | 0.67 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
20 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-5 | Nos | 1 | 182.286 | 0.27 | 0.67 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
21 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 6.0m wide-1 | Nos | 1 | 279.3507 | 0.27 | 0.67 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
22 | BWDB/Sunam/HFMLIP/PW-04 Dharmapasha Rui Beel (Division-1) | Construction of Submersible embankment-34.94km | Km | 34.94 | 1564.32 | 0.98 | 1 | SUNM/PW-04 | New | 11 | 0 | N-12 | SUNM
23 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Dahar 4vent (1.50m X 1.80m)-1 Regulator | Nos | 1 | 283.3851 | 0.5 | 1 | SUNM/PW-05 | New | 3 | 0 | N-12 | SUNM
24 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Deola 2 vent (1.50m X 1.80m)-1 Regulator | Nos | 1 | 267.8703 | 0.4 | 1 | SUNM/PW-05 | New | 3 | 0 | N-12 | SUNM
25 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Manani Causeway 6.0m wide-1 | Nos | 1 | 225.81 | 0 | 1 | SUNM/PW-05 | New | 5 | 0 | N-12 | SUNM
26 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Dahar Causeway 4.0m wide-1 | Nos | 1 | 301.6651 | 0.4 | 1 | SUNM/PW-05 | New | 5 | 0 | N-12 | SUNM
27 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Daharagang Causeway 4.0m wide-2 | Nos | 1 | 187.8663 | 0.8 | 1 | SUNM/PW-05 | New | 5 | 0 | N-12 | SUNM
28 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Chandrasona Causeway 4.0m wide-3 | Nos | 1 | 191.3901 | 0.8 | 1 | SUNM/PW-05 | New | 5 | 0 | N-12 | SUNM
29 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Khurma Khal | km | 7.18 | 36.0889 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
30 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Udani Khal | km | 3.828 | 54.377 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
31 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Deola Khal | km | 1.965 | 70.1082 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
32 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Shaitan Khal | km | 13.8 | 565.0549 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
33 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Banni Khal2 | km | 2.913 | 36.3507 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
34 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Rui Beel Khal | km | 3.414 | 62.7308 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
35 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Dahar Gang | km | 6.832 | 176.7629 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
36 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Gobra Khal | km | 2.893 | 45.6733 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
37 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Banni Khal1 | km | 2.622 | 39.8891 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
38 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Dagar Khal | km | 2.665 | 15.5116 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
39 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Rajpur Khal | km | 3.595 | 37.8562 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
40 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Kolma Khal | km | 2.204 | 17.6969 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
41 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Agunia khal | km | 7.611 | 157.1547 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
42 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Kakura Khal | km | 1.305 | 32.5728 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
43 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Dharam Beel Khal | km | 1.105 | 37.7084 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
44 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Bararia Khal | km | 2.11 | 14.6001 | 1 | 1 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
45 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Const. of Box Drainage Outlet-1 | Nos | 1 | 45.13 | 0 | 1 | SUNM/PW-06 | New | 4 | 0 | N-12 | SUNM
46 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Irrigation Inlet | Nos | 12 | 131.38 | 0 | 1 | SUNM/PW-06 | New | 1 | 0 | N-12 | SUNM

## Package_Name
| sl | Package_No | Payment_30_06_2020
0 | 1 | KISH/PW-01 | 51.09
1 | 2 | KISH/PW-02 | 347.71
2 | 3 | KISH/PW-03 | 625.93
3 | 4 | KISH/PW-04 | 714.69
4 | 5 | KISH/PW-05 | 575.15
5 | 6 | KISH/PW-06 | 837.25
6 | 7 | KISH/PW-07 | 565.07
7 | 8 | KISH/PW-08 | 0
8 | 9 | KISH/PW-09 | 712.33
9 | 10 | KISH/PW-10 | 409.68
10 | 11 | KISH/PW-11 | 522.86
11 | 12 | KISH/PW-12 | 705.59
12 | 13 | KISH/PW-13 | 647.2
13 | 14 | KISH/PW-14 | 806.89
14 | 15 | KISH/PW-15 | 333.94
15 | 16 | KISH/PW-16 | 721.62
16 | 17 | KISH/PW-17 | 1451.95
17 | 18 | KISH/PW-18 | 711.02
18 | 19 | KISH/PW-19 | 331.35
19 | 20 | KISH/PW-20 | 501.12
20 | 21 | KISH/PW-21 | 268.24
21 | 22 | KISH/PW-22 | 281.05
22 | 23 | KISH/PW-23 | 720.33
23 | 24 | KISH/PW-24 | 890.42
24 | 25 | KISH/PW-25 | 749.37
25 | 26 | KISH/PW-26 | 501.12
26 | 27 | KISH/PW-27 | 0
27 | 28 | KISH/PW-28 | 0
28 | 29 | KISH/PW-29 | 0
29 | 30 | KISH/PW-30 | 0
30 | 31 | KISH/PW-31 | 0
31 | 32 | KISH/PW-32 | 0
32 | 33 | KISH/PW-33 | 0
33 | 34 | KISH/PW-34 | 0
34 | 35 | KISH/PW-35 | 0
35 | 36 | KISH/PW-36 | 0
36 | 37 | KISH/PW-37 | 0
37 | 38 | KISH/PW-38 | 0
38 | 39 | NETR/PW-01 | 817.97
39 | 40 | NETR/PW-02 | 475.85
40 | 41 | NETR/PW-03 | 712.73
41 | 42 | NETR/PW-04 | 844.17
42 | 43 | NETR/PW-05 | 635.34
43 | 44 | NETR/PW-06 | 375.82
44 | 45 | NETR/PW-07 | 567.71
45 | 46 | NETR/PW-08 | 134.16
46 | 47 | SUNM/PW-01 | 913.55
47 | 48 | SUNM/PW-02 | 926.3
48 | 49 | SUNM/PW-03 | 511.73
49 | 50 | SUNM/PW-04 | 1521.41
50 | 51 | SUNM/PW-05 | 1061.82
51 | 52 | SUNM/PW-06 | 1268.067
52 | 53 | SUNM/PW-07 | 0

## Value_of_Work_Done
| Package | Structure Code | Component | Unit | Qnty | Cost | Present_Progress | Projected_progress | VDW_30_06_2020 | VDW_30_06_2021 | Work_Done_20_21 | Payment_30_06_2020
0 | SUNM/PW-01 | 11 | Submersible Embankment between km10.600 to 49.426 total 33.849km | km | 33.849 | 867.33 | 0.58 | 1 | 503.0514 | 867.33 | 364.2786 | 0
1 | SUNM/PW-01 | 7 | Re-Excavation of Dariabaz Khal | km | 1.48 | 18.8287 | 0.84 | 1 | 15.8161 | 18.8287 | 3.0126 | 0
2 | SUNM/PW-01 | 7 | Re-Excavation of Juriganga Khal | km | 1.438 | 32.0288 | 0.84 | 1 | 26.9042 | 32.0288 | 5.1246 | 0
3 | SUNM/PW-01 | 7 | Re-Excavation of Purukania Khal | km | 1.56 | 41.0489 | 0.84 | 1 | 34.4811 | 41.0489 | 6.5678 | 0
4 | SUNM/PW-01 | 7 | Re-Excavation of Muktakhai River | Km | 3.2 | 176.4745 | 0.84 | 1 | 148.2386 | 176.4745 | 28.2359 | 0
5 | SUNM/PW-01 | 4 | Box Drainage Outlet-1 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
6 | SUNM/PW-01 | 4 | Box Drainage Outlet-2 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
7 | SUNM/PW-01 | 4 | Box Drainage Outlet-3 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
8 | SUNM/PW-01 | 4 | Box Drainage Outlet-4 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
9 | SUNM/PW-01 | 4 | Box Drainage Outlet-5 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
10 | SUNM/PW-01 | 4 | Box Drainage Outlet-6 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
11 | SUNM/PW-01 | 4 | Box Drainage Outlet-7 | Nos | 1 | 45.09 | 0.54 | 1 | 24.3486 | 45.09 | 20.7414 | 0
12 | SUNM/PW-01 | 1 | Irrigation Inlet | Nos | 9 | 10.66 | 0 | 1 | 0 | 10.66 | 10.66 | 0
13 | SUNM/PW-02 | 7 | Re-excavation of Piyan River from km 19.000 to km 55.575 total 36.575km | Km | 36.575 | 1193.75 | 0.8 | 1 | 955 | 1193.75 | 238.75 | 0
14 | SUNM/PW-03 | 3 | 1 vent (1.50m X 1.80m)-1 | Nos | 1 | 183.3461 | 0.6 | 1 | 110.0077 | 183.3461 | 73.3384 | 0
15 | SUNM/PW-03 | 3 | 2 vent (1.50m X 1.80m)-1 | Nos | 1 | 308.0018 | 0.6 | 1 | 184.8011 | 308.0018 | 123.2007 | 0
16 | SUNM/PW-03 | 5 | Causeway 4.0m wide-1 | Nos | 1 | 182.286 | 0.27 | 0.67 | 49.2172 | 122.1316 | 72.9144 | 0
17 | SUNM/PW-03 | 5 | Causeway 4.0m wide-2 | Nos | 1 | 182.286 | 0.27 | 0.67 | 49.2172 | 122.1316 | 72.9144 | 0
18 | SUNM/PW-03 | 5 | Causeway 4.0m wide-3 | Nos | 1 | 182.286 | 0.27 | 0.67 | 49.2172 | 122.1316 | 72.9144 | 0
19 | SUNM/PW-03 | 5 | Causeway 4.0m wide-4 | Nos | 1 | 182.286 | 0.27 | 0.67 | 49.2172 | 122.1316 | 72.9144 | 0
20 | SUNM/PW-03 | 5 | Causeway 4.0m wide-5 | Nos | 1 | 182.286 | 0.27 | 0.67 | 49.2172 | 122.1316 | 72.9144 | 0
21 | SUNM/PW-03 | 5 | Causeway 6.0m wide-1 | Nos | 1 | 279.3507 | 0.27 | 0.67 | 75.4247 | 187.165 | 111.7403 | 0
22 | SUNM/PW-04 | 11 | Construction of Submersible embankment-34.94km | Km | 34.94 | 1564.32 | 0.98 | 1 | 1533.0336 | 1564.32 | 31.2864 | 0
23 | SUNM/PW-05 | 3 | Dahar 4vent (1.50m X 1.80m)-1 Regulator | Nos | 1 | 283.3851 | 0.5 | 1 | 141.6926 | 283.3851 | 141.6926 | 0
24 | SUNM/PW-05 | 3 | Deola 2 vent (1.50m X 1.80m)-1 Regulator | Nos | 1 | 267.8703 | 0.4 | 1 | 107.1481 | 267.8703 | 160.7222 | 0
25 | SUNM/PW-05 | 5 | Manani Causeway 6.0m wide-1 | Nos | 1 | 225.81 | 0 | 1 | 0 | 225.81 | 225.81 | 0
26 | SUNM/PW-05 | 5 | Dahar Causeway 4.0m wide-1 | Nos | 1 | 301.6651 | 0.4 | 1 | 120.666 | 301.6651 | 180.9991 | 0
27 | SUNM/PW-05 | 5 | Daharagang Causeway 4.0m wide-2 | Nos | 1 | 187.8663 | 0.8 | 1 | 150.293 | 187.8663 | 37.5733 | 0
28 | SUNM/PW-05 | 5 | Chandrasona Causeway 4.0m wide-3 | Nos | 1 | 191.3901 | 0.8 | 1 | 153.1121 | 191.3901 | 38.278 | 0
29 | SUNM/PW-06 | 7 | Khurma Khal | km | 7.18 | 36.0889 | 1 | 1 | 36.0889 | 36.0889 | 0 | 0
30 | SUNM/PW-06 | 7 | Udani Khal | km | 3.828 | 54.377 | 1 | 1 | 54.377 | 54.377 | 0 | 0
31 | SUNM/PW-06 | 7 | Deola Khal | km | 1.965 | 70.1082 | 1 | 1 | 70.1082 | 70.1082 | 0 | 0
32 | SUNM/PW-06 | 7 | Shaitan Khal | km | 13.8 | 565.0549 | 1 | 1 | 565.0549 | 565.0549 | 0 | 0
33 | SUNM/PW-06 | 7 | Banni Khal2 | km | 2.913 | 36.3507 | 1 | 1 | 36.3507 | 36.3507 | 0 | 0
34 | SUNM/PW-06 | 7 | Rui Beel Khal | km | 3.414 | 62.7308 | 1 | 1 | 62.7308 | 62.7308 | 0 | 0
35 | SUNM/PW-06 | 7 | Dahar Gang | km | 6.832 | 176.7629 | 1 | 1 | 176.7629 | 176.7629 | 0 | 0
36 | SUNM/PW-06 | 7 | Gobra Khal | km | 2.893 | 45.6733 | 1 | 1 | 45.6733 | 45.6733 | 0 | 0
37 | SUNM/PW-06 | 7 | Banni Khal1 | km | 2.622 | 39.8891 | 1 | 1 | 39.8891 | 39.8891 | 0 | 0
38 | SUNM/PW-06 | 7 | Dagar Khal | km | 2.665 | 15.5116 | 1 | 1 | 15.5116 | 15.5116 | 0 | 0
39 | SUNM/PW-06 | 7 | Rajpur Khal | km | 3.595 | 37.8562 | 1 | 1 | 37.8562 | 37.8562 | 0 | 0
40 | SUNM/PW-06 | 7 | Kolma Khal | km | 2.204 | 17.6969 | 1 | 1 | 17.6969 | 17.6969 | 0 | 0
41 | SUNM/PW-06 | 7 | Agunia khal | km | 7.611 | 157.1547 | 1 | 1 | 157.1547 | 157.1547 | 0 | 0
42 | SUNM/PW-06 | 7 | Kakura Khal | km | 1.305 | 32.5728 | 1 | 1 | 32.5728 | 32.5728 | 0 | 0
43 | SUNM/PW-06 | 7 | Dharam Beel Khal | km | 1.105 | 37.7084 | 1 | 1 | 37.7084 | 37.7084 | 0 | 0
44 | SUNM/PW-06 | 7 | Bararia Khal | km | 2.11 | 14.6001 | 1 | 1 | 14.6001 | 14.6001 | 0 | 0
45 | SUNM/PW-06 | 4 | Const. of Box Drainage Outlet-1 | Nos | 1 | 45.13 | 0 | 1 | 0 | 45.13 | 45.13 | 0
46 | SUNM/PW-06 | 1 | Irrigation Inlet | Nos | 12 | 131.38 | 0 | 1 | 0 | 131.38 | 131.38 | 0

## Package_wise_payment
| Package_No | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | KISH/PW-01 | 0 | 0 | 51.09 | -51.09
1 | KISH/PW-02 | 0 | 0 | 347.71 | -347.71
2 | KISH/PW-03 | 0 | 0 | 625.93 | -625.93
3 | KISH/PW-04 | 0 | 0 | 714.69 | -714.69
4 | KISH/PW-05 | 0 | 0 | 575.15 | -575.15
5 | KISH/PW-06 | 0 | 0 | 837.25 | -837.25
6 | KISH/PW-07 | 0 | 0 | 565.07 | -565.07
7 | KISH/PW-08 | 0 | 0 | 0 | 0
8 | KISH/PW-09 | 0 | 0 | 712.33 | -712.33
9 | KISH/PW-10 | 0 | 0 | 409.68 | -409.68
10 | KISH/PW-11 | 0 | 0 | 522.86 | -522.86
11 | KISH/PW-12 | 0 | 0 | 705.59 | -705.59
12 | KISH/PW-13 | 0 | 0 | 647.2 | -647.2
13 | KISH/PW-14 | 0 | 0 | 806.89 | -806.89
14 | KISH/PW-15 | 0 | 0 | 333.94 | -333.94
15 | KISH/PW-16 | 0 | 0 | 721.62 | -721.62
16 | KISH/PW-17 | 0 | 0 | 1451.95 | -1451.95
17 | KISH/PW-18 | 0 | 0 | 711.02 | -711.02
18 | KISH/PW-19 | 0 | 0 | 331.35 | -331.35
19 | KISH/PW-20 | 0 | 0 | 501.12 | -501.12
20 | KISH/PW-21 | 0 | 0 | 268.24 | -268.24
21 | KISH/PW-22 | 0 | 0 | 281.05 | -281.05
22 | KISH/PW-23 | 0 | 0 | 720.33 | -720.33
23 | KISH/PW-24 | 0 | 0 | 890.42 | -890.42
24 | KISH/PW-25 | 0 | 0 | 749.37 | -749.37
25 | KISH/PW-26 | 0 | 0 | 501.12 | -501.12
26 | KISH/PW-27 | 0 | 0 | 0 | 0
27 | KISH/PW-28 | 0 | 0 | 0 | 0
28 | KISH/PW-29 | 0 | 0 | 0 | 0
29 | KISH/PW-30 | 0 | 0 | 0 | 0
30 | KISH/PW-31 | 0 | 0 | 0 | 0
31 | KISH/PW-32 | 0 | 0 | 0 | 0
32 | KISH/PW-33 | 0 | 0 | 0 | 0
33 | KISH/PW-34 | 0 | 0 | 0 | 0
34 | KISH/PW-35 | 0 | 0 | 0 | 0
35 | KISH/PW-36 | 0 | 0 | 0 | 0
36 | KISH/PW-37 | 0 | 0 | 0 | 0
37 | KISH/PW-38 | 0 | 0 | 0 | 0
38 | NETR/PW-01 | 0 | 0 | 817.97 | -817.97
39 | NETR/PW-02 | 0 | 0 | 475.85 | -475.85
40 | NETR/PW-03 | 0 | 0 | 712.73 | -712.73
41 | NETR/PW-04 | 0 | 0 | 844.17 | -844.17
42 | NETR/PW-05 | 0 | 0 | 635.34 | -635.34
43 | NETR/PW-06 | 0 | 0 | 375.82 | -375.82
44 | NETR/PW-07 | 0 | 0 | 567.71 | -567.71
45 | NETR/PW-08 | 0 | 0 | 134.16 | -134.16
46 | SUNM/PW-01 | 898.9316 | 1462.001 | 913.55 | 548.451
47 | SUNM/PW-02 | 955 | 1193.75 | 926.3 | 267.45
48 | SUNM/PW-03 | 616.3195 | 1289.171 | 511.73 | 777.441
49 | SUNM/PW-04 | 1533.0336 | 1564.32 | 1521.41 | 42.91
50 | SUNM/PW-05 | 672.9118 | 1457.9869 | 1061.82 | 396.1669
51 | SUNM/PW-06 | 1400.1366 | 1576.6466 | 1268.067 | 308.5796
52 | SUNM/PW-07 | 0 | 0 | 0 | 0

## Structure_Wise_payment
| Items | Code | DPP_Item | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | Construction of Irrigation Inlet | 1 | Inlet | 0 | 142.04 | 291.81 | -149.77
1 | Rehab Regulator Rehab Haor | 2 | Reg_Rehab_Rehab | 0 | 0 | 0 | 0
2 | Regulator | 3 | Reg_CW_Box | 543.6495 | 1042.6034 | 6503.97 | -5461.3666
3 | Box Drainage Outlet | 4 | Reg_CW_Box | 170.4402 | 360.76 | 0 | 360.76
4 | Causeway | 5 | Reg_CW_Box | 745.5819 | 1704.5545 | 0 | 1704.5545
5 | Bridge | 6 | Reg_CW_Box | 0 | 0 | 0 | 0
6 | Khal_River Reexcavation(New Haor) | 7 | Khal_Riv_New | 2580.5766 | 2862.2676 | 2546.54 | 315.7276
7 | Khal_River Reexcavation(Rehab Haor) | 8 | Khal_Riv_Rehab | 0 | 0 | 51.09 | -51.09
8 | Embankment Rehablitation | 9 | Full_Emb_Rehab | 0 | 0 | 0 | 0
9 | Submersible Embankment Rehabilitation | 10 | Sub_Emb_Rehab | 0 | 0 | 0 | 0
10 | Submersible Embankment Construction | 11 | Sub_Emb_Const | 2036.085 | 2431.65 | 5833.04 | -3401.39
11 | Rehab Regulator New Haor | 12 | Reg_Rehab_New | 0 | 0 | 0 | 0
12 | Thrashing Floor Construction | 14 | Thr_Fl_Cost | 0 | 0 | 0 | 0
13 | Construction of WMG | 15 | Wmg_Office | 0 | 0 | 0 | 0
14 | M&E GATE Repair | 16 | Gate_Repair | 0 | 0 | 0 | 0

## DPP_Wise_payment
| DPP_Item | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | Inlet | 0 | 142.04 | 0 | 142.04
1 | Reg_Rehab_Rehab | 0 | 0 | 0 | 0
2 | Reg_CW_Box | 1459.67 | 3107.92 | 1769.37 | 1338.55
3 | Khal_Riv_New | 2580.58 | 2862.27 | 2317 | 545.27
4 | Khal_Riv_Rehab | 0 | 0 | 0 | 0
5 | Full_Emb_Rehab | 0 | 0 | 0 | 0
6 | Sub_Emb_Rehab | 0 | 0 | 0 | 0
7 | Sub_Emb_Const | 2036.08 | 2431.65 | 2117.11 | 314.54
8 | Reg_Rehab_New | 0 | 0 | 0 | 0
9 | Thr_Fl_Cost | 0 | 0 | 0 | 0
10 | Wmg_Office | 0 | 0 | 0 | 0
11 | Gate_Repair | 0 | 0 | 0 | 0
|  | 6076.33 | 8543.88 | 6203.48 | 2340.4