## Resource_List
Code | Name | Unit
101 | Mixture Machine | Nos
102 | Excavator | Nos
103 | Compaction Ruller | Nos
104 | Form Work | Nos
201 | Cement | Bag
202 | Sand 1.5 FM | cum
203 | Stone Chips | cum
204 | Geotextile Filter | sqm
205 | Filter Sand | cum
206 | Peagravel | cum
207 | CC Block | Nos
301 | Labor | m-day
401 | Labor payment | BDT Lac

## Allocation
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05
CC Block Manufacture(40X40X40) | 8 | 25 | 16 | 3 | 0 | 0 | 2500 | 350 | 36 | 80 | 0 | 0 | 0 | 0 | 120 | 0.3
CC Block Manufacture(40X40X20) | 8 | 25 | 16 | 2 | 0 | 0 | 500 | 90 | 8 | 18 | 0 | 0 | 0 | 0 | 30 | 0.075
Embankment Construction | 8 | 41 | 34 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05
Placing Sand Filter | 41 | 50 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 30 | 0.075
Placing Geotextile Filter | 51 | 60 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 30 | 0.075
Placing Pea Gravel Filter | 61 | 70 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 30 | 0.075
Placing CC Block | 71 | 80 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 150 | 0.375
Ancilary Work for Site Completion | 81 | 87 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05

## Main
Name | Start | Finish | Allocation_Sheet_Name
Type_A_211M_724_To_935_R | 1 | 87 | Type_A_211M_724_To_935_R
Type_A_50M_965_TO_1015_R | 1 | 67 | Type_A_50M_965_TO_1015_R
Type_A_40M_4500_TO_4570_R | 1 | 67 | Type_A_40M_4500_TO_4570_R
Type_A_40M_35020_TO_35100_R | 1 | 67 | Type_A_40M_35020_TO_35100_R
FF_30M_at_KM_1_R | 1 | 72 | FF_30M_at_KM_1
FF_15M_at_KM_35500_R | 1 | 72 | FF_15M_at_KM_35500
FF_15M_at_KM_4520_R | 1 | 72 | FF_15M_at_KM_4520

## Summary_Project
Name | Start | Finish | Allocation_Sheet_Name
Slope_Protection_Suanm_Ganj_SUNM_07 | 1 | 87 | Type_A_211M_724_To_935_R

## Type_A_211M_724_To_935_R
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
CC Block Manufacture(40X40X40) | 8 | 25 | 16 | 1 | 0 | 0 | 320 | 105 | 9 | 20 | 0 | 0 | 0 | 0 | 30 | 0.06
CC Block Manufacture(40X40X20) | 8 | 25 | 16 | 3 | 0 | 0 | 2100 | 350 | 30 | 66 | 0 | 0 | 0 | 0 | 90 | 0.18
Embankment Construction | 8 | 41 | 34 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
Placing Sand Filter | 41 | 50 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 100 | 0.2
Placing Geotextile Filter | 51 | 60 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610 | 0 | 0 | 0 | 100 | 0.2
Placing Pea Gravel Filter | 61 | 70 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 100 | 0.2
Placing CC Block | 71 | 80 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 150 | 0.375
Ancilary Work for Site Completion | 81 | 87 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05

## tempalate
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
CC Block Manufacture(40X40X40) | 8 | 25 | 16 | 1 | 0 | 0 | 320 | 105 | 9 | 20 | 0 | 0 | 0 | 0 | 30 | 0.06
CC Block Manufacture(40X40X20) | 8 | 25 | 16 | 3 | 0 | 0 | 2100 | 350 | 30 | 66 | 0 | 0 | 0 | 0 | 90 | 0.18
Embankment Construction | 8 | 41 | 34 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
Placing Sand Filter | 41 | 50 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 100 | 0.2
Placing Geotextile Filter | 51 | 60 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610 | 0 | 0 | 0 | 100 | 0.2
Placing Pea Gravel Filter | 61 | 70 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 100 | 0.2
Placing CC Block | 71 | 80 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 150 | 0.375
Ancilary Work for Site Completion | 81 | 87 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05

## Type_A_50M_965_TO_1015_R
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
CC Block Manufacture(30X30X30) | 8 | 25 | 16 | 0.25 | 0 | 0 | 75 | 350 | 36 | 80 | 0 | 0 | 0 | 0 | 9 | 0.02
CC Block Manufacture(40X40X20) | 8 | 25 | 16 | 0.75 | 0 | 0 | 500 | 90 | 8 | 18 | 0 | 0 | 0 | 0 | 21 | 0.04
Embankment Construction | 8 | 15 | 7 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
Placing Sand Filter | 41 | 45 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 30 | 0.06
Placing Geotextile Filter | 45 | 50 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 30 | 0.06
Placing Pea Gravel Filter | 50 | 55 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 30 | 0.06
Placing CC Block | 55 | 60 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 75 | 0.15
Ancilary Work for Site Completion | 60 | 67 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04

## Type_A_40M_4500_TO_4570_R
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
CC Block Manufacture(30X30X30) | 8 | 25 | 16 | 0.25 | 0 | 0 | 60 | 20 | 2 | 4 | 0 | 0 | 0 | 0 | 9 | 0.02
CC Block Manufacture(40X40X20) | 8 | 25 | 16 | 0.75 | 0 | 0 | 260 | 45 | 4 | 8 | 0 | 0 | 0 | 0 | 21 | 0.04
Embankment Construction | 8 | 15 | 7 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
Placing Sand Filter | 41 | 45 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 30 | 0.06
Placing Geotextile Filter | 45 | 50 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 30 | 0.06
Placing Pea Gravel Filter | 50 | 55 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 30 | 0.06
Placing CC Block | 55 | 60 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 50 | 0.1
Ancilary Work for Site Completion | 60 | 67 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04

## Type_A_40M_35020_TO_35100_R
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
CC Block Manufacture(30X30X30) | 8 | 25 | 16 | 0.25 | 0 | 0 | 60 | 20 | 2 | 4 | 0 | 0 | 0 | 0 | 9 | 0.02
CC Block Manufacture(40X40X20) | 8 | 25 | 16 | 0.75 | 0 | 0 | 260 | 45 | 4 | 8 | 0 | 0 | 0 | 0 | 21 | 0.04
Embankment Construction | 8 | 15 | 7 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
Placing Sand Filter | 41 | 45 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 30 | 0.06
Placing Geotextile Filter | 45 | 50 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 30 | 0.06
Placing Pea Gravel Filter | 50 | 55 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 30 | 0.06
Placing CC Block | 55 | 60 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 50 | 0.1
Ancilary Work for Site Completion | 60 | 67 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04

## TYPE_A_40M
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05
CC Block Manufacture(30X30X30)-39933 Nos | 8 | 25 | 17 | 3 | 0 | 0 | 2500 | 350 | 36 | 80 | 0 | 0 | 0 | 0 | 90 | 0.3
CC Block Manufacture(40X40X20)-8701 Nos | 8 | 25 | 17 | 1 | 0 | 0 | 600 | 90 | 8 | 18 | 0 | 0 | 0 | 0 | 30 | 0.075
Embankment Construction-9880 cum | 8 | 39 | 31 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05
Placing Sand Filter-601 cum | 38 | 49 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 30 | 0.075
Placing Geotextile Filter-6617 sqm | 48 | 59 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 30 | 0.075
Placing Pea Gravel Filter-620 cum | 58 | 69 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 30 | 0.075
Placing CC Block-1492 cum | 68 | 79 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 150 | 0.375
Ancilary Work for Site Completion-1 LS | 79 | 86 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05

## FF_15M_at_KM_35500
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
CC Block Manufacture(50X50X50)-1355 Nos | 8 | 25 | 17 | 0.63 | 0 | 0 | 85 | 55 | 11 | 16 | 0 | 0 | 0 | 0 | 18 | 0.036
CC Block Manufacture(50X50X30)-4795 Nos | 8 | 25 | 17 | 0.37 | 0 | 0 | 300 | 116 | 22 | 32 | 0 | 0 | 0 | 0 | 12 | 0.024
CC Block Manufacture(40X40X40)-1782 Nos | 8 | 25 | 17 | 0.5 | 0 | 0 | 120 | 38 | 8 | 11 | 0 | 0 | 0 | 0 | 15 | 0.03
CC Block Manufacture(30X30X30)-3917 Nos | 8 | 25 | 17 | 0.5 | 0 | 0 | 250 | 35 | 7 | 10 | 0 | 0 | 0 | 0 | 15 | 0.03
Ring Bundh construction (2052 cum)-1482 cum | 8 | 16 | 8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0.12
Excavation-1192 cum | 16 | 21 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.06
Embankment Construction-1082 cum | 16 | 21 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.06
Placing Sand Filter-268 Cum | 25 | 32 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 60 | 0.12
Placing Geotextile Filter-1838 sqm | 33 | 40 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263 | 0 | 0 | 0 | 60 | 0.12
Placing Pea Gravel Filter-357 cum | 40 | 19 | -21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 60 | 0.12
Placing CC Block-630 cum | 57 | 64 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 60 | 0.12
Ring Bundh Removal | 64 | 72 | 8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0.12

## FF_15M_at_KM_4520
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
CC Block Manufacture(50X50X50)-1355 Nos | 8 | 25 | 17 | 0.63 | 0 | 0 | 85 | 55 | 11 | 16 | 0 | 0 | 0 | 0 | 18 | 0.036
CC Block Manufacture(50X50X30)-4795 Nos | 8 | 25 | 17 | 0.37 | 0 | 0 | 300 | 116 | 22 | 32 | 0 | 0 | 0 | 0 | 12 | 0.024
CC Block Manufacture(40X40X40)-1782 Nos | 8 | 25 | 17 | 0.5 | 0 | 0 | 120 | 38 | 8 | 11 | 0 | 0 | 0 | 0 | 15 | 0.03
CC Block Manufacture(30X30X30)-3917 Nos | 8 | 25 | 17 | 0.5 | 0 | 0 | 250 | 35 | 7 | 10 | 0 | 0 | 0 | 0 | 15 | 0.03
Ring Bundh construction (2052 cum)-1482 cum | 8 | 16 | 8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0.12
Excavation-1192 cum | 16 | 21 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.06
Embankment Construction-1082 cum | 16 | 21 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.06
Placing Sand Filter-268 Cum | 25 | 32 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 60 | 0.12
Placing Geotextile Filter-1838 sqm | 33 | 40 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263 | 0 | 0 | 0 | 60 | 0.12
Placing Pea Gravel Filter-357 cum | 40 | 19 | -21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 60 | 0.12
Placing CC Block-630 cum | 57 | 64 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 60 | 0.12
Ring Bundh Removal | 64 | 72 | 8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0.12

## FF_30M_at_KM_1
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
CC Block Manufacture(50X50X50)-2670 Nos | 8 | 25 | 17 | 1.25 | 0 | 0 | 168 | 108 | 10 | 20 | 0 | 0 | 0 | 0 | 35 | 0.07
CC Block Manufacture(50X50X30)-4795 Nos | 8 | 25 | 17 | 1.35 | 0 | 0 | 300 | 116 | 11 | 22 | 0 | 0 | 0 | 0 | 40 | 0.08
CC Block Manufacture(40X40X40)-3653 Nos | 8 | 25 | 17 | 0.85 | 0 | 0 | 230 | 76 | 7 | 14 | 0 | 0 | 0 | 0 | 25 | 0.05
CC Block Manufacture(40X40X20)-2555 Nos | 8 | 25 | 17 | 0.55 | 0 | 0 | 160 | 27 | 3 | 5 | 0 | 0 | 0 | 0 | 15 | 0.03
Ring Bundh construction (2052 cum)-1482 cum | 8 | 16 | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.06
Excavation-2525 cum | 16 | 21 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0.12
Embankment Construction-1771 cum | 16 | 21 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.06
Placing Sand Filter-361 Cum | 25 | 32 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 70 | 0.14
Placing Geotextile Filter-2547 sqm | 33 | 40 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363 | 0 | 0 | 0 | 70 | 0.14
Placing Pea Gravel Filter-481 cum | 40 | 19 | -21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 0 | 70 | 0.14
Placing CC Block-630 cum/13673 Nos | 57 | 64 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 70 | 0.14
Ring Bundh Removal | 64 | 72 | 8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0.12

## FF_30M_at_KM_1_Backup
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04
CC Block Manufacture(50X50X50)-1355 Nos | 8 | 25 | 17 | 0.63 | 0 | 0 | 85 | 55 | 11 | 16 | 0 | 0 | 0 | 0 | 18 | 0.036
CC Block Manufacture(50X50X30)-4795 Nos | 8 | 25 | 17 | 0.37 | 0 | 0 | 300 | 116 | 22 | 32 | 0 | 0 | 0 | 0 | 12 | 0.024
CC Block Manufacture(40X40X40)-1782 Nos | 8 | 25 | 17 | 0.5 | 0 | 0 | 120 | 38 | 8 | 11 | 0 | 0 | 0 | 0 | 15 | 0.03
CC Block Manufacture(30X30X30)-3917 Nos | 8 | 25 | 17 | 0.5 | 0 | 0 | 250 | 35 | 7 | 10 | 0 | 0 | 0 | 0 | 15 | 0.03
Ring Bundh construction (2052 cum)-1482 cum | 8 | 16 | 8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0.12
Excavation-1192 cum | 16 | 21 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.06
Embankment Construction-1082 cum | 16 | 21 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.06
Placing Sand Filter-268 Cum | 25 | 32 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 60 | 0.12
Placing Geotextile Filter-1838 sqm | 33 | 40 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263 | 0 | 0 | 0 | 60 | 0.12
Placing Pea Gravel Filter-357 cum | 40 | 19 | -21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 60 | 0.12
Placing CC Block-630 cum | 57 | 64 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 60 | 0.12
Ring Bundh Removal | 64 | 72 | 8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0.12
|  | 1355 | 84.6875 | 101: 10.625; 102: 0.62963
|  | 4795 | 299.6875 | 101: 6.375; 102: 0.37778; 202: 15.0057; 203: 31.7767; 204: 10.3945; 205: 9.533
|  | 1782 | 111.375 | 101: 5.44; 102: 0.32237
|  | 3917 | 244.8125 | 101: 2.295; 102: 0.136
11849
|  |  | 262.5714 | 102: 38.2857; 103: 51

## FF_30M_at_KM_1_Backup (2)
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.04 | 4000 | 0.04
CC Block Manufacture(50X50X50)-2670 Nos | 8 | 25 | 17 | 1.25 | 0 | 0 | 168 | 108 | 10 | 20 | 0 | 0 | 0 | 0 | 35 | 0.07 | 7000 | 0.07
CC Block Manufacture(50X50X30)-4795 Nos | 8 | 25 | 17 | 1.35 | 0 | 0 | 300 | 116 | 11 | 22 | 0 | 0 | 0 | 0 | 40 | 0.08 | 8000 | 0.08
CC Block Manufacture(40X40X40)-3653 Nos | 8 | 25 | 17 | 0.85 | 0 | 0 | 230 | 76 | 7 | 14 | 0 | 0 | 0 | 0 | 25 | 0.05 | 5000 | 0.05
CC Block Manufacture(40X40X20)-2555 Nos | 8 | 25 | 17 | 0.55 | 0 | 0 | 160 | 27 | 3 | 5 | 0 | 0 | 0 | 0 | 15 | 0.03 | 3000 | 0.03
Ring Bundh construction (2052 cum)-1482 cum | 8 | 16 | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.06 | 6000 | 0.06
Excavation-2525 cum | 16 | 21 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0.12 | 12000 | 0.12
Embankment Construction-1771 cum | 16 | 21 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0.06 | 6000 | 0.06
Placing Sand Filter-361 Cum | 25 | 32 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 70 | 0.14 | 14000 | 0.14
Placing Geotextile Filter-2547 sqm | 33 | 40 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363 | 0 | 0 | 0 | 70 | 0.14 | 14000 | 0.14
Placing Pea Gravel Filter-481 cum | 40 | 19 | -21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 0 | 70 | 0.14 | 14000 | 0.14
Placing CC Block-630 cum/13673 Nos | 57 | 64 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 70 | 0.14 | 14000 | 0.14
Ring Bundh Removal | 64 | 72 | 8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0.12 | 12000 | 0.12
|  | 2670 | 166.875 | 101: 20.8594; 102: 1.2361; 103: 1.25
|  | 4795 | 299.6875 | 22.4766 | 1.3319 | 1.35 |  | cement | 107.0132 | 115.3435 | 75.1322 | 26.2471
|  | 3653 | 228.3125 | 14.612 | 0.8659 | 0.85 |  | sand | 9.2893 | 10.0125 | 6.5219 | 2.2784
|  | 2555 | 159.6875 | 7.665 | 0.45422 | 0.55 |  | stone | 20.3766 | 21.9628 | 14.3061 | 4.9978
13673
|  |  | 262.5714 | 102: 38.2857; 103: 51; 202: 51.5714
363.8571
[9 empty] | 68.7143 | 1953.2857