## WBS3
TaskNo | Name | Duration | Predecessor | order
0 | Contract | 0 | 4,5
1 | Mobilization and Site Preparation | 7 | 3,4 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 5 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 2 | 6
4 | Embankment Construction | 34 | -1 | 2
5 | Placing Sand Filter | 10 | -1 | 3

## WBS
TaskNo | Name | Duration | Predecessor | order
1 | Mobilization and Site Preparation | 7 | -1 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 1 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 1 | 6
4 | Embankment Construction | 34 | 1 | 2
5 | Placing Sand Filter | 10 | 4 | 3
6 | Placing Geotextile Filter | 10 | 5 | 4
7 | Placing Pea Gravel Filter | 10 | 6 | 5
8 | Placing CC Block | 10 | 2,3,7 | 8
9 | Ancilary Work for Site Completion | 7 | 8 | 9

## Main
Name | Start | Finish | Allocation_Sheet_Name
Type_A_211M_724_To_935_S | 1 | 87 | Type_A_211M_724_To_935_S
Type_A_50M_965_TO_1015_S | 1 | 87 | Type_A_50M_965_TO_1015_S

## Type_A_211M_724_To_935_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100
2 | CC Block Manufacture(30X30X30) | 16 | 1 | Nos | 33338
3 | CC Block Manufacture(40X40X20) | 16 | 1 | Nos | 5012
4 | Curing CC Block | 21 | 2,3 | Percent | 100
5 | Embankment Construction | 34 | 1 | Cum | 6974
6 | Placing Sand Filter | 10 | 5 | Cum | 560
7 | Placing Geotextile Filter | 10 | 6 | sqm | 6098
8 | Placing Pea Gravel Filter | 10 | 7 | Cum | 560
9 | Placing CC Block | 10 | 3,8 | Nos | 38350
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100

## Type_A_50M_965_TO_1015_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100
2 | CC Block Manufacture(30X30X30) | 5 | 1 | Nos | 1188
3 | CC Block Manufacture(40X40X20) | 5 | 1 | Nos | 7900
4 | Curing | 21 | 2,3 | Percent | 100
5 | Embankment Construction | 34 | 1 | Cum | 1653
6 | Placing Sand Filter | 10 | 5 | Cum | 133
7 | Placing Geotextile Filter | 10 | 6 | Cum | 1445
8 | Placing Pea Gravel Filter | 10 | 7 | Cum | 133
9 | Placing CC Block | 10 | 3,8 | Nos | 328
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100

## Type_A_40M_4500_TO_4570_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100
2 | CC Block Manufacture(30X30X30) | 16 | 1 | Nos | 950
3 | CC Block Manufacture(40X40X20) | 16 | 1 | Nos | 4151
4 | Embankment Construction | 34 | 1 | Cum | 330
5 | Placing Sand Filter | 10 | 4 | Cum | 68
6 | Placing Geotextile Filter | 10 | 5 | Cum | 770
7 | Placing Pea Gravel Filter | 10 | 6 | Cum | 68
8 | Placing CC Block | 10 | 2,3,7 | Nos | 193
9 | Ancilary Work for Site Completion | 7 | 8 | Percent | 100

## Type_A_40M_35020_TO_35100_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100
2 | CC Block Manufacture(30X30X30) | 16 | 1 | Nos | 950
3 | CC Block Manufacture(40X40X20) | 16 | 1 | Nos | 4151
4 | Embankment Construction | 34 | 1 | Cum | 330
5 | Placing Sand Filter | 10 | 4 | Cum | 68
6 | Placing Geotextile Filter | 10 | 5 | Cum | 770
7 | Placing Pea Gravel Filter | 10 | 6 | Cum | 68
8 | Placing CC Block | 10 | 2,3,7 | Nos | 193
9 | Ancilary Work for Site Completion | 7 | 8 | Percent | 100