## Revised
Package Name | Component | Unit | Qnty | Cost | Remarks | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code
BWDB/Brah/HFMLIP/PW-01 | Regulator Rehablitation | nos | 2 | 87.5 |  | BRAH/PW-01 | New | 16 |  | R-14 | BRAH
BWDB/Brah/HFMLIP/PW-01 | Regulator Rehablitation | nos | 2 | 87.5 |  | BRAH/PW-01 | New | 16 |  | R-15 | BRAH
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Rehablitation of Submersible Embankment | Km | 0 | 0 |  | HOBI/PW-01 |  | 1 | 0 | R-8 | HOBI
BWDB/Hobi/HFMLIP/PW-01 Bashira River |  | nos. | 1 | 27.05 | Need rehabilitation of existing 3-vent regulator instead of reinstallation of 2-vent regulator. | HOBI/PW-01 | Rehab | 2 |  | R-8 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Construction of Causeway for Aralia (4&6m). | nos. | 1 | 300 | Need 6.0 m causeway instead of 4.0 m causeway. | HOBI/PW-01 | Rehab | 2 |  | R-8 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of Irrigation Inlet | Km | 19.695 | 857.52 |  | HOBI/PW-01 | Rehab | 8 | 664867.22 | R-8 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of 4.0m wide Causeway | Km | 16.76 | 385.43 | 2.40 Km length will be increased. | HOBI/PW-01 | Rehab | 10 | 127061.11 | R-8 | HOBI
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Re-excavation of Khal/River (Rehab. Khal 2.295 km & River 17.40 km) | nos. | 2 | 458.88 | 1 no. additional 4 m width Causeway will be needed. | HOBI/PW-02 | Rehab | 2 |  | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Replacement of Reg. Gates & other related works | nos. | 0 | 0 |  | HOBI/PW-02 | Rehab | 4 |  | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | 4m Causeway | Km | 3.312 | 53.87 |  | HOBI/PW-02 | Rehab | 8 | 124772.75 | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of Box Drainage Outlet | Km | 25.44 | 800.11 | Length of embkt. will be increased by 1.50 m. | HOBI/PW-02 | Rehab | 10 | 408978.43 | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of 6.0m wide Causeway | km | 5.7 | 179.27 | Length of embkt. will be increased by 1.50 m. | HOBI/PW-02 | Rehab | 10 |  | R-8 | HOBI
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Regulator Gate repair | Nos | 4 | 10.37 |  | HOBI/PW-02 |  | 16 |  | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-hab of Regulator | Nos | 9 | 23.32 |  | HOBI/PW-02 |  | 16 |  | R-5 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-excavation of Khal (New Haor) | Km | 23.815 | 1161.49 | Concerned XEN proposed to raise the height of embkt. | HOBI/PW-04 | New | 11 | 256912.018 | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Const of Box Drainage Outlet | nos. | 1 | 315 |  | HOBI/PW-05 | New | 3 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Re-excavation of Khal (Rehab. Kairdhala & Aralia Beel ) | nos. | 5 | 742.4 |  | HOBI/PW-05 | New | 3 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Rehab. of submersible Embankment (Re-section Kairadhala-16.02 km & Aralia-14.124 km and Const. Aralia-8.36 km) | nos. | 1 | 218.3 |  | HOBI/PW-05 | New | 3 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Replacement of Reg. Gates & other related works | nos. | 0 | 0 |  | HOBI/PW-05 | New | 5 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-01 Bashira River | (a) Re-Inatallation of Reguator((one no.32 vent 1.50mx1.80m ) | nos. | 15 | 134 |  | HOBI/PW-06 | New | 1 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Rehab. of submersible Embankment ( Aralia-22.484 km) | nos. | 9 | 540 |  | HOBI/PW-06 | New | 4 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-04 Mokhar Haor | Const. of Submersible Embankment | nos. | 2 | 356.4 | Size of pitching block will be enhanced. | HOBI/PW-06 | New | 5 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 4 vent (1.50 mx1.80m) | nos. | 2 | 529.6 |  | HOBI/PW-06 | New | 5 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 1 vent (1.50 mx1.80m) | Km | 18.048 | 606.84 |  | HOBI/PW-07 | New | 7 | 403996.842 | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 2 vent (1.50 mx1.80m) | Km | 12.01 | 319.92 |  | HOBI/PW-07 | New | 7 | 208662.994 | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-excavation of River (New Haor) | nos. | 1 | 9.69 |  | HOBI/PW-07 | New | 12 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-07 | O&M During Construction | LS | 0 | 0 |  | HOBI/PW-08 | New | 17 |  | A-1 | HOBI
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Rehab. Regulaors | Km | 1.22 | 52.46 |  | KISH/PW-01 | Rehab | 8 | 304227.48 | R-1 | KISH
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Irrigation Inlet | Km | 2.151 | 92.47 |  | KISH/PW-01 | Rehab | 8 | 304227.48 | R-2 | KISH
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Box Drainge Outlet | Km | 8.18 | 351.62 |  | KISH/PW-01 | Rehab | 8 | 304227.48 | R-3 | KISH
BWDB/Kish/HFMLIP/PW-32 Dakshiner Haor | Construction of Submersible Embankment with Slope/Crest Protection work Dak Type-A 0.235 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 6 | 25.64 |  | KISH/PW-01 | Rehab | 16 |  | R-4 | KISH
BWDB/Kish/HFMLIP/PW-32 Naogaon Haor | Construction of Submersible Embankment with Slope/Crest Protection work Dak Type-A 0.235 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 2 | 8.55 |  | KISH/PW-01 | Rehab | 16 |  | R-3 | KISH
BWDB/Kish/HFMLIP/PW-32 Noapara Haor | Construction of Submersible Embankment with Slope/Crest Protection work Dak Type-A 0.235 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 3 | 12.81 |  | KISH/PW-01 | Rehab | 16 |  | R-2 | KISH
BWDB/Kish/HFMLIP/PW-32 Nunnir Haor | Construction of Submersible Embankment with Slope/Crest Protection work Dak Type-A 0.235 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 2 | 8.55 |  | KISH/PW-01 | Rehab | 16 |  | R-1 | KISH
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 124.01 |  | KISH/PW-02 | New | 3 |  | N-1 | KISH
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | Km | 11.095 | 210.4 |  | KISH/PW-02 | New | 7 | 211770.02 | N-1 | KISH
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of 4.0 m width Causeway | Km | 0.315 | 15.09 |  | KISH/PW-02 | New | 11 | 2953 | N-1 | KISH
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Re-excavation of Khal (New Haor) | nos. | 1 | 155.52 |  | KISH/PW-03 | New | 3 |  | N-2 | KISH
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Re-excavation of Khal (New Haor) | Km | 10.383 | 554.48 |  | KISH/PW-03 | New | 11 | 109104.8 | N-2 | KISH
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | C onst. of Submersible Embankment | nos. | 2 | 198 |  | KISH/PW-04 | New | 3 |  | N-2 | KISH
BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 256.5 |  | KISH/PW-04 | New | 3 |  | N-2 | KISH
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Submersible Embankment | Km | 6.471 | 266 |  | KISH/PW-04 | New | 11 | 50421.04 | N-2 | KISH
BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of Submersible Embankment | nos. | 1 | 220 |  | KISH/PW-05 | New | 3 |  | N-2 | KISH
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Irrigation Inlet | Km | 12.214 | 580 |  | KISH/PW-05 | New | 11 | 98770 | N-2 | KISH
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 222 |  | KISH/PW-06 | New | 3 |  | N-2 | KISH
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | Km | 20 | 618 |  | KISH/PW-06 | New | 7 | 577707.02 | N-2 | KISH
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | Km | 25.7 | 680 |  | KISH/PW-07 | New | 7 | 945139.04 | N-3 | KISH
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Box Drainge Outlet | Km | 0.8 | 23 |  | KISH/PW-07 | New | 11 | 12696 | N-3 | KISH
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 70 |  | KISH/PW-09 | New | 4 |  | N-2 | KISH
BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of 6.00 m causeway | nos. | 1 | 237.5 |  | KISH/PW-09 | New | 5 |  | N-2 | KISH
BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 170 | Regulators are converted to causeway. | KISH/PW-09 | New | 5 |  | N-3 | KISH
BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of Submersible Embankment | nos. | 1 | 237.5 |  | KISH/PW-09 | New | 5 |  | N-3 | KISH
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 150 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 3 |  | N-4 | KISH
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 243 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 5 |  | N-4 | KISH
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Re-excavation of Khal (New Haor) | Km | 11.98 | 618 |  | KISH/PW-10 | New | 11 | 121988 | N-4 | KISH
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of Submersible Embankment | nos. | 1 | 326.37 |  | KISH/PW-11 | New | 3 |  | N-4 | KISH
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Submersible Embankment | Km | 10.86 | 538.74 |  | KISH/PW-11 | New | 11 | 109155.3 | N-4 | KISH
BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 227 |  | KISH/PW-12 | New | 3 |  | N-4 | KISH
BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of Submersible Embankment | nos. | 1 | 240 |  | KISH/PW-12 | New | 3 |  | N-4 | KISH
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | Km | 3.857 | 260 |  | KISH/PW-12 | New | 7 | 371757.99 | N-4 | KISH
BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 235 |  | KISH/PW-13 | New | 3 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Re-excavation of Khal (New Haor) | nos. | 1 | 175 |  | KISH/PW-13 | New | 3 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Irrigation Inlet | Km | 10 | 490 |  | KISH/PW-13 | New | 11 | 215922 | N-5 | KISH
BWDB/Kish/HFMLIP/PW-07 Boro Haor | Re-excavation of Khal | nos. | 1 | 219.6 |  | KISH/PW-14 | New | 3 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-07 Boro Haor | Const. of Submersible Embankment | nos. | 0 | 0 |  | KISH/PW-14 | New | 3 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of New Regulators 5 vent (1.50mx1.80m) | Km | 16.9 | 705.4 |  | KISH/PW-14 | New | 11 | 194853 | N-5 | KISH
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 0 | 0 | Regulator c onverted by 6.00 m causeway | KISH/PW-15 | New | 5 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Box Drainge Outlet | Km | 9 | 600 |  | KISH/PW-15 | New | 11 | 133316.13 | N-5 | KISH
BWDB/Kish/HFMLIP/PW-09 Boro Haor | Construction of Box Drainnage Outlet | nos. | 1 | 404.5 |  | KISH/PW-16 | New | 3 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 6.0 m width Causeway | Km | 14.12 | 531.3 |  | KISH/PW-16 | New | 11 | 143610.85 | N-5 | KISH
PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 25 | 274.32 |  | KISH/PW-17 | New | 1 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 6 m width | nos. | 1 | 675 |  | KISH/PW-17 | New | 3 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 4 m width | nos. | 1 | 115.24 |  | KISH/PW-17 | New | 3 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 5 | 177.44 |  | KISH/PW-17 | New | 4 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 4.0 m width Causeway | Km | 13.17 | 561 |  | KISH/PW-17 | New | 11 | 202851.03 | N-5 | KISH
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Submersible Embankment | nos. | 1 | 537 |  | KISH/PW-18 | New | 5 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 4.0 m width Causeway | nos. | 1 | 445 |  | KISH/PW-18 | New | 5 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | Km | 26.035 | 615 |  | KISH/PW-18 | New | 7 | 453822.6 | N-5 | KISH
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | Km | 22.933 | 975 |  | KISH/PW-19 | New | 7 | 577753.68 | N-5 | KISH
PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | nos. | 16 | 160 |  | KISH/PW-20 | New | 1 |  | N-2 | KISH
PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | nos. | 3 | 30 |  | KISH/PW-20 | New | 1 |  | N-3 | KISH
PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | nos. | 9 | 90 |  | KISH/PW-20 | New | 1 |  | N-4 | KISH
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 3 | 128.25 |  | KISH/PW-20 | New | 4 |  | N-2 | KISH
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Khal (New) | nos. | 0 | 0 |  | KISH/PW-20 | New | 4 |  | N-3 | KISH
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 42.75 |  | KISH/PW-20 | New | 4 |  | N-4 | KISH
BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of Submersible Embankment | nos. | 1 | 178 |  | KISH/PW-20 | New | 5 |  | N-2 | KISH
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Irrigation Inlet | nos. | 2 | 356 |  | KISH/PW-20 | New | 5 |  | N-3 | KISH
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 178 |  | KISH/PW-20 | New | 5 |  | N-4 | KISH
BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 6 m width | nos. | 1 | 355.6 |  | KISH/PW-21 | New | 3 |  | N-6 | KISH
BWDB/Kish/HFMLIP/PW-10 Noapara Haor | 1 No. Regulator 1-vent (1.5mx1.80m) | nos. | 1 | 208.09 |  | KISH/PW-21 | New | 3 |  | N-6 | KISH
BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 1 vent (1.50mx1.80m) | Km | 10 | 310.69 |  | KISH/PW-21 | New | 11 | 121065.93 | N-6 | KISH
BWDB/Kish/HFMLIP/PW-29 O&M During Construction | O&M During Construction | nos. | 5 | 139.1 |  | KISH/PW-21 | New | 12 |  | N-6 | KISH
PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 6 | 73 |  | KISH/PW-22 | New | 1 |  | N-6 | KISH
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of Submersible Embankment | nos. | 3 | 116 |  | KISH/PW-22 | New | 4 |  | N-6 | KISH
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 6.m width Causeway | nos. | 1 | 195 |  | KISH/PW-22 | New | 5 |  | N-6 | KISH
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | Km | 9.92 | 210 |  | KISH/PW-22 | New | 7 | 146641.43 | N-6 | KISH
BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 6 vent (1.50mx1.80m) | Km | 11 | 290 |  | KISH/PW-22 | New | 11 | 91984.7 | N-6 | KISH
PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 4 | 47.87 |  | KISH/PW-23 | New | 1 |  | N-7 | KISH
BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of New 1 No. 6 m width Causeway | nos. | 2 | 640.67 |  | KISH/PW-23 | New | 3 |  | N-7 | KISH
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 39.54 |  | KISH/PW-23 | New | 4 |  | N-7 | KISH
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 2 vent (1.50mx1.80m) | Km | 1.925 | 32.63 |  | KISH/PW-23 | New | 7 | 23149.28 | N-7 | KISH
BWDB/Kish/HFMLIP/PW-27 | Const. of Box Drainge Outlet | Km | 4.51 | 105.29 |  | KISH/PW-23 | New | 11 | 51688.691 | N-7 | KISH
BWDB/Kish/HFMLIP/PW-27 | Const. of 6.0 m width Causeway | Km | 19.843 | 860 |  | KISH/PW-24 | New | 11 | 214238.2 | N-8 | KISH
PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 15 | 125 |  | KISH/PW-25 | New | 1 |  | N-8 | KISH
BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of Submersible Embankment | nos. | 1 | 397 |  | KISH/PW-25 | New | 3 |  | N-8 | KISH
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 44 |  | KISH/PW-25 | New | 4 |  | N-8 | KISH
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Re-excavation of Khal (New Haor) | nos. | 1 | 265 |  | KISH/PW-25 | New | 5 |  | N-8 | KISH
BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Re-excavation of River by Dredger/ Mechanical (Berachapra 15.82 km + Ataplal 7.113 km) | nos. | 1 | 349 |  | KISH/PW-25 | New | 5 |  | N-8 | KISH
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 1 vent (1.50mx1.80m) | Km | 11 | 420 |  | KISH/PW-25 | New | 7 | 342244.7 | N-8 | KISH
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of Submersible Embankment | Km | 22.7 | 479 |  | KISH/PW-26 | New | 7 | 468821.04 | N-9 | KISH
BWDB/Kish/HFMLIP/PW-28 WMG Office Building | Const. of WMG Training Office at Kishoregonj, Netrokona, Sunamgonj & Hobigonj district. | Km | 0.54 | 23 |  | KISH/PW-26 | New | 11 | 11787.77 | N-9 | KISH
BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 314 |  | KISH/PW-27 | New | 3 |  | N-9 | KISH
BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of Submersible Embankment | nos. | 0 | 0 |  | KISH/PW-27 | New | 3 |  | N-9 | KISH
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of Submersible Embankment | nos. | 4 | 49 |  | KISH/PW-27 | New | 4 |  | N-9 | KISH
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 1 | 440 |  | KISH/PW-27 | New | 5 |  | N-9 | KISH
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 1 | 160 |  | KISH/PW-27 | New | 5 |  | N-9 | KISH
BWDB/Kish/HFMLIP/PW-31 Naogaon Haor Part -B Kishoreganj | Construction of Submersible Embankment with Slope/Crest Protection work (Type-A 0.73 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 30 | 1050 |  | KISH/PW-28 | New | 15 |  | A-1 | KISH
BWDB/Kish/HFMLIP/PW-33 Threshing Floor Construction | O&M During Construction | L.S. | 1 | 100 |  | KISH/PW-29 | New | 17 |  | A-1 | KISH
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.381 | 1469.83 | KISH/PW-30 | KISH/PW-30 | New | 11 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.66 | 1122.28 | KISH/PW-31 | KISH/PW-31 | New | 11 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.654 | 1563.73 | KISH/PW-32 | KISH/PW-32 | New | 11 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.275 | 1742.1 | KISH/PW-32 | KISH/PW-33 | New | 11 |  | N-5 | KISH
BWDB/Kish/HFMLIP/PW-33 Dakshiner Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.206 | 1203.35 | KISH/PW-33 | KISH/PW-34 | New | 11 |  | N-8 | KISH
BWDB/Kish/HFMLIP/PW-33 Sonair Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 1.545 | 914.62 | KISH/PW-34 | KISH/PW-35 | New | 11 |  | N-8 | KISH
BWDB/Kish/HFMLIP/PW-33 | Construction of Submersible Embankment with Slope Protection Work | Km | 3.15 | 0 | KISH/PW-35 | KISH/PW-35 | New | 11 |  | N-4 | KISH
BWDB/Kish/HFMLIP/PW-33 | Construction of Submersible Embankment with Slope Protection Work | Km | 0.35 | 0 |  | KISH/PW-35 | New | 11 |  | N-2 | KISH
BWDB/Kish/HFMLIP/PW-33 | Construction of Submersible Embankment with Slope Protection Work | Km | 0 | 0 |  | KISH/PW-35 | New | 11 |  | N-2 | KISH
BWDB/Kish/HFMLIP/PW-34 | Construction of threshing floor | Nos | 5 | 225 |  | KISH/PW-36 | New | 14 |  | N-5 | KISH
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of New Regulators 1 vent (1.50mx1.80m) | Km | 10.69 | 345.15 |  | NETR/PW-01 | Rehab | 9 |  | R-11 | NETR
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | Km | 35.52 | 1137.85 |  | NETR/PW-01 | Rehab | 9 | 603554.12 | R-9 | NETR
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Replacement of Reg. Gates & other related works | Km | 30.98 | 507.2842 |  | NETR/PW-02 | Rehab | 8 | 914740.64 | R-10 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-excavation of Khal (Rehab.) (including 4.925 km river dredging) | Km | 6.133 | 100.4252 |  | NETR/PW-02 | Rehab | 8 | 914740.64 | R-11 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Replacement of Reg. Gates & other related works | Km | 13.27 | 217.2906 |  | NETR/PW-02 | Rehab | 8 | 914740.64 | R-9 | NETR
BWDB/Netra/HFMLIP/PW-02 Damara, Kangsha & Singer Beel | Re-Excavation of Khal Project (b) Kangsha River Scheme (30.98 Km) | nos. | 1 | 389.57 |  | NETR/PW-03 | Rehab | 2 |  | R-9 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Replacement of Reg. Gates & other related works | km | 20.9 | 552.43 |  | NETR/PW-03 |  | 9 | 312275.643 | R-10 | NETR
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of Submersible Embankment | Km | 3.56 | 68 |  | NETR/PW-03 | Rehab | 10 | 14852.987 | R-11 | NETR
BWDB/Netra/HFMLIP/PW-07 Dharmapasah Rui Beel | Re-excavation of River (Lower Kongsha River 10.50 km & Gunai River 11.44 Km) | Nos | 16 | 40 |  | NETR/PW-03 |  | 16 |  | R-10 | NETR
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Irrigation Inlet | Nos | 6 | 15 |  | NETR/PW-03 |  | 16 |  | R-11 | NETR
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Submersible Embankment | Nos | 10 | 25 |  | NETR/PW-03 |  | 16 |  | R-9 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-excavation of Khal (Rehab.) (including 4.925 km river dredging) | Km | 10.195 | 484.75 |  | NETR/PW-04 | Rehab | 8 | 792075.56 | R-12 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-Sectioning of Submersible Embankment | Km | 13.838 | 680.25 |  | NETR/PW-04 | Rehab | 8 | 792075.56 | R-13 | NETR
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const. of Irrigation Inlet | Km | 9.75 | 315 |  | NETR/PW-04 | Rehab | 10 | 191943.37 | R-12 | NETR
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of New Regulators 2 vent (1.50mx1.80m) | Nos | 16 | 40 |  | NETR/PW-04 |  | 16 |  | R-12 | NETR
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Box Drainage Outlet | Nos | 8 | 20 |  | NETR/PW-04 |  | 16 |  | R-13 | NETR
BWDB/Netra/HFMLIP/PW-02 Damara, Kangsha & Singer Beel | Re-Excavation of Khal (Rehab.) (c) Singer Beel Scheme (6.133 Km) | nos. | 3 | 712.43 |  | NETR/PW-05 | New | 3 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-02 Damara, Kangsha & Singer Beel | Re-Excavation of Khal (Rehab.) (a) Damapara Water Management Project.(13.27 Km) | nos. | 1 | 439.67 |  | NETR/PW-05 | New | 3 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const. of Box Drainage Outlet | Km | 3.071 | 57.25 |  | NETR/PW-05 | New | 11 | 25797.655 | N-11 | NETR
BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Re-Sectioning of Full Embankment (Singer Beel-10.69) | nos. | 0 | 0 |  | NETR/PW-06 | New | 1 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | (a) Re-Sectioning of Full Embankment (Kangsha)- 20.90 km. | nos. | 2 | 83 |  | NETR/PW-06 | New | 4 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Replacement of Reg. Gates & other related works | Km | 11.65 | 470 |  | NETR/PW-06 | New | 7 | 368599.89 | N-11 | NETR
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Rehabilitation of existing Regulator 4 vent | nos. | 1 | 12 |  | NETR/PW-06 | New | 12 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Replacement of Reg. Gates & other related works | Km | 21.94 | 995 |  | NETR/PW-07 | New | 7 | 677328 | N-12 | NETR
BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Re-Sectioning of Full Embankment (Dampara-35.828) | nos. | 3 | 37 |  | NETR/PW-08 | New | 1 |  | N-12 | NETR
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Re-Installation of Regulator 5 vent (1.50mx1.80m, Dampara) | nos. | 2 | 490 |  | NETR/PW-08 | New | 3 |  | N-12 | NETR
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | (b) Re-Sectioning of Submersible Embankment (Singer beel)- 3.56 Km. | nos. | 5 | 300 |  | NETR/PW-08 | New | 4 |  | N-12 | NETR
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Re-excavation of Khal (New) | Km | 0 | 0 |  | NETR/PW-08 | New | 11 |  | N-12 | NETR
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Box Drainage Outlet | nos. | 9 | 107.07 |  | SUNM/PW-01 | New | 1 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of 4.0 m width Causeway | nos. | 7 | 301.63 |  | SUNM/PW-01 | New | 4 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of 4.0 m width Causeway | Km | 13.928 | 603.75 | Need more 6 nos. Khal for re-excavation extra cost will remain same. | SUNM/PW-01 | New | 7 | 206690 | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-07 Dharmapasha Rui Bill Haor | Const of Submersible Embankment with Slope/Crest Protection Work (Type-A -0.700 km,Type-B 2.800 km & Fuse Type-0.025 ) | Km | 17.06 | 551 | XEN reported that no need 17.34 km embkt. | SUNM/PW-01 | New | 11 | 399171.48 | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Irrigation Inlet | Km | 36.58 | 1275 |  | SUNM/PW-02 | New | 7 | 913100 | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-02 Dhakua Haor (Divn-2) | Re-excavation of River (New Haor) (Piain River) | nos. | 1 | 221.62 |  | SUNM/PW-03 | New | 3 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 345.16 |  | SUNM/PW-03 | New | 3 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 3 | 578.71 |  | SUNM/PW-03 | New | 5 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 259.36 |  | SUNM/PW-03 | New | 5 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Box Drainage Outlet | Km | 34.94 | 1564 |  | SUNM/PW-04 | New | 11 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Re-excavation of Khal (New Haor)(4 Nos. Khal) | nos. | 1 | 270 |  | SUNM/PW-05 | New | 3 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Submersible Embankment | nos. | 1 | 318 |  | SUNM/PW-05 | New | 3 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of 6.0 m width Causeway | nos. | 1 | 290 |  | SUNM/PW-05 | New | 5 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-04 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Submersible Embankment | nos. | 3 | 722 |  | SUNM/PW-05 | New | 5 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Irrigation Inlet | nos. | 12 | 131.28 |  | SUNM/PW-06 | New | 1 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 45.13 |  | SUNM/PW-06 | New | 4 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of 6.0 m width Causeway | Km | 66.043 | 1423.59 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
Construction of Submersible Embankment with Slope Protection Work | Re-excavation of Khal (New Haor) | Km | 3.44 | 1170.07 |  | SUNM/PW-07 | New | 11 |  | N-12 | SUNM

## Kishoregonj
Package No./Name of Haor | Date of Invitation for Tender | Date of Signing Contract | Date of Commence-ment as per Contract | Date of Complection as per Contract | Component | Unit | Qnty | Cost | Time Extention required period (If any) | Actual/ Tentative date of Complection | Required contract variation cost component wise (if any) | Component | Unit | Qnty | Cost | Remarks | Package | Haor Type | Structure Code | Structure Code | Haor Code | Haor
PW-01 4 Nos. Rehabilitation Haor | 1 |  |  |  | Replacement of Reg. Gates & other related works | nos. | 13 | 32.5 |  |  |  | Replacement of Reg. Gates & other related works | nos. | 0 | 32.5 |  | KISH/PW-01 | Rehab | 2
PW-01 4 Nos. Rehabilitation Haor | 2 |  |  |  | Re-excavation of Khal (Rehab) | Km | 14 | 140 |  |  |  | Re-excavation of Khal (Rehab) | Km | 11.55 | 255 |  | KISH/PW-01 | Rehab | 8
PW-01 4 Nos. Rehabilitation Haor | 3 |  |  |  | Re-sectioning of Full Embankment | Km | 5 | 25 |  |  |  | Re-sectioning of Full Embankment | Km | 2 | 10 |  | KISH/PW-01 | Rehab | 9
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | 4 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 123.45 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 123.45 |  | KISH/PW-02 | New | 3
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | 5 |  |  |  | Re-excavation of Khal (New Haor) | Km | 11.095 | 263.82 |  |  |  | Re-excavation of Khal (New Haor) | Km | 1.095 | 211.74 |  | KISH/PW-02 | New | 7
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | 6 |  |  |  | C onst. of Submersible Embankment | Km | 0.315 | 14.81 |  |  |  | C onst. of Submersible Embankment | Km | 0.315 | 14.81 |  | KISH/PW-02 | New | 11
BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | 7 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 155.51 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 155.51 |  | KISH/PW-03 | New | 3
BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | 8 |  |  |  | Const. of Submertible Embankment | Km | 10.383 | 533.94 |  |  |  | Const. of Submertible Embankment | Km | 10.383 | 554.48 |  | KISH/PW-03 | New | 11
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | 9 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 198 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 198 |  | KISH/PW-04 | New | 3
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | 10 |  |  |  | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 255.65 |  |  |  | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 255.65 |  | KISH/PW-04 | New | 3
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | 11 |  |  |  | Const. of Submertible Embankment | Km | 6.471 | 256.87 |  |  |  | Const. of Submertible Embankment | Km | 6.471 | 291.35 |  | KISH/PW-04 | New | 11
BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | 12 |  |  |  | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 193.49 |  |  |  | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 193.49 |  | KISH/PW-05 | New | 3
BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | 13 |  |  |  | Const. of Submertible Embankment | Km | 12.214 | 577.36 |  |  |  | Const. of Submertible Embankment | Km | 12.214 | 621.24 |  | KISH/PW-05 | New | 11
BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | 14 |  |  |  | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 232.99 |  |  |  | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 242.57 |  | KISH/PW-06 | New | 3
BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | 15 |  |  |  | Re-excavation of Khal (New Haor) | Km | 20 | 557.47 |  |  |  | Re-excavation of Khal (New Haor) | Km | 20 | 557.47 |  | KISH/PW-06 | New | 7
BWDB/Kish/HFMLIP/PW-07 Boro Haor | 16 |  |  |  | Re-excavation of Khal | Km | 32.406 | 854.17 |  |  |  | Re-excavation of Khal | Km | 32.406 | 690 |  | KISH/PW-07 | New | 7
BWDB/Kish/HFMLIP/PW-07 Boro Haor | 17 |  |  |  | Const. of Submertible Embankment | Km | 3.879 | 91.08 |  |  |  | Const. of Submertible Embankment | Km | 3.879 | 20 |  | KISH/PW-07 | New | 11
BWDB/Kish/HFMLIP/PW-09 Boro Haor | 18 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 327 |  |  |  | Const. of New Causeway 4 m width | nos. | 2 | 327 | Regulators are converted to causeway. | KISH/PW-09 | New | 5
BWDB/Kish/HFMLIP/PW-09 Boro Haor | 19 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 406.78 |  |  |  | Const. of New Causeway 6 m width | nos. | 2 | 403 |  | KISH/PW-09 | New | 5
BWDB/Kish/HFMLIP/PW-10 Noapara Haor | 20 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 266.03 |  |  |  | 1 No. Regulator 1-vent (1.5mx1.80m) | nos. | 1 | 150 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 3
BWDB/Kish/HFMLIP/PW-10 Noapara Haor | 21 |  |  |  | Const. of 6m width Cause way | nos. | 1 | 266.03 |  |  |  | Const. of New 1 No. 6 m width Causeway | nos. | 1 | 200 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 5
BWDB/Kish/HFMLIP/PW-10 Noapara Haor | 22 |  |  |  | Const. of Submertible Embankment | Km | 11.98 | 615 |  |  |  | Const. of Submertible Embankment | Km | 11.98 | 615 |  | KISH/PW-10 | New | 11
BWDB/Kish/HFMLIP/PW-11 Noapara Haor | 23 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 274.5 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 295.37 |  | KISH/PW-11 | New | 3
BWDB/Kish/HFMLIP/PW-11 Noapara Haor | 24 |  |  |  | Const. of Submertible Embankment | Km | 10.86 | 557.63 |  |  |  | Const. of Submertible Embankment | Km | 10.86 | 550 |  | KISH/PW-11 | New | 11
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | 25 |  |  |  | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 227.49 |  |  |  | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 227.49 |  | KISH/PW-12 | New | 3
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | 26 |  |  |  | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 303.33 |  |  |  | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 303.33 |  | KISH/PW-12 | New | 3
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | 27 |  |  |  | Re-excavation of Khal (New) | Km | 10.757 | 422.65 |  |  |  | Re-excavation of Khal (New) | Km | 10.757 | 422.65 |  | KISH/PW-12 | New | 7
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | 28 |  |  |  | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 270 |  |  |  | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 235.33 |  | KISH/PW-13 | New | 3
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | 29 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 180 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 173 |  | KISH/PW-13 | New | 3
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | 30 |  |  |  | Const. of Submertible Embankment | Km | 10 | 700 |  |  |  | Const. of Submertible Embankment | Km | 10 | 576.67 |  | KISH/PW-13 | New | 11
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | 31 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 170.86 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 219.16 |  | KISH/PW-14 | New | 3
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | 32 |  |  |  | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 256.29 |  |  |  | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 0 | 0 |  | KISH/PW-14 | New | 3
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | 33 |  |  |  | Const. of Submertible Embankment | Km | 16.9 | 576.67 |  |  |  | Const. of Submertible Embankment | Km | 16.9 | 680.42 |  | KISH/PW-14 | New | 11
BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | 34 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 176.58 |  |  |  | Const. of 6.00 m causeway | nos. | 1 | 166.9 | Regulator c onverted by 6.00 m causeway | KISH/PW-15 | New | 3
BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | 35 |  |  |  | Const. of Submertible Embankment | Km | 9 | 680.42 |  |  |  | Const. of Submertible Embankment | Km | 9 | 616.92 |  | KISH/PW-15 | New | 11
BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | 36 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 404.5 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 404.5 |  | KISH/PW-16 | New | 3
BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | 37 |  |  |  | Const. of Submertible Embankment | Km | 14.12 | 511.3 |  |  |  | Const. of Submertible Embankment | Km | 14.12 | 511.3 |  | KISH/PW-16 | New | 11
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | 38 |  |  |  | Const. of Irrigation Inlet | nos. | 25 | 274.46 |  |  |  | Const. of Irrigation Inlet | nos. | 25 | 274.46 |  | KISH/PW-17 | New | 1
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | 39 |  |  |  | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 450.95 |  |  |  | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 600 |  | KISH/PW-17 | New | 3
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | 40 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 115.24 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 115.24 |  | KISH/PW-17 | New | 3
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | 41 |  |  |  | Const. of Box Drainge Outlet | nos. | 5 | 177.44 |  |  |  | Const. of Box Drainge Outlet | nos. | 5 | 177.44 |  | KISH/PW-17 | New | 4
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | 42 |  |  |  | Const. of Submertible Embankment | Km | 13.17 | 550.04 |  |  |  | Const. of Submertible Embankment | Km | 13.17 | 550.04 |  | KISH/PW-17 | New | 11
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | 43 |  |  |  | Const. of 4.0 m width Causeway | nos. | 3 | 499.16 |  |  |  | Const. of 4.0 m width Causeway | nos. | 3 | 600 |  | KISH/PW-18 | New | 5
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | 44 |  |  |  | Const. of 6.6 m width Causeway | nos. | 1 | 274.54 |  |  |  | Const. of 6.m width Causeway | nos. | 1 | 274.54 |  | KISH/PW-18 | New | 5
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | 45 |  |  |  | Re-excavation of Khal (New Haor) | Km | 26.035 | 615.6 |  |  |  | Re-excavation of Khal (New Haor) | Km | 26.035 | 615.6 |  | KISH/PW-18 | New | 7
BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | 46 |  |  |  | Re-excavation of River by Dredger/ Mechanical (Berachapra 15.82 km + Ataplal 7.113 km) | Km | 22.933 | 968.51 |  |  |  | Re-excavation of River by Dredger/ Mechanical (Berachapra 15.82 km + Ataplal 7.113 km) | Km | 22.933 | 1065 |  | KISH/PW-19 | New | 7
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | 47 |  |  |  | Const. Irrigation Inlet | nos. | 36 | 284.55 |  |  |  | Const. Irrigation Inlet | nos. | 36 | 284.55 |  | KISH/PW-20 | New | 1
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | 48 |  |  |  | Const. of Box Drainge Outlet | nos. | 4 | 170.42 |  |  |  | Const. of Box Drainge Outlet | nos. | 4 | 170.42 |  | KISH/PW-20 | New | 4
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | 49 |  |  |  | Const. of 4.0 m width Causeway | nos. | 4 | 656.83 |  |  |  | Const. of 4.0 m width Causeway | nos. | 4 | 712 |  | KISH/PW-20 | New | 5
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | 50 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 225 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 225 |  | KISH/PW-21 | New | 3
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | 51 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 140 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 160 |  | KISH/PW-21 | New | 3
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | 52 |  |  |  | Const. of Submertible Embankment | Km | 10 | 500 |  |  |  | Const. of Submertible Embankment | Km | 10 | 478.31 |  | KISH/PW-21 | New | 11
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | 53 |  |  |  | Rehab. Regulaors | nos. | 5 | 125 |  |  |  | Rehab. Regulaors | nos. | 5 | 125 |  | KISH/PW-21 | New | 12
BWDB/Kish/HFMLIP/PW-22 Badla Haor | 54 |  |  |  | Const. of Irrigation Inlet | nos. | 6 | 72.88 |  |  |  | Const. of Irrigation Inlet | nos. | 6 | 72.88 |  | KISH/PW-22 | New | 1
BWDB/Kish/HFMLIP/PW-22 Badla Haor | 55 |  |  |  | Const. of Box Drainge Outlet | nos. | 3 | 116.03 |  |  |  | Const. of Box Drainge Outlet | nos. | 3 | 116.03 |  | KISH/PW-22 | New | 4
BWDB/Kish/HFMLIP/PW-22 Badla Haor | 56 |  |  |  | Const. of 4.0 m width Causeway | nos. | 1 | 194.91 |  |  |  | Const. of 4.0 m width Causeway | nos. | 1 | 194.91 |  | KISH/PW-22 | New | 5
BWDB/Kish/HFMLIP/PW-22 Badla Haor | 57 |  |  |  | Re-excavation of Khal (New Haor) | Km | 9.92 | 209.47 |  |  |  | Re-excavation of Khal (New Haor) | Km | 9.92 | 209.47 |  | KISH/PW-22 | New | 7
BWDB/Kish/HFMLIP/PW-22 Badla Haor | 58 |  |  |  | Const. of Submertible Embankment | Km | 11 | 252.89 |  |  |  | Const. of Submertible Embankment | Km | 11 | 252.89 |  | KISH/PW-22 | New | 11
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | 59 |  |  |  | Const. of Irrigation Inlet | nos. | 4 | 41.87 |  |  |  | Const. of Irrigation Inlet | nos. | 4 | 41.87 |  | KISH/PW-23 | New | 1
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | 60 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 567.12 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 567.12 |  | KISH/PW-23 | New | 3
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | 61 |  |  |  | Const. of Box Drainge Outlet | nos. | 1 | 39.54 |  |  |  | Const. of Box Drainge Outlet | nos. | 1 | 39.54 |  | KISH/PW-23 | New | 4
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | 62 |  |  |  | Re-excavation of Khal (New Haor) | Km | 1.925 | 32.63 |  |  |  | Re-excavation of Khal (New Haor) | Km | 1.925 | 32.63 |  | KISH/PW-23 | New | 7
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | 63 |  |  |  | Const. of Submertible Embankment | Km | 4.51 | 105.29 |  |  |  | Const. of Submertible Embankment | Km | 4.51 | 105.29 |  | KISH/PW-23 | New | 11
BWDB/Kish/HFMLIP/PW-24 Dakshiner Haor | 64 |  |  |  | Const. of Submertible Embankment | Km | 19.843 | 918.58 |  |  |  | Const. of Submertible Embankment | Km | 19.843 | 918.58 |  | KISH/PW-24 | New | 11
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | 65 |  |  |  | Const. of Irrigation Inlet | nos. | 15 | 124.68 |  |  |  | Const. of Irrigation Inlet | nos. | 15 | 124.68 |  | KISH/PW-25 | New | 1 | 42.278 | 1220.72
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | 66 |  |  |  | Const. of New Regulators 5 vent (1.50mx1.80m) | nos. | 1 | 396.96 |  |  |  | Const. of New Regulators 5 vent (1.50mx1.80m) | nos. | 1 | 396.96 |  | KISH/PW-25 | New | 3
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | 67 |  |  |  | Const. of Box Drainge Outlet | nos. | 1 | 43.25 |  |  |  | Const. of Box Drainge Outlet | nos. | 1 | 43.25 |  | KISH/PW-25 | New | 4
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | 68 |  |  |  | Const. of 6.0 m width Causeway | nos. | 2 | 450.435 |  |  |  | Const. of 6.0 m width Causeway | nos. | 2 | 450.435 |  | KISH/PW-25 | New | 5
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | 69 |  |  |  | Const. of 4.0 m width Causeway | nos. | 1 | 150.145 |  |  |  | Const. of 4.0 m width Causeway | nos. | 1 | 150.145 |  | KISH/PW-25 | New | 5
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | 70 |  |  |  | Re-excavation of Khal (9.20 km) and River (1.80 km) | Km | 11 | 424.98 |  |  |  | Re-excavation of Khal (9.20 km) and River (1.80 km) | Km | 11 | 424.98 |  | KISH/PW-25 | New | 7
BWDB/Kish/HFMLIP/PW-26 Sonair Haor | 71 |  |  |  | Re-excavation of Khal (New) | Km | 22.7 | 486.56 |  |  |  | Re-excavation of Khal (New) | Km | 22.7 | 486.56 |  | KISH/PW-26 | New | 7
BWDB/Kish/HFMLIP/PW-26 Sonair Haor | 72 |  |  |  | Const. of Submertible Embankment | Km | 0.54 | 22.72 |  |  |  | Const. of Submertible Embankment | Km | 0.54 | 10 |  | KISH/PW-26 | New | 11
BWDB/Kish/HFMLIP/PW-27 | 73 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 3 | 420 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 3 | 420 |  | KISH/PW-27 | New | 3
BWDB/Kish/HFMLIP/PW-27 | 74 |  |  |  | Const. of New Regulators 6 vent (1.50mx1.80m) | nos. | 1 | 443 |  |  |  | Const. of New Regulators 6 vent (1.50mx1.80m) | nos. | 0 | 0 |  | KISH/PW-27 | New | 3
BWDB/Kish/HFMLIP/PW-27 | 75 |  |  |  | Const. of Box Drainge Outlet | nos. | 0 | 0 |  |  |  | Const. of Box Drainge Outlet | nos. | 4 | 195 |  | KISH/PW-27 | New | 4
BWDB/Kish/HFMLIP/PW-27 | 76 |  |  |  | Const. of 6.0 m width Causeway | nos. | 0 | 0 |  |  |  | Const. of 6.0 m width Causeway | nos. | 1 | 250 |  | KISH/PW-27 | New | 5
BWDB/Kish/HFMLIP/PW-27 | 77 |  |  |  | Const. of 6.0 m width Causeway | nos. | 2 | 350 |  |  |  | Const. of 4.0 m width Causeway | nos. | 1 | 150 |  | KISH/PW-27 | New | 5
BWDB/Kish/HFMLIP/PW-28 WMG Office Building | 78 |  |  |  | Const. of WMG Training Office at Kishoregonj, Netrokona, Sunamgonj & Hobigonj district. | nos. | 60 | 1380 |  |  |  | Const. of WMG Training Office at Kishoregonj, Netrokona, Sunamgonj & Hobigonj district. | nos. | 40 | 1135 |  | KISH/PW-28 | New | 13

## HaorCode
Name | Code
Chandpur Haor Sub-Project | N-1
Nunnir Haor Sub-Project | N-2
Boro Haor Sub-Project | N-3
Noapara Haor Sub-Project | N-4
Naogaon Haor Sub-Project | N-5
Badla Haor Sub-Project | N-6
Chatal Haor Sub-Project | N-7
Dakhshiner Haor Sub-Project | N-8
Suniar Haor Sub-Project | N-9
Mokhar Haor Sub-Project | N-10
Ganesh Haor Sub-Project | N-11
Dharmapasha Rui Beel Sub-Project | N-12
Jaliar Haor Sub-Project | N-13
Dhakua Haor Sub-Project | N-14
Alalia-Bahadia Sub-Project | R-1
Modkhola-Bairagir Char Sub-Project | R-2
Ganakkhali Sub-Project | R-3
Boraikhali Khal Sub-Project | R-4
Koirdahla Ratna Sub-Project | R-5
Guingajuri Sub-Project | R-6
Aralia Khal Sub-Project | R-7
Bashira River Re-excavation Sub-Project | R-8
Dampara Water Management Scheme | R-9
Kangsha River Scheme | R-10
Singer Beel Sub-Project | R-11
Khaliajuri FCD Polder-2 | R-12
Khaliajuri FCD Polder-4 | R-13
Chandal Beel Sub-Project | R-14
Satdona Beel Scheme | R-15
All Haor | A-1

## Structure_Type
DPP Item | Initial | Code | Kishoreganj |  | Hobiganj |  | Netrokona |  | Sunamganj |  | Total |  | DPP_Code | GOB | RPA
|  |  | Quantyity | Amount | Quantyity | Amount | Quantyity | Amount | Quantyity | Amount | Quantity | Amount
Construction of Irrigation Inlet | IRRI_C | 1 | 86 | 798.44 | 18 | 164 | 5 | 122.01 | 21 | 227.19 | 130 | 1311.64 | D1 | 157.3968 | 1154.2432 |  |  |  |  | 1
Rehab Regulator Rehab Haor | REG_R_REHAB | 2 | 0 | 32.5 | 1 | 27.05 | 1 | 389.57 | 0 | 0 | 2 | 449.12 | D2 | 53.8944 | 395.2256 |  |  |  |  | 2
Regulator | REG_C | 3 | 26 | 5828.07 | 6 | 1155.79 | 5 | 1519.65 | 4 | 1101.19 | 41 | 9604.7 | D3 | 1152.564 | 8452.136 |  |  |  |  | 3
Box Drainage Outlet | DROU_C | 4 | 18 | 741.68 | 11 | 640 | 7 | 316.92 | 8 | 360.75 | 44 | 2059.35 | D3 | 247.122 | 1812.228 |  |  |  |  | 4
Causeway | CW_C | 5 | 19 | 3712.03 | 8 | 1911 | 0 | 0 | 10 | 1948.32 | 37 | 7571.35 | D3 | 908.562 | 6662.788 |  |  |  |  | 5
Bridge | BRI_C | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | D3 | 0 | 0 | 122 | 19235.4 | 2308.248 | 16927.152 | 6
Khal_River Reexcavation(New Haor) | REX_KH_RIV_NEW | 7 | 158.771 | 4716.1 | 30.058 | 790.96 | 33.436 | 1356.38 | 116.546 | 3074.76 | 338.811 | 9938.2 | D4 | 1192.584 | 8745.616 |  |  |  |  | 7
Khal_River Reexcavation(Rehab Haor) | REX_KH_RIV_REHAB | 8 | 11.55 | 255 | 23.007 | 912.14 | 50.383 | 1778.44 | 0 | 0 | 84.94 | 2945.58 | D5 | 353.4696 | 2592.1104 |  |  |  |  | 8
Embankment Rehablitation | EMB_R | 9 | 2 | 10 | 0 | 0 | 70.67 | 1772.96 | 0 | 0 | 72.67 | 1782.96 | D6 | 213.9552 | 1569.0048 |  |  |  |  | 9
Submersible Embankment Rehabilitation | SEMB_R | 10 | 0 | 0 | 49.712 | 1212.41 | 5 | 200 | 0 | 0 | 54.712 | 1412.41 | D7 | 169.4892 | 1242.9208 |  |  |  |  | 10
Submersible Embankment Construction | SEMB_C | 11 | 165.185 | 7367.3 | 23.815 | 1161.49 | 3.071 | 57.25 | 51.48 | 2236.52 | 243.551 | 10822.56 | D8 | 1298.7072 | 9523.8528 |  |  |  |  | 11
Rehab Regulator New Haor | REG_R_NEW | 12 | 5 | 125 | 1 | 9.69 | 1 | 19.43 | 0 | 0 | 7 | 154.12 | D9 | 18.4944 | 135.6256 |  |  |  |  | 12
Embankment Slope Protection Work | EMB_PRO | 13
Thrashing Floor Construction | THF_CONS | 14
Construction of WMG | WMG_OFF | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | D12 | 0 | 0 |  |  |  |  | 13
M&E GATE Repair | GATE_REP | 16
O&M During Construction | O&M_DU_CONST | 17
Total | [11 empty] | 48051.99 |  | 5766.2388 | 42285.7512
|  |  |  | 23586.12 |  | 7984.53

## Tendered3
Package Name | Component | Unit | Qnty | Cost | Remarks | Package | Haor Type | Structure Code
BWDB/Hobi/HFMLIP/PW-01 Bashira River | (a) Re-Inatallation of Reguator((one no. 2 vent 1.50mx1.80m ) | nos. | 1 | 153.89 | Need rehabilitation of existing 3-vent regulator instead of reinstallation of 2-vent regulator. | HOBI/PW-01 | Rehab | 2 | 0
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Irrigation Inlet | nos. | 0 | 0 |  | HOBI/PW-01 | Rehab | 1 | 1
BWDB/Hobi/HFMLIP/PW-01 Bashira River | (B) Causeway (one no. 6.0m wide). | nos. | 1 | 232.27 | Need 6.0 m causeway instead of 4.0 m causeway. | HOBI/PW-01 | Rehab | 5 | 2
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Re-excavation of Khal/River (Rehab. Khal 2.295 km & River 17.40 km) | Km | 19.695 | 842.501 |  | HOBI/PW-01 | Rehab | 8 | 3
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Rehab. of submersible Embankment (Re-section 7.00 Km & Const. 7.00 Km) | Km | 14 | 317.77 | 2.40 Km length will be increased. | HOBI/PW-01 | Rehab | 10 | 4
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Construction of Causeway for Aralia (46m). | nos. | 1 | 168.36 | 1 no. additional 4 m width Causeway will be needed. | HOBI/PW-02 | Rehab | 5 | 5
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Re-excavation of Khal (Rehab. Kairdhala & Aralia Beel ) | Km | 65.2 | 221.64 |  | HOBI/PW-02 | Rehab | 8 | 6
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Const of Box Drainage Outlet | nos. | 0 | 0 |  | HOBI/PW-02 | Rehab | 4 | 7
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Rehab. of submersible Embankment (Re-section Kairadhala-16.02 km & Aralia-14.124 km and Const. Aralia-8.36 km) | Km | 38.504 | 965.47 | Length of embkt. will be increased by 1.50 m. | HOBI/PW-02 | Rehab | 10 | 8
BWDB/Hobi/HFMLIP/PW-04 Mokhar Haor | Const. of Submersible Embankment | Km | 23.815 | 1161.49 | Concerned XEN proposed to raise the height of embkt. | HOBI/PW-04 | New | 11 | 9
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 4 vent (1.50 mx1.80m) | nos. | 1 | 463.84 |  | HOBI/PW-05 | New | 3 | 10
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 1 vent (1.50 mx1.80m) | nos. | 5 | 579.8 |  | HOBI/PW-05 | New | 3 | 11
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 2 vent (1.50 mx1.80m) | nos. | 1 | 231.95 |  | HOBI/PW-05 | New | 3 | 12
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | 4m Causeway | nos. | 0 | 0 |  | HOBI/PW-05 | New | 5 | 13
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of Irrigation Inlet | nos. | 15 | 134 |  | HOBI/PW-06 | New | 1 | 14
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of Box Drainage Outlet | nos. | 9 | 550 | Size of pitching block will be enhanced. | HOBI/PW-06 | New | 4 | 15
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of 4.0m wide Causeway | nos. | 2 | 366.4 |  | HOBI/PW-06 | New | 5 | 16
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of 6.0m wide Causeway | nos. | 2 | 549.6 |  | HOBI/PW-06 | New | 5 | 17
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-excavation of Khal (New Haor) | Km | 24.619 | 603.66 |  | HOBI/PW-07 | New | 7 | 18
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-excavation of River (New Haor) | Km | 15.54 | 303.64 |  | HOBI/PW-07 | New | 7 | 19
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-hab of regulator | nos. | 1 | 9.69 |  | HOBI/PW-07 | New | 12 | 20
PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 13 | 32.5 |  | KISH/PW-01 | Rehab | 2 | 21
PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 14 | 140 |  | KISH/PW-01 | Rehab | 8 | 22
PW-01 4 Nos. Rehabilitation Haor | Re-sectioning of Full Embankment | Km | 5 | 25 |  | KISH/PW-01 | Rehab | 9 | 23
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 123.45 |  | KISH/PW-02 | New | 3 | 24
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Re-excavation of Khal (New Haor) | Km | 11.095 | 263.82 |  | KISH/PW-02 | New | 7 | 25
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | C onst. of Submersible Embankment | Km | 0.315 | 14.81 |  | KISH/PW-02 | New | 11 | 26
BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 155.51 |  | KISH/PW-03 | New | 3 | 27
BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of Submersible Embankment | Km | 10.383 | 533.94 |  | KISH/PW-03 | New | 11 | 28
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 198 |  | KISH/PW-04 | New | 3 | 29
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 255.65 |  | KISH/PW-04 | New | 3 | 30
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of Submersible Embankment | Km | 6.471 | 256.87 |  | KISH/PW-04 | New | 11 | 31
BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 193.49 |  | KISH/PW-05 | New | 3 | 32
BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of Submersible Embankment | Km | 12.214 | 577.36 |  | KISH/PW-05 | New | 11 | 33
BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 232.99 |  | KISH/PW-06 | New | 3 | 34
BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Re-excavation of Khal (New Haor) | Km | 20 | 557.47 |  | KISH/PW-06 | New | 7 | 35
BWDB/Kish/HFMLIP/PW-07 Boro Haor | Re-excavation of Khal | Km | 32.406 | 854.17 |  | KISH/PW-07 | New | 7 | 36
BWDB/Kish/HFMLIP/PW-07 Boro Haor | Const. of Submersible Embankment | Km | 3.879 | 91.08 |  | KISH/PW-07 | New | 11 | 37
BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 327 | Regulators are converted to causeway. | KISH/PW-09 | New | 5 | 38
BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 406.78 |  | KISH/PW-09 | New | 5 | 39
BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 266.03 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 3 | 40
BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of 6m width Cause way | nos. | 0 | 0 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 5 | 41
BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of Submersible Embankment | Km | 11.98 | 617.94 |  | KISH/PW-10 | New | 11 | 42
BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 274.5 |  | KISH/PW-11 | New | 3 | 43
BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of Submersible Embankment | Km | 10.86 | 557.63 |  | KISH/PW-11 | New | 11 | 44
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 227.49 |  | KISH/PW-12 | New | 3 | 45
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 303.33 |  | KISH/PW-12 | New | 3 | 46
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Khal (New) | Km | 10.757 | 422.65 |  | KISH/PW-12 | New | 7 | 47
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 247.15 |  | KISH/PW-13 | New | 3 | 48
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 180 |  | KISH/PW-13 | New | 3 | 49
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 10 | 576.67 |  | KISH/PW-13 | New | 11 | 50
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 176.58 |  | KISH/PW-14 | New | 3 | 51
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 0 | 0 |  | KISH/PW-14 | New | 3 | 52
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 16.9 | 680.42 |  | KISH/PW-14 | New | 11 | 53
BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 166.9 | Regulator c onverted by 6.00 m causeway | KISH/PW-15 | New | 3 | 54
BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of Submersible Embankment | Km | 9 | 616.92 |  | KISH/PW-15 | New | 11 | 55
BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 404.5 |  | KISH/PW-16 | New | 3 | 56
BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of Submersible Embankment | Km | 14.12 | 511.3 |  | KISH/PW-16 | New | 11 | 57
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Irrigation Inlet | nos. | 25 | 274.46 |  | KISH/PW-17 | New | 1 | 58
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 450.95 |  | KISH/PW-17 | New | 3 | 59
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 115.24 |  | KISH/PW-17 | New | 3 | 60
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 5 | 177.44 |  | KISH/PW-17 | New | 4 | 61
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Submersible Embankment | Km | 13.17 | 550.04 |  | KISH/PW-17 | New | 11 | 62
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 4.0 m width Causeway | nos. | 3 | 499.16 |  | KISH/PW-18 | New | 5 | 63
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 6.6 m width Causeway | nos. | 1 | 274.54 |  | KISH/PW-18 | New | 5 | 64
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Re-excavation of Khal (New Haor) | Km | 26.035 | 615.6 |  | KISH/PW-18 | New | 7 | 65
BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Re-excavation of River by Dredger/ Mechanical (Berachapra 15.82 km + Ataplal 7.113 km) | Km | 22.933 | 968.51 |  | KISH/PW-19 | New | 7 | 66
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 36 | 284.55 |  | KISH/PW-20 | New | 1 | 67
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 4 | 170.42 |  | KISH/PW-20 | New | 4 | 68
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 4 | 656.83 |  | KISH/PW-20 | New | 5 | 69
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 225 |  | KISH/PW-21 | New | 3 | 70
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 160 |  | KISH/PW-21 | New | 3 | 71
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of Submersible Embankment | Km | 10 | 478.31 |  | KISH/PW-21 | New | 11 | 72
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Rehab. Regulaors | nos. | 5 | 125 |  | KISH/PW-21 | New | 12 | 73
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Irrigation Inlet | nos. | 6 | 72.88 |  | KISH/PW-22 | New | 1 | 74
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Box Drainge Outlet | nos. | 3 | 116.03 |  | KISH/PW-22 | New | 4 | 75
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of 4.0 m width Causeway | nos. | 1 | 194.91 |  | KISH/PW-22 | New | 5 | 76
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Re-excavation of Khal (New Haor) | Km | 9.92 | 209.47 |  | KISH/PW-22 | New | 7 | 77
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Submersible Embankment | Km | 11 | 252.89 |  | KISH/PW-22 | New | 11 | 78
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Irrigation Inlet | nos. | 4 | 41.87 |  | KISH/PW-23 | New | 1 | 79
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 567.12 |  | KISH/PW-23 | New | 3 | 80
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Box Drainge Outlet | nos. | 1 | 39.54 |  | KISH/PW-23 | New | 4 | 81
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Re-excavation of Khal (New Haor) | Km | 1.925 | 32.63 |  | KISH/PW-23 | New | 7 | 82
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Submersible Embankment | Km | 4.51 | 105.29 |  | KISH/PW-23 | New | 11 | 83
BWDB/Kish/HFMLIP/PW-24 Dakshiner Haor | Const. of Submersible Embankment | Km | 19.843 | 918.58 |  | KISH/PW-24 | New | 11 | 84
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Irrigation Inlet | nos. | 15 | 124.68 |  | KISH/PW-25 | New | 1 | 85
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of New Regulators 5 vent (1.50mx1.80m) | nos. | 1 | 396.96 |  | KISH/PW-25 | New | 3 | 86
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Box Drainge Outlet | nos. | 1 | 43.25 |  | KISH/PW-25 | New | 4 | 87
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 6.0 m width Causeway | nos. | 2 | 450.435 |  | KISH/PW-25 | New | 5 | 88
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 4.0 m width Causeway | nos. | 1 | 150.145 |  | KISH/PW-25 | New | 5 | 89
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Re-excavation of Khal (9.20 km) and River (1.80 km) | Km | 11 | 424.98 |  | KISH/PW-25 | New | 7 | 90
BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Re-excavation of Khal (New) | Km | 22.7 | 486.56 |  | KISH/PW-26 | New | 7 | 91
BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Const. of Submersible Embankment | Km | 0.54 | 22.72 |  | KISH/PW-26 | New | 11 | 92
BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 3 | 420 |  | KISH/PW-27 | New | 3 | 93
BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 6 vent (1.50mx1.80m) | nos. | 1 | 443 |  | KISH/PW-27 | New | 3 | 94
BWDB/Kish/HFMLIP/PW-27 | Const. of Box Drainge Outlet | nos. | 0 | 0 |  | KISH/PW-27 | New | 4 | 95
BWDB/Kish/HFMLIP/PW-27 | Const. of 6.0 m width Causeway | nos. | 0 | 0 |  | KISH/PW-27 | New | 5 | 96
BWDB/Kish/HFMLIP/PW-27 | Const. of 6.0 m width Causeway | nos. | 2 | 350 |  | KISH/PW-27 | New | 5 | 97
BWDB/Kish/HFMLIP/PW-28 WMG Office Building | Const. of WMG Training Office at Kishoregonj, Netrokona, Sunamgonj & Hobigonj district. | nos. | 40 | 1150 |  | KISH/PW-28 | New | 13 | 98
BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Re-Sectioning of Full Embankment (Dampara-35.828+Singer Beel-10.69) | Km | 46.21 | 1362.53 |  | NETR/PW-01 | Rehab | 9 | 99
BWDB/Netra/HFMLIP/PW-02 Damara, Kangsha & Singer Beel | Re-Excavation of Khal (Rehab.) (a) Damapara Water Management Project.(13.27 Km) (b) Kangsha River Scheme (30.98 Km) (c) Singer Beel Scheme (6.133 Km) | Km | 50.383 | 956.73 |  | NETR/PW-02 | Rehab | 8 | 100
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Re-Installation of Regulator 5 vent (1.50mx1.80m, Dampara) | nos. | 1 | 389.57 |  | NETR/PW-03 | Rehab | 2 | 101
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | (a) Re-Sectioning of Full Embankment (Kangsha)- 20.90 km. (b) Re-Sectioning of Submersible Embankment (Singer beel)- 3.56 Km. | Km | 24.46 | 557.3 |  | NETR/PW-03 | Rehab | 9 | 102
BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-excavation of Khal (Rehab.) (including 4.925 km river dredging) | Km | 24.033 | 1113.44 |  | NETR/PW-04 | Rehab | 8 | 103
BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-Sectioning of Submersible Embankment | Km | 9.75 | 413.43 | Not need for re-sectioning of 7.75 Km embkt. | NETR/PW-04 | Rehab | 10 | 104
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 3 | 725.48 |  | NETR/PW-05 | New | 3 | 105
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 406.65 |  | NETR/PW-05 | New | 3 | 106
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of Submersible Embankment | Km | 3.071 | 57.25 |  | NETR/PW-05 | New | 11 | 107
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const. of Irrigation Inlet | nos. | 2 | 85.01 |  | NETR/PW-06 | New | 1 | 108
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const. of Box Drainage Outlet | nos. | 2 | 16.92 |  | NETR/PW-06 | New | 4 | 109
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Re-excavation of Khal (New) | Km | 11.996 | 528.98 |  | NETR/PW-06 | New | 7 | 110
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Rehabilitation of existing Regulator 4 vent | nos. | 1 | 19.43 |  | NETR/PW-06 | New | 12 | 111
BWDB/Netra/HFMLIP/PW-07 Dharmapasah Rui Beel | Re-excavation of River (Lower Kongsha River 15.00 km & Gunai River 11.44 Km) | Km | 24 | 906.38 |  | NETR/PW-07 | New | 7 | 112
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Irrigation Inlet | nos. | 3 | 37 |  | NETR/PW-08 | New | 1 | 113
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 513 |  | NETR/PW-08 | New | 3 | 114
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Box Drainage Outlet | nos. | 5 | 300 |  | NETR/PW-08 | New | 4 | 115
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Submersible Embankment | Km | 0 | 0 |  | NETR/PW-08 | New | 11 | 116
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Irrigation Inlet | nos. | 9 | 95.91 |  | SUNM/PW-01 | New | 1 | 117
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Box Drainage Outlet | nos. | 7 | 315.62 |  | SUNM/PW-01 | New | 4 | 118
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Re-excavation of Khal (New Haor)(4 Nos. Khal) | Km | 7.678 | 268.41 | Need more 6 nos. Khal for re-excavation extra cost will remain same. | SUNM/PW-01 | New | 7 | 119
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Submersible Embankment | Km | 33.849 | 884.27 | XEN reported that no need 17.34 km embkt. | SUNM/PW-01 | New | 11 | 120
BWDB/Sunam/HFMLIP/PW-02 Dhakua Haor (Divn-2) | Re-excavation of River (New Haor) (Piain River) | Km | 36.575 | 1193.75 |  | SUNM/PW-02 | New | 7 | 121
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 177.84 |  | SUNM/PW-03 | New | 3 | 122
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 355.67 |  | SUNM/PW-03 | New | 3 | 123
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of 4.0 m width Causeway | nos. | 5 | 775.65 |  | SUNM/PW-03 | New | 5 | 124
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of 6.0 m width Causeway | nos. | 1 | 232.7 |  | SUNM/PW-03 | New | 5 | 125
BWDB/Sunam/HFMLIP/PW-04 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Submersible Embankment | Km | 34.94 | 1564.32 |  | SUNM/PW-04 | New | 11 | 126
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 267.87 |  | SUNM/PW-05 | New | 3 | 127
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 299.81 |  | SUNM/PW-05 | New | 3 | 128
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of 6.0 m width Causeway | nos. | 1 | 232.06 |  | SUNM/PW-05 | New | 5 | 129
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of 4.0 m width Causeway | nos. | 3 | 707.91 |  | SUNM/PW-05 | New | 5 | 130
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Irrigation Inlet | nos. | 12 | 131.28 |  | SUNM/PW-06 | New | 1 | 131
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Box Drainage Outlet | nos. | 1 | 45.13 |  | SUNM/PW-06 | New | 4 | 132
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | Re-excavation of Khal (New Haor) | Km | 70 | 1402.17 |  | SUNM/PW-06 | New | 7 | 133

## Tendered
Package Name | Component | Unit | Qnty | Cost | Remarks | Package | Haor Type | Structure Code
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Irrigation Inlet | nos. | 0 | 0 |  | HOBI/PW-01 | Rehab | 1
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of Irrigation Inlet | nos. | 15 | 134 |  | HOBI/PW-06 | New | 1
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Irrigation Inlet | nos. | 25 | 274.46 |  | KISH/PW-17 | New | 1
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 36 | 284.55 |  | KISH/PW-20 | New | 1
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Irrigation Inlet | nos. | 6 | 72.88 |  | KISH/PW-22 | New | 1
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Irrigation Inlet | nos. | 4 | 41.87 |  | KISH/PW-23 | New | 1
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Irrigation Inlet | nos. | 15 | 124.68 |  | KISH/PW-25 | New | 1
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const. of Irrigation Inlet | nos. | 2 | 85.01 |  | NETR/PW-06 | New | 1
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Irrigation Inlet | nos. | 3 | 37 |  | NETR/PW-08 | New | 1
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Irrigation Inlet | nos. | 9 | 95.91 |  | SUNM/PW-01 | New | 1
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Irrigation Inlet | nos. | 12 | 131.28 |  | SUNM/PW-06 | New | 1
BWDB/Hobi/HFMLIP/PW-01 Bashira River | (a) Re-Inatallation of Reguator((one no. 2 vent 1.50mx1.80m ) | nos. | 1 | 153.89 | Need rehabilitation of existing 3-vent regulator instead of reinstallation of 2-vent regulator. | HOBI/PW-01 | Rehab | 2
PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 13 | 32.5 |  | KISH/PW-01 | Rehab | 2
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Re-Installation of Regulator 5 vent (1.50mx1.80m, Dampara) | nos. | 1 | 389.57 |  | NETR/PW-03 | Rehab | 2
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 4 vent (1.50 mx1.80m) | nos. | 1 | 463.84 |  | HOBI/PW-05 | New | 3
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 1 vent (1.50 mx1.80m) | nos. | 5 | 579.8 |  | HOBI/PW-05 | New | 3
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 2 vent (1.50 mx1.80m) | nos. | 1 | 231.95 |  | HOBI/PW-05 | New | 3
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 123.45 |  | KISH/PW-02 | New | 3
BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 155.51 |  | KISH/PW-03 | New | 3
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 198 |  | KISH/PW-04 | New | 3
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 255.65 |  | KISH/PW-04 | New | 3
BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 193.49 |  | KISH/PW-05 | New | 3
BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 232.99 |  | KISH/PW-06 | New | 3
BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 266.03 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 3
BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 274.5 |  | KISH/PW-11 | New | 3
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 227.49 |  | KISH/PW-12 | New | 3
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 303.33 |  | KISH/PW-12 | New | 3
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 247.15 |  | KISH/PW-13 | New | 3
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 180 |  | KISH/PW-13 | New | 3
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 176.58 |  | KISH/PW-14 | New | 3
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 0 | 0 |  | KISH/PW-14 | New | 3
BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 166.9 | Regulator c onverted by 6.00 m causeway | KISH/PW-15 | New | 3
BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 404.5 |  | KISH/PW-16 | New | 3
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 450.95 |  | KISH/PW-17 | New | 3
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 115.24 |  | KISH/PW-17 | New | 3
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 225 |  | KISH/PW-21 | New | 3
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 160 |  | KISH/PW-21 | New | 3
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 567.12 |  | KISH/PW-23 | New | 3
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of New Regulators 5 vent (1.50mx1.80m) | nos. | 1 | 396.96 |  | KISH/PW-25 | New | 3
BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 3 | 420 |  | KISH/PW-27 | New | 3
BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 6 vent (1.50mx1.80m) | nos. | 1 | 443 |  | KISH/PW-27 | New | 3
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 3 | 725.48 |  | NETR/PW-05 | New | 3
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 406.65 |  | NETR/PW-05 | New | 3
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 490 |  | NETR/PW-08 | New | 3
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 177.84 |  | SUNM/PW-03 | New | 3
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 355.67 |  | SUNM/PW-03 | New | 3
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 267.87 |  | SUNM/PW-05 | New | 3
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 299.81 |  | SUNM/PW-05 | New | 3
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Const of Box Drainage Outlet | nos. | 0 | 0 |  | HOBI/PW-02 | Rehab | 4
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of Box Drainage Outlet | nos. | 9 | 550 | Size of pitching block will be enhanced. | HOBI/PW-06 | New | 4
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 5 | 177.44 |  | KISH/PW-17 | New | 4
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | nos. | 4 | 170.42 |  | KISH/PW-20 | New | 4
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Box Drainge Outlet | nos. | 3 | 116.03 |  | KISH/PW-22 | New | 4
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Box Drainge Outlet | nos. | 1 | 39.54 |  | KISH/PW-23 | New | 4
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Box Drainge Outlet | nos. | 1 | 43.25 |  | KISH/PW-25 | New | 4
BWDB/Kish/HFMLIP/PW-27 | Const. of Box Drainge Outlet | nos. | 0 | 0 |  | KISH/PW-27 | New | 4
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const. of Box Drainage Outlet | nos. | 2 | 16.92 |  | NETR/PW-06 | New | 4
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Box Drainage Outlet | nos. | 5 | 300 |  | NETR/PW-08 | New | 4
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Box Drainage Outlet | nos. | 7 | 315.62 |  | SUNM/PW-01 | New | 4
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Box Drainage Outlet | nos. | 1 | 45.13 |  | SUNM/PW-06 | New | 4
BWDB/Hobi/HFMLIP/PW-01 Bashira River | (B) Causeway (one no. 4.0m wide). | nos. | 1 | 232.27 | Need 6.0 m causeway instead of 4.0 m causeway. | HOBI/PW-01 | Rehab | 5
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Construction of Causeway for Aralia (4m). | nos. | 1 | 168.36 | 1 no. additional 4 m width Causeway will be needed. | HOBI/PW-02 | Rehab | 5
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | 4m Causeway | nos. | 0 | 0 |  | HOBI/PW-05 | New | 5
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of 4.0m wide Causeway | nos. | 2 | 366.4 |  | HOBI/PW-06 | New | 5
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of 6.0m wide Causeway | nos. | 2 | 549.6 |  | HOBI/PW-06 | New | 5
BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 327 | Regulators are converted to causeway. | KISH/PW-09 | New | 5
BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 406.78 |  | KISH/PW-09 | New | 5
BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of 6m width Cause way | nos. | 0 | 0 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 5
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 4.0 m width Causeway | nos. | 3 | 499.16 |  | KISH/PW-18 | New | 5
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 6.6 m width Causeway | nos. | 1 | 274.54 |  | KISH/PW-18 | New | 5
BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | nos. | 4 | 656.83 |  | KISH/PW-20 | New | 5
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of 4.0 m width Causeway | nos. | 1 | 194.91 |  | KISH/PW-22 | New | 5
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 6.0 m width Causeway | nos. | 2 | 450.435 |  | KISH/PW-25 | New | 5
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 4.0 m width Causeway | nos. | 1 | 150.145 |  | KISH/PW-25 | New | 5
BWDB/Kish/HFMLIP/PW-27 | Const. of 6.0 m width Causeway | nos. | 0 | 0 |  | KISH/PW-27 | New | 5
BWDB/Kish/HFMLIP/PW-27 | Const. of 4.0 m width Causeway | nos. | 2 | 350 |  | KISH/PW-27 | New | 5
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of 4.0 m width Causeway | nos. | 5 | 775.65 |  | SUNM/PW-03 | New | 5
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of 6.0 m width Causeway | nos. | 1 | 232.7 |  | SUNM/PW-03 | New | 5
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of 6.0 m width Causeway | nos. | 1 | 232.06 |  | SUNM/PW-05 | New | 5
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of 4.0 m width Causeway | nos. | 3 | 707.91 |  | SUNM/PW-05 | New | 5
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-excavation of Khal (New Haor) | Km | 24.619 | 603.66 |  | HOBI/PW-07 | New | 7
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-excavation of River (New Haor) | Km | 15.54 | 319.92 |  | HOBI/PW-07 | New | 7
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Re-excavation of Khal (New Haor) | Km | 11.095 | 263.82 |  | KISH/PW-02 | New | 7
BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Re-excavation of Khal (New Haor) | Km | 20 | 557.47 |  | KISH/PW-06 | New | 7
BWDB/Kish/HFMLIP/PW-07 Boro Haor | Re-excavation of Khal | Km | 32.406 | 854.17 |  | KISH/PW-07 | New | 7
BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Khal (New) | Km | 10.757 | 422.65 |  | KISH/PW-12 | New | 7
BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Re-excavation of Khal (New Haor) | Km | 26.035 | 615.6 |  | KISH/PW-18 | New | 7
BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Re-excavation of River by Dredger/ Mechanical (Berachapra 15.82 km + Ataplal 7.113 km) | Km | 22.933 | 968.51 |  | KISH/PW-19 | New | 7
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Re-excavation of Khal (New Haor) | Km | 9.92 | 209.47 |  | KISH/PW-22 | New | 7
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Re-excavation of Khal (New Haor) | Km | 1.925 | 32.63 |  | KISH/PW-23 | New | 7
BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Re-excavation of Khal (9.20 km) and River (1.80 km) | Km | 11 | 424.98 |  | KISH/PW-25 | New | 7
BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Re-excavation of Khal (New) | Km | 22.7 | 486.56 |  | KISH/PW-26 | New | 7
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Re-excavation of Khal (New) | Km | 11.996 | 528.98 |  | NETR/PW-06 | New | 7
BWDB/Netra/HFMLIP/PW-07 Dharmapasah Rui Beel | Re-excavation of River (Lower Kongsha River 15.00 km & Gunai River 11.44 Km) | Km | 24 | 906.38 |  | NETR/PW-07 | New | 7
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Re-excavation of Khal (New Haor)(4 Nos. Khal) | Km | 7.678 | 268.41 | Need more 6 nos. Khal for re-excavation extra cost will remain same. | SUNM/PW-01 | New | 7
BWDB/Sunam/HFMLIP/PW-02 Dhakua Haor (Divn-2) | Re-excavation of River (New Haor) (Piain River) | Km | 36.575 | 1193.75 |  | SUNM/PW-02 | New | 7
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | Re-excavation of Khal (New Haor) | Km | 66.043 | 1402.17 |  | SUNM/PW-06 | New | 7
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Re-excavation of Khal/River (Rehab. Khal 2.295 km & River 17.40 km) | Km | 19.695 | 842.501 |  | HOBI/PW-01 | Rehab | 8
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Re-excavation of Khal (Rehab. Kairdhala & Aralia Beel ) | Km | 6.2 | 221.64 |  | HOBI/PW-02 | Rehab | 8
PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | Km | 14 | 140 |  | KISH/PW-01 | Rehab | 8
BWDB/Netra/HFMLIP/PW-02 Damara, Kangsha & Singer Beel | Re-Excavation of Khal (Rehab.) (a) Damapara Water Management Project.(13.27 Km) (b) Kangsha River Scheme (30.98 Km) (c) Singer Beel Scheme (6.133 Km) | Km | 50.383 | 956.73 |  | NETR/PW-02 | Rehab | 8
BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-excavation of Khal (Rehab.) (including 4.925 km river dredging) | Km | 24.033 | 1113.44 |  | NETR/PW-04 | Rehab | 8
PW-01 4 Nos. Rehabilitation Haor | Re-sectioning of Full Embankment | Km | 5 | 25 |  | KISH/PW-01 | Rehab | 9
BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Re-Sectioning of Full Embankment (Dampara-35.828+Singer Beel-10.69) | Km | 46.21 | 1362.53 |  | NETR/PW-01 | Rehab | 9
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | (a) Re-Sectioning of Full Embankment (Kangsha)- 20.90 km. | Km | 20.9 | 531.02 |  | NETR/PW-03 | Rehab | 9
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Rehab. of submersible Embankment (Re-section 7.00 Km & Const. 7.00 Km) | Km | 14 | 317.77 | 2.40 Km length will be increased. | HOBI/PW-01 | Rehab | 10
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Rehab. of submersible Embankment (Re-section Kairadhala-16.02 km & Aralia-14.124 km and Const. Aralia-8.36 km) | Km | 38.504 | 965.47 | Length of embkt. will be increased by 1.50 m. | HOBI/PW-02 | Rehab | 10
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | (b) Re-Sectioning of Submersible Embankment (Singer beel)- 3.56 Km. | Km | 3.56 | 26.274 |  | NETR/PW-03 | Rehab | 10
BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-Sectioning of Submersible Embankment | Km | 9.75 | 413.43 | Not need for re-sectioning of 7.75 Km embkt. | NETR/PW-04 | Rehab | 10
BWDB/Hobi/HFMLIP/PW-04 Mokhar Haor | Const. of Submersible Embankment | Km | 23.815 | 1161.49 | Concerned XEN proposed to raise the height of embkt. | HOBI/PW-04 | New | 11
BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | C onst. of Submersible Embankment | Km | 0.315 | 14.81 |  | KISH/PW-02 | New | 11
BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of Submersible Embankment | Km | 10.383 | 533.94 |  | KISH/PW-03 | New | 11
BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of Submersible Embankment | Km | 6.471 | 256.87 |  | KISH/PW-04 | New | 11
BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of Submersible Embankment | Km | 12.214 | 577.36 |  | KISH/PW-05 | New | 11
BWDB/Kish/HFMLIP/PW-07 Boro Haor | Const. of Submersible Embankment | Km | 3.879 | 91.08 |  | KISH/PW-07 | New | 11
BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of Submersible Embankment | Km | 11.98 | 617.94 |  | KISH/PW-10 | New | 11
BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of Submersible Embankment | Km | 10.86 | 557.63 |  | KISH/PW-11 | New | 11
BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 10 | 576.67 |  | KISH/PW-13 | New | 11
BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of Submersible Embankment | Km | 16.9 | 680.42 |  | KISH/PW-14 | New | 11
BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of Submersible Embankment | Km | 9 | 616.92 |  | KISH/PW-15 | New | 11
BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of Submersible Embankment | Km | 14.12 | 511.3 |  | KISH/PW-16 | New | 11
BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Submersible Embankment | Km | 13.17 | 550.04 |  | KISH/PW-17 | New | 11
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of Submersible Embankment | Km | 10 | 478.31 |  | KISH/PW-21 | New | 11
BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Submersible Embankment | Km | 10.463 | 252.89 |  | KISH/PW-22 | New | 11
BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Submersible Embankment | Km | 4.51 | 105.29 |  | KISH/PW-23 | New | 11
BWDB/Kish/HFMLIP/PW-24 Dakshiner Haor | Const. of Submersible Embankment | Km | 19.843 | 918.58 |  | KISH/PW-24 | New | 11
BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Const. of Submersible Embankment | Km | 0.54 | 22.72 |  | KISH/PW-26 | New | 11
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of Submersible Embankment | Km | 3.071 | 57.25 |  | NETR/PW-05 | New | 11
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Submersible Embankment | Km | 0 | 0 |  | NETR/PW-08 | New | 11
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Submersible Embankment | Km | 33.849 | 884.27 | XEN reported that no need 17.34 km embkt. | SUNM/PW-01 | New | 11
BWDB/Sunam/HFMLIP/PW-04 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Submersible Embankment | Km | 34.94 | 1564.32 |  | SUNM/PW-04 | New | 11
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-hab of regulator | nos. | 1 | 9.69 |  | HOBI/PW-07 | New | 12
BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Rehab. Regulaors | nos. | 5 | 125 |  | KISH/PW-21 | New | 12
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Rehabilitation of existing Regulator 4 vent | nos. | 1 | 19.43 |  | NETR/PW-06 | New | 12
BWDB/Kish/HFMLIP/PW-28 WMG Office Building | Const. of WMG Training Office at Kishoregonj, Netrokona, Sunamgonj & Hobigonj district. | nos. | 60 | 1150 |  | KISH/PW-28 | New | 13

## DPP_Cost
Item Name | Unit | Quantity | Amount(Total) | Amount(Gob) | Amount(RPA)
Construction of Irrigation Inlet (New Haors) | nos | 130 | 1311.64 | 183.6296 | 1128.0104 | D1
Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | nos | 2 | 449.12 | 62.8768 | 386.2432 | D2
Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | nos | 122 | 19235.4 | 2692.956 | 16542.444 | D3
Re-excavation of Khal/River (New Haors) (Earth Volume: 76.42 Lakh cum) | km | 338.811 | 9938.2 | 1391.348 | 8546.852 | D4
Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 20.12 Lakh cum) | km | 84.94 | 2945.58 | 412.3812 | 2533.1988 | D5
Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) | km | 72.67 | 1782.96 | 249.6144 | 1533.3456 | D6
Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 6.44 lakh cum) | Km | 54.712 | 1412.41 | 197.7374 | 1214.6726 | D7
Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km | 243.551 | 10822.56 | 1515.1584 | 9307.4016 | D8
Rehabilitation of Regulator (New Haors) | nos | 7 | 154.12 | 21.5768 | 132.5432 | D9
Embankment Slope Protection Work | km | 0 | 0 | 0 | 0 | D10
Construction of Threshing Floor | nos | 0 | 0 | 0 | 0 | D11
Construction of WMG Office | nos | 60 | 2400 | 336 | 2064 | D12
Total |  |  | 50451.99 | 7063.2786 | 43388.7114

## Haor List
Code | Haor Name | District | Type
28 | Chandal Beel Sub-Project | Brahaman baria | Rehab
29 | Satdona Beel Scheme | Brahaman baria | Rehab
10 | Mokhar Haor Sub-Project | Habiganj | New
19 | Koirdahla Ratna Sub-Project | Habiganj | Rehab
20 | Guingajuri Sub-Project | Habiganj | Rehab
21 | Aralia Khal Sub-Project | Habiganj | Rehab
22 | Bashira River Re-excavation Sub-Project | Habiganj | Rehab
1 | Chandpur Haor Sub-Project | Kishoreganj | New
2 | Nunnir Haor Sub-Project | Kishoreganj | New
3 | Boro Haor Sub-Project | Kishoreganj | New
4 | Noapara Haor Sub-Project | Kishoreganj | New
5 | Naogaon Haor Sub-Project | Kishoreganj | New
6 | Badla Haor Sub-Project | Kishoreganj | New
7 | Chatal Haor Sub-Project | Kishoreganj | New
15 | Alalia-Bahadia Sub-Project | Kishoreganj | Rehab
16 | Modkhola-Bairagir Char Sub-Project | Kishoreganj | Rehab
17 | Ganakkhali Sub-Project | Kishoreganj | Rehab
8 | Dakhshiner Haor Sub-Project | Kishoreganj & Habiganj | New
9 | Suniar Haor Sub-Project | Kishoreganj & Netrokona | New
18 | Boraikhali Khal Sub-Project | Kishoreganj Mymensingh | Rehab
11 | Ganesh Haor Sub-Project | Netrokona | New
23 | Dampara Water Management Scheme | Netrokona | Rehab
24 | Kangsha River Scheme | Netrokona | Rehab
25 | Singer Beel Sub-Project | Netrokona | Rehab
26 | Khaliajuri FCD Polder-2 | Netrokona | Rehab
27 | Khaliajuri FCD Polder-4 | Netrokona | Rehab
13 | Jaliar Haor Sub-Project | Sunamganj | New
14 | Dhakua Haor Sub-Project | Sunamganj | New
12 | Dharmapasha Rui Beel Sub-Project | Sunamganj &Netrokona | New

## Sheet2
25.44 | 0.81696 | 979.38 | 800.1101
5.7 | 0.18304 | 979.38 | 179.2699
31.14 |  |  | 979.38
4 | 0.30769 | 33.69 | 10.3662
9 | 0.69231 | 33.69 | 23.3238

## Habigonj
Package No./Name of Haor | Date of Invitation for Tender | Date of Signing Contract | Date of Commence-ment as per Contract | Date of Complection as per Contract | Component | Unit | Qnty | Cost | Time Extention required period (If any) | Actual/ Tentative date of Complection | Required contract variation cost component wise (if any) | Component | Unit | Qnty | Cost | Remarks | Package | Haor Type | Structure Code
BWDB/Hobi/HFMLIP/PW-01 Bashira River | 1 |  |  |  | (a) Re-Inatallation of Reguator((one no. 2 vent 1.50mx1.80m ) | nos. | 1 | 153.89 |  |  |  | (a) Re-Inatallation of Reguator((one no. 2 vent 1.50mx1.80m ) | nos. | 1 | 27.05 | Need rehabilitation of existing 3-vent regulator instead of reinstallation of 2-vent regulator. | HOBI/PW-01 | Rehab | 2
BWDB/Hobi/HFMLIP/PW-01 Bashira River | 2 |  |  |  |  | nos. | 0 | 0 |  |  |  | Irrigation Inlet | nos. | 3 | 30 |  | HOBI/PW-01 |  | 1
BWDB/Hobi/HFMLIP/PW-01 Bashira River | 3 |  |  |  | (B) Causeway (one no. 4.0m wide). | nos. | 1 | 232.27 |  |  |  | (B) Causeway (one no. 6.0m wide). | nos. | 1 | 300 | Need 6.0 m causeway instead of 4.0 m causeway. | HOBI/PW-01 | Rehab | 5
BWDB/Hobi/HFMLIP/PW-01 Bashira River | 4 |  |  |  | Re-excavation of Khal/River (Rehab. Khal 2.295 km & River 17.40 km) | Km | 19.695 | 842.501 |  |  |  | Re-excavation of Khal/River (Rehab. Khal 2.295 km & River 17.40 km) | Km | 19.695 | 857.32 |  | HOBI/PW-01 | Rehab | 8
BWDB/Hobi/HFMLIP/PW-01 Bashira River | 5 |  |  |  | Rehab. of submersible Embankment (Re-section 7.00 Km & Const. 7.00 Km) | Km | 14 | 317.77 |  |  |  | Rehab. of submersible Embankment (Re-section 7.00 Km & Const. 7.00 Km) | Km | 16.76 | 317.77 | 2.40 Km length will be increased. | HOBI/PW-01 | Rehab | 10
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | 6 |  |  |  | Construction of Causeway for Aralia (4 m). | nos. | 1 | 168.36 |  |  |  | Construction of Causeway for Aralia (46m). | nos. | 2 | 570 | 1 no. additional 4 m width Causeway will be needed. | HOBI/PW-02 | Rehab | 5
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | 7 |  |  |  | Re-excavation of Khal (Rehab. Kairdhala & Aralia Beel ) | Km | 65.2 | 221.64 |  |  |  | Re-excavation of Khal (Rehab. Kairdhala & Aralia Beel ) | Km | 3.312 | 54.82 |  | HOBI/PW-02 | Rehab | 8
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | 8 |  |  |  |  | nos. | 0 | 0 |  |  |  | Const of Box Drainage Outlet | nos. | 2 | 90 |  | HOBI/PW-02 | Rehab | 4
BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | 9 |  |  |  | Rehab. of submersible Embankment (Re-section Kairadhala-16.02 km & Aralia-14.124 km and Const. Aralia-8.36 km) | Km | 38.504 | 965.47 |  |  |  | Rehab. of submersible Embankment (Re-section Kairadhala-16.02 km & Aralia-14.124 km and Const. Aralia-8.36 km) | Km | 32.952 | 894.64 | Length of embkt. will be increased by 1.50 m. | HOBI/PW-02 | Rehab | 10
BWDB/Hobi/HFMLIP/PW-04 Mokhar Haor | 10 |  |  |  | Const. of Submersible Embankment | Km | 23.815 | 1161.49 |  |  |  | Const. of Submersible Embankment | Km | 23.815 | 1161.49 | Concerned XEN proposed to raise the height of embkt. | HOBI/PW-04 | New | 11
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | 11 |  |  |  | Const. of New Regulator 4 vent (1.50 mx1.80m) | nos. | 1 | 463.84 |  |  |  | Const. of New Regulator 4 vent (1.50 mx1.80m) | nos. | 1 | 463.84 |  | HOBI/PW-05 | New | 3
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | 12 |  |  |  | Const. of New Regulator 1 vent (1.50 mx1.80m) | nos. | 5 | 579.8 |  |  |  | Const. of New Regulator 1 vent (1.50 mx1.80m) | nos. | 4 | 460 |  | HOBI/PW-05 | New | 3
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | 13 |  |  |  | Const. of New Regulator 2 vent (1.50 mx1.80m) | nos. | 1 | 231.95 |  |  |  | Const. of New Regulator 2 vent (1.50 mx1.80m) | nos. | 1 | 231.95 |  | HOBI/PW-05 | New | 3
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | 14 |  |  |  |  | nos. | [5 empty] | 4m Causeway | nos. | 1 | 125 |  |  |  | 5 | 1280.79
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | 15 |  |  |  | Const. of Irrigation Inlet | nos. | 15 | 134 |  |  |  | Const. of Irrigation Inlet | nos. | 15 | 134 |  | HOBI/PW-06 |  | 1
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | 16 |  |  |  | Const. of Box Drainage Outlet | nos. | 9 | 550 |  |  |  | Const. of Box Drainage Outlet | nos. | 9 | 550 |  | HOBI/PW-06 | New | 4
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | 17 |  |  |  | Const. of 4.0m wide Causeway | nos. | 2 | 366.4 |  |  |  | Const. of 4.0m wide Causeway | nos. | 2 | 366.4 | Size of pitching block will be enhanced. | HOBI/PW-06 | New | 5
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | 18 |  |  |  | Const. of 6.0m wide Causeway | nos. | 2 | 549.6 |  |  |  | Const. of 6.0m wide Causeway | nos. | 2 | 549.6 |  | HOBI/PW-06 | New | 5
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | 19 |  |  |  | Re-excavation of Khal (New Haor) | Km | 24.619 | 606.84 |  |  |  | Re-excavation of Khal (New Haor) | Km | 18.048 | 500.96 |  | HOBI/PW-07 | New | 7
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | 20 |  |  |  | Re-excavation of River (New Haor) | Km | 1554 | 319.92 |  |  |  | Re-excavation of River (New Haor) | Km | 12.01 | 290 |  | HOBI/PW-07 | New | 7
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | 21 |  |  |  | Rehab Regulator | nos. | 0 | 0 |  |  |  | Rehablitation of Regulator (New Haor) | nos. | 1 | 9.69 |  | HOBI/PW-07 | New | 12

## Netrokona
Package No./Name of Haor | Date of Invitation for Tender | Date of Signing Contract | Date of Commence-ment as per Contract | Date of Complection as per Contract | Component | Unit | Qnty | Cost | Time Extention required period (If any) | Actual/ Tentative date of Complection | Required contract variation cost component wise (if any) | Component | Unit | Qnty | Cost | Remarks | Package | Haor Type | Structure Code
BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) |  |  |  |  | Re-Sectioning of Full Embankment (Dampara-35.828+Singer Beel-10.69) | Km | 46.21 | 1362.53 |  |  |  | Re-Sectioning of Full Embankment (Dampara-35.828+Singer Beel-10.69) | Km | 46.21 | 1162.53 |  | NETR/PW-01 | Rehab | 9
BWDB/Netra/HFMLIP/PW-02 Damara, Kangsha & Singer Beel |  |  |  |  | Re-Excavation of Khal (Rehab.) (a) Damapara Water Management Project.(13.27 Km) (b) Kangsha River Scheme (30.98 Km) (c) Singer Beel Scheme (6.133 Km) | Km | 50.383 | 956.73 |  |  |  | Re-Excavation of Khal (Rehab.) (a) Damapara Water Management Project.(13.27 Km) (b) Kangsha River Scheme (30.98 Km) (c) Singer Beel Scheme (6.133 Km) | Km | 50.383 | 815 |  | NETR/PW-02 | Rehab | 8
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel |  |  |  |  | Re-Installation of Regulator 5 vent (1.50mx1.80m, Dampara) | nos. | 1 | 389.57 |  |  |  | Re-Installation of Regulator 5 vent (1.50mx1.80m, Dampara) | nos. | 1 | 389.57 |  | NETR/PW-03 | Rehab | 2
BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel |  |  |  |  | (a) Re-Sectioning of Full Embankment (Kangsha)- 20.90 km. (b) Re-Sectioning of Submersible Embankment (Singer beel)- 3.56 Km. | Km | 24.46 | 557.3 |  |  |  | (a) Re-Sectioning of Full Embankment (Kangsha)- 20.90 km. (b) Re-Sectioning of Submersible Embankment (Singer beel)- 3.56 Km. | Km | 24.46 | 610.43 |  | NETR/PW-03 | Rehab | 9
BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 |  |  |  |  | Re-excavation of Khal (Rehab.) (including 4.925 km river dredging) | Km | 24.033 | 1113.44 |  |  |  | Re-excavation of Khal (Rehab.) (including 4.925 km river dredging) | Km | 24.0.33 | 963.44 |  | NETR/PW-04 | Rehab | 8
BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 |  |  |  |  | Re-Sectioning of Submersible Embankment | Km | 9.75 | 413.43 |  |  |  | Re-Sectioning of Submersible Embankment | Km | 5 | 200 | Not need for re-sectioning of 7.75 Km embkt. | NETR/PW-04 | Rehab | 10
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor |  |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 3 | 725.48 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 2 | 600 |  | NETR/PW-05 | New | 3
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor |  |  |  |  | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 406.65 |  |  |  | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 406.65 |  | NETR/PW-05 | New | 3
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor |  |  |  |  | Const. of Submersible Embankment | Km | 3.071 | 57.25 |  |  |  | Const. of Submersible Embankment | Km | 3.071 | 57.25 |  | NETR/PW-05 | New | 11
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor |  |  |  |  | Const. of Irrigation Inlet | nos. | 2 | 85.01 |  |  |  | Const. of Irrigation Inlet | nos. | 2 | 85.01 |  | NETR/PW-06 | New | 1
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor |  |  |  |  | Const. of Box Drainage Outlet | nos. | 2 | 16.92 |  |  |  | Const. of Box Drainage Outlet | nos. | 2 | 16.92 |  | NETR/PW-06 | New | 4
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor |  |  |  |  | Re-excavation of Khal (New) | Km | 11.996 | 528.98 |  |  |  | Re-excavation of Khal (New) | Km | 11.996 | 450 |  | NETR/PW-06 | New | 7
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor |  |  |  |  | Rehabilitation of existing Regulator 4 vent | nos. | 1 | 19.43 |  |  |  | Rehabilitation of existing Regulator 4 vent | nos. | 1 | 19.43 |  | NETR/PW-06 | New | 12
BWDB/Netra/HFMLIP/PW-07 Dharmapasah Rui Beel |  |  |  |  | Re-excavation of River (Lower Kongsha River 15.00 km & Gunai River 11.44 Km) | Km | 24 | 906.38 |  |  |  | Re-excavation of River (Lower Kongsha River 15.00 km & Gunai River 11.44 Km) | Km | 21.44 | 906.38 |  | NETR/PW-07 | New | 7
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel |  |  |  |  | Const. of Irrigation Inlet | nos. | 3 | 35.17 |  |  |  | Const. of Irrigation Inlet | nos. | 3 | 37 |  | NETR/PW-08 | New | 1
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel |  |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 558.88 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 513 |  | NETR/PW-08 | New | 3
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel |  |  |  |  | Const. of Box Drainage Outlet | nos. | 5 | 307.66 |  |  |  | Const. of Box Drainage Outlet | nos. | 5 | 300 |  | NETR/PW-08 | New | 4
BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel |  |  |  |  | Const. of Submersible Embankment | Km | 1 | 33 |  |  |  | Const. of Submersible Embankment | Km | 0 | 0 |  | NETR/PW-08 | New | 11

## Sunamgonj
Package No./Name of Haor | Date of Invitation for Tender | Date of Signing Contract | Date of Commence-ment as per Contract | Date of Complection as per Contract | Component | Unit | Qnty | Cost | Time Extention required period (If any) | Actual/ Tentative date of Complection | Required contract variation cost component wise (if any) | Component | Unit | Qnty | Cost | Remarks | Package | Haor Type | Structure Code
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | 1 |  |  |  | Const. of Irrigation Inlet | nos. | 9 | 95.91 |  |  |  | Const. of Irrigation Inlet | nos. | 9 | 95.91 |  | SUNM/PW-01 | New | 1
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | 2 |  |  |  | Const. of Box Drainage Outlet | nos. | 7 | 315.62 |  |  |  | Const. of Box Drainage Outlet | nos. | 7 | 315.62 |  | SUNM/PW-01 | New | 4
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | 3 |  |  |  | Re-excavation of Khal (New Haor)(4 Nos. Khal) | Km | 7.678 | 268.41 |  |  |  | Re-excavation of Khal (New Haor)(4 Nos. Khal) | Km | 13.928 | 478.84 | Need more 6 nos. Khal for re-excavation extra cost will remain same. | SUNM/PW-01 | New | 7
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | 4 |  |  |  | Const. of Submersible Embankment | Km | 33.849 | 884.27 |  |  |  | Const. of Submersible Embankment | Km | 16.54 | 672.2 | XEN reported that no need 17.34 km embkt. | SUNM/PW-01 | New | 11
BWDB/Sunam/HFMLIP/PW-02 Dhakua Haor (Divn-2) | 5 |  |  |  | Re-excavation of River (New Haor) (Piain River) | Km | 36.575 | 1193.75 |  |  |  | Re-excavation of River (New Haor) (Piain River) | Km | 36.575 | 1193.75 |  | SUNM/PW-02 | New | 7
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | 6 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 177.84 |  |  |  | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 177.84 |  | SUNM/PW-03 | New | 3
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | 7 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 355.67 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 355.67 |  | SUNM/PW-03 | New | 3
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | 8 |  |  |  | Const. of 4.0 m width Causeway | nos. | 5 | 775.65 |  |  |  | Const. of 4.0 m width Causeway | nos. | 5 | 775.65 |  | SUNM/PW-03 | New | 5
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | 9 |  |  |  | Const. of 6.0 m width Causeway | nos. | 1 | 232.7 |  |  |  | Const. of 6.0 m width Causeway | nos. | 1 | 232.7 |  | SUNM/PW-03 | New | 5
BWDB/Sunam/HFMLIP/PW-04 Dharmapasha Rui Bill Haor (Divn-1) | 10 |  |  |  | Const. of Submersible Embankment | Km | 34.94 | 1564.32 |  |  |  | Const. of Submersible Embankment | Km | 34.94 | 1564.32 |  | SUNM/PW-04 | New | 11
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | 11 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 235 |  |  |  | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 267.87 |  | SUNM/PW-05 | New | 3
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | 12 |  |  |  | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 330 |  |  |  | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 299.81 |  | SUNM/PW-05 | New | 3
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | 13 |  |  |  | Const. of 6.0 m width Causeway | nos. | 1 | 190 |  |  |  | Const. of 6.0 m width Causeway | nos. | 1 | 232.06 |  | SUNM/PW-05 | New | 5
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | 14 |  |  |  | Const. of 4.0 m width Causeway | nos. | 5 | 665 |  |  |  | Const. of 4.0 m width Causeway | nos. | 3 | 707.91 |  | SUNM/PW-05 | New | 5
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | 15 |  |  |  | Const. of Irrigation Inlet | nos. | 12 | 131.28 |  |  |  | Const. of Irrigation Inlet | nos. | 12 | 131.28 |  | SUNM/PW-06 | New | 1
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | 16 |  |  |  | Const. of Box Drainage Outlet | nos. | 1 | 45.13 |  |  |  | Const. of Box Drainage Outlet | nos. | 1 | 45.13 |  | SUNM/PW-06 | New | 4
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | 17 |  |  |  | Re-excavation of Khal (New Haor) | Km | 70 | 1402.17 |  |  |  | Re-excavation of Khal (New Haor) | Km | 66.043 | 1402.17 |  | SUNM/PW-06 | New | 7