## Input_sheet
| Package Name | Component | Unit | Qnty | Cost | Remarks | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code
0 | BWDB/Brah/HFMLIP/PW-01 | Regulator Rehablitation | nos | 2 | 87.5 | 0 | BRAH/PW-01 | New | 16 | 0 | R-14 | BRAH
1 | BWDB/Brah/HFMLIP/PW-01 | Regulator Rehablitation | nos | 2 | 87.5 | 0 | BRAH/PW-01 | New | 16 | 0 | R-15 | BRAH
2 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Rehablitation of Submersible Embankment | Km | 0 | 0 | 0 | HOBI/PW-01 | 0 | 1 | 0 | R-8 | HOBI
3 | BWDB/Hobi/HFMLIP/PW-01 Bashira River |  | nos. | 1 | 27.05 | Need rehabilitation of existing 3-vent regulator instead of reinstallation of 2-vent regulator. | HOBI/PW-01 | Rehab | 2 |  | R-8 | HOBI
4 | BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Construction of Causeway for Aralia (4&6m). | nos. | 1 | 300 | Need 6.0 m causeway instead of 4.0 m causeway. | HOBI/PW-01 | Rehab | 2 | 0 | R-8 | HOBI
5 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of Irrigation Inlet | Km | 19.695 | 857.52 | 0 | HOBI/PW-01 | Rehab | 8 | 664867.22 | R-8 | HOBI
6 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of 4.0m wide Causeway | Km | 16.76 | 385.43 | 2.40 Km length will be increased. | HOBI/PW-01 | Rehab | 10 | 127061.11 | R-8 | HOBI
7 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Re-excavation of Khal/River (Rehab. Khal 2.295 km & River 17.40 km) | nos. | 2 | 456 | 1 no. additional 4 m width Causeway will be needed. | HOBI/PW-02 | Rehab | 2 | 0 | R-7 | HOBI
8 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Replacement of Reg. Gates & other related works | nos. | 0 | 0 | 0 | HOBI/PW-02 | Rehab | 4 | 0 | R-7 | HOBI
9 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | 4m Causeway | Km | 3.312 | 54.82 | 0 | HOBI/PW-02 | Rehab | 8 | 124772.75 | R-7 | HOBI
10 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of Box Drainage Outlet | Km | 26.952 | 825.18 | Length of embkt. will be increased by 1.50 m. | HOBI/PW-02 | Rehab | 10 | 408978.43 | R-7 | HOBI
11 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Const. of 6.0m wide Causeway | km | 5.64 | 154.82 | Length of embkt. will be increased by 1.50 m. | HOBI/PW-02 | Rehab | 10 | 0 | R-8 | HOBI
12 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Regulator Gate repair | Nos | 4 | 13.77 | 0 | HOBI/PW-02 | 0 | 16 | 0 | R-7 | HOBI
13 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-hab of Regulator | Nos | 9 | 21.23 | 0 | HOBI/PW-02 | 0 | 16 | 0 | R-5 | HOBI
14 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-excavation of Khal (New Haor) | Km | 23.815 | 1161.49 | Concerned XEN proposed to raise the height of embkt. | HOBI/PW-04 | New | 11 | 256912.018 | N-10 | HOBI
15 | BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Const of Box Drainage Outlet | nos. | 1 | 400 | 0 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
16 | BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Re-excavation of Khal (Rehab. Kairdhala & Aralia Beel ) | nos. | 4 | 460 | 0 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
17 | BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Rehab. of submersible Embankment (Re-section Kairadhala-16.02 km & Aralia-14.124 km and Const. Aralia-8.36 km) | nos. | 1 | 231.95 | 0 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
18 | BWDB/Hobi/HFMLIP/PW-02 Aralia Khal | Replacement of Reg. Gates & other related works | nos. | 1 | 125 | 0 | HOBI/PW-05 | New | 5 | 0 | N-10 | HOBI
19 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | (a) Re-Inatallation of Reguator((one no.32 vent 1.50mx1.80m ) | nos. | 15 | 134 | 0 | HOBI/PW-06 | New | 1 | 0 | N-10 | HOBI
20 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Rehab. of submersible Embankment ( Aralia-22.484 km) | nos. | 9 | 540 | 0 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
21 | BWDB/Hobi/HFMLIP/PW-04 Mokhar Haor | Const. of Submersible Embankment | nos. | 2 | 356.4 | Size of pitching block will be enhanced. | HOBI/PW-06 | New | 5 | 0 | N-10 | HOBI
22 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 4 vent (1.50 mx1.80m) | nos. | 2 | 529.6 | 0 | HOBI/PW-06 | New | 5 | 0 | N-10 | HOBI
23 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 1 vent (1.50 mx1.80m) | Km | 18.048 | 606.84 | 0 | HOBI/PW-07 | New | 7 | 403996.842 | N-10 | HOBI
24 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Const. of New Regulator 2 vent (1.50 mx1.80m) | Km | 12.01 | 319.92 | 0 | HOBI/PW-07 | New | 7 | 208662.994 | N-10 | HOBI
25 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Re-excavation of River (New Haor) | nos. | 1 | 9.69 | 0 | HOBI/PW-07 | New | 12 | 0 | N-10 | HOBI
26 | BWDB/Hobi/HFMLIP/PW-07 | O&M During Construction | LS | 0 | 0 | 0 | HOBI/PW-08 | New | 17 | 0 | A-1 | HOBI
27 | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Rehab. Regulaors | Km | 1.22 | 52.46 | 0 | KISH/PW-01 | Rehab | 8 | 304227.48 | R-1 | KISH
28 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Irrigation Inlet | Km | 2.151 | 92.47 | 0 | KISH/PW-01 | Rehab | 8 | 304227.48 | R-2 | KISH
29 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Box Drainge Outlet | Km | 8.18 | 351.62 | 0 | KISH/PW-01 | Rehab | 8 | 304227.48 | R-3 | KISH
30 | BWDB/Kish/HFMLIP/PW-32 Dakshiner Haor | Construction of Submersible Embankment with Slope/Crest Protection work Dak Type-A 0.235 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 6 | 25.64 | 0 | KISH/PW-01 | Rehab | 16 | 0 | R-4 | KISH
31 | BWDB/Kish/HFMLIP/PW-32 Naogaon Haor | Construction of Submersible Embankment with Slope/Crest Protection work Dak Type-A 0.235 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 2 | 8.55 | 0 | KISH/PW-01 | Rehab | 16 | 0 | R-3 | KISH
32 | BWDB/Kish/HFMLIP/PW-32 Noapara Haor | Construction of Submersible Embankment with Slope/Crest Protection work Dak Type-A 0.235 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 3 | 12.81 | 0 | KISH/PW-01 | Rehab | 16 | 0 | R-2 | KISH
33 | BWDB/Kish/HFMLIP/PW-32 Nunnir Haor | Construction of Submersible Embankment with Slope/Crest Protection work Dak Type-A 0.235 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 2 | 8.55 | 0 | KISH/PW-01 | Rehab | 16 | 0 | R-1 | KISH
34 | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 124.01 | 0 | KISH/PW-02 | New | 3 | 0 | N-1 | KISH
35 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | Km | 11.095 | 210.4 | 0 | KISH/PW-02 | New | 7 | 211770.02 | N-1 | KISH
36 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of 4.0 m width Causeway | Km | 0.315 | 15.59 | 0 | KISH/PW-02 | New | 11 | 2953 | N-1 | KISH
37 | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | Re-excavation of Khal (New Haor) | nos. | 1 | 155.52 | 0 | KISH/PW-03 | New | 3 | 0 | N-2 | KISH
38 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Re-excavation of Khal (New Haor) | Km | 10.383 | 554.48 | 0 | KISH/PW-03 | New | 11 | 109104.8 | N-2 | KISH
39 | BWDB/Kish/HFMLIP/PW-02 Chandpur Haor | C onst. of Submersible Embankment | nos. | 2 | 198 | 0 | KISH/PW-04 | New | 3 | 0 | N-2 | KISH
40 | BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 256 | 0 | KISH/PW-04 | New | 3 | 0 | N-2 | KISH
41 | BWDB/Kish/HFMLIP/PW-22 Badla Haor | Const. of Submersible Embankment | Km | 6.471 | 266 | 0 | KISH/PW-04 | New | 11 | 50421.04 | N-2 | KISH
42 | BWDB/Kish/HFMLIP/PW-03 Nunnir Haor (Part-A) | Const. of Submersible Embankment | nos. | 1 | 220 | 0 | KISH/PW-05 | New | 3 | 0 | N-2 | KISH
43 | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Irrigation Inlet | Km | 12.214 | 580 | 0 | KISH/PW-05 | New | 11 | 98770 | N-2 | KISH
44 | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 222 | 0 | KISH/PW-06 | New | 3 | 0 | N-2 | KISH
45 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | Km | 20 | 618 | 0 | KISH/PW-06 | New | 7 | 577707.02 | N-2 | KISH
46 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | Km | 25.7 | 680 | 0 | KISH/PW-07 | New | 7 | 945139.04 | N-3 | KISH
47 | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Box Drainge Outlet | Km | 0.8 | 23 | 0 | KISH/PW-07 | New | 11 | 12696 | N-3 | KISH
48 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 70 | 0 | KISH/PW-09 | New | 4 | 0 | N-2 | KISH
49 | BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of 6.00 m causeway | nos. | 1 | 237.5 | 0 | KISH/PW-09 | New | 5 | 0 | N-2 | KISH
50 | BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 170 | Regulators are converted to causeway. | KISH/PW-09 | New | 5 | 0 | N-3 | KISH
51 | BWDB/Kish/HFMLIP/PW-16 Noagaon Haor (Part-B) | Const. of Submersible Embankment | nos. | 1 | 237.5 | 0 | KISH/PW-09 | New | 5 | 0 | N-3 | KISH
52 | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 150 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 3 | 0 | N-4 | KISH
53 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 243 | 1 vent regulator at Gazipur convedrted by 6.00 m causeway. | KISH/PW-10 | New | 5 | 0 | N-4 | KISH
54 | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Re-excavation of Khal (New Haor) | Km | 11.98 | 618 | 0 | KISH/PW-10 | New | 11 | 121988 | N-4 | KISH
55 | BWDB/Kish/HFMLIP/PW-04 Nunnir Haor (Part B&C) | Const. of Submersible Embankment | nos. | 1 | 326.37 | 0 | KISH/PW-11 | New | 3 | 0 | N-4 | KISH
56 | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Const. of Submersible Embankment | Km | 10.86 | 558 | 0 | KISH/PW-11 | New | 11 | 109155.3 | N-4 | KISH
57 | BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 227.49 | 0 | KISH/PW-12 | New | 3 | 0 | N-4 | KISH
58 | BWDB/Kish/HFMLIP/PW-05 Nuunir Haor (Part A&C) | Const. of Submersible Embankment | nos. | 1 | 303.33 | 0 | KISH/PW-12 | New | 3 | 0 | N-4 | KISH
59 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of Box Drainge Outlet | Km | 6.857 | 260 | 0 | KISH/PW-12 | New | 7 | 371757.99 | N-4 | KISH
60 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 235 | 0 | KISH/PW-13 | New | 3 | 0 | N-5 | KISH
61 | BWDB/Kish/HFMLIP/PW-06 Nunnir Haor (Part-A) | Re-excavation of Khal (New Haor) | nos. | 1 | 175 | 0 | KISH/PW-13 | New | 3 | 0 | N-5 | KISH
62 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Irrigation Inlet | Km | 10 | 490 | 0 | KISH/PW-13 | New | 11 | 215922 | N-5 | KISH
63 | BWDB/Kish/HFMLIP/PW-07 Boro Haor | Re-excavation of Khal | nos. | 1 | 219.6 | 0 | KISH/PW-14 | New | 3 | 0 | N-5 | KISH
64 | BWDB/Kish/HFMLIP/PW-07 Boro Haor | Const. of Submersible Embankment | nos. | 0 | 0 | 0 | KISH/PW-14 | New | 3 | 0 | N-5 | KISH
65 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of New Regulators 5 vent (1.50mx1.80m) | Km | 16.9 | 705.4 | 0 | KISH/PW-14 | New | 11 | 194853 | N-5 | KISH
66 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Box Drainge Outlet | nos. | 0 | 0 | Regulator c onverted by 6.00 m causeway | KISH/PW-15 | New | 5 | 0 | N-5 | KISH
67 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of Box Drainge Outlet | Km | 9 | 600 | 0 | KISH/PW-15 | New | 11 | 133316.13 | N-5 | KISH
68 | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Construction of Box Drainnage Outlet | nos. | 1 | 404.5 | 0 | KISH/PW-16 | New | 3 | 0 | N-5 | KISH
69 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 6.0 m width Causeway | Km | 14.12 | 531.3 | 0 | KISH/PW-16 | New | 11 | 143610.85 | N-5 | KISH
70 | PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 25 | 274.32 | 0 | KISH/PW-17 | New | 1 | 0 | N-5 | KISH
71 | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 6 m width | nos. | 1 | 675 | 0 | KISH/PW-17 | New | 3 | 0 | N-5 | KISH
72 | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 4 m width | nos. | 1 | 115.24 | 0 | KISH/PW-17 | New | 3 | 0 | N-5 | KISH
73 | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 5 | 177.44 | 0 | KISH/PW-17 | New | 4 | 0 | N-5 | KISH
74 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Const. of 4.0 m width Causeway | Km | 13.17 | 561 | 0 | KISH/PW-17 | New | 11 | 202851.03 | N-5 | KISH
75 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Submersible Embankment | nos. | 1 | 537 | 0 | KISH/PW-18 | New | 5 | 0 | N-5 | KISH
76 | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 4.0 m width Causeway | nos. | 1 | 445 | 0 | KISH/PW-18 | New | 5 | 0 | N-5 | KISH
77 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | Km | 26.035 | 615 | 0 | KISH/PW-18 | New | 7 | 453822.6 | N-5 | KISH
78 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | Km | 22.933 | 1065 | 0 | KISH/PW-19 | New | 7 | 577753.68 | N-5 | KISH
79 | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | nos. | 16 | 160 | 0 | KISH/PW-20 | New | 1 | 0 | N-2 | KISH
80 | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | nos. | 3 | 30 | 0 | KISH/PW-20 | New | 1 | 0 | N-3 | KISH
81 | PW-01 4 Nos. Rehabilitation Haor | Re-excavation of Khal (Rehab) | nos. | 9 | 90 | 0 | KISH/PW-20 | New | 1 | 0 | N-4 | KISH
82 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 3 | 128.25 | 0 | KISH/PW-20 | New | 4 | 0 | N-2 | KISH
83 | BWDB/Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Khal (New) | nos. | 0 | 0 | 0 | KISH/PW-20 | New | 4 | 0 | N-3 | KISH
84 | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 42.75 | 0 | KISH/PW-20 | New | 4 | 0 | N-4 | KISH
85 | BWDB/Kish/HFMLIP/PW-15 Naogaon Haor (Part-B) | Const. of Submersible Embankment | nos. | 1 | 178 | 0 | KISH/PW-20 | New | 5 | 0 | N-2 | KISH
86 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of Irrigation Inlet | nos. | 2 | 356 | 0 | KISH/PW-20 | New | 5 | 0 | N-3 | KISH
87 | BWDB/Kish/HFMLIP/PW-17 Naogaon Haor (Part-B) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 178 | 0 | KISH/PW-20 | New | 5 | 0 | N-4 | KISH
88 | BWDB/Kish/HFMLIP/PW-09 Boro Haor | Const. of New Causeway 6 m width | nos. | 1 | 225 | 0 | KISH/PW-21 | New | 3 | 0 | N-6 | KISH
89 | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | 1 No. Regulator 1-vent (1.5mx1.80m) | nos. | 1 | 160 | 0 | KISH/PW-21 | New | 3 | 0 | N-6 | KISH
90 | BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 1 vent (1.50mx1.80m) | Km | 10 | 463.48 | 0 | KISH/PW-21 | New | 11 | 121065.93 | N-6 | KISH
91 | BWDB/Kish/HFMLIP/PW-29 O&M During Construction | O&M During Construction | nos. | 5 | 125 | 0 | KISH/PW-21 | New | 12 | 0 | N-6 | KISH
92 | PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 6 | 73 | 0 | KISH/PW-22 | New | 1 | 0 | N-6 | KISH
93 | BWDB/Kish/HFMLIP/PW-13 Naogaon Haor (Part-A) | Const. of Submersible Embankment | nos. | 3 | 116 | 0 | KISH/PW-22 | New | 4 | 0 | N-6 | KISH
94 | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Const. of 6.m width Causeway | nos. | 1 | 195 | 0 | KISH/PW-22 | New | 5 | 0 | N-6 | KISH
95 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. of 4.0 m width Causeway | Km | 9.92 | 210 | 0 | KISH/PW-22 | New | 7 | 146641.43 | N-6 | KISH
96 | BWDB/Kish/HFMLIP/PW-27 | Const. of New Regulators 6 vent (1.50mx1.80m) | Km | 11 | 290 | 0 | KISH/PW-22 | New | 11 | 91984.7 | N-6 | KISH
97 | PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 4 | 47.87 | 0 | KISH/PW-23 | New | 1 | 0 | N-7 | KISH
98 | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of New 1 No. 6 m width Causeway | nos. | 2 | 640.67 | 0 | KISH/PW-23 | New | 3 | 0 | N-7 | KISH
99 | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 39.54 | 0 | KISH/PW-23 | New | 4 | 0 | N-7 | KISH
100 | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 2 vent (1.50mx1.80m) | Km | 1.925 | 32.63 | 0 | KISH/PW-23 | New | 7 | 23149.28 | N-7 | KISH
101 | BWDB/Kish/HFMLIP/PW-27 | Const. of Box Drainge Outlet | Km | 4.51 | 105.29 | 0 | KISH/PW-23 | New | 11 | 51688.691 | N-7 | KISH
102 | BWDB/Kish/HFMLIP/PW-27 | Const. of 6.0 m width Causeway | Km | 19.843 | 860 | 0 | KISH/PW-24 | New | 11 | 214238.2 | N-8 | KISH
103 | PW-01 4 Nos. Rehabilitation Haor | Replacement of Reg. Gates & other related works | nos. | 15 | 125 | 0 | KISH/PW-25 | New | 1 | 0 | N-8 | KISH
104 | BWDB/Kish/HFMLIP/PW-10 Noapara Haor | Const. of Submersible Embankment | nos. | 1 | 397 | 0 | KISH/PW-25 | New | 3 | 0 | N-8 | KISH
105 | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of New Regulators 3 vent (1.50mx1.80m) | nos. | 1 | 44 | 0 | KISH/PW-25 | New | 4 | 0 | N-8 | KISH
106 | BWDB/Kish/HFMLIP/PW-18 Naogaon Haor (Part-B) | Re-excavation of Khal (New Haor) | nos. | 1 | 265 | 0 | KISH/PW-25 | New | 5 | 0 | N-8 | KISH
107 | BWDB/Kish/HFMLIP/PW-19 Noagon Haor (Part-A) | Re-excavation of River by Dredger/ Mechanical (Berachapra 15.82 km + Ataplal 7.113 km) | nos. | 1 | 349 | 0 | KISH/PW-25 | New | 5 | 0 | N-8 | KISH
108 | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of New Regulators 1 vent (1.50mx1.80m) | Km | 11 | 420 | 0 | KISH/PW-25 | New | 7 | 342244.7 | N-8 | KISH
109 | BWDB/Kish/HFMLIP/PW-21 (Badla Haor) | Const. of Submersible Embankment | Km | 22.7 | 479 | 0 | KISH/PW-26 | New | 7 | 468821.04 | N-9 | KISH
110 | BWDB/Kish/HFMLIP/PW-28 WMG Office Building | Const. of WMG Training Office at Kishoregonj, Netrokona, Sunamgonj & Hobigonj district. | Km | 0.54 | 23 | 0 | KISH/PW-26 | New | 11 | 11787.77 | N-9 | KISH
111 | BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 2 | 314 | 0 | KISH/PW-27 | New | 3 | 0 | N-9 | KISH
112 | BWDB/Kish/HFMLIP/PW-11 Noapara Haor | Const. of Submersible Embankment | nos. | 0 | 0 | 0 | KISH/PW-27 | New | 3 | 0 | N-9 | KISH
113 | BWDB/Kish/HFMLIP/PW-14 Naogaon Haor (Part-A) | Const. of Submersible Embankment | nos. | 4 | 49 | 0 | KISH/PW-27 | New | 4 | 0 | N-9 | KISH
114 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 1 | 440 | 0 | KISH/PW-27 | New | 5 | 0 | N-9 | KISH
115 | BWDB/Kish/HFMLIP/PW-20 Nunni, Boro & Noapara Haor | Const. Irrigation Inlet | nos. | 1 | 160 | 0 | KISH/PW-27 | New | 5 | 0 | N-9 | KISH
116 | BWDB/Kish/HFMLIP/PW-31 Naogaon Haor Part -B Kishoreganj | Construction of Submersible Embankment with Slope/Crest Protection work (Type-A 0.73 km , Type-B 0.84 Km ,Type-D 1.200 Km & Fuse type -0.007 Km ) | nos. | 55 | 1618 | 0 | KISH/PW-28 | New | 15 | 0 | A-1 | KISH
117 | BWDB/Kish/HFMLIP/PW-33 Threshing Floor Construction | O&M During Construction | L.S. | 1 | 120 | 0 | KISH/PW-29 | New | 17 | 0 | A-1 | KISH
118 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.381 | 1548.66 | 0 | KISH/PW-30-Lot-01 | New | 11 | 0 | N-5 | KISH
119 | BWDB/Kish/HFMLIP/PW-25 Dakshiner Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.66 | 1404.81 | 0 | KISH/PW-30-Lot-02 | New | 11 | 0 | N-5 | KISH
120 | BWDB/Kish/HFMLIP/PW-26 Sonair Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.654 | 1803.66 | 0 | KISH/PW-31 | New | 11 | 0 | N-5 | KISH
121 | BWDB/Kish/HFMLIP/PW-23 Chatal Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.275 | 1743.01 | 0 | KISH/PW-32 | New | 11 | 0 | N-5 | KISH
122 | BWDB/Kish/HFMLIP/PW-33 Dakshiner Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 2.206 | 1392.29 | 0 | KISH/PW-33-Lot-1 | New | 11 | 0 | N-8 | KISH
123 | BWDB/Kish/HFMLIP/PW-33 Sonair Haor | Construction of Submersible Embankment with Slope Protection Work | Km | 1.545 | 1509.92 | 0 | KISH/PW-33-Lot-2 | New | 11 | 0 | N-8 | KISH
124 | BWDB/Kish/HFMLIP/PW-33 | Construction of Submersible Embankment with Slope Protection Work | Km | 3.15 | 0 | 0 | KISH/PW-33-Lot-2 | New | 11 | 0 | N-4 | KISH
125 | BWDB/Kish/HFMLIP/PW-33 | Construction of Submersible Embankment with Slope Protection Work | Km | 0.35 | 0 | 0 | KISH/PW-33-Lot-2 | New | 11 | 0 | N-2 | KISH
126 | BWDB/Kish/HFMLIP/PW-33 | Construction of Submersible Embankment with Slope Protection Work | Km | 0 | 0 | 0 | KISH/PW-33-Lot-2 | New | 11 | 0 | N-2 | KISH
127 | BWDB/Kish/HFMLIP/PW-34 | Construction of threshing floor | Nos | 5 | 225 | 0 | KISH/PW-34 | New | 14 | 0 | N-5 | KISH
128 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of New Regulators 1 vent (1.50mx1.80m) | Km | 10.69 | 345.15 | 0 | NETR/PW-01 | Rehab | 9 | 0 | R-11 | NETR
129 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of New Regulators 4 vent (1.50mx1.80m) | Km | 35.52 | 1137.85 | 0 | NETR/PW-01 | Rehab | 9 | 603554.12 | R-9 | NETR
130 | BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Replacement of Reg. Gates & other related works | Km | 30.98 | 507.2842 | 0 | NETR/PW-02 | Rehab | 8 | 914740.64 | R-10 | NETR
131 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-excavation of Khal (Rehab.) (including 4.925 km river dredging) | Km | 6.133 | 100.4252 | 0 | NETR/PW-02 | Rehab | 8 | 914740.64 | R-11 | NETR
132 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Replacement of Reg. Gates & other related works | Km | 13.27 | 217.2906 | 0 | NETR/PW-02 | Rehab | 8 | 914740.64 | R-9 | NETR
133 | BWDB/Netra/HFMLIP/PW-02 Damara, Kangsha & Singer Beel | Re-Excavation of Khal Project (b) Kangsha River Scheme (30.98 Km) | nos. | 1 | 389.57 | 0 | NETR/PW-03 | Rehab | 2 | 0 | R-9 | NETR
134 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Replacement of Reg. Gates & other related works | km | 20.9 | 552.43 | 0 | NETR/PW-03 | 0 | 9 | 312275.643 | R-10 | NETR
135 | BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const. of Submersible Embankment | Km | 3.56 | 68 | 0 | NETR/PW-03 | Rehab | 10 | 14852.987 | R-11 | NETR
136 | BWDB/Netra/HFMLIP/PW-07 Dharmapasah Rui Beel | Re-excavation of River (Lower Kongsha River 10.50 km & Gunai River 11.44 Km) | Nos | 16 | 40 | 0 | NETR/PW-03 | 0 | 16 | 0 | R-10 | NETR
137 | BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Irrigation Inlet | Nos | 6 | 15 | 0 | NETR/PW-03 | 0 | 16 | 0 | R-11 | NETR
138 | BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Submersible Embankment | Nos | 10 | 25 | 0 | NETR/PW-03 | 0 | 16 | 0 | R-9 | NETR
139 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-excavation of Khal (Rehab.) (including 4.925 km river dredging) | Km | 10.195 | 484.75 | 0 | NETR/PW-04 | Rehab | 8 | 792075.56 | R-12 | NETR
140 | BWDB/Netra/HFMLIP/PW-04 Khaliajuri Polder-2 & Polder-4 | Re-Sectioning of Submersible Embankment | Km | 13.838 | 680.25 | 0 | NETR/PW-04 | Rehab | 8 | 792075.56 | R-13 | NETR
141 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const. of Irrigation Inlet | Km | 9.75 | 315 | 0 | NETR/PW-04 | Rehab | 10 | 191943.37 | R-12 | NETR
142 | BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of New Regulators 2 vent (1.50mx1.80m) | Nos | 16 | 40 | 0 | NETR/PW-04 | 0 | 16 | 0 | R-12 | NETR
143 | BWDB/Netra/HFMLIP/PW-08 Dharmapasah Rui Beel | Const. of Box Drainage Outlet | Nos | 8 | 20 | 0 | NETR/PW-04 | 0 | 16 | 0 | R-13 | NETR
144 | BWDB/Netra/HFMLIP/PW-02 Damara, Kangsha & Singer Beel | Re-Excavation of Khal (Rehab.) (c) Singer Beel Scheme (6.133 Km) | nos. | 3 | 712.43 | 0 | NETR/PW-05 | New | 3 | 0 | N-11 | NETR
145 | BWDB/Netra/HFMLIP/PW-02 Damara, Kangsha & Singer Beel | Re-Excavation of Khal (Rehab.) (a) Damapara Water Management Project.(13.27 Km) | nos. | 1 | 439.67 | 0 | NETR/PW-05 | New | 3 | 0 | N-11 | NETR
146 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const. of Box Drainage Outlet | Km | 3.071 | 57.25 | 0 | NETR/PW-05 | New | 11 | 25797.655 | N-11 | NETR
147 | BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Re-Sectioning of Full Embankment (Singer Beel-10.69) | nos. | 2 | 16.92 | 0 | NETR/PW-06 | New | 1 | 0 | N-11 | NETR
148 | BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | (a) Re-Sectioning of Full Embankment (Kangsha)- 20.90 km. | nos. | 2 | 83 | 0 | NETR/PW-06 | New | 4 | 0 | N-11 | NETR
149 | BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Replacement of Reg. Gates & other related works | Km | 9.5 | 370 | 0 | NETR/PW-06 | New | 7 | 368599.89 | N-11 | NETR
150 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Rehabilitation of existing Regulator 4 vent | nos. | 1 | 12 | 0 | NETR/PW-06 | New | 12 | 0 | N-11 | NETR
151 | BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Replacement of Reg. Gates & other related works | Km | 21.94 | 995 | 0 | NETR/PW-07 | New | 7 | 677328 | N-12 | NETR
152 | BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Re-Sectioning of Full Embankment (Dampara-35.828) | nos. | 3 | 37 | 0 | NETR/PW-08 | New | 1 | 0 | N-12 | NETR
153 | BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | Re-Installation of Regulator 5 vent (1.50mx1.80m, Dampara) | nos. | 2 | 490 | 0 | NETR/PW-08 | New | 3 | 0 | N-12 | NETR
154 | BWDB/Netra/HFMLIP/PW-03 Dampara, Kangsha & Singer Beel | (b) Re-Sectioning of Submersible Embankment (Singer beel)- 3.56 Km. | nos. | 5 | 300 | 0 | NETR/PW-08 | New | 4 | 0 | N-12 | NETR
155 | BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Re-excavation of Khal (New) | Km | 0 | 0 | 0 | NETR/PW-08 | New | 11 | 0 | N-12 | NETR
156 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Box Drainage Outlet | nos. | 9 | 107.07 | 0 | SUNM/PW-01 | New | 1 | 0 | N-14 | SUNM
157 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of 4.0 m width Causeway | nos. | 7 | 301.63 | 0 | SUNM/PW-01 | New | 4 | 0 | N-14 | SUNM
158 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of 4.0 m width Causeway | Km | 13.928 | 603.75 | Need more 6 nos. Khal for re-excavation extra cost will remain same. | SUNM/PW-01 | New | 7 | 206690 | N-14 | SUNM
159 | BWDB/Sunam/HFMLIP/PW-07 Dharmapasha Rui Bill Haor | Const of Submersible Embankment with Slope/Crest Protection Work (Type-A -0.700 km,Type-B 2.800 km & Fuse Type-0.025 ) | Km | 16.54 | 541.12 | XEN reported that no need 17.34 km embkt. | SUNM/PW-01 | New | 11 | 399171.48 | N-14 | SUNM
160 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Irrigation Inlet | Km | 36.58 | 1275 | 0 | SUNM/PW-02 | New | 7 | 913100 | N-14 | SUNM
161 | BWDB/Sunam/HFMLIP/PW-02 Dhakua Haor (Divn-2) | Re-excavation of River (New Haor) (Piain River) | nos. | 1 | 221.62 | 0 | SUNM/PW-03 | New | 3 | 0 | N-14 | SUNM
162 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of New Regulators 1 vent (1.50mx1.80m) | nos. | 1 | 345.16 | 0 | SUNM/PW-03 | New | 3 | 0 | N-14 | SUNM
163 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 3 | 578.71 | 0 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
164 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of New Regulators 4 vent (1.50mx1.80m) | nos. | 1 | 259.36 | 0 | SUNM/PW-03 | New | 5 | 0 | N-14 | SUNM
165 | BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Box Drainage Outlet | Km | 34.94 | 1564 | 0 | SUNM/PW-04 | New | 11 | 0 | N-12 | SUNM
166 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Re-excavation of Khal (New Haor)(4 Nos. Khal) | nos. | 1 | 270 | 0 | SUNM/PW-05 | New | 3 | 0 | N-12 | SUNM
167 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Submersible Embankment | nos. | 1 | 318 | 0 | SUNM/PW-05 | New | 3 | 0 | N-12 | SUNM
168 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of 6.0 m width Causeway | nos. | 1 | 290 | 0 | SUNM/PW-05 | New | 5 | 0 | N-12 | SUNM
169 | BWDB/Sunam/HFMLIP/PW-04 Dharmapasha Rui Bill Haor (Divn-1) | Const. of Submersible Embankment | nos. | 3 | 722 | 0 | SUNM/PW-05 | New | 5 | 0 | N-12 | SUNM
170 | BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Divn-2) | Const. of Irrigation Inlet | nos. | 12 | 131.28 | 0 | SUNM/PW-06 | New | 1 | 0 | N-12 | SUNM
171 | BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Divn-1) | Const. of New Regulators 2 vent (1.50mx1.80m) | nos. | 1 | 45.13 | 0 | SUNM/PW-06 | New | 4 | 0 | N-12 | SUNM
172 | BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Bill Haor (Divn-1) | Const. of 6.0 m width Causeway | Km | 66.043 | 1423.59 | 0 | SUNM/PW-06 | New | 7 | 0 | N-12 | SUNM
173 | Construction of Submersible Embankment with Slope Protection Work | Re-excavation of Khal (New Haor) | Km | 3.545 | 1474.48 | 0 | SUNM/PW-07 | New | 11 | 0 | N-12 | SUNM

## haor_wise_quantity
| Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
0 | Chandpur Haor Sub-Project | N-1 | 0 | 0 | 1 | 0 | 0 | 0 | 11.095 | 0 | 0 | 0 | 0.315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
1 | Nunnir Haor Sub-Project | N-2 | 16 | 0 | 6 | 4 | 2 | 0 | 20 | 0 | 0 | 0 | 29.418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
2 | Boro Haor Sub-Project | N-3 | 3 | 0 | 0 | 0 | 4 | 0 | 25.7 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
3 | Noapara Haor Sub-Project | N-4 | 9 | 0 | 4 | 1 | 2 | 0 | 6.857 | 0 | 0 | 0 | 25.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
4 | Naogaon Haor Sub-Project | N-5 | 25 | 0 | 6 | 5 | 2 | 0 | 48.968 | 0 | 0 | 0 | 73.16 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 6
5 | Badla Haor Sub-Project | N-6 | 6 | 0 | 2 | 3 | 1 | 0 | 9.92 | 0 | 0 | 0 | 21 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 7
6 | Chatal Haor Sub-Project | N-7 | 4 | 0 | 2 | 1 | 0 | 0 | 1.925 | 0 | 0 | 0 | 4.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
7 | Dakhshiner Haor Sub-Project | N-8 | 15 | 0 | 1 | 1 | 2 | 0 | 11 | 0 | 0 | 0 | 23.594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
8 | Suniar Haor Sub-Project | N-9 | 0 | 0 | 2 | 4 | 2 | 0 | 22.7 | 0 | 0 | 0 | 0.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
9 | Mokhar Haor Sub-Project | N-10 | 15 | 0 | 6 | 9 | 5 | 0 | 30.058 | 0 | 0 | 0 | 23.815 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11
10 | Ganesh Haor Sub-Project | N-11 | 2 | 0 | 4 | 2 | 0 | 0 | 9.5 | 0 | 0 | 0 | 3.071 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12
11 | Dharmapasha Rui Beel Sub-Project | N-12 | 15 | 0 | 4 | 6 | 4 | 0 | 87.983 | 0 | 0 | 0 | 38.485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
12 | Jaliar Haor Sub-Project | N-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
13 | Dhakua Haor Sub-Project | N-14 | 9 | 0 | 2 | 7 | 4 | 0 | 50.508 | 0 | 0 | 0 | 16.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
14 | Alalia-Bahadia Sub-Project | R-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 16
15 | Modkhola-Bairagir Char Sub-Project | R-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 17
16 | Ganakkhali Sub-Project | R-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 18
17 | Boraikhali Khal Sub-Project | R-4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 19
18 | Koirdahla Ratna Sub-Project | R-5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 20
19 | Guingajuri Sub-Project | R-6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
20 | Aralia Khal Sub-Project | R-7 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3.312 | 0 | 26.952 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 22
21 | Bashira River Re-excavation Sub-Project | R-8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 19.695 | 0 | 22.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
22 | Dampara Water Management Scheme | R-9 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13.27 | 35.52 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 24
23 | Kangsha River Scheme | R-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.98 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 25
24 | Singer Beel Sub-Project | R-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.133 | 10.69 | 3.56 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 26
25 | Khaliajuri FCD Polder-2 | R-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.195 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 27
26 | Khaliajuri FCD Polder-4 | R-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 28
27 | Chandal Beel Sub-Project | R-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 29
28 | Satdona Beel Scheme | R-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 30
29 | All Haors | A-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 1 | 0 | 31

## haor_wise_cost
| Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
0 | Chandpur Haor Sub-Project | N-1 | 0 | 0 | 124.01 | 0 | 0 | 0 | 210.4 | 0 | 0 | 0 | 15.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
1 | Nunnir Haor Sub-Project | N-2 | 160 | 0 | 1051.52 | 198.25 | 415.5 | 0 | 618 | 0 | 0 | 0 | 1400.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
2 | Boro Haor Sub-Project | N-3 | 30 | 0 | 0 | 0 | 763.5 | 0 | 680 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
3 | Noapara Haor Sub-Project | N-4 | 90 | 0 | 1007.19 | 42.75 | 421 | 0 | 260 | 0 | 0 | 0 | 1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
4 | Naogaon Haor Sub-Project | N-5 | 274.32 | 0 | 1824.34 | 177.44 | 982 | 0 | 1680 | 0 | 0 | 0 | 9387.84 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 6
5 | Badla Haor Sub-Project | N-6 | 73 | 0 | 385 | 116 | 195 | 0 | 210 | 0 | 0 | 0 | 753.48 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 7
6 | Chatal Haor Sub-Project | N-7 | 47.87 | 0 | 640.67 | 39.54 | 0 | 0 | 32.63 | 0 | 0 | 0 | 105.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
7 | Dakhshiner Haor Sub-Project | N-8 | 125 | 0 | 397 | 44 | 614 | 0 | 420 | 0 | 0 | 0 | 3762.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
8 | Suniar Haor Sub-Project | N-9 | 0 | 0 | 314 | 49 | 600 | 0 | 479 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
9 | Mokhar Haor Sub-Project | N-10 | 134 | 0 | 1091.95 | 540 | 1011 | 0 | 926.76 | 0 | 0 | 0 | 1161.49 | 9.69 | 0 | 0 | 0 | 0 | 0 | 0 | 11
10 | Ganesh Haor Sub-Project | N-11 | 16.92 | 0 | 1152.1 | 83 | 0 | 0 | 370 | 0 | 0 | 0 | 57.25 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12
11 | Dharmapasha Rui Beel Sub-Project | N-12 | 168.28 | 0 | 1078 | 345.13 | 1012 | 0 | 2418.59 | 0 | 0 | 0 | 3038.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
12 | Jaliar Haor Sub-Project | N-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
13 | Dhakua Haor Sub-Project | N-14 | 107.07 | 0 | 566.78 | 301.63 | 838.07 | 0 | 1878.75 | 0 | 0 | 0 | 541.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
14 | Alalia-Bahadia Sub-Project | R-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.55 | 0 | 0 | 16
15 | Modkhola-Bairagir Char Sub-Project | R-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.81 | 0 | 0 | 17
16 | Ganakkhali Sub-Project | R-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.55 | 0 | 0 | 18
17 | Boraikhali Khal Sub-Project | R-4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.64 | 0 | 0 | 19
18 | Koirdahla Ratna Sub-Project | R-5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.23 | 0 | 0 | 20
19 | Guingajuri Sub-Project | R-6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
20 | Aralia Khal Sub-Project | R-7 | 0 | 456 | 0 | 0 | 0 | 0 | 0 | 54.82 | 0 | 825.18 | 0 | 0 | 0 | 0 | 0 | 13.77 | 0 | 0 | 22
21 | Bashira River Re-excavation Sub-Project | R-8 | 0 | 327.05 | 0 | 0 | 0 | 0 | 0 | 857.52 | 0 | 540.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
22 | Dampara Water Management Scheme | R-9 | 0 | 389.57 | 0 | 0 | 0 | 0 | 0 | 217.2906 | 1137.85 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 24
23 | Kangsha River Scheme | R-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 507.2842 | 552.43 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 25
24 | Singer Beel Sub-Project | R-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.4252 | 345.15 | 68 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 26
25 | Khaliajuri FCD Polder-2 | R-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484.75 | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 27
26 | Khaliajuri FCD Polder-4 | R-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 28
27 | Chandal Beel Sub-Project | R-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.5 | 0 | 0 | 29
28 | Satdona Beel Scheme | R-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.5 | 0 | 0 | 30
29 | All Haors | A-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1618 | 0 | 120 | 0 | 31

## Package_wise_quantity
| Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
0 | KISH/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 2
1 | KISH/PW-02 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 11.095 | 0 | 0 | 0 | 0.315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
2 | KISH/PW-03 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
3 | KISH/PW-04 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
4 | KISH/PW-05 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
5 | KISH/PW-06 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
6 | KISH/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.7 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
7 | KISH/PW-09 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
8 | KISH/PW-10 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
9 | KISH/PW-11 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
10 | KISH/PW-12 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 6.857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
11 | KISH/PW-13 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
12 | KISH/PW-14 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
13 | KISH/PW-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
14 | KISH/PW-16 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
15 | KISH/PW-17 | 0 | 25 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 13.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
16 | KISH/PW-18 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 26.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
17 | KISH/PW-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
18 | KISH/PW-20 | 0 | 28 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
19 | KISH/PW-21 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 21
20 | KISH/PW-22 | 0 | 6 | 0 | 0 | 3 | 1 | 0 | 9.92 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
21 | KISH/PW-23 | 0 | 4 | 0 | 2 | 1 | 0 | 0 | 1.925 | 0 | 0 | 0 | 4.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
22 | KISH/PW-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
23 | KISH/PW-25 | 0 | 15 | 0 | 1 | 1 | 2 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
24 | KISH/PW-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7 | 0 | 0 | 0 | 0.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
25 | KISH/PW-27 | 0 | 0 | 0 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
26 | KISH/PW-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 28
27 | KISH/PW-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 29
28 | KISH/PW-30-Lot-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
29 | KISH/PW-30-Lot-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
30 | KISH/PW-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
31 | KISH/PW-32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33
32 | KISH/PW-33-Lot-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
33 | KISH/PW-33-Lot-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
34 | KISH/PW-34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 36
35 | HOBI/PW-01 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 19.695 | 0 | 16.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37
36 | HOBI/PW-02 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3.312 | 0 | 32.592 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 38
37 | HOBI/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39
38 | HOBI/PW-05 | 0 | 0 | 0 | 6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
39 | HOBI/PW-06 | 0 | 15 | 0 | 0 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41
40 | HOBI/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.058 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 42
41 | HOBI/PW-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43
42 | NETR/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
43 | NETR/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
44 | NETR/PW-03 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 20.9 | 3.56 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 46
45 | NETR/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.033 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 47
46 | NETR/PW-05 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
47 | NETR/PW-06 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 9.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 49
48 | NETR/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
49 | NETR/PW-08 | 0 | 3 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
50 | SUNM/PW-01 | 0 | 9 | 0 | 0 | 7 | 0 | 0 | 13.928 | 0 | 0 | 0 | 16.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
51 | SUNM/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53
52 | SUNM/PW-03 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54
53 | SUNM/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
54 | SUNM/PW-05 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56
55 | SUNM/PW-06 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | 66.043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57
56 | SUNM/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58
57 | BRAH/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 59

## Package_wise_cost
| Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
0 | KISH/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.55 | 0 | 0 | 2
1 | KISH/PW-02 | 0 | 0 | 0 | 124.01 | 0 | 0 | 0 | 210.4 | 0 | 0 | 0 | 15.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
2 | KISH/PW-03 | 0 | 0 | 0 | 155.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
3 | KISH/PW-04 | 0 | 0 | 0 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
4 | KISH/PW-05 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
5 | KISH/PW-06 | 0 | 0 | 0 | 222 | 0 | 0 | 0 | 618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
6 | KISH/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
7 | KISH/PW-09 | 0 | 0 | 0 | 0 | 70 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
8 | KISH/PW-10 | 0 | 0 | 0 | 150 | 0 | 243 | 0 | 0 | 0 | 0 | 0 | 618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
9 | KISH/PW-11 | 0 | 0 | 0 | 326.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
10 | KISH/PW-12 | 0 | 0 | 0 | 530.82 | 0 | 0 | 0 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
11 | KISH/PW-13 | 0 | 0 | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
12 | KISH/PW-14 | 0 | 0 | 0 | 219.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
13 | KISH/PW-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
14 | KISH/PW-16 | 0 | 0 | 0 | 404.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
15 | KISH/PW-17 | 0 | 274.32 | 0 | 790.24 | 177.44 | 0 | 0 | 0 | 0 | 0 | 0 | 561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
16 | KISH/PW-18 | 0 | 0 | 0 | 0 | 0 | 982 | 0 | 615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
17 | KISH/PW-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
18 | KISH/PW-20 | 0 | 280 | 0 | 0 | 171 | 712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
19 | KISH/PW-21 | 0 | 0 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 463.48 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 21
20 | KISH/PW-22 | 0 | 73 | 0 | 0 | 116 | 195 | 0 | 210 | 0 | 0 | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
21 | KISH/PW-23 | 0 | 47.87 | 0 | 640.67 | 39.54 | 0 | 0 | 32.63 | 0 | 0 | 0 | 105.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
22 | KISH/PW-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
23 | KISH/PW-25 | 0 | 125 | 0 | 397 | 44 | 614 | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
24 | KISH/PW-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
25 | KISH/PW-27 | 0 | 0 | 0 | 314 | 49 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
26 | KISH/PW-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1618 | 0 | 0 | 0 | 28
27 | KISH/PW-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 29
28 | KISH/PW-30-Lot-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1548.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
29 | KISH/PW-30-Lot-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1404.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
30 | KISH/PW-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
31 | KISH/PW-32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1743.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33
32 | KISH/PW-33-Lot-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1392.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34
33 | KISH/PW-33-Lot-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
34 | KISH/PW-34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 36
35 | HOBI/PW-01 | 0 | 0 | 327.05 | 0 | 0 | 0 | 0 | 0 | 857.52 | 0 | 385.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37
36 | HOBI/PW-02 | 0 | 0 | 456 | 0 | 0 | 0 | 0 | 0 | 54.82 | 0 | 980 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 38
37 | HOBI/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1161.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39
38 | HOBI/PW-05 | 0 | 0 | 0 | 1091.95 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
39 | HOBI/PW-06 | 0 | 134 | 0 | 0 | 540 | 886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41
40 | HOBI/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 926.76 | 0 | 0 | 0 | 0 | 9.69 | 0 | 0 | 0 | 0 | 0 | 0 | 42
41 | HOBI/PW-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43
42 | NETR/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
43 | NETR/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
44 | NETR/PW-03 | 0 | 0 | 389.57 | 0 | 0 | 0 | 0 | 0 | 0 | 552.43 | 68 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 46
45 | NETR/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165 | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 47
46 | NETR/PW-05 | 0 | 0 | 0 | 1152.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
47 | NETR/PW-06 | 0 | 16.92 | 0 | 0 | 83 | 0 | 0 | 370 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 49
48 | NETR/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
49 | NETR/PW-08 | 0 | 37 | 0 | 490 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
50 | SUNM/PW-01 | 0 | 107.07 | 0 | 0 | 301.63 | 0 | 0 | 603.75 | 0 | 0 | 0 | 541.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
51 | SUNM/PW-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53
52 | SUNM/PW-03 | 0 | 0 | 0 | 566.78 | 0 | 838.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54
53 | SUNM/PW-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
54 | SUNM/PW-05 | 0 | 0 | 0 | 588 | 0 | 1012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56
55 | SUNM/PW-06 | 0 | 131.28 | 0 | 0 | 45.13 | 0 | 0 | 1423.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57
56 | SUNM/PW-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1474.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58
57 | BRAH/PW-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | 0 | 59

## Structure_wise_cost
| name | stcode | Dpptransfer | Unit | Quantity | GoB | RPA | DPA | Total | Annex_input_Transfer | Dpp_Transfer_row
0 | Construction of Irrigation Inlet | 1 | 1 | Nos | 119 | 171.7044 | 1054.7556 | 0 | 1226.46 | 0 | 0
1 | Rehab Regulator Rehab Haor | 2 | 2 | Nos | 5 | 164.1668 | 1008.4532 | 0 | 1172.62 | 0 | 0
2 | Regulator | 3 | 3 | Nos | 40 | 1348.5584 | 8284.0016 | 0 | 9632.56 | 0 | 0
3 | Box Drainage Outlet | 4 | 3 | Nos | 43 | 271.1436 | 1665.5964 | 0 | 1936.74 | 0 | 0
4 | Causeway | 5 | 3 | Nos | 28 | 959.2898 | 5892.7802 | 0 | 6852.07 | 0 | 0
5 | Bridge | 6 | 3 | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Khal_River Reexcavation(New Haor) | 7 | 4 | Km | 336.214 | 1425.7782 | 8758.3518 | 0 | 10184.13 | 0 | 0
7 | Khal_River Reexcavation(Rehab Haor) | 8 | 5 | Km | 108.974 | 475.8446 | 2923.0454 | 0 | 3398.89 | 0 | 0
8 | Embankment Rehablitation | 9 | 6 | Km | 67.11 | 284.9602 | 1750.4698 | 0 | 2035.43 | 0 | 0
9 | Submersible Embankment Rehabilitation | 10 | 7 | Km | 62.662 | 244.7802 | 1503.6498 | 0 | 1748.43 | 0 | 0
10 | Submersible Embankment Construction | 11 | 8 | Km | 261.238 | 3002.3322 | 18442.8978 | 0 | 21445.23 | 0 | 0
11 | Rehab Regulator New Haor | 12 | 9 | Nos | 7 | 20.5366 | 126.1534 | 0 | 146.69 | 0 | 0
12 | Embankment Slope Protection Work | 13 | 8 | Km | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Thrashing Floor Construction | 14 | 10 | Nos | 5 | 31.5 | 193.5 | 0 | 225 | 0 | 0
14 | Construction of WMG | 15 | 11 | Nos | 55 | 226.52 | 1391.48 | 0 | 1618 | 0 | 0
15 | Gate Repair By M&E | 16 | 12 | Nos | 86 | 56.777 | 348.773 | 0 | 405.55 | 0 | 0
16 | O&M During Construction | 17 | 13 | LS | 1 | 120 | 0 | 0 | 120 | 0 | 0

## Civil_Works_Cost
| Code | Description | rindex | unit | Quantity | GOB | RPA | DPA | TOTAL | Unitcost | Tindex
0 | 4111306 | Construction of Irrigation Inlet (New Haors) | 58 | Nos | 119 | 171.7044 | 1054.7556 | 0 | 1226.46 | 10.3064 | 2
1 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 59 | Nos | 5 | 164.1668 | 1008.4532 | 0 | 1172.62 | 234.524 | 3
2 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 60 | Nos | 111 | 2578.9918 | 15842.3782 | 0 | 18421.37 | 165.9583 | 4
3 | 4111307 | Re-excavation of Khal/River (New Haors) | 61 | Km | 336.214 | 1425.7782 | 8758.3518 | 0 | 10184.13 | 30.2906 | 5
4 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 62 | Km | 108.974 | 475.8446 | 2923.0454 | 0 | 3398.89 | 31.1899 | 6
5 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 63 | Km | 67.11 | 284.9602 | 1750.4698 | 0 | 2035.43 | 30.3298 | 7
6 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 64 | Km | 62.662 | 244.7802 | 1503.6498 | 0 | 1748.43 | 27.9026 | 8
7 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 65 | Km | 261.238 | 3002.3322 | 18442.8978 | 0 | 21445.23 | 82.0908 | 9
8 | 4111201 | Rehabilitation of Regulator (New Haors) | 66 | Nos | 7 | 20.5366 | 126.1534 | 0 | 146.69 | 20.9557 | 10
9 | 4111201 | Threshing Floor Construction | 67 | Nos | 5 | 31.5 | 193.5 | 0 | 225 | 45 | 11
10 | 4111201 | Construction of WMG Office | 68 | Nos | 55 | 226.52 | 1391.48 | 0 | 1618 | 29.4182 | 12
11 | 3258114 | Gate Repair By M&E | 40 | Nos | 86 | 56.777 | 348.773 | 0 | 405.55 | 4.7157 | 13
12 | 4111201 | O&M During Construction | 69 | LS | 1 | 120 | 0 | 0 | 120 | 120 | 14

## district_wise_quantity
| Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | rrow_index
0 | Kishoreganj | KISH | 78 | 0 | 24 | 19 | 15 | 0 | 158.165 | 11.551 | 0 | 0 | 179.327 | 5 | 0 | 5 | 55 | 13 | 1 | 0 | 2
1 | Hobiganj | HOBI | 15 | 4 | 6 | 9 | 5 | 0 | 30.058 | 23.007 | 0 | 49.352 | 23.815 | 1 | 0 | 0 | 0 | 13 | 0 | 0 | 3
2 | Netrokona | NETR | 5 | 1 | 6 | 7 | 0 | 0 | 31.44 | 74.416 | 67.11 | 13.31 | 3.071 | 1 | 0 | 0 | 0 | 56 | 0 | 0 | 4
3 | Sunamgonj | SUNM | 21 | 0 | 4 | 8 | 8 | 0 | 116.551 | 0 | 0 | 0 | 55.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
4 | Brahmanbaria | BRAH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 6

## district_wise_cost
| Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | rrow_index
0 | Kishoreganj | KISH | 800.19 | 0 | 5743.73 | 666.98 | 3991 | 0 | 4590.03 | 496.55 | 0 | 0 | 16646.89 | 125 | 0 | 225 | 1618 | 55.55 | 120 | 35078.92 | 2
1 | Hobiganj | HOBI | 134 | 783.05 | 1091.95 | 540 | 1011 | 0 | 926.76 | 912.34 | 0 | 1365.43 | 1161.49 | 9.69 | 0 | 0 | 0 | 35 | 0 | 7970.71 | 3
2 | Netrokona | NETR | 53.92 | 389.57 | 1642.1 | 383 | 0 | 0 | 1365 | 1990 | 2035.43 | 383 | 57.25 | 12 | 0 | 0 | 0 | 140 | 0 | 8451.27 | 4
3 | Sunamgonj | SUNM | 238.35 | 0 | 1154.78 | 346.76 | 1850.07 | 0 | 3302.34 | 0 | 0 | 0 | 3579.6 | 0 | 0 | 0 | 0 | 0 | 0 | 10471.9 | 5
4 | Brahmanbaria | BRAH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | 175 | 6

## code_wise_costcomaprision
| Code | Description | Quantity_1st | GOB_1st | RPA_1st | DPA_1st | TOTAL_1st | rindex | Quantity_2nd | GOB_2nd | RPA_2nd | DPA_2nd | TOTAL_2nd | Quantity_diff | GOB_Diff | RPA_diff | DPA_diff | TOTAL_diff | Tindex | annex2_input_index | annex9_input_index | UintCost | units | Distribution _code
0 | 3111302 | Conveyance Allowance | 1 Item | 10 | 0 | 0 | 10 | 12 | 1 Item | 5 | 0 | 0 | 5 | 0 | -5 | 0 | 0 | -5 | 2 | 2 | 2 | 5 | 0 | 1
1 | 3111327 | Overtime Allowance | 1 Item | 10 | 0 | 0 | 10 | 13 | 1 Item | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 10 | 0 | 1
2 | 3111338 | Other Allowance | 1 Item | 140 | 0 | 0 | 140 | 14 | 1 Item | 140 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 140 | 0 | 1
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 1 Item | 100 | 0 | 0 | 100 | 16 | 1 Item | 120 | 0 | 0 | 120 | 0 | 20 | 0 | 0 | 20 | 5 | 5 | 5 | 120 | 0 | 1
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 1 Item | 245 | 0 | 0 | 245 | 17 | 1 Item | 245 | 0 | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 245 | 0 | 1
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 1 Item | 2596.27 | 0 | 0 | 2596.27 | 18 | 1 Item | 2874.35 | 0 | 0 | 2874.35 | 0 | 278.08 | 0 | 0 | 278.08 | 7 | 7 | 7 | 2874.35 | 0 | 1
6 | 3211119 | Postage | 1 Item | 25 | 0 | 0 | 25 | 19 | 1 Item | 5 | 0 | 0 | 5 | 0 | -20 | 0 | 0 | -20 | 8 | 8 | 8 | 5 | 0 | 1
7 | 3211120 | Telephones/Telegram/Teleprinter | 1 Item | 25 | 0 | 0 | 25 | 20 | 1 Item | 5 | 0 | 0 | 5 | 0 | -20 | 0 | 0 | -20 | 9 | 9 | 9 | 5 | 0 | 1
8 | 3211117 | Telex/Fax/Internet | 1 Item | 25 | 0 | 0 | 25 | 21 | 1 Item | 5 | 0 | 0 | 5 | 0 | -20 | 0 | 0 | -20 | 10 | 10 | 10 | 5 | 0 | 1
9 | 3221104 | Registration Fee (Vehicles) | 1 Item | 15 | 0 | 0 | 15 | 22 | 1 Item | 20 | 0 | 0 | 20 | 0 | 5 | 0 | 0 | 5 | 11 | 11 | 11 | 20 | 0 | 1
10 | 3211115 | Water | 1 Item | 10 | 0 | 0 | 10 | 23 | 1 Item | 5 | 0 | 0 | 5 | 0 | -5 | 0 | 0 | -5 | 12 | 12 | 12 | 5 | 0 | 1
11 | 3211113 | Electricity | 1 Item | 15 | 0 | 0 | 15 | 24 | 1 Item | 20 | 0 | 0 | 20 | 0 | 5 | 0 | 0 | 5 | 13 | 13 | 13 | 20 | 0 | 1
12 | 3243102 | Gas & Fuel | 1 Item | 200 | 0 | 0 | 200 | 25 | 1 Item | 40 | 0 | 0 | 40 | 0 | -160 | 0 | 0 | -160 | 14 | 14 | 14 | 40 | 0 | 2
13 | 3243101 | Petrol and Lubricant | 1 Item | 150 | 0 | 0 | 150 | 26 | 1 Item | 170 | 0 | 0 | 170 | 0 | 20 | 0 | 0 | 20 | 15 | 15 | 15 | 170 | 0 | 2
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 1 Item | 3 | 0 | 0 | 3 | 27 | 1 Item | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 3 | 0 | 1
15 | 3255102 | Printing & Binding | 1 Item | 35 | 0 | 0 | 35 | 28 | 1 Item | 50 | 0 | 0 | 50 | 0 | 15 | 0 | 0 | 15 | 17 | 17 | 17 | 50 | 0 | 1
16 | 3255104 | Stationery, Seals & Stamps | 1 Item | 150 | 0 | 0 | 150 | 29 | 1 Item | 120 | 0 | 0 | 120 | 0 | -30 | 0 | 0 | -30 | 18 | 18 | 18 | 120 | 0 | 1
17 | 3211127 | Books & Periodicals | 1 Item | 2 | 0 | 0 | 2 | 30 | 1 Item | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 19 | 2 | 0 | 1
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 1 Item | 0 | 238.54 | 0 | 238.54 | 32 | 1 Item | 0 | 119 | 0 | 119 | 0 | 0 | -119.54 | 0 | -119.54 | 20 | 20 | 20 | 119 | 0 | 3
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 1 Item | 47.81 | 350.6 | 0 | 398.41 | 33 | 1 Item | 64.4 | 472.3 | 0 | 536.7 | 0 | 16.59 | 121.7 | 0 | 138.29 | 21 | 21 | 21 | 536.7 | 0 | 3
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 1 Item | 304 | 2229.34 | 0 | 2533.34 | 34 | 1 Item | 373.9 | 2756.2 | 0 | 3130.1 | 0 | 69.9 | 526.86 | 0 | 596.76 | 22 | 22 | 22 | 3130.1 | 0 | 3
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 1 Item | 158.6 | 1163.08 | 0 | 1321.68 | 35 | 1 Item | 159.7 | 1171.5 | 0 | 1331.2 | 0 | 1.1 | 8.42 | 0 | 9.52 | 23 | 23 | 23 | 1331.2 | 0 | 3
22 | 3211109 | Casual labour/Job worker | 1 Item | 15 | 0 | 0 | 15 | 36 | 1 Item | 22 | 0 | 0 | 22 | 0 | 7 | 0 | 0 | 7 | 24 | 24 | 24 | 22 | 0 | 1
23 | 3256103 | Consumable Stores | 1 Item | 25 | 0 | 0 | 25 | 37 | 1 Item | 15 | 0 | 0 | 15 | 0 | -10 | 0 | 0 | -10 | 25 | 25 | 25 | 15 | 0 | 1
24 | 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | 71+234 | 0 | 0 | 7901.4 | 7901.4 | 38 | 56+532 | 0 | 0 | 7901.4 | 7901.4 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 26 | 0 | MM | 4
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 1 Item | 25 | 0 | 0 | 25 | 39 | 1 Item | 30 | 0 | 0 | 30 | 0 | 5 | 0 | 0 | 5 | 27 | 27 | 27 | 30 | 0 | 1
26 | 3111332 | b) Interim Evaluation | 1 Item | 10 | 0 | 0 | 10 | 40 | 1 Item | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 28 | 10 | 0 | 1
27 | 3111332 | c) Progress Monitoring | 1 Item | 10 | 0 | 0 | 10 | 41 | 1 Item | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 29 | 10 | 0 | 1
28 | 3257104 | Survey | 1 Item | 162 | 0 | 0 | 162 | 42 | 1 Item | 162 | 0 | 0 | 162 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 162 | 0 | 1
29 | 3255101 | Computer Consumables | 1 Item | 50 | 0 | 0 | 50 | 43 | 1 Item | 60 | 0 | 0 | 60 | 0 | 10 | 0 | 0 | 10 | 31 | 31 | 31 | 60 | 0 | 1
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 1 Item | 1700 | 0 | 0 | 1700 | 44 | 1 Item | 1700 | 0 | 0 | 1700 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 1700 | 0 | 1
31 | 3258101 | Motor Vehicles | L.S. | 100 | 0 | 0 | 100 | 46 | L.S. | 125 | 0 | 0 | 125 | 0 | 25 | 0 | 0 | 25 | 33 | 33 | 33 | 125 | 0 | 5
32 | 3258102 | Furnitures & Fixtures | L.S. | 15 | 0 | 0 | 15 | 47 | L.S. | 10 | 0 | 0 | 10 | 0 | -5 | 0 | 0 | -5 | 34 | 34 | 34 | 10 | 0 | 5
33 | 3258103 | Computers & office equipments | L.S. | 25 | 0 | 0 | 25 | 48 | L.S. | 15 | 0 | 0 | 15 | 0 | -10 | 0 | 0 | -10 | 35 | 35 | 35 | 15 | 0 | 5
34 | 3258105 | Machineries & Equipments | L.S. | 25 | 0 | 0 | 25 | 49 | L.S. | 10 | 0 | 0 | 10 | 0 | -15 | 0 | 0 | -15 | 36 | 36 | 36 | 10 | 0 | 5
35 | 3258107 | Office Building : Repair & Maintenance | L.S. | 20 | 0 | 0 | 20 | 50 | L.S. | 25 | 0 | 0 | 25 | 0 | 5 | 0 | 0 | 5 | 37 | 37 | 37 | 25 | 0 | 5
36 | 3258106 | Residential Building : Repair & Maintenance | L.S. | 20 | 0 | 0 | 20 | 51 | L.S. | 40 | 0 | 0 | 40 | 0 | 20 | 0 | 0 | 20 | 38 | 38 | 38 | 40 | 0 | 5
37 | 3258105 | Engineering Equipments | L.S. | 25 | 0 | 0 | 25 | 52 | L.S. | 20 | 0 | 0 | 20 | 0 | -5 | 0 | 0 | -5 | 39 | 39 | 39 | 20 | 0 | 5
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 104 | 43.5 | 319 | 0 | 362.5 | 54 | 86 | 56.777 | 348.773 | 0 | 405.55 | 0 | 13.277 | 29.773 | 0 | 43.05 | 40 | 40 | 40 | 405.55 | 0 | 8
39 | 3258128 | Water Transport : Repair of Speedboat(s) | L.S. | 10 | 0 | 0 | 10 | 55 | L.S. | 5 | 0 | 0 | 5 | 0 | -5 | 0 | 0 | -5 | 41 | 41 | 41 | 5 | 0 | 5
40 | 3258107 | Others : Repair & Maintenance | L.S. | 25 | 0 | 0 | 25 | 56 | L.S. | 40 | 0 | 0 | 40 | 0 | 15 | 0 | 0 | 15 | 42 | 42 | 42 | 40 | 0 | 5
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 10 | 702.5 | 0 | 0 | 702.5 | 68 | 10 | 702.5 | 0 | 0 | 702.5 | 0 | 0 | 0 | 0 | 0 | 43 | 43 | 43 | 70.25 | Nos | 6
42 | 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | 35 | 68.25 | 0 | 0 | 68.25 | 69 | 45 | 68.25 | 0 | 0 | 68.25 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 1.52 | Nos | 6
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | 6 | 100 | 0 | 0 | 100 | 71 | 5 | 90 | 0 | 0 | 90 | 0 | -10 | 0 | 0 | -10 | 45 | 45 | 45 | 18 | Nos | 6
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 7 | 8.97 | 0 | 0 | 8.97 | 73 | 7 | 8.97 | 0 | 0 | 8.97 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 46 | 1.28 | Nos | 6
45 | 4112316 | Fax -2 nos (PMO 2 Nos.). | 7 | 5 | 0 | 0 | 5 | 74 | 2 | 1 | 0 | 0 | 1 | 0 | -4 | 0 | 0 | -4 | 47 | 47 | 47 | 0.5 | Nos | 6
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 17 | 20.5 | 0 | 0 | 20.5 | 76 | 17 | 20.5 | 0 | 0 | 20.5 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 48 | 20.5 | Nos | 6
47 | 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | 6 | 6 | 0 | 0 | 6 | 77 | 3 | 3 | 0 | 0 | 3 | 0 | -3 | 0 | 0 | -3 | 49 | 49 | 49 | 1 | Nos | 6
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | L.S | 50 | 0 | 0 | 50 | 78 | L.S | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 6
49 | 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 30 | 19.5 | 0 | 0 | 19.5 | 80 | 37 | 24.5 | 0 | 0 | 24.5 | 0 | 5 | 0 | 0 | 5 | 51 | 51 | 51 | 0.66 | Nos | 6
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 11 | 13.75 | 0 | 0 | 13.75 | 81 | 11 | 13.75 | 0 | 0 | 13.75 | 0 | 0 | 0 | 0 | 0 | 52 | 52 | 52 | 1.25 | Nos | 6
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | 2 | 1.5 | 0 | 0 | 1.5 | 82 | 2 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 53 | 53 | 53 | 0.75 | Nos | 6
52 | 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | 11 | 5.25 | 0 | 0 | 5.25 | 83 | 17 | 5.25 | 0 | 0 | 5.25 | 0 | 0 | 0 | 0 | 0 | 54 | 54 | 54 | 0.31 | Nos | 6
53 | 4112314 | Furnitures & Fixtures | LS | 50 | 0 | 0 | 50 | 84 | LS | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 50 | 0 | 6
54 | 4112303 | Aircooler | 15 | 15 | 0 | 0 | 15 | 85 | 15 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 56 | 1 | Nos | 6
55 | 4141101 | Land Acquisition ( 470 hectare) | 470 | 24000 | 0 | 0 | 24000 | 87 | 470 | 18386.72 | 0 | 0 | 18386.72 | 0 | -5613.28 | 0 | 0 | -5613.28 | 57 | 57 | 57 | 39.12 | ha | 7
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | 131 | 151.32 | 1109.68 | 0 | 1261 | 90 | 119 | 171.7044 | 1054.7556 | 0 | 1226.46 | 0 | 20.3844 | -54.9244 | 0 | -34.54 | 58 | 58 | 58 | 10.31 | Nos | 8
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 7(2+5) | 181.8 | 1333.2 | 0 | 1515 | 92 | 5 | 164.1668 | 1008.4532 | 0 | 1172.62 | 0 | -17.6332 | -324.7468 | 0 | -342.38 | 59 | 59 | 59 | 234.52 | Nos | 8
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 137(57+35+14) | 2437.32 | 17873.68 | 0 | 20311 | 93 | 111 | 2578.9918 | 15842.3782 | 0 | 18421.37 | 0 | 141.6718 | -2031.3018 | 0 | -1889.63 | 60 | 60 | 60 | 165.96 | Nos | 8
59 | 4111307 | Re-excavation of Khal/River (New Haors) | 318 | 1167.48 | 8561.52 | 0 | 9729 | 94 | 336.214 | 1425.7782 | 8758.3518 | 0 | 10184.13 | 0 | 258.2982 | 196.8318 | 0 | 455.13 | 61 | 61 | 61 | 30.29 | Km | 8
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 143 | 301.8 | 2213.2 | 0 | 2515 | 96 | 108.974 | 475.8446 | 2923.0454 | 0 | 3398.89 | 0 | 174.0446 | 709.8454 | 0 | 883.89 | 62 | 62 | 62 | 31.19 | Km | 8
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 84.31 | 306 | 2244 | 0 | 2550 | 97 | 67.11 | 284.9602 | 1750.4698 | 0 | 2035.43 | 0 | -21.0398 | -493.5302 | 0 | -514.57 | 63 | 63 | 63 | 30.33 | Km | 8
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 87.03 | 214.2 | 1570.8 | 0 | 1785 | 98 | 62.662 | 244.7802 | 1503.6498 | 0 | 1748.43 | 0 | 30.5802 | -67.1502 | 0 | -36.57 | 64 | 64 | 64 | 27.9 | Km | 8
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 263.24 | 1434.3 | 10518.2 | 0 | 11952.5 | 99 | 261.238 | 9320.5402 | 12124.6898 | 0 | 21445.23 | 0 | 7886.2402 | 1606.4898 | 0 | 9492.73 | 65 | 65 | 65 | 0 | Km | 8
64 | 4111201 | Rehabilitation of Regulator (New Haors) | 8 | 19.92 | 146.08 | 0 | 166 | 100 | 7 | 20.5366 | 126.1534 | 0 | 146.69 | 0 | 0.6166 | -19.9266 | 0 | -19.31 | 66 | 66 | 66 | 20.96 | Nos | 8
65 | 4111201 | Threshing Floor Construction | 0 | 0 | 0 | 0 | 0 | 101 | 5 | 31.5 | 193.5 | 0 | 225 | 0 | 31.5 | 193.5 | 0 | 225 | 67 | 67 | 67 | 45 | Nos | 8
66 | 4111201 | Construction of WMG Office | 60 | 165.6 | 1214.4 | 0 | 1380 | 102 | 55 | 226.52 | 1391.48 | 0 | 1618 | 0 | 60.92 | 177.08 | 0 | 238 | 68 | 68 | 68 | 29.42 | Nos | 8
67 | 4111201 | O&M During Construction | L.S | 200 | 0 | 0 | 200 | 103 | 1 | 120 | 0 | 0 | 120 | 0 | -80 | 0 | 0 | -80 | 69 | 69 | 69 | 0 | Iten | 8
68 | 0 | (c) Physical Contingency ( Lump sum): | L.S. | 100 | 158 | 0 | 258 | 106 | L.S. | 30.51 | 0 | 0 | 30.51 | 0 | -69.49 | -158 | 0 | -227.49 | 70 | 70 | 70 | 0 | Item | 9
69 | 0 | (d) Price Contingency (Lump sum): | L.S. | 100.76 | 301.38 | 0 | 402.14 | 107 | L.S. | 10 | 0 | 0 | 10 | 0 | -90.76 | -301.38 | 0 | -392.14 | 71 | 71 | 71 | 0 | Item | 9

## Yearwise-cost-projection
| Code | Description | rindex | Unit Cost | Quantity | TotalCost | Weight | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2020-21-P | 2021-22-P | Investment_Cost_Index | Total_upto_19_20 | Remaining | EC_FACTOR
0 | 3111302 | Conveyance Allowance | 10 | 5 | 1 Item | 5 | 5e-05 | 0 | 0.3 | 0.13 | 0.28 | 0.3 | 0.5 | 2.0242 | 1.4658 | 0.58 | 0.42 | 9 | 1.51 | 3.49 | 0.902
1 | 3111327 | Overtime Allowance | 11 | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 3.7 | 0.63 | 0.37 | 10 | 0 | 10 | 0.902
2 | 3111338 | Other Allowance | 12 | 140 | 1 Item | 140 | 0.00139 | 0 | 0 | 0 | 25 | 11.61 | 14 | 53.634 | 35.756 | 0.6 | 0.4 | 11 | 50.61 | 89.39 | 0.902
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 14 | 120 | 1 Item | 120 | 0.00119 | 0.99 | 11.92 | 14.98 | 17.96 | 12.7 | 14.97 | 28.8176 | 17.6624 | 0.62 | 0.38 | 13 | 73.52 | 46.48 | 0.902
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 15 | 245 | 1 Item | 245 | 0.00243 | 0 | 16.25 | 31.35 | 34.86 | 34.21 | 34.21 | 58.3544 | 35.7656 | 0.62 | 0.38 | 14 | 150.88 | 94.12 | 0.812
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 16 | 2874.35 | 1 Item | 2874.35 | 0.02852 | 223.75 | 464.64 | 327.7 | 337.33 | 249.75 | 177.18 | 634.52 | 459.48 | 0.58 | 0.42 | 15 | 1780.35 | 1094 | 0.812
6 | 3211119 | Postage | 17 | 5 | 1 Item | 5 | 5e-05 | 0 | 0.05 | 0.13 | 0.22 | 0.37 | 0.48 | 2.175 | 1.575 | 0.58 | 0.42 | 16 | 1.25 | 3.75 | 0.812
7 | 3211120 | Telephones/Telegram/Teleprinter | 18 | 5 | 1 Item | 5 | 5e-05 | 0.21 | 0.24 | 0.29 | 0.15 | 0.08 | 0.07 | 2.4156 | 1.5444 | 0.61 | 0.39 | 17 | 1.04 | 3.96 | 0.812
8 | 3211117 | Telex/Fax/Internet | 19 | 5 | 1 Item | 5 | 5e-05 | 0.25 | 0.001 | 0.09 | 0.05 | 0.05 | 0.1 | 2.497 | 1.962 | 0.56 | 0.44 | 18 | 0.541 | 4.459 | 0.812
9 | 3221104 | Registration Fee (Vehicles) | 20 | 20 | 1 Item | 20 | 0.0002 | 1.1 | 8.37 | 0.08 | 0 | 2.37 | 0.17 | 4.9833 | 2.9267 | 0.63 | 0.37 | 19 | 12.09 | 7.91 | 0.812
10 | 3211115 | Water | 21 | 5 | 1 Item | 5 | 5e-05 | 0 | 0.12 | 0.23 | 0.37 | 0.4 | 0.55 | 2.0313 | 1.2987 | 0.61 | 0.39 | 20 | 1.67 | 3.33 | 0.812
11 | 3211113 | Electricity | 22 | 20 | 1 Item | 20 | 0.0002 | 0.19 | 1.67 | 1.78 | 2.31 | 2.78 | 2.89 | 4.609 | 3.771 | 0.55 | 0.45 | 21 | 11.62 | 8.38 | 0.812
12 | 3243102 | Gas & Fuel | 23 | 40 | 1 Item | 40 | 0.0004 | 0.94 | 3.7 | 3 | 4 | 5.89 | 4.02 | 11.2545 | 7.1955 | 0.61 | 0.39 | 22 | 21.55 | 18.45 | 0.812
13 | 3243101 | Petrol and Lubricant | 24 | 170 | 1 Item | 170 | 0.00169 | 0.62 | 6.99 | 18.97 | 18 | 20 | 24.18 | 46.3068 | 34.9332 | 0.57 | 0.43 | 23 | 88.76 | 81.24 | 0.72
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 25 | 3 | 1 Item | 3 | 3e-05 | 0.08 | 0.749 | 0.01 | 0.22 | 0.1 | 0.91 | 0.51205 | 0.41895 | 0.55 | 0.45 | 24 | 2.069 | 0.931 | 0.902
15 | 3255102 | Printing & Binding | 26 | 50 | 1 Item | 50 | 0.0005 | 0.2 | 6.994 | 16.99 | 6 | 3.98 | 0.5 | 9.355 | 5.981 | 0.61 | 0.39 | 25 | 34.664 | 15.336 | 0.812
16 | 3255104 | Stationery, Seals & Stamps | 27 | 120 | 1 Item | 120 | 0.00119 | 0.97 | 6.972 | 11.2 | 12.79 | 17.98 | 19.95 | 31.5869 | 18.5511 | 0.63 | 0.37 | 26 | 69.862 | 50.138 | 0.812
17 | 3211127 | Books & Periodicals | 28 | 2 | 1 Item | 2 | 2e-05 | 0 | 0.1 | 0.03 | 0.05 | 0.1 | 0.2 | 0.8816 | 0.6384 | 0.58 | 0.42 | 27 | 0.48 | 1.52 | 0.812
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 30 | 119 | 1 Item | 119 | 0.00118 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 1 | 0 | 29 | 0 | 119 | 0.902
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 31 | 536.7 | 1 Item | 536.7 | 0.00533 | 0 | 9.22 | 29.86 | 86.55 | 175.87 | 22.21 | 127.794 | 85.196 | 0.6 | 0.4 | 30 | 323.71 | 212.99 | 0.902
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 32 | 3130.1 | 1 Item | 3130.1 | 0.03106 | 0 | 0 | 199.49 | 524.89 | 622.25 | 338.12 | 910.5705 | 534.7795 | 0.63 | 0.37 | 31 | 1684.75 | 1445.35 | 0.902
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 33 | 1331.2 | 1 Item | 1331.2 | 0.01321 | 0 | 0 | 119.7 | 224.29 | 234.21 | 82.97 | 368.5165 | 301.5135 | 0.55 | 0.45 | 32 | 661.17 | 670.03 | 0.902
22 | 3211109 | Casual labour/Job worker | 34 | 22 | 1 Item | 22 | 0.00022 | 0.25 | 2.11 | 2.35 | 2 | 4.25 | 3.49 | 4.681 | 2.869 | 0.62 | 0.38 | 33 | 14.45 | 7.55 | 0.902
23 | 3256103 | Consumable Stores | 35 | 15 | 1 Item | 15 | 0.00015 | 0 | 0.99 | 0.75 | 1 | 1 | 3 | 4.7908 | 3.4692 | 0.58 | 0.42 | 34 | 6.74 | 8.26 | 0.812
24 | 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | 36 | 0 | 56+532 | 7901.4 | 0.0784 | 849.67 | 1849.425 | 1123.15 | 689.33 | 686.43 | 450 | 1374.571 | 878.824 | 0.61 | 0.39 | 35 | 5648.005 | 2253.395 | 0.902
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 37 | 30 | 1 Item | 30 | 0.0003 | 0.4 | 1.33 | 1.5 | 4.5 | 5 | 3 | 8.2766 | 5.9934 | 0.58 | 0.42 | 36 | 15.73 | 14.27 | 0.902
26 | 3111332 | b) Interim Evaluation | 38 | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0.27 | 0.25 | 0.77 | 0.41 | 8.3 | 0 | 1 | 0 | 37 | 1.7 | 8.3 | 0.902
27 | 3111332 | c) Progress Monitoring | 39 | 10 | 1 Item | 10 | 0.0001 | 0 | 0 | 0.3 | 0.25 | 0.75 | 0.41 | 4.145 | 4.145 | 0.5 | 0.5 | 38 | 1.71 | 8.29 | 0.902
28 | 3257104 | Survey | 40 | 162 | 1 Item | 162 | 0.00161 | 0 | 7.62 | 17.47 | 30 | 29.93 | 30 | 26.7786 | 20.2014 | 0.57 | 0.43 | 39 | 115.02 | 46.98 | 0.902
29 | 3255101 | Computer Consumables | 41 | 60 | 1 Item | 60 | 0.0006 | 0.49 | 1.499 | 4.5 | 6.48 | 7.5 | 10 | 16.242 | 13.2889 | 0.55 | 0.45 | 40 | 30.469 | 29.531 | 0.902
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 42 | 1700 | 1 Item | 1700 | 0.01687 | 0 | 84.31 | 227.97 | 263.24 | 299.93 | 299.96 | 299.0163 | 225.5737 | 0.57 | 0.43 | 41 | 1175.41 | 524.59 | 0.86
31 | 3258101 | Motor Vehicles | 44 | 125 | L.S. | 125 | 0.00124 | 0.98 | 5.967 | 12 | 21.99 | 20.46 | 14.97 | 26.7481 | 21.8849 | 0.55 | 0.45 | 43 | 76.367 | 48.633 | 0.86
32 | 3258102 | Furnitures & Fixtures | 45 | 10 | L.S. | 10 | 0.0001 | 0 | 0.49 | 0.74 | 0.98 | 0.99 | 1.11 | 3.414 | 2.276 | 0.6 | 0.4 | 44 | 4.31 | 5.69 | 0.86
33 | 3258103 | Computers & office equipments | 46 | 15 | L.S. | 15 | 0.00015 | 0 | 0.5 | 0.85 | 2 | 1.99 | 3 | 3.9294 | 2.7306 | 0.59 | 0.41 | 45 | 8.34 | 6.66 | 0.86
34 | 3258105 | Machineries & Equipments | 47 | 10 | L.S. | 10 | 0.0001 | 0 | 0.22 | 0.01 | 0.5 | 0.5 | 1.99 | 4.1358 | 2.6442 | 0.61 | 0.39 | 46 | 3.22 | 6.78 | 0.86
35 | 3258107 | Office Building : Repair & Maintenance | 48 | 25 | L.S. | 25 | 0.00025 | 0 | 0 | 0 | 9.98 | 10 | 0 | 2.9618 | 2.0582 | 0.59 | 0.41 | 47 | 19.98 | 5.02 | 0.765
36 | 3258106 | Residential Building : Repair & Maintenance | 49 | 40 | L.S. | 40 | 0.0004 | 0 | 0 | 0 | 8.95 | 5.58 | 4.95 | 11.9016 | 8.6184 | 0.58 | 0.42 | 48 | 19.48 | 20.52 | 0.765
37 | 3258105 | Engineering Equipments | 50 | 20 | L.S. | 20 | 0.0002 | 0 | 0.09 | 0.3 | 0.5 | 0.5 | 2 | 9.1355 | 7.4745 | 0.55 | 0.45 | 49 | 3.39 | 16.61 | 0.86
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 52 | 405.55 | 86 | 405.55 | 0.00402 | 0 | 0 | 59.7 | 24.34 | 10.99 | 33.17 | 174.7305 | 102.6195 | 0.63 | 0.37 | 51 | 128.2 | 277.35 | 0.812
39 | 3258128 | Water Transport : Repair of Speedboat(s) | 53 | 5 | L.S. | 5 | 5e-05 | 0 | 0.9 | 0 | 0.75 | 0.74 | 0.38 | 1.3603 | 0.8697 | 0.61 | 0.39 | 52 | 2.77 | 2.23 | 0.812
40 | 3258107 | Others : Repair & Maintenance | 54 | 40 | L.S. | 40 | 0.0004 | 0 | 0 | 0 | 2.5 | 4.98 | 1.49 | 17.3768 | 13.6532 | 0.56 | 0.44 | 53 | 8.97 | 31.03 | 0.902
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 59 | 70.25 | 10 | 702.5 | 0.00697 | 346.3 | 138.6 | 0 | 122 | 0 | 0 | 95.6 | 0 | 1 | 0 | 58 | 606.9 | 95.6 | 0.68
42 | 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | 60 | 1.52 | 45 | 68.25 | 0.00068 | 5.83 | 26.31 | 10.08 | 8 | 0 | 0 | 18.03 | 0 | 1 | 0 | 59 | 50.22 | 18.03 | 0.68
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | 62 | 18 | 5 | 90 | 0.00089 | 0 | 0 | 40.29 | 21 | 0 | 0 | 28.71 | 0 | 1 | 0 | 61 | 61.29 | 28.71 | 0.68
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 64 | 1.28 | 7 | 8.97 | 9e-05 | 3.73 | 2.74 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 8.97 | 0 | 0.812
45 | 4112316 | Fax -2 nos (PMO 2 Nos.). | 65 | 0.5 | 2 | 1 | 1e-05 | 0.79 | 0 | 0 | 0 | 0 | 0 | 0.21 | 0 | 1 | 0 | 64 | 0.79 | 0.21 | 0.812
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 67 | 20.5 | 17 | 20.5 | 0.0002 | 0 | 5.55 | 11.15 | 3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 20.5 | 0 | 0.68
47 | 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | 68 | 1 | 3 | 3 | 3e-05 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 3 | 0 | 0.68
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 69 | 0 | L.S | 50 | 0.0005 | 0 | 0 | 0 | 7.89 | 1.6 | 5 | 35.51 | 0 | 1 | 0 | 68 | 14.49 | 35.51 | 0.68
49 | 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 71 | 0.66 | 37 | 24.5 | 0.00024 | 3.88 | 7.14 | 6.18 | 2.27 | 0 | 0 | 5.03 | 0 | 1 | 0 | 70 | 19.47 | 5.03 | 0.812
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 72 | 1.25 | 11 | 13.75 | 0.00014 | 3.744 | 0 | 2.986 | 3.15 | 0 | 0 | 3.87 | 0 | 1 | 0 | 71 | 9.88 | 3.87 | 0.812
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | 73 | 0.75 | 2 | 1.5 | 1e-05 | 0 | 0.2 | 0 | 0 | 0 | 0 | 1.3 | 0 | 1 | 0 | 72 | 0.2 | 1.3 | 0.812
52 | 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | 74 | 0.31 | 17 | 5.25 | 5e-05 | 2.97 | 0.2 | 0 | 0.91 | 0 | 0 | 1.17 | 0 | 1 | 0 | 73 | 4.08 | 1.17 | 0.812
53 | 4112314 | Furnitures & Fixtures | 75 | 50 | LS | 50 | 0.0005 | 7.96 | 8.45 | 8.99 | 9.96 | 9.97 | 0 | 2.8954 | 1.7746 | 0.62 | 0.38 | 74 | 45.33 | 4.67 | 0.812
54 | 4112303 | Aircooler | 76 | 1 | 15 | 15 | 0.00015 | 0 | 0 | 3.77 | 2 | 3.96 | 2.99 | 1.3908 | 0.8892 | 0.61 | 0.39 | 75 | 12.72 | 2.28 | 0.812
55 | 4141101 | Land Acquisition ( 470 hectare) | 78 | 39.12 | 470 | 18386.72 | 0.18243 | 0 | 0 | 4649.65 | 5794.05 | 3879.9 | 1000 | 1531.56 | 1531.56 | 0.5 | 0.5 | 77 | 15323.6 | 3063.12 | 0.902
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | 81 | 10.31 | 119 | 1226.46 | 0.01217 | 0 | 0 | 0 | 0 | 116.72 | 192.22 | 532.1616 | 385.3584 | 0.58 | 0.42 | 80 | 308.94 | 917.52 | 0.902
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 83 | 234.52 | 5 | 1172.62 | 0.01163 | 0 | 0 | 0 | 0 | 0 | 0 | 668.3934 | 504.2266 | 0.57 | 0.43 | 82 | 0 | 1172.62 | 0.765
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 84 | 165.96 | 111 | 18421.37 | 0.18278 | 0 | 0 | 293.15 | 2773.9 | 3076.61 | 4075.22 | 4347.3197 | 3855.1703 | 0.53 | 0.47 | 83 | 10218.88 | 8202.49 | 0.765
59 | 4111307 | Re-excavation of Khal/River (New Haors) | 85 | 30.29 | 336.214 | 10184.13 | 0.10105 | 0 | 0 | 349.16 | 840.8 | 4821.52 | 2673.22 | 839.6808 | 659.7492 | 0.56 | 0.44 | 84 | 8684.7 | 1499.43 | 0.761
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 87 | 31.19 | 108.974 | 3398.89 | 0.03372 | 0 | 0 | 0 | 0 | 455.04 | 726.54 | 1219.5205 | 997.7895 | 0.55 | 0.45 | 86 | 1181.58 | 2217.31 | 0.761
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 88 | 30.33 | 67.11 | 2035.43 | 0.0202 | 0 | 0 | 0 | 0 | 452.46 | 253.65 | 771.0056 | 558.3144 | 0.58 | 0.42 | 87 | 706.11 | 1329.32 | 0.761
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 89 | 27.9 | 62.662 | 1748.43 | 0.01735 | 0 | 0 | 0 | 0 | 341.85 | 179.68 | 674.795 | 552.105 | 0.55 | 0.45 | 88 | 521.53 | 1226.9 | 0.761
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 90 | 0 | 261.238 | 21445.23 | 0.21273 | 0 | 0 | 336.91 | 3910 | 1880.15 | 2923.61 | 7188.8448 | 5205.7152 | 0.58 | 0.42 | 89 | 9050.67 | 12394.56 | 0.761
64 | 4111201 | Rehabilitation of Regulator (New Haors) | 91 | 20.96 | 7 | 146.69 | 0.00146 | 0 | 0 | 0 | 0 | 73.26 | 0 | 40.3865 | 33.0435 | 0.55 | 0.45 | 90 | 73.26 | 73.43 | 0.761
65 | 4111201 | Threshing Floor Construction | 92 | 45 | 5 | 225 | 0.00223 | 0 | 0 | 0 | 0 | 0 | 0 | 123.75 | 101.25 | 0.55 | 0.45 | 91 | 0 | 225 | 2.761
66 | 4111201 | Construction of WMG Office | 93 | 29.42 | 55 | 1618 | 0.01605 | 0 | 0 | 0 | 0 | 42.09 | 93.33 | 845.0706 | 637.5094 | 0.57 | 0.43 | 92 | 135.42 | 1482.58 | 0.765
67 | 4111201 | O&M During Construction | 94 | 0 | 1 | 120 | 0.00119 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 54 | 0.55 | 0.45 | 93 | 0 | 120 | 0.761
68 | 0 | (c) Physical Contingency ( Lump sum): | 97 | 0 | L.S. | 30.51 | 0.0003 | 0 | 0 | 0 | 0 | 0 | 0 | 16.1703 | 14.3397 | 0.53 | 0.47 | 96 | 0 | 30.51 | 0.765
69 | 0 | (d) Price Contingency (Lump sum): | 98 | 0 | L.S. | 10 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 4.6 | 0.54 | 0.46 | 97 | 0 | 10 | 0

## Annex-9_detail_phasing
| Code | Description | rindex | Total-cum | GoB-cum | RPA-cum | DPA-cum | Total-19-20 | GoB-19-20 | RPA-19-20 | DPA-19-20 | Total-20-21 | GoB-20-21 | RPA-20-21 | DPA-20-21 | Total-21-22 | GoB-21-22 | RPA-21-22 | DPA-21-22 | Total-DPP-Cost | Total-Phased-Cost-1 | Total-Phased-GoB | Total-Phased-RPA | Total-Phased-DPA | Total-Phased-Cost-2 | Check1 | Check2
0 | 3111302 | Conveyance Allowance | 11 | 1.01 | 1.01 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 2.0242 | 2.0242 | 0 | 0 | 1.4658 | 1.4658 | 0 | 0 | 5 | 4.5 | 4.5 | 0 | 0 | 4.5 | 0.5 | 0.5
1 | 3111327 | Overtime Allowance | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 6.3 | 0 | 0 | 3.7 | 3.7 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
2 | 3111338 | Other Allowance | 13 | 36.61 | 36.61 | 0 | 0 | 14 | 14 | 0 | 0 | 53.634 | 53.634 | 0 | 0 | 35.756 | 35.756 | 0 | 0 | 140 | 126 | 126 | 0 | 0 | 126 | 14 | 14
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 15 | 58.54 | 58.54 | 0 | 0 | 14.97 | 14.97 | 0 | 0 | 28.8176 | 28.8176 | 0 | 0 | 17.6624 | 17.6624 | 0 | 0 | 120 | 105.02 | 105.02 | 0 | 0 | 105.02 | 14.98 | 14.98
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 16 | 116.67 | 116.67 | 0 | 0 | 34.21 | 34.21 | 0 | 0 | 58.3544 | 58.3544 | 0 | 0 | 35.7656 | 35.7656 | 0 | 0 | 245 | 210.79 | 210.79 | 0 | 0 | 210.79 | 34.21 | 34.21
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 17 | 1603.18 | 1603.18 | 0 | 0 | 177.18 | 177.18 | 0 | 0 | 634.52 | 634.52 | 0 | 0 | 459.48 | 459.48 | 0 | 0 | 2874.35 | 2697.18 | 2697.18 | 0 | 0 | 2697.18 | 177.17 | 177.17
6 | 3211119 | Postage | 18 | 0.77 | 0.77 | 0 | 0 | 0.48 | 0.48 | 0 | 0 | 2.175 | 2.175 | 0 | 0 | 1.575 | 1.575 | 0 | 0 | 5 | 4.52 | 4.52 | 0 | 0 | 4.52 | 0.48 | 0.48
7 | 3211120 | Telephones/Telegram/Teleprinter | 19 | 0.97 | 0.97 | 0 | 0 | 0.07 | 0.07 | 0 | 0 | 2.4156 | 2.4156 | 0 | 0 | 1.5444 | 1.5444 | 0 | 0 | 5 | 4.93 | 4.93 | 0 | 0 | 4.93 | 0.07 | 0.07
8 | 3211117 | Telex/Fax/Internet | 20 | 0.44 | 0.44 | 0 | 0 | 0.1 | 0.1 | 0 | 0 | 2.497 | 2.497 | 0 | 0 | 1.962 | 1.962 | 0 | 0 | 5 | 4.899 | 4.899 | 0 | 0 | 4.899 | 0.101 | 0.101
9 | 3221104 | Registration Fee (Vehicles) | 21 | 11.92 | 11.92 | 0 | 0 | 0.17 | 0.17 | 0 | 0 | 4.9833 | 4.9833 | 0 | 0 | 2.9267 | 2.9267 | 0 | 0 | 20 | 19.83 | 19.83 | 0 | 0 | 19.83 | 0.17 | 0.17
10 | 3211115 | Water | 22 | 1.11 | 1.11 | 0 | 0 | 0.55 | 0.55 | 0 | 0 | 2.0313 | 2.0313 | 0 | 0 | 1.2987 | 1.2987 | 0 | 0 | 5 | 4.44 | 4.44 | 0 | 0 | 4.44 | 0.56 | 0.56
11 | 3211113 | Electricity | 23 | 8.74 | 8.74 | 0 | 0 | 2.89 | 2.89 | 0 | 0 | 4.609 | 4.609 | 0 | 0 | 3.771 | 3.771 | 0 | 0 | 20 | 17.12 | 17.12 | 0 | 0 | 17.12 | 2.88 | 2.88
12 | 3243102 | Gas & Fuel | 24 | 17.52 | 17.52 | 0 | 0 | 4.02 | 4.02 | 0 | 0 | 11.2545 | 11.2545 | 0 | 0 | 7.1955 | 7.1955 | 0 | 0 | 40 | 35.97 | 35.97 | 0 | 0 | 35.97 | 4.03 | 4.03
13 | 3243101 | Petrol and Lubricant | 25 | 64.59 | 64.59 | 0 | 0 | 24.18 | 24.18 | 0 | 0 | 46.3068 | 46.3068 | 0 | 0 | 34.9332 | 34.9332 | 0 | 0 | 170 | 145.83 | 145.83 | 0 | 0 | 145.83 | 24.17 | 24.17
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 26 | 1.16 | 1.16 | 0 | 0 | 0.91 | 0.91 | 0 | 0 | 0.51205 | 0.51205 | 0 | 0 | 0.41895 | 0.41895 | 0 | 0 | 3 | 2.091 | 2.091 | 0 | 0 | 2.091 | 0.909 | 0.909
15 | 3255102 | Printing & Binding | 27 | 34.16 | 34.16 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 9.355 | 9.355 | 0 | 0 | 5.981 | 5.981 | 0 | 0 | 50 | 49.496 | 49.496 | 0 | 0 | 49.496 | 0.504 | 0.504
16 | 3255104 | Stationery, Seals & Stamps | 28 | 49.91 | 49.91 | 0 | 0 | 19.95 | 19.95 | 0 | 0 | 31.5869 | 31.5869 | 0 | 0 | 18.5511 | 18.5511 | 0 | 0 | 120 | 100.048 | 100.048 | 0 | 0 | 100.048 | 19.952 | 19.952
17 | 3211127 | Books & Periodicals | 29 | 0.28 | 0.28 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0.8816 | 0.8816 | 0 | 0 | 0.6384 | 0.6384 | 0 | 0 | 2 | 1.8 | 1.8 | 0 | 0 | 1.8 | 0.2 | 0.2
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 119 | 119 | 0 | 119 | 0 | 119 | 0 | 0
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 32 | 301.5 | 22.54 | 278.96 | 0 | 22.21 | 2.3809 | 19.8291 | 0 | 127.794 | 13.6995 | 114.0945 | 0 | 85.196 | 9.133 | 76.063 | 0 | 536.7 | 514.49 | 45.3725 | 469.1175 | 0 | 514.49 | 22.21 | 22.21
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 33 | 1346.63 | 80.34 | 1266.29 | 0 | 338.12 | 36.2465 | 301.8735 | 0 | 910.5705 | 97.6132 | 812.9573 | 0 | 534.7795 | 57.3284 | 477.4511 | 0 | 3130.1 | 2791.98 | 235.2815 | 2556.6985 | 0 | 2791.98 | 338.12 | 338.12
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 34 | 578.2 | 35.47 | 542.73 | 0 | 82.97 | 8.8944 | 74.0756 | 0 | 368.5165 | 39.505 | 329.0115 | 0 | 301.5135 | 32.3222 | 269.1913 | 0 | 1331.2 | 1248.23 | 107.2972 | 1140.9328 | 0 | 1248.23 | 82.97 | 82.97
22 | 3211109 | Casual labour/Job worker | 35 | 10.96 | 10.96 | 0 | 0 | 3.49 | 3.49 | 0 | 0 | 4.681 | 4.681 | 0 | 0 | 2.869 | 2.869 | 0 | 0 | 22 | 18.51 | 18.51 | 0 | 0 | 18.51 | 3.49 | 3.49
23 | 3256103 | Consumable Stores | 36 | 3.74 | 3.74 | 0 | 0 | 3 | 3 | 0 | 0 | 4.7908 | 4.7908 | 0 | 0 | 3.4692 | 3.4692 | 0 | 0 | 15 | 12 | 12 | 0 | 0 | 12 | 3 | 3
24 | 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | 37 | 5168.01 | 0 | 0 | 5168.01 | 450 | 0 | 0 | 450 | 1374.571 | 0 | 0 | 1374.571 | 878.824 | 0 | 0 | 878.824 | 7901.4 | 7421.405 | 0 | 0 | 7421.405 | 7421.405 | 479.995 | 479.995
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 38 | 12.73 | 12.73 | 0 | 0 | 3 | 3 | 0 | 0 | 8.2766 | 8.2766 | 0 | 0 | 5.9934 | 5.9934 | 0 | 0 | 30 | 27 | 27 | 0 | 0 | 27 | 3 | 3
26 | 3111332 | b) Interim Evaluation | 39 | 1.29 | 1.29 | 0 | 0 | 0.41 | 0.41 | 0 | 0 | 8.3 | 8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 9.59 | 9.59 | 0 | 0 | 9.59 | 0.41 | 0.41
27 | 3111332 | c) Progress Monitoring | 40 | 1.3 | 1.3 | 0 | 0 | 0.41 | 0.41 | 0 | 0 | 4.145 | 4.145 | 0 | 0 | 4.145 | 4.145 | 0 | 0 | 10 | 9.59 | 9.59 | 0 | 0 | 9.59 | 0.41 | 0.41
28 | 3257104 | Survey | 41 | 85.02 | 85.02 | 0 | 0 | 30 | 30 | 0 | 0 | 26.7786 | 26.7786 | 0 | 0 | 20.2014 | 20.2014 | 0 | 0 | 162 | 132 | 132 | 0 | 0 | 132 | 30 | 30
29 | 3255101 | Computer Consumables | 42 | 20.47 | 20.47 | 0 | 0 | 10 | 10 | 0 | 0 | 16.242 | 16.242 | 0 | 0 | 13.2889 | 13.2889 | 0 | 0 | 60 | 50.001 | 50.001 | 0 | 0 | 50.001 | 9.999 | 9.999
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 43 | 875.46 | 875.46 | 0 | 0 | 299.96 | 299.96 | 0 | 0 | 299.0163 | 299.0163 | 0 | 0 | 225.5737 | 225.5737 | 0 | 0 | 1700 | 1400.05 | 1400.05 | 0 | 0 | 1400.05 | 299.95 | 299.95
31 | 3258101 | Motor Vehicles | 45 | 61.4 | 61.4 | 0 | 0 | 14.97 | 14.97 | 0 | 0 | 26.7481 | 26.7481 | 0 | 0 | 21.8849 | 21.8849 | 0 | 0 | 125 | 110.033 | 110.033 | 0 | 0 | 110.033 | 14.967 | 14.967
32 | 3258102 | Furnitures & Fixtures | 46 | 3.2 | 3.2 | 0 | 0 | 1.11 | 1.11 | 0 | 0 | 3.414 | 3.414 | 0 | 0 | 2.276 | 2.276 | 0 | 0 | 10 | 8.89 | 8.89 | 0 | 0 | 8.89 | 1.11 | 1.11
33 | 3258103 | Computers & office equipments | 47 | 5.34 | 5.34 | 0 | 0 | 3 | 3 | 0 | 0 | 3.9294 | 3.9294 | 0 | 0 | 2.7306 | 2.7306 | 0 | 0 | 15 | 12 | 12 | 0 | 0 | 12 | 3 | 3
34 | 3258105 | Machineries & Equipments | 48 | 1.22 | 1.22 | 0 | 0 | 1.99 | 1.99 | 0 | 0 | 4.1358 | 4.1358 | 0 | 0 | 2.6442 | 2.6442 | 0 | 0 | 10 | 8 | 8 | 0 | 0 | 8 | 2 | 2
35 | 3258107 | Office Building : Repair & Maintenance | 49 | 19.98 | 19.98 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9618 | 2.9618 | 0 | 0 | 2.0582 | 2.0582 | 0 | 0 | 25 | 25 | 25 | 0 | 0 | 25 | 0 | 0
36 | 3258106 | Residential Building : Repair & Maintenance | 50 | 14.53 | 14.53 | 0 | 0 | 4.95 | 4.95 | 0 | 0 | 11.9016 | 11.9016 | 0 | 0 | 8.6184 | 8.6184 | 0 | 0 | 40 | 35.05 | 35.05 | 0 | 0 | 35.05 | 4.95 | 4.95
37 | 3258105 | Engineering Equipments | 51 | 1.39 | 1.39 | 0 | 0 | 2 | 2 | 0 | 0 | 9.1355 | 9.1355 | 0 | 0 | 7.4745 | 7.4745 | 0 | 0 | 20 | 18 | 18 | 0 | 0 | 18 | 2 | 2
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 53 | 95.03 | 10.83 | 84.2 | 0 | 33.17 | 4.8826 | 28.2874 | 0 | 174.7305 | 25.7203 | 149.0102 | 0 | 102.6195 | 15.1056 | 87.5139 | 0 | 405.55 | 372.38 | 51.6559 | 320.7241 | 0 | 372.38 | 33.17 | 33.17
39 | 3258128 | Water Transport : Repair of Speedboat(s) | 54 | 2.39 | 2.39 | 0 | 0 | 0.38 | 0.38 | 0 | 0 | 1.3603 | 1.3603 | 0 | 0 | 0.8697 | 0.8697 | 0 | 0 | 5 | 4.62 | 4.62 | 0 | 0 | 4.62 | 0.38 | 0.38
40 | 3258107 | Others : Repair & Maintenance | 55 | 7.48 | 7.48 | 0 | 0 | 1.49 | 1.49 | 0 | 0 | 17.3768 | 17.3768 | 0 | 0 | 13.6532 | 13.6532 | 0 | 0 | 40 | 38.51 | 38.51 | 0 | 0 | 38.51 | 1.49 | 1.49
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 60 | 606.9 | 606.9 | 0 | 0 | 0 | 0 | 0 | 0 | 95.6 | 95.6 | 0 | 0 | 0 | 0 | 0 | 0 | 702.5 | 702.5 | 702.5 | 0 | 0 | 702.5 | 0 | 0
42 | 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | 61 | 50.22 | 50.22 | 0 | 0 | 0 | 0 | 0 | 0 | 18.03 | 18.03 | 0 | 0 | 0 | 0 | 0 | 0 | 68.25 | 68.25 | 68.25 | 0 | 0 | 68.25 | 0 | 0
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | 63 | 61.29 | 61.29 | 0 | 0 | 0 | 0 | 0 | 0 | 28.71 | 28.71 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 90 | 0 | 0 | 90 | 0 | 0
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 65 | 8.97 | 8.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.97 | 8.97 | 8.97 | 0 | 0 | 8.97 | 0 | 0
45 | 4112316 | Fax -2 nos (PMO 2 Nos.). | 66 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.21 | 1.21 | 0 | 0 | 1.21 | -0.21 | -0.21
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 68 | 20.5 | 20.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.5 | 20.5 | 20.5 | 0 | 0 | 20.5 | 0 | 0
47 | 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | 69 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 0
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 70 | 9.49 | 9.49 | 0 | 0 | 5 | 5 | 0 | 0 | 35.51 | 35.51 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 45 | 45 | 0 | 0 | 45 | 5 | 5
49 | 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 72 | 19.47 | 19.47 | 0 | 0 | 0 | 0 | 0 | 0 | 5.03 | 5.03 | 0 | 0 | 0 | 0 | 0 | 0 | 24.5 | 24.5 | 24.5 | 0 | 0 | 24.5 | 0 | 0
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 73 | 9.88 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 3.87 | 3.87 | 0 | 0 | 0 | 0 | 0 | 0 | 13.75 | 13.75 | 13.75 | 0 | 0 | 13.75 | 0 | 0
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | 74 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 1.5 | 0 | 0 | 1.5 | 0 | 0
52 | 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | 75 | 4.08 | 4.08 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 5.25 | 5.25 | 0 | 0 | 5.25 | 0 | 0
53 | 4112314 | Furnitures & Fixtures | 76 | 45.32 | 45.32 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8954 | 2.8954 | 0 | 0 | 1.7746 | 1.7746 | 0 | 0 | 50 | 49.99 | 49.99 | 0 | 0 | 49.99 | 0.01 | 0.01
54 | 4112303 | Aircooler | 77 | 9.73 | 9.73 | 0 | 0 | 2.99 | 2.99 | 0 | 0 | 1.3908 | 1.3908 | 0 | 0 | 0.8892 | 0.8892 | 0 | 0 | 15 | 12.01 | 12.01 | 0 | 0 | 12.01 | 2.99 | 2.99
55 | 4141101 | Land Acquisition ( 470 hectare) | 79 | 14323.6 | 14323.6 | 0 | 0 | 1000 | 1000 | 0 | 0 | 1531.56 | 1531.56 | 0 | 0 | 1531.56 | 1531.56 | 0 | 0 | 18386.72 | 17386.72 | 17386.72 | 0 | 0 | 17386.72 | 1000 | 1000
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | 82 | 116.72 | 16.34 | 100.38 | 0 | 192.22 | 26.9108 | 165.3092 | 0 | 532.1616 | 74.5026 | 457.659 | 0 | 385.3584 | 53.9502 | 331.4082 | 0 | 1226.46 | 1034.24 | 144.7928 | 889.4472 | 0 | 1034.24 | 192.22 | 192.22
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668.3934 | 93.5751 | 574.8183 | 0 | 504.2266 | 70.5917 | 433.6349 | 0 | 1172.62 | 1172.62 | 164.1668 | 1008.4532 | 0 | 1172.62 | 0 | 0
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 85 | 6143.66 | 889.49 | 5254.17 | 0 | 4075.22 | 570.5308 | 3504.6892 | 0 | 4347.3197 | 608.6248 | 3738.6949 | 0 | 3855.1703 | 539.7238 | 3315.4465 | 0 | 18421.37 | 14346.15 | 2037.8386 | 12308.3114 | 0 | 14346.15 | 4075.22 | 4075.22
59 | 4111307 | Re-excavation of Khal/River (New Haors) | 86 | 6011.48 | 791.08 | 5220.4 | 0 | 2673.22 | 374.2508 | 2298.9692 | 0 | 839.6808 | 117.5553 | 722.1255 | 0 | 659.7492 | 92.3649 | 567.3843 | 0 | 10184.13 | 7510.91 | 1001.0002 | 6509.9098 | 0 | 7510.91 | 2673.22 | 2673.22
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 88 | 455.04 | 64.36 | 390.68 | 0 | 726.54 | 101.7156 | 624.8244 | 0 | 1219.5205 | 170.7329 | 1048.7876 | 0 | 997.7895 | 139.6905 | 858.099 | 0 | 3398.89 | 2672.35 | 374.7834 | 2297.5666 | 0 | 2672.35 | 726.54 | 726.54
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 89 | 452.46 | 63.49 | 388.97 | 0 | 253.65 | 35.511 | 218.139 | 0 | 771.0056 | 107.9408 | 663.0648 | 0 | 558.3144 | 78.164 | 480.1504 | 0 | 2035.43 | 1781.78 | 249.5948 | 1532.1852 | 0 | 1781.78 | 253.65 | 253.65
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 90 | 341.85 | 48.84 | 293.01 | 0 | 179.68 | 25.1552 | 154.5248 | 0 | 674.795 | 94.4713 | 580.3237 | 0 | 552.105 | 77.2947 | 474.8103 | 0 | 1748.43 | 1568.75 | 220.606 | 1348.144 | 0 | 1568.75 | 179.68 | 179.68
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 91 | 6127.06 | 779.02 | 5348.04 | 0 | 2923.61 | 409.3054 | 2514.3046 | 0 | 7188.8448 | 1006.4383 | 6182.4065 | 0 | 5205.7152 | 728.8001 | 4476.9151 | 0 | 21445.23 | 18521.62 | 2514.2584 | 16007.3616 | 0 | 18521.62 | 2923.61 | 2923.61
64 | 4111201 | Rehabilitation of Regulator (New Haors) | 92 | 73.26 | 9.77 | 63.49 | 0 | 0 | 0 | 0 | 0 | 40.3865 | 5.6541 | 34.7324 | 0 | 33.0435 | 4.6261 | 28.4174 | 0 | 146.69 | 146.69 | 20.0502 | 126.6398 | 0 | 146.69 | 0 | 2.8422e-14
65 | 4111201 | Threshing Floor Construction | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123.75 | 17.325 | 106.425 | 0 | 101.25 | 14.175 | 87.075 | 0 | 225 | 225 | 31.5 | 193.5 | 0 | 225 | 0 | 0
66 | 4111201 | Construction of WMG Office | 94 | 42.09 | 5.47 | 36.62 | 0 | 93.33 | 13.0662 | 80.2638 | 0 | 845.0706 | 118.3099 | 726.7607 | 0 | 637.5094 | 89.2513 | 548.2581 | 0 | 1618 | 1524.67 | 213.0312 | 1311.6388 | 0 | 1524.67 | 93.33 | 93.33
67 | 4111201 | O&M During Construction | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 9.24 | 56.76 | 0 | 54 | 7.56 | 46.44 | 0 | 120 | 120 | 16.8 | 103.2 | 0 | 120 | 0 | 1.4211e-14
68 | 0 | (c) Physical Contingency ( Lump sum): | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.1703 | 16.1703 | 0 | 0 | 14.3397 | 14.3397 | 0 | 0 | 30.51 | 30.51 | 30.51 | 0 | 0 | 30.51 | 0 | 0
69 | 0 | (d) Price Contingency (Lump sum): | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 5.4 | 0 | 0 | 4.6 | 4.6 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0

## EIRR_INPUT
| Financial_Year | Financial_Cost | Economic_Cost | Financial _Input_Index | Financial _Input_Index.1
0 | Year-1 | 1456.294 | 1212.6888 | 8 | 8
1 | Year-2 | 2682.927 | 2329.3642 | 9 | 9
2 | Year-3 | 7942.686 | 6957.1397 | 10 | 10
3 | Year-4 | 15867.59 | 13168.0538 | 11 | 11
4 | Year-5 | 17642.42 | 14304.0085 | 12 | 12
5 | Year-6 | 13726.97 | 10812.9973 | 13 | 13
6 | Year-7 | 23494.4094 | 18938.1404 | 14 | 14
7 | Year-8 | 17972.7036 | 14494.9743 | 15 | 15

## Distribution_of_cost
| Item | costcode | rindex | 1st Revised | 2nd revised | difference
0 | Office Administration | 1 | 2 | 5403.27 | 5638.35 | 235.08
1 | Fuel & Lubricant | 2 | 3 | 350 | 210 | -140
2 | Training and Livelihood | 3 | 4 | 4491.97 | 5117 | 625.03
3 | Consulatantcy | 4 | 5 | 7901.4 | 7901.4 | 0
4 | Repair & Maintenance | 5 | 6 | 265 | 290 | 25
5 | Vehicle & Equipments | 6 | 7 | 1066.22 | 1054.22 | -12
6 | Land Acquisition | 7 | 8 | 24000 | 18386.72 | -5613.28
7 | Civilworks | 8 | 9 | 53727 | 62147.8 | 8420.8
8 | contingency | 9 | 10 | 660.14 | 40.51 | -619.63

## quantity_comaprision
| Code | Description | U1 | Q1 | U2 | Q2 | U3 | Q3 | rindex | annex_index
0 | 3111302 | Conveyance Allowance | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 12 | 2
1 | 3111327 | Overtime Allowance | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 13 | 3
2 | 3111338 | Other Allowance | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 14 | 4
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 16 | 5
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 17 | 6
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 18 | 7
6 | 3211119 | Postage | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 19 | 8
7 | 3211120 | Telephones/Telegram/Teleprinter | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 20 | 9
8 | 3211117 | Telex/Fax/Internet | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 21 | 10
9 | 3221104 | Registration Fee (Vehicles) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 22 | 11
10 | 3211115 | Water | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 23 | 12
11 | 3211113 | Electricity | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 24 | 13
12 | 3243102 | Gas & Fuel | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 25 | 14
13 | 3243101 | Petrol and Lubricant | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 26 | 15
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 27 | 16
15 | 3255102 | Printing & Binding | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 28 | 17
16 | 3255104 | Stationery, Seals & Stamps | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 29 | 18
17 | 3211127 | Books & Periodicals | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 30 | 19
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 32 | 20
19 | 0 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 33 | 21
20 | 0 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 34 | 22
21 | 0 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 35 | 23
22 | 3211109 | Casual labour/Job worker | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 36 | 24
23 | 3256103 | Consumable Stores | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 37 | 25
24 | 3257101 | Consultancy : International - 71 M/M National - 324 M/M | MM | 71+234 | MM | 56+532 | 0 | 0 | 38 | 26
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 39 | 27
26 | 0 | b) Interim Evaluation | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 40 | 28
27 | 0 | c) Progress Monitoring | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 41 | 29
28 | 3257104 | Survey | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 42 | 30
29 | 3255101 | Computer Consumables | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 43 | 31
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 0 | 1 Item | 0 | 1 Item | 0 | 0 | 44 | 32
31 | 3258101 | Motor Vehicles | 0 | L.S. | 0 | L.S. | 0 | 0 | 46 | 33
32 | 3258102 | Furnitures & Fixtures | 0 | L.S. | 0 | L.S. | 0 | 0 | 47 | 34
33 | 3258103 | Computers & office equipments | 0 | L.S. | 0 | L.S. | 0 | 0 | 48 | 35
34 | 3258105 | Machineries & Equipments | 0 | L.S. | 0 | L.S. | 0 | 0 | 49 | 36
35 | 3258107 | Office Building : Repair & Maintenance | 0 | L.S. | 0 | L.S. | 0 | 0 | 50 | 37
36 | 3258106 | Residential Building : Repair & Maintenance | 0 | L.S. | 0 | L.S. | 0 | 0 | 51 | 38
37 | 3258105 | Engineering Equipments | 0 | L.S. | 0 | L.S. | 0 | 0 | 52 | 39
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 0 | 104 | 0 | 86 | 0 | 0 | 54 | 40
39 | 3258128 | Water Transport : Repair of Speedboat(s) | 0 | L.S. | 0 | L.S. | 0 | 0 | 55 | 41
40 | 3258107 | Others : Repair & Maintenance | 0 | L.S. | 0 | L.S. | 0 | 0 | 56 | 42
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos | 10 | Nos | 10 | Nos | 0 | 68 | 43
42 | 4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | Nos | 35 | Nos | 45 | Nos | 0 | 69 | 44
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | Nos | 6 | Nos | 5 | Nos | 0 | 71 | 45
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos | 7 | Nos | 7 | Nos | 0 | 73 | 46
45 | 4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos | 7 | Nos | 2 | Nos | 0 | 74 | 47
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos | 17 | Nos | 17 | Nos | 0 | 76 | 48
47 | 4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos | 6 | Nos | 3 | Nos | 0 | 77 | 49
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 0 | L.S | 0 | L.S | 0 | 0 | 78 | 50
49 | 4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | Nos | 30 | Nos | 37 | Nos | 0 | 80 | 51
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos | 11 | Nos | 11 | Nos | 0 | 81 | 52
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | Nos | 2 | Nos | 2 | Nos | 0 | 82 | 53
52 | 4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos | 11 | Nos | 17 | Nos | 0 | 83 | 54
53 | 4112314 | Furnitures & Fixtures | 0 | LS | 0 | LS | 0 | 0 | 84 | 55
54 | 4112303 | Aircooler | Nos | 15 | Nos | 15 | Nos | 0 | 85 | 56
55 | 4141101 | Land Acquisition ( 470 hectare) | ha | 470 | ha | 470 | ha | 0 | 87 | 57
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | Nos | 131 | Nos | 119 | Nos | 0 | 90 | 58
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | Nos | 7(2+5) | Nos | 5 | Nos | 0 | 92 | 59
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos | 137(57+35+14) | Nos | 111 | Nos | 0 | 93 | 60
59 | 4111307 | Re-excavation of Khal/River (New Haors) | Km | 318 | Km | 336.214 | Km | 0 | 94 | 61
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | Km | 143 | Km | 108.974 | Km | 0 | 96 | 62
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | Km | 84.31 | Km | 67.11 | Km | 0 | 97 | 63
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | Km | 87.03 | Km | 62.662 | Km | 0 | 98 | 64
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km | 263.24 | Km | 261.238 | Km | 0 | 99 | 65
64 | 4111201 | Rehabilitation of Regulator (New Haors) | Nos | 8 | Nos | 7 | Nos | 0 | 100 | 66
65 | 4111201 | Threshing Floor Construction | Nos | 0 | Nos | 5 | Nos | 0 | 102 | 67
66 | 4111201 | Construction of WMG Office | Nos | 60 | Nos | 55 | Nos | 0 | 103 | 68
67 | 4111201 | O&M During Construction | Iten | L.S | Nos | 1 | 0 | 0 | 104 | 69
68 | 0 | (c) Physical Contingency ( Lump sum): | Item | L.S. | Item | L.S. | 0 | 0 | 107 | 0
69 | 0 | (d) Price Contingency (Lump sum): | Item | L.S. | Item | L.S. | 0 | 0 | 108 | 0

## Annex-9_detail_phasing_modified
| Code | Description | rindex | Total-cum | GoB-cum | RPA-cum | DPA-cum | Total-20-21 | GoB-20-21 | RPA-20-21 | DPA-20-21 | Total-21-22 | GoB-21-22 | RPA-21-22 | DPA-21-22 | Alloc_Total | Alloc_GoB | Alloc_RPA | Alloc_DPA | Remaining_Total | Remaining_Gob | Remaining_RPA | Remaining_DPA | Total-DPP-Cost | Total-Phased-Cost-1 | Total-Phased-GoB | Total-Phased-RPA | Total-Phased-DPA | Total-Phased-Cost-2 | Check1 | Check2
0 | 3111302 | Conveyance Allowance | 11 | 1.51 | 1.51 | 0 | 0 | 2.0242 | 2.0242 | 0 | 0 | 1.4658 | 1.4658 | 0 | 0 | 5 | 5 | 0 | 0 | 3.49 | 3.49 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
1 | 3111327 | Overtime Allowance | 12 | 0 | 0 | 0 | 0 | 6.3 | 6.3 | 0 | 0 | 3.7 | 3.7 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
2 | 3111338 | Other Allowance | 13 | 50.61 | 50.61 | 0 | 0 | 53.634 | 53.634 | 0 | 0 | 35.756 | 35.756 | 0 | 0 | 140 | 140 | 0 | 0 | 89.39 | 89.39 | 0 | 0 | 140 | 140 | 140 | 0 | 0 | 140 | 0 | 0
3 | 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 15 | 73.523 | 73.523 | 0 | 0 | 28.8176 | 28.8176 | 0 | 0 | 17.6624 | 17.6624 | 0 | 0 | 120 | 120 | 0 | 0 | 46.477 | 46.477 | 0 | 0 | 120 | 120.003 | 120.003 | 0 | 0 | 120.003 | -0.003 | -0.003
4 | 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 16 | 150.88 | 150.88 | 0 | 0 | 58.3544 | 58.3544 | 0 | 0 | 35.7656 | 35.7656 | 0 | 0 | 245 | 245 | 0 | 0 | 94.12 | 94.12 | 0 | 0 | 245 | 245 | 245 | 0 | 0 | 245 | 0 | 0
5 | 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 17 | 1780.35 | 1780.35 | 0 | 0 | 634.52 | 634.52 | 0 | 0 | 459.48 | 459.48 | 0 | 0 | 2874.35 | 2874.35 | 0 | 0 | 1094 | 1094 | 0 | 0 | 2874.35 | 2874.35 | 2874.35 | 0 | 0 | 2874.35 | 0 | 0
6 | 3211119 | Postage | 18 | 1.25 | 1.25 | 0 | 0 | 2.175 | 2.175 | 0 | 0 | 1.575 | 1.575 | 0 | 0 | 5 | 5 | 0 | 0 | 3.75 | 3.75 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
7 | 3211120 | Telephones/Telegram/Teleprinter | 19 | 1.04 | 1.04 | 0 | 0 | 2.4156 | 2.4156 | 0 | 0 | 1.5444 | 1.5444 | 0 | 0 | 5 | 5 | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
8 | 3211117 | Telex/Fax/Internet | 20 | 0.541 | 0.541 | 0 | 0 | 2.497 | 2.497 | 0 | 0 | 1.962 | 1.962 | 0 | 0 | 5 | 5 | 0 | 0 | 4.459 | 4.459 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
9 | 3221104 | Registration Fee (Vehicles) | 21 | 12.09 | 12.09 | 0 | 0 | 4.9833 | 4.9833 | 0 | 0 | 2.9267 | 2.9267 | 0 | 0 | 20 | 20 | 0 | 0 | 7.91 | 7.91 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 20 | 0 | 0
10 | 3211115 | Water | 22 | 1.67 | 1.67 | 0 | 0 | 2.0313 | 2.0313 | 0 | 0 | 1.2987 | 1.2987 | 0 | 0 | 5 | 5 | 0 | 0 | 3.33 | 3.33 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
11 | 3211113 | Electricity | 23 | 11.62 | 11.62 | 0 | 0 | 4.609 | 4.609 | 0 | 0 | 3.771 | 3.771 | 0 | 0 | 20 | 20 | 0 | 0 | 8.38 | 8.38 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 20 | 0 | 0
12 | 3243102 | Gas & Fuel | 24 | 21.55 | 21.55 | 0 | 0 | 11.2545 | 11.2545 | 0 | 0 | 7.1955 | 7.1955 | 0 | 0 | 40 | 40 | 0 | 0 | 18.45 | 18.45 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 40 | -7.1054e-15 | -7.1054e-15
13 | 3243101 | Petrol and Lubricant | 25 | 88.76 | 88.76 | 0 | 0 | 46.3068 | 46.3068 | 0 | 0 | 34.9332 | 34.9332 | 0 | 0 | 170 | 170 | 0 | 0 | 81.24 | 81.24 | 0 | 0 | 170 | 170 | 170 | 0 | 0 | 170 | 0 | 0
14 | 3221108 | Insurance/Bank Charges (including Vehicles) | 26 | 2.07 | 2.07 | 0 | 0 | 0.51205 | 0.51205 | 0 | 0 | 0.41895 | 0.41895 | 0 | 0 | 3 | 3 | 0 | 0 | 0.93 | 0.93 | 0 | 0 | 3 | 3.001 | 3.001 | 0 | 0 | 3.001 | -0.001 | -0.001
15 | 3255102 | Printing & Binding | 27 | 34.664 | 34.664 | 0 | 0 | 9.355 | 9.355 | 0 | 0 | 5.981 | 5.981 | 0 | 0 | 50 | 50 | 0 | 0 | 15.336 | 15.336 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 50 | -7.1054e-15 | -7.1054e-15
16 | 3255104 | Stationery, Seals & Stamps | 28 | 69.862 | 69.862 | 0 | 0 | 31.5869 | 31.5869 | 0 | 0 | 18.5511 | 18.5511 | 0 | 0 | 120 | 120 | 0 | 0 | 50.138 | 50.138 | 0 | 0 | 120 | 120 | 120 | 0 | 0 | 120 | 0 | 0
17 | 3211127 | Books & Periodicals | 29 | 0.48 | 0.48 | 0 | 0 | 0.8816 | 0.8816 | 0 | 0 | 0.6384 | 0.6384 | 0 | 0 | 2 | 2 | 0 | 0 | 1.52 | 1.52 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0
18 | 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 31 | 0 | 0 | 0 | 0 | 119 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 119 | 0 | 119 | 0 | 119 | 0 | 119 | 119 | 0 | 119 | 0 | 119 | 0 | 0
19 | 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 32 | 323.71 | 25.25 | 298.46 | 0 | 127.794 | 23.4885 | 104.3055 | 0 | 85.196 | 15.659 | 69.537 | 0 | 536.7 | 64.4 | 472.3 | 0 | 212.99 | 39.15 | 173.84 | 0 | 536.7 | 536.7 | 64.3976 | 472.3024 | 0 | 536.7 | 0 | 0
20 | 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 33 | 1684.75 | 114.81 | 1569.94 | 0 | 910.5705 | 163.2653 | 747.3052 | 0 | 534.7795 | 95.886 | 438.8935 | 0 | 3130.1 | 373.9 | 2756.2 | 0 | 1445.35 | 259.09 | 1186.26 | 0 | 3130.1 | 3130.1 | 373.9613 | 2756.1387 | 0 | 3130.1 | 0 | -4.5475e-13
21 | 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 34 | 661.17 | 42.58 | 618.59 | 0 | 368.5165 | 64.4167 | 304.0998 | 0 | 301.5135 | 52.7046 | 248.8089 | 0 | 1331.2 | 159.7 | 1171.5 | 0 | 670.03 | 117.12 | 552.91 | 0 | 1331.2 | 1331.2 | 159.7012 | 1171.4988 | 0 | 1331.2 | 0 | -2.2737e-13
22 | 3211109 | Casual labour/Job worker | 35 | 14.45 | 14.45 | 0 | 0 | 4.681 | 4.681 | 0 | 0 | 2.869 | 2.869 | 0 | 0 | 22 | 22 | 0 | 0 | 7.55 | 7.55 | 0 | 0 | 22 | 22 | 22 | 0 | 0 | 22 | 0 | 0
23 | 3256103 | Consumable Stores | 36 | 6.74 | 6.74 | 0 | 0 | 4.7908 | 4.7908 | 0 | 0 | 3.4692 | 3.4692 | 0 | 0 | 15 | 15 | 0 | 0 | 8.26 | 8.26 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0
24 | 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | 37 | 5648.005 | 0 | 0 | 5648.005 | 1374.571 | 0 | 0 | 1374.571 | 878.824 | 0 | 0 | 878.824 | 7901.4 | 0 | 0 | 7901.4 | 2253.395 | 0 | 0 | 2253.395 | 7901.4 | 7901.4 | 0 | 0 | 7901.4 | 7901.4 | 0 | 0
25 | 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 38 | 15.73 | 15.73 | 0 | 0 | 8.2766 | 8.2766 | 0 | 0 | 5.9934 | 5.9934 | 0 | 0 | 30 | 30 | 0 | 0 | 14.27 | 14.27 | 0 | 0 | 30 | 30 | 30 | 0 | 0 | 30 | 0 | 0
26 | 3111332 | b) Interim Evaluation | 39 | 1.7 | 1.7 | 0 | 0 | 8.3 | 8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 8.3 | 8.3 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
27 | 3111332 | c) Progress Monitoring | 40 | 1.71 | 1.71 | 0 | 0 | 4.145 | 4.145 | 0 | 0 | 4.145 | 4.145 | 0 | 0 | 10 | 10 | 0 | 0 | 8.29 | 8.29 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
28 | 3257104 | Survey | 41 | 115.02 | 115.02 | 0 | 0 | 26.7786 | 26.7786 | 0 | 0 | 20.2014 | 20.2014 | 0 | 0 | 162 | 162 | 0 | 0 | 46.98 | 46.98 | 0 | 0 | 162 | 162 | 162 | 0 | 0 | 162 | 0 | 0
29 | 3255101 | Computer Consumables | 42 | 30.469 | 30.469 | 0 | 0 | 16.242 | 16.242 | 0 | 0 | 13.2889 | 13.2889 | 0 | 0 | 60 | 60 | 0 | 0 | 29.531 | 29.531 | 0 | 0 | 60 | 60 | 60 | 0 | 0 | 60 | 0 | 0
30 | 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 43 | 1175.41 | 1175.41 | 0 | 0 | 299.0163 | 299.0163 | 0 | 0 | 225.5737 | 225.5737 | 0 | 0 | 1700 | 1700 | 0 | 0 | 524.59 | 524.59 | 0 | 0 | 1700 | 1700 | 1700 | 0 | 0 | 1700 | 0 | 0
31 | 3258101 | Motor Vehicles | 45 | 76.367 | 76.367 | 0 | 0 | 26.7481 | 26.7481 | 0 | 0 | 21.8849 | 21.8849 | 0 | 0 | 125 | 125 | 0 | 0 | 48.633 | 48.633 | 0 | 0 | 125 | 125 | 125 | 0 | 0 | 125 | 0 | 0
32 | 3258102 | Furnitures & Fixtures | 46 | 4.31 | 4.31 | 0 | 0 | 3.414 | 3.414 | 0 | 0 | 2.276 | 2.276 | 0 | 0 | 10 | 10 | 0 | 0 | 5.69 | 5.69 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
33 | 3258103 | Computers & office equipments | 47 | 8.34 | 8.34 | 0 | 0 | 3.9294 | 3.9294 | 0 | 0 | 2.7306 | 2.7306 | 0 | 0 | 15 | 15 | 0 | 0 | 6.66 | 6.66 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0
34 | 3258105 | Machineries & Equipments | 48 | 3.22 | 3.22 | 0 | 0 | 4.1358 | 4.1358 | 0 | 0 | 2.6442 | 2.6442 | 0 | 0 | 10 | 10 | 0 | 0 | 6.78 | 6.78 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0
35 | 3258107 | Office Building : Repair & Maintenance | 49 | 19.98 | 19.98 | 0 | 0 | 2.9618 | 2.9618 | 0 | 0 | 2.0582 | 2.0582 | 0 | 0 | 25 | 25 | 0 | 0 | 5.02 | 5.02 | 0 | 0 | 25 | 25 | 25 | 0 | 0 | 25 | 0 | 0
36 | 3258106 | Residential Building : Repair & Maintenance | 50 | 19.48 | 19.48 | 0 | 0 | 11.9016 | 11.9016 | 0 | 0 | 8.6184 | 8.6184 | 0 | 0 | 40 | 40 | 0 | 0 | 20.52 | 20.52 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 40 | 0 | 0
37 | 3258105 | Engineering Equipments | 51 | 3.39 | 3.39 | 0 | 0 | 9.1355 | 9.1355 | 0 | 0 | 7.4745 | 7.4745 | 0 | 0 | 20 | 20 | 0 | 0 | 16.61 | 16.61 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 20 | 0 | 0
38 | 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 53 | 128.2 | 14.98 | 113.22 | 0 | 174.7305 | 26.3319 | 148.3986 | 0 | 102.6195 | 15.4648 | 87.1547 | 0 | 405.55 | 56.777 | 348.773 | 0 | 277.35 | 41.797 | 235.553 | 0 | 405.55 | 405.55 | 56.7766 | 348.7734 | 0 | 405.55 | 0 | -5.6843e-14
39 | 3258128 | Water Transport : Repair of Speedboat(s) | 54 | 2.77 | 2.77 | 0 | 0 | 1.3603 | 1.3603 | 0 | 0 | 0.8697 | 0.8697 | 0 | 0 | 5 | 5 | 0 | 0 | 2.23 | 2.23 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 0
40 | 3258107 | Others : Repair & Maintenance | 55 | 8.97 | 8.97 | 0 | 0 | 17.3768 | 17.3768 | 0 | 0 | 13.6532 | 13.6532 | 0 | 0 | 40 | 40 | 0 | 0 | 31.03 | 31.03 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 40 | 0 | 0
41 | 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 60 | 606.9 | 606.9 | 0 | 0 | 95.6 | 95.6 | 0 | 0 | 0 | 0 | 0 | 0 | 702.5 | 702.5 | 0 | 0 | 95.6 | 95.6 | 0 | 0 | 702.5 | 702.5 | 702.5 | 0 | 0 | 702.5 | 0 | 0
42 | 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | 61 | 50.22 | 50.22 | 0 | 0 | 18.03 | 18.03 | 0 | 0 | 0 | 0 | 0 | 0 | 68.25 | 68.25 | 0 | 0 | 18.03 | 18.03 | 0 | 0 | 68.25 | 68.25 | 68.25 | 0 | 0 | 68.25 | 0 | 0
43 | 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | 63 | 61.29 | 61.29 | 0 | 0 | 28.71 | 28.71 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 0 | 0 | 28.71 | 28.71 | 0 | 0 | 90 | 90 | 90 | 0 | 0 | 90 | 0 | 0
44 | 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 65 | 8.97 | 8.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.97 | 8.97 | 0 | 0 | 0 | 0 | 0 | 0 | 8.97 | 8.97 | 8.97 | 0 | 0 | 8.97 | 0 | 0
45 | 4112316 | Fax -2 nos (PMO 2 Nos.). | 66 | 0.79 | 0.79 | 0 | 0 | 0.21 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0.21 | 0.21 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0
46 | 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 68 | 20.5 | 20.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.5 | 20.5 | 0 | 0 | 0 | 0 | 0 | 0 | 20.5 | 20.5 | 20.5 | 0 | 0 | 20.5 | 0 | 0
47 | 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | 69 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 3 | 0 | 0
48 | 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 70 | 14.49 | 14.49 | 0 | 0 | 35.51 | 35.51 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 35.51 | 35.51 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 50 | 0 | 0
49 | 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 72 | 19.47 | 19.47 | 0 | 0 | 5.03 | 5.03 | 0 | 0 | 0 | 0 | 0 | 0 | 24.5 | 24.5 | 0 | 0 | 5.03 | 5.03 | 0 | 0 | 24.5 | 24.5 | 24.5 | 0 | 0 | 24.5 | 0 | 0
50 | 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 73 | 9.88 | 9.88 | 0 | 0 | 3.87 | 3.87 | 0 | 0 | 0 | 0 | 0 | 0 | 13.75 | 13.75 | 0 | 0 | 3.87 | 3.87 | 0 | 0 | 13.75 | 13.75 | 13.75 | 0 | 0 | 13.75 | 0 | 0
51 | 4112202 | A3 Combo Printer 2 no ( PMO) | 74 | 0.2 | 0.2 | 0 | 0 | 1.3 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 1.3 | 1.3 | 0 | 0 | 1.5 | 1.5 | 1.5 | 0 | 0 | 1.5 | 0 | 0
52 | 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | 75 | 4.08 | 4.08 | 0 | 0 | 1.17 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 5.25 | 0 | 0 | 1.17 | 1.17 | 0 | 0 | 5.25 | 5.25 | 5.25 | 0 | 0 | 5.25 | 0 | 0
53 | 4112314 | Furnitures & Fixtures | 76 | 45.33 | 45.33 | 0 | 0 | 2.8954 | 2.8954 | 0 | 0 | 1.7746 | 1.7746 | 0 | 0 | 50 | 50 | 0 | 0 | 4.67 | 4.67 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 50 | 0 | 0
54 | 4112303 | Aircooler | 77 | 12.72 | 12.72 | 0 | 0 | 1.3908 | 1.3908 | 0 | 0 | 0.8892 | 0.8892 | 0 | 0 | 15 | 15 | 0 | 0 | 2.28 | 2.28 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 15 | 0 | 0
55 | 4141101 | Land Acquisition ( 470 hectare) | 79 | 15323.6 | 15323.6 | 0 | 0 | 1531.56 | 1531.56 | 0 | 0 | 1531.56 | 1531.56 | 0 | 0 | 18386.72 | 18386.72 | 0 | 0 | 3063.12 | 3063.12 | 0 | 0 | 18386.72 | 18386.72 | 18386.72 | 0 | 0 | 18386.72 | 0 | 0
56 | 4111306 | Construction of Irrigation Inlet (New Haors) | 82 | 308.94 | 40.42 | 268.52 | 0 | 532.1616 | 76.1523 | 456.0093 | 0 | 385.3584 | 55.1448 | 330.2136 | 0 | 1226.46 | 171.7044 | 1054.7556 | 0 | 917.52 | 131.2844 | 786.2356 | 0 | 1226.46 | 1226.46 | 171.7171 | 1054.7429 | 0 | 1226.46 | 0 | 2.2737e-13
57 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 84 | 0 | 0 | 0 | 0 | 668.3934 | 93.5751 | 574.8183 | 0 | 504.2266 | 70.5917 | 433.6349 | 0 | 1172.62 | 164.1668 | 1008.4532 | 0 | 1172.62 | 164.1668 | 1008.4532 | 0 | 1172.62 | 1172.62 | 164.1668 | 1008.4532 | 0 | 1172.62 | 0 | 0
58 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 85 | 10218.88 | 1398.89 | 8819.99 | 0 | 4347.3197 | 625.5793 | 3721.7404 | 0 | 3855.1703 | 554.759 | 3300.4113 | 0 | 18421.37 | 2578.9918 | 15842.3782 | 0 | 8202.49 | 1180.1018 | 7022.3882 | 0 | 18421.37 | 18421.37 | 2579.2283 | 15842.1417 | 0 | 18421.37 | 0 | 0
59 | 4111307 | Re-excavation of Khal/River (New Haors) | 86 | 8684.7 | 1125.23 | 7559.47 | 0 | 839.6808 | 168.272 | 671.4088 | 0 | 659.7492 | 132.2137 | 527.5355 | 0 | 10184.13 | 1425.7782 | 8758.3518 | 0 | 1499.43 | 300.5482 | 1198.8818 | 0 | 10184.13 | 10184.13 | 1425.7158 | 8758.4142 | 0 | 10184.13 | 1.819e-12 | 1.819e-12
60 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 88 | 1181.58 | 155.18 | 1026.4 | 0 | 1219.5205 | 176.3427 | 1043.1778 | 0 | 997.7895 | 144.2804 | 853.5091 | 0 | 3398.89 | 475.8446 | 2923.0454 | 0 | 2217.31 | 320.6646 | 1896.6454 | 0 | 3398.89 | 3398.89 | 475.803 | 2923.087 | 0 | 3398.89 | -4.5475e-13 | -9.0949e-13
61 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 89 | 706.11 | 95.2 | 610.91 | 0 | 771.0056 | 110.0225 | 660.9831 | 0 | 558.3144 | 79.6715 | 478.6429 | 0 | 2035.43 | 284.9602 | 1750.4698 | 0 | 1329.32 | 189.7602 | 1139.5598 | 0 | 2035.43 | 2035.43 | 284.894 | 1750.536 | 0 | 2035.43 | -2.2737e-13 | 0
62 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 90 | 521.53 | 71.3 | 450.23 | 0 | 674.795 | 95.416 | 579.379 | 0 | 552.105 | 78.0676 | 474.0374 | 0 | 1748.43 | 244.7802 | 1503.6498 | 0 | 1226.9 | 173.4802 | 1053.4198 | 0 | 1748.43 | 1748.43 | 244.7837 | 1503.6463 | 0 | 1748.43 | 0 | -2.2737e-13
63 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 91 | 9050.67 | 1144.47 | 7906.2 | 0 | 7188.8448 | 4741.762 | 2447.0828 | 0 | 5205.7152 | 3433.6897 | 1772.0255 | 0 | 21445.23 | 9320.5402 | 12124.6898 | 0 | 12394.56 | 8176.0702 | 4218.4898 | 0 | 21445.23 | 21445.23 | 9319.9218 | 12125.3082 | 0 | 21445.23 | 0 | 3.638e-12
64 | 4111201 | Rehabilitation of Regulator (New Haors) | 92 | 73.26 | 9.77 | 63.49 | 0 | 40.3865 | 5.9207 | 34.4658 | 0 | 33.0435 | 4.8442 | 28.1993 | 0 | 146.69 | 20.5366 | 126.1534 | 0 | 73.43 | 10.7666 | 62.6634 | 0 | 146.69 | 146.69 | 20.5348 | 126.1552 | 0 | 146.69 | 0 | 0
65 | 4111201 | Threshing Floor Construction | 93 | 0 | 0 | 0 | 0 | 123.75 | 17.325 | 106.425 | 0 | 101.25 | 14.175 | 87.075 | 0 | 225 | 31.5 | 193.5 | 0 | 225 | 31.5 | 193.5 | 0 | 225 | 225 | 31.5 | 193.5 | 0 | 225 | 0 | 0
66 | 4111201 | Construction of WMG Office | 94 | 135.42 | 17.14 | 118.28 | 0 | 845.0706 | 119.324 | 725.7466 | 0 | 637.5094 | 90.0163 | 547.4931 | 0 | 1618 | 226.52 | 1391.48 | 0 | 1482.58 | 209.38 | 1273.2 | 0 | 1618 | 1618 | 226.4803 | 1391.5197 | 0 | 1618 | 2.2737e-13 | 2.2737e-13
67 | 4111201 | O&M During Construction | 95 | 0 | 0 | 0 | 0 | 66 | 66 | 0 | 0 | 54 | 54 | 0 | 0 | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 120 | 120 | 120 | 0 | 0 | 120 | 0 | 0
68 | 0 | (c) Physical Contingency ( Lump sum): | 98 | 0 | 0 | 0 | 0 | 16.1703 | 16.1703 | 0 | 0 | 14.3397 | 14.3397 | 0 | 0 | 30.51 | 30.51 | 0 | 0 | 30.51 | 30.51 | 0 | 0 | 30.51 | 30.51 | 30.51 | 0 | 0 | 30.51 | 0 | 0
69 | 0 | (d) Price Contingency (Lump sum): | 99 | 0 | 0 | 0 | 0 | 5.4 | 5.4 | 0 | 0 | 4.6 | 4.6 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0