## Sheet1
Kishoreganj Water Development Division
Sl No. | Package Name | Haor Name | Date Of Commencement | Date Of completion | 1st Revision | Date of Approval | 2nd Revision | Remarks
1 | BWDB/HFMLIP/Kish/PW-05 | Nunnir Haor (Part-A & C) | 15-01-17 | 30-04-18 | 15.03.2020 | 02.05.19 | 30.04.2021 (as on 21.6.2020) | 1st Revisied Time is Over
2 | BWDB/HFMLIP/Kish/PW-07 | Boro Haor | 2017-12-02 | 15-05-17 | 31.05.2020 | 13.05.19 |  | 1st Revisied Time is Over
3 | BWDB/HFMLIP/Kish/PW-17 | Naogaon Haor (Part-B) | 28-12-17 | 15-05-19 | 31.05.2020 | 04.07.19 |  | 1st Revisied Time is Over
4 | BWDB/HFMLIP/Kish/PW-19 | Naogaon Haor (Part-A) | 20-02-18 | 20-06-19 | 15.7.2020 | 24.09.19
5 | BWDB/HFMLIP/Kish/PW-10 | Noapara Haor | 24-12-17 | 31-05-19 | 21.05.2020 | 05.01.2020 |  | 1st Revisied Time is Over
6 | BWDB/HFMLIP/Kish/PW-11 | Noapara Haor | 24-12-17 | 31-05-19 | 21.05.2020 | 05.01.2020 |  | 1st Revisied Time is Over
7 | BWDB/HFMLIP/Kish/PW-20 | Nunnir, Boro & Noapara Haor | 2018-05-04 | 30-05-19 | 31.05.2020 | 09.01.2020 |  | 1st Revisied Time is Over
8 | BWDB/HFMLIP/Kish/PW-18 | Naogaon Haor (Part-A &B) | 2018-08-02 | 2019-02-01 | 31.03.2020 | 14.07.2019 |  | 1st Revisied Time is Over
9 | BWDB/HFMLIP/Kish/PW-09 | Boro Haor | 2018-10-01 | 15-05-19 | 30.04.2020 | 13.02.2020 |  | 1st Revisied Time is Over
10 | BWDB/HFMLIP/Kish/PW-16 | Naogaon Haor (Part-B) | 2018-10-01 | 15-05-19 | 31.05.2020 | 13.02.2020 |  | 1st Revisied Time is Over
11 | BWDB/HFMLIP/Kish/PW-03 | Nunnir Haor (Part-A) | 15-01-17 | 30-04-18 | 31.05.2020 | 13.02.2020 |  | 1st Revisied Time is Over
12 | BWDB/HFMLIP/Kish/PW-26 | Sonai Haor | 20-02-18 | 20-06-19 | 21.05.2020 | 13.02.2020 |  | 1st Revisied Time is Over
13 | BWDB/HFMLIP/Kish/PW-12 | Noapara Haor | 12.02.18 | 20.06.19 | 30.07.2020 | 19.02.2020
14 | BWDB/HFMLIP/Kish/PW-14 | Naogaon Haor (Part-A) | 2017-12-01 | 28-05-18 | 25.05.2020 | 19.02.2020 |  | 1st Revisied Time is Over
15 | BWDB/HFMLIP/Kish/PW-04 | Nunnir Haor (Part B+C) | 2017-06-01 | 30-04-18 | 31.03.2020 | 24.02.2020 |  | 1st Revisied Time is Over
16 | BWDB/HFMLIP/Kish/PW-13 | Naogaon Haor (Part-A) | 2017-06-01 | 30-04-18 | 31.05.2020 | 24.02.2020 |  | 1st Revisied Time is Over
17 | BWDB/HFMLIP/Kish/PW-02 | Chandpur Haor | 13-12-16 | 30-04-18 | 15.06.2020 | 25.03.2020
18 | BWDB/HFMLIP/Kish/PW-24 | Dakshiner Haor | 21-12-17 | 2019-05-06 | 15.06.2020 | 25.03.2020
19 | BWDB/HFMLIP/Kish/PW-06 | Nunnir Haor (Part A) | 20-12-16 | 30-04-18 | 25-05-19 | 19-02-19 | 02-03-2020 as on 25-03-2020