## Resource_List
Code | Name | Unit
101 | Mixture Machine | Nos
102 | Excavator | Nos
103 | Compaction Ruller | Nos
104 | Form Work | Nos
201 | Cement | Bag
202 | Sand 1.5 FM | cum
203 | Stone Chips | cum
204 | Geotextile Filter | sqm
205 | Filter Sand | cum
206 | Peagravel | cum
207 | CC Block | Nos
301 | Labor | m-day
401 | Labor payment | BDT Lac

## Allocation
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05
CC Block Manufacture(30X30X30) | 8 | 25 | 16 | 3 | 0 | 0 | 2500 | 350 | 36 | 80 | 0 | 0 | 0 | 0 | 120 | 0.3
CC Block Manufacture(40X40X20) | 8 | 25 | 16 | 2 | 0 | 0 | 500 | 90 | 8 | 18 | 0 | 0 | 0 | 0 | 120 | 0.3
Embankment Construction | 8 | 41 | 34 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05
Placing Sand Filter | 41 | 50 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 30 | 0.075
Placing Geotextile Filter | 51 | 60 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 30 | 0.075
Placing Pea Gravel Filter | 61 | 70 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 30 | 0.075
Placing CC Block | 71 | 80 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 150 | 0.375
Ancilary Work for Site Completion | 81 | 87 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Gantt1
Resources | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56 | D57 | D58 | D59 | D60 | D61 | D62 | D63 | D64 | D65 | D66 | D67 | D68 | D69 | D70 | D71 | D72 | D73 | D74 | D75 | D76 | D77 | D78 | D79 | D80 | D81 | D82 | D83 | D84 | D85 | D86 | D87 | D88 | D89 | D90 | D91 | D92 | D93
Mixture Machine
Excavator
Compaction Ruller
Form Work
Cement
Sand 1.5 FM
Stone Chips
Geotextile Filter
Filter Sand
Peagravel
CC Block
Labor
Labor payment