## Mobilization_Dist
Sl No | IPCNo | Inlet | Reg_Rehab_Rehab | Reg_CW_Box | Khal_Riv_New | Khal_Riv_Rehab | Full_Emb_Rehab | Sub_Emb_Rehab | Sub_Emb_Const | Reg_Rehab_New | Wmg_Office | Gate_Repair | Total | Gob | Rpa | Package No | IPC No | Month | Voucher No
1 | 126/Kish-02 1st Bill | [11 empty] | 0 | 0 | 0 | KISH-02 | 2 | 2 | 126
2 | 149/Kish-07 1st Bill | [11 empty] | 0 | 0 | 0 | KISH-07 | 7 | 3 | 149
3 | 152/Kish-02 Bill | [11 empty] | 81748.26 | 9809.7912 | 71938.4688 | KISH-02 | 2 | 3 | 152
4 | 176/Kish-13 1st Bill | [11 empty] | 437177.89 | 52461.3468 | 384716.5432 | KISH-13 | 1 | 4 | 176
5 | 197/Kish-14 1st Bill | [11 empty] | 0 | 0 | 0 | KISH-14 | 1 | 5 | 197
6 | 198/Kish-5 1st Bill | [11 empty] | 0 | 0 | 0 | KISH-05 | 1 | 5 | 198
7 | 201/Kish-6 1st Bill | [11 empty] | 0 | 0 | 0 | KISH-06 | 1 | 5 | 201
10 | 234/Kish-13 2nd Bill | [11 empty] | 0 | 0 | 0 | KISH-13 | 2 | 6 | 234
11 | 241/Kish-07 2nd Bill | [11 empty] | 0 | 0 | 0 | KISH-07 | 2 | 6 | 241
12 | 242/Kish-03 1st Bill | [11 empty] | 646973.9 | 77636.868 | 569337.032 | KISH-03 | 1 | 6 | 242

## IPC_Dist
Sl No | IPCNo | Inlet | Reg_Rehab_Rehab | Reg_CW_Box | Khal_Riv_New | Khal_Riv_Rehab | Full_Emb_Rehab | Sub_Emb_Rehab | Sub_Emb_Const | Reg_Rehab_New | Wmg_Office | Gate_Repair | Total | Gob | Rpa | Package No | IPC No | Month | Voucher No
1 | 126/Kish-02 1st Bill |  |  |  |  | 9871121 | [7 empty] | 1085823 | 8785298 | KISH-02 | 2 | 2 | 126
2 | 149/Kish-07 1st Bill |  |  |  | 9485898 | [8 empty] | 1138308 | 8442449 | KISH-07 | 7 | 3 | 149
3 | 152/Kish-02 .. Bill |  |  | 14978253 | [9 empty] | 888885.2088 | 13108924.5312 | KISH-02 | 2 | 3 | 152
4 | 176/Kish-13 1st Bill |  |  | 14259856 | [9 empty] | 1801319.6532 | 12021358.4568 | KISH-13 | 1 | 4 | 176
5 | 197/Kish-14 1st Bill | [7 empty] | 4144654 |  |  |  |  | 497358 | 3647296 | KISH-14 | 1 | 5 | 197
6 | 198/Kish-5 1st Bill | [7 empty] | 9280540 |  |  |  |  | 1113665 | 8166875 | KISH-05 | 1 | 5 | 198
7 | 201/Kish-6 1st Bill |  |  | 4132973.5 | 6195366.883 | [8 empty] | 1239401 | 9088939 | KISH-06 | 1 | 5 | 201
10 | 234/Kish-13 2nd Bill | [7 empty] | 2555298.56 |  |  |  |  | 332188.81 | 2223109.74 | KISH-13 | 2 | 6 | 234
11 | 241/Kish-07 2nd Bill | [7 empty] | 967951 |  |  |  |  | 116154 | 851797 | KISH-07 | 2 | 6 | 241
12 | 242/Kish-03 1st Bill |  |  | 2963861 |  |  |  |  | 2323597 |  |  |  |  | 556858.132 | 4083625.968 | KISH-03 | 1 | 6 | 242

## Package_wise_str_df
Package_No | Item | Inlet | Reg_Rehab_Rehab | Reg_CW_Box | Khal_Riv_New | Khal_Riv_Rehab | Full_Emb_Rehab | Sub_Emb_Rehab | Sub_Emb_Const | Reg_Rehab_New | WMG_OFF | Gate_Repair
KISH-01 | Mobilization | 0 | 0.0902 | 0 | 0 | 0.9098 | 0 | 0 | 0 | 0 | 0 | 0
KISH-02 | Mobilization | 0 | 0 | 0.3592 | 0.6066 | 0 | 0 | 0 | 0.0342 | 0 | 0 | 0
KISH-03 | Mobilization | 0 | 0 | 0.2256 | 0 | 0 | 0 | 0 | 0.7744 | 0 | 0 | 0
KISH-04 | Mobilization | 0 | 0 | 0.6385 | 0 | 0 | 0 | 0 | 0.3615 | 0 | 0 | 0
KISH-05 | Mobilization | 0 | 0 | 0.2478 | 0 | 0 | 0 | 0 | 0.7522 | 0 | 0 | 0
KISH-06 | Mobilization | 0 | 0 | 0.2942 | 0.7058 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-07 | Mobilization | 0 | 0 | 0 | 0.9138 | 0 | 0 | 0 | 0.0862 | 0 | 0 | 0
KISH-09 | Mobilization | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-10 | Mobilization | 0 | 0 | 0.3009 | 0 | 0 | 0 | 0 | 0.6991 | 0 | 0 | 0
KISH-11 | Mobilization | 0 | 0 | 0.3299 | 0 | 0 | 0 | 0 | 0.6701 | 0 | 0 | 0
KISH-12 | Mobilization | 0 | 0 | 0.5699 | 0.4301 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-13 | Mobilization | 0 | 0 | 0.4248 | 0 | 0 | 0 | 0 | 0.5752 | 0 | 0 | 0
KISH-14 | Mobilization | 0 | 0 | 0.206 | 0 | 0 | 0 | 0 | 0.794 | 0 | 0 | 0
KISH-15 | Mobilization | 0 | 0 | 0.2129 | 0 | 0 | 0 | 0 | 0.7871 | 0 | 0 | 0
KISH-16 | Mobilization | 0 | 0 | 0.3438 | 0 | 0 | 0 | 0 | 0.6562 | 0 | 0 | 0
KISH-17 | Mobilization | 0.175 | 0 | 0.4743 | 0 | 0 | 0 | 0 | 0.3508 | 0 | 0 | 0
KISH-18 | Mobilization | 0 | 0 | 0.588 | 0.412 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-19 | Mobilization | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-20 | Mobilization | 0.2897 | 0 | 0.7103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-21 | Mobilization | 0 | 0 | 0.5153 | 0 | 0 | 0 | 0 | 0.3547 | 0.1299 | 0 | 0
KISH-22 | Mobilization | 0 | 0 | 0.424 | 0.2481 | 0 | 0 | 0 | 0.3279 | 0 | 0 | 0
KISH-23 | Mobilization | 0.0823 | 0 | 0.7347 | 0.0424 | 0 | 0 | 0 | 0.1406 | 0 | 0 | 0
KISH-24 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
KISH-25 | Mobilization | 0.0672 | 0 | 0.7206 | 0.2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-26 | Mobilization | 0 | 0 | 0 | 0.9537 | 0 | 0 | 0 | 0.0463 | 0 | 0 | 0
KISH-27 | Mobilization | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NETR-01 | Mobilization | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
NETR-02 | Mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
NETR-03 | Mobilization | 0 | 0.4483 | 0 | 0 | 0 | 0.5181 | 0.0336 | 0 | 0 | 0 | 0
NETR-04 | Mobilization | 0 | 0 | 0 | 0 | 0.7364 | 0 | 0.2636 | 0 | 0 | 0 | 0
NETR-05 | Mobilization | 0 | 0 | 0.9519 | 0 | 0 | 0 | 0.0481 | 0 | 0 | 0 | 0
NETR-06 | Mobilization | 0.0268 | 0 | 0.1338 | 0.8086 | 0 | 0 | 0 | 0 | 0.0308 | 0 | 0
NETR-07 | Mobilization | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NETR-08 | Mobilization | 0.0417 | 0 | 0.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUNM-01 | Mobilization | 0.0073 | 0 | 0.2159 | 0.1836 | 0 | 0 | 0 | 0.5932 | 0 | 0 | 0
SUNM-02 | Mobilization | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUNM-03 | Mobilization | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUNM-04 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
SUNM-05 | Mobilization | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUNM-06 | Mobilization | 0.0833 | 0 | 0.0286 | 0.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HOBI-01 | Mobilization | 0 | 0 | 0.2538 | 0 | 0.5472 | 0 | 0.199 | 0 | 0 | 0 | 0
HOBI-02 | Mobilization | 0 | 0 | 0.2215 | 0 | 0.142 | 0 | 0.6366 | 0 | 0 | 0 | 0
HOBI-04 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
HOBI-05 | Mobilization | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HOBI-06 | Mobilization | 0.0953 | 0 | 0.9047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HOBI-07 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KISH-28/Lot-1 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
KISH-28/Lot-2 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
KISH-28/Lot-3 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
KISH-28/Lot-4 | Mobilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0

## Sheet1
id | Code | Description
57 | 4111306 | Construction of Irrigation Inlet (New Haors) | 4111306_Construction of Irrigation Inlet (New Haors)
58 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 4111307_ Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects)
59 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 4111307_ Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors)
60 | 4111307 | Re-excavation of Khal/River (New Haors) | 4111307_ Re-excavation of Khal/River (New Haors)
61 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 4111201_ Re-excavation of Khal/River (Rehabilitation Sub-Projects)
62 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 4111201_ Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects)
63 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 4111201_ Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects)
64 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 4111201_Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum)
65 | 4111201 | Rehabilitation of Regulator (New Haors) | 4111201_ Rehabilitation of Regulator (New Haors)
66 | 4111201 | Construction of WMG Office | 4111201_Construction of WMG Office
67 | 4111201 | O&M During Construction | 4111201_O&M During Construction

## Sheet5
| 7146.032 | 156388 |  |  | Khal | Box
| 2175338.384 | 582066.296 |  |  | 2651098.73 | 3807686.27 | 6458785 |  | Chtra Khal CW | 3058698.583
| 442686.376 | 132743.207 |  |  | 0.41046 | 0.58954 |  |  | Nabinpur Khal CW | 3991659.935
| 25927.941 | 2610.381 |  | GoB | 331387.7 | 475961.3 |  |  | Dipjuri KHal CW | 2816996.163
total | 2651098.733 | 71523.693 |  | RPA | 2319711.03 | 3331724.97 | 5651436 |  | Sudhi Khal CW | 3363880.156
|  | 769684.617 |  |  | 2651098.73 |  |  |  | Box Sluice | 808976.339 | DF | GoB | RPA
|  | 776580.144 | [6 empty] | Sub-Total Structure | 14040211.176 | 0.93161 | 1755026.3105 | 12285185.1049
|  | 2491596.338 | [6 empty] | Irrigation Inlet | 1030629.567 | 0.068386 | 128828.6895 | 901800.8951
|  |  | 2491596.338 | [6 empty] | 15070840.743 |  | 1883855 | 13186986 | 15070841
Kish-22 1st IPC
[9 empty] | Embankment | Khal |  |  | DF | GoB | RPA
[9 empty] | 5478066.24 | 6284471.15 | Embankment | 5478066.24 | 0.45355 | 616282.5073 | 4313977.0978
[10 empty] | 315745.97 | Khal | 6600217.12 | 0.54645 | 742524.4927 | 5197670.9022
[8 empty] | Total | 5478066.24 | 6600217.12 |  |  | 1 | 1358807 | 9511648
[8 empty] | GT |  | 12078283.36
Kish-22 2nd IPC
[9 empty] | Embankment | Khal |  |  | DF | GoB | RPA
[9 empty] | 5478066.24 | 6284471.15 | Embankment | 5478066.24 | 0.45355 | 68476.0357 | 479330.4359
[10 empty] | 315745.97 | Khal | 6600217.12 | 0.54645 | 82502.9643 | 577518.5641
[8 empty] | Total | 5478066.24 | 6600217.12 |  |  | 1 | 150979 | 1056849 | 1207828
[8 empty] | GT |  | 12078283.36
Kis -17 9th RA Bill
[11 empty] | Embankment | 5923319.27
[11 empty] | Block Road | 317931.49
[11 empty] | Total | 6241250.76 |  |  |  | DF | GoB | RPA
[11 empty] | Bagdia Khal Regulator | 1361092.04 |  | Emb | 6241250.76 | 0.33151 | 769465.2938 | 5386258.0511
[11 empty] | Neora Khal Regulator | 0 |  | Reg/Box | 6996164.259 | 0.37161 | 862536.3399 | 6037755.4942
[11 empty] | Pipe Inlet | 5589090.31 |  | Inlet | 5589090.31 | 0.29687 | 689062.3663 | 4823437.4548
[11 empty] | Box Drainage Outlet | 5635072.219 |  |  | 18826505.329 | 1 | 2321064 | 16247451
[11 empty] | Total | 12585254.569
[11 empty] | GT | 18826505.329
[11 empty] | Kish -10 4th RA Bill |  | DF
[11 empty] | EMB | 4734271.736 | 0.52055 | 591783.8037 | 4142488.1874
[11 empty] | Regulator | 4360514.774 | 0.47945 | 545064.1963 | 3815450.8126
[12 empty] | 9094786.51 | 1 | 1136848 | 7957939 | 9094787
[11 empty] | Kish -11 4th RA Bill |  | DF
[11 empty] | EMB | 0 | 0.52055 | 591783.8037 | 4142488.1874
[11 empty] | Regulator | 3214491.54 | 0.47945 | 545064.1963 | 3815450.8126
[13 empty] | 1 | 1136848 | 7957939 | 9094787
[11 empty] | Kish -25 5th RA Bill |  |  |  | DF | GoB | RPA
[11 empty] | Khal | 5702443.78 | Khal | 5702443.78 | 0.4773 | 712805.5214 | 4989638.1727
[11 empty] | Regulator | 6070081.27 | Regulator | 6244931.4 | 0.5227 | 780616.4786 | 5464314.8273
[11 empty] | Mobilization | 174850.13 |  |  | 1 | 1493422 | 10453953
[11 empty] | Regulator | 6244931.4
11947375.18
[11 empty] | Kish -13 5th RA Bill |  |  |  | DF | GoB | RPA
[11 empty] | Emb | 4129593.08 | Khal | 5702443.78 | 0.4773 | 712805.5214 | 4989638.1727
[11 empty] | Regulator |  | Regulator | 6244931.4 | 0.5227 | 780616.4786 | 5464314.8273
[11 empty] | Mobilization | 174850.13 |  |  | 1 | 1493422 | 10453953
[11 empty] | Regulator | 6244931.4
11947375.18

## Sheet3
|  | EMB | Khal
|  | 17644936.1 | 204301.34
|  | -166123.08 | 98414.79
|  | 4900152.1 | 3557905.85
|  | 286245 | 866744.93
|  | 619378.33 | 161285.36
|  | 23284588.45 | 15775.98
|  | 28737182.92 | 14288.02
|  | 5452594.47 | 53423.24
4972139.51
| Khal | Emb
| 875966.733 | 46900.13
| 906433.664 | 2590080.18
| 1782400.397 | 1949709.13
| 7172327.33 | 1366206.83
| 5389926.933 | 739134.85
379009.28
600581.7
7671622.1
358/Kish-06 13th/Final RA Bill | 5035264.49 |  |  | 1253692.11 | 786119.575 | 5502837.025

## Sheet2
372/Kish-25 7th RA Bill | 2004423.12 | 2200388.38 |  |  | 27775 |  | 529073 | 4232587
363/Kish-24 8th/Final RA Bill |  |  |  |  | 10277493 |  | 1284687 | 8992806
358/Kish-06 13th/Final RA Bill |  | 5035264.49 |  |  |  | 1253692.11 | 786119.575 | 5502837.025
364/Kish-02 7th RA Bill |  | 1360415.54 |  |  | 455742.37 | 1831376.254 | 455942 | 3191592
376/Kish-23 5th RA Bill | 5389926.93 | 1782400.4 |  |  |  |  | 896541 | 6275786
365/Kish-19 6th RA Bill |  |  |  |  | 3499306 |  | 437413 | 3061893
366/Netr-01 6th RA Bill |  |  |  | 20826914 |  |  | 2603364 | 18223550
367/Netr-02 5th RA Bill |  |  | 3669874 |  |  |  | 458734 | 3211140
368/Netr-03 6th RA Bill |  |  |  | 24327546 |  |  | 3040943 | 21286603

## Mobilization_Dist_prep
Sl No | IPCNo | Inlet | Reg_Rehab_Rehab | Reg_CW_Box | Khal_Riv_New | Khal_Riv_Rehab | Full_Emb_Rehab | Sub_Emb_Rehab | Sub_Emb_Const | Reg_Rehab_New | Wmg_Office | Gate_Repair | Total | Gob | Rpa | Package No | IPC No | Month
1 | 75/hobi-06 3rd Bill |  |  | 2821414 | [8 empty] | 0 | 0 | 0 | HOBI-06 | 3 | 10
2 | 124/kish-02 5th Bill |  |  | 788965.62 |  |  |  |  | 855983.51 |  |  |  | 125699 | 17597.86 | 108101.14 | KISH-02 | 5 | 12
3 | 142/kish-09 2nd Bill |  |  | 7908184 | [8 empty] | 0 | 0 | 0 | KISH-09 | 2 | 12
4 | 143/kish-18 3rd Bill |  |  | 3391138.5 | 8657627.44 | [7 empty] | 0 | 0 | 0 | KISH-18 | 3 | 12
5 | 149/kish-17 5th Bill | 654830.495 |  | 1764444.173 |  |  |  |  | 5957470.4 |  |  |  | 0 | 0 | 0 | KISH-17 | 5 | 12
6 | 171/kish-12 2nd Bill |  |  | 9832217.68 | 5030725.98 | [7 empty] | 0 | 0 | 0 | KISH-12 | 2 | 1
7 | 174/hobi-02 1st Bill |  |  |  |  | 21505835 | [6 empty] | 150000 | 21000 | 129000 | HOBI-02 | 1 | 1
8 | 182/kish-18 4th Bill |  |  | 3103589.69 | 8782672.1 | [7 empty] | 0 | 0 | 0 | KISH-18 | 4 | 1
9 | 196/kish-25 1st Bill |  |  | 9825070 | [8 empty] | 0 | 0 | 0 | KISH-25 | 1 | 1
10 | 197(/Sunm-1)-04 1st Bill | [7 empty] | 51500068 |  |  |  | 925082.2 | 129511.508 | 795570.692 | SUNM-04 | 1 | 1
11 | 199/kish-06 7 th Bill |  |  | 4766083.62 | 1203653.29 | [7 empty] | 0 | 0 | 0 | KISH-06 | 7 | 1
12 | 203/hobi-01 1st Bill | [5 empty] | 23055022.97 | [5 empty] | 476165.12 | 66663.1168 | 409502.0032 | HOBI-01 | 1 | 2
13 | 209/hobi-06 4th Bill |  |  | 17372657 | [8 empty] | 847500 | 118650 | 728850 | KISH-06 | 4 | 2
14 | 215/kish-16 6th Bill | [7 empty] | 5353824.14 |  |  |  | 0 | 0 | 0 | KISH-16 | 6 | 2
15 | 214/kish-19 2nd Bill |  |  |  | 7212480 | [7 empty] | 0 | 0 | 0 | KISH-19 | 2 | 2
16 | 223/netr-2 1st Bill |  |  |  |  | 8064231.791 | [6 empty] | 70000 | 9800 | 60200 | NETR-02 | 1 | 2
17 | 225/hobi-02 2nd Bill | [6 empty] | 20423243 |  |  |  |  | 0 | 0 | 0 | HOBI-02 | 2 | 2
18 | 226/hobi-04 3rd Bill | [7 empty] | 11032342 |  |  |  | 0 | 0 | 0 | HOBI-04 | 3 | 2
19 | 233/kish-15 3rd Bill | [7 empty] | 5159158.9 |  |  |  | 0 | 0 | 0 | KISH-15 | 3 | 2
20 | 235(/Sunm-1)-04 2nd Bill | [7 empty] | 36727928 |  |  |  | 0 | 0 | 0 | SUNM-04 | 2 | 2
21 | 234(/Sunm-1)-06 1st Bill |  |  | 23244978 | [8 empty] | 101467 | 14205.38 | 87261.62 | SUNM-06 | 1 | 2
22 | 232/kish-18 5th Bill |  |  |  | 16844694 | [7 empty] | 0 | 0 | 0 | KISH-18 | 5 | 2
23 | 236/kish-12 3th Bill |  |  | 7363341 | 3051784.77 | [7 empty] | 116119.27 | 16256.6978 | 99862.5722 | KISH-12 | 3 | 2
24 | 237(Sunm-2)-01 1st Bill | [7 empty] | 15061663 |  |  |  | 624567 | 87439.38 | 537127.62 | SUNM-01 | 1 | 2
25 | 238/kish-20 2nd Bill |  |  | 21472510 | [8 empty] | 452722.57 | 63381.1598 | 389341.4102 | KISH-20 | 2 | 2
26 | 246/kish-17 6th Bill | [7 empty] | 15753462 |  |  |  | 0 | 0 | 0 | KISH-17 | 6 | 2
27 | 253/Netr-6 1st Bill |  |  |  | 2017067 | [7 empty] | 0 | 0 | 0 | NETR-06 | 1 | 2
28 | 254/Netr-4 1st Bill |  |  |  | 19766138 | [7 empty] | 0 | 0 | 0 | NETR-04 | 1 | 2
29 | 257/kish-09 3th Bill |  |  | 12158123 | [8 empty] | 0 | 0 | 0 | KISH-09 | 3 | 2
30 | 265/kish-06 8th Bill |  |  | 2366092 | [8 empty] | 0 | 0 | 0 | KISH-06 | 8 | 2
31 | 266/kish-26 3th Bill |  |  |  | 7400966 | [7 empty] | 0 | 0 | 0 | KISH-26 | 3 | 3
32 | 267/Netr-1 2nd Bill | [5 empty] | 24987347 | [5 empty] | 0 | 0 | 0 | NETR-01 | 2 | 3
33 | 269/kish-19 3th Bill |  |  |  | 7803383 | [7 empty] | 0 | 0 | 0 | KISH-19 | 3 | 3
34 | 275(Sunm-1)-06 2nd Bill |  |  | 22263325 | [8 empty] | 0 | 0 | 0 | SUNM-06 | 2 | 3
35 | 272/kish-07 7th Bill |  |  |  | 5347170 | [7 empty] | 0 | 0 | 0 | KISH-07 | 7 | 3
36 | 276/kish-12 4th Bill |  |  |  | 6516132 | [7 empty] | 0 | 0 | 0 | KISH-12 | 4 | 3
37 | 279/Hobi-06 5th Bill |  |  | 35514537 | [8 empty] | 1022500 | 143150 | 879350 | HOBI-06 | 5 | 3
38 | 273/Hobi-05 1st Bill |  |  | 5347170 | [8 empty] | 150000 | 21000 | 129000 | HOBI-05 | 1 | 3
39 | 277/Hobi-01 2nd Bill | [6 empty] | 34155772 |  |  |  |  | 0 | 0 | 0 | HOBI-01 | 2 | 3
40 | 274/Netr-2 2nd Bill |  |  |  |  | 15079860 | [6 empty] | 230000 | 32200 | 197800 | NETR-02 | 2 | 3
41 | 280/kish-18 6th Bill |  |  | 4552593.85 | 3078009.85 | [7 empty] | 170123.64 | 23817.3096 | 146306.3304 | KISH-18 | 6 | 3
42 | 288(Sunm-1)-03 1st Bill |  |  | 26816203.76 | [8 empty] | 0 | 0 | 0 | SUNM-03 | 1 | 3
43 | 289/Netr-6 2nd Bill |  |  |  | 11969055 | [7 empty] | 0 | 0 | 0 | NETR-06 | 2 | 4
44 | 298/kish-06 9th Bill |  |  | 2292340 | [8 empty] | 0 | 0 | 0 | KISH-06 | 9 | 4
45 | 299/kish-16 7th Bill | [7 empty] | 3478937 |  |  |  | 0 | 0 | 0 | KISH-16 | 7 | 4
46 | 307/kish-25 2nd Bill |  |  | 15241072.86 | 7702950.48 | [7 empty] | 777078.66 | 108791.0124 | 668287.6476 | KISH-25 | 2 | 4
47 | 312(Sunm-1)-06 3rd Bill |  |  | 10168500 | [8 empty] | 0 | 0 | 0 | SUNM-06 | 3 | 4
48 | 313(Sunm-1)-04 3rd Bill | [7 empty] | 15531785 |  |  |  | 0 | 0 | 0 | SUNM-04 | 3 | 4
49 | 312(Sunm-1)-01 2nd Bill |  |  |  | 17634405.79 |  |  |  | 12267921.66 |  |  |  | 256226 | 35871.64 | 220354.36 | SUNM-01 | 2 | 4
50 | 311/Netr-3 1st Bill | [6 empty] | 14883526 |  |  |  |  | 200000 | 28000 | 172000 | NETR-03 | 1 | 4
51 | 325/kish-26 4th Bill |  |  |  | 3264155 | [7 empty] | 0 | 0 | 0 | KISH-26 | 4 | 5
52 | 326/kish-12 5th Bill |  |  | 6038020.19 | 350222.81 | [7 empty] | 0 | 0 | 0 | KISH-12 | 5 | 5
53 | 327/kish-19 4th Bill |  |  |  | 3574390 | [7 empty] | 0 | 0 | 0 | KISH-19 | 4 | 5
54 | 351/Netr-04 2nd Bill |  |  |  |  | 14918906 | [6 empty] | 0 | 0 | 0 | NETR-04 | 2 | 5
55 | 352/kish-18 7th Bill |  |  | 3809899.07 | 5431835.93 | [7 empty] | 0 | 0 | 0 | KISH-18 | 7 | 5
56 | 366/kish-25 3rd Bill |  |  | 5853043.08 | 5592440.87 | [7 empty] | 0 | 0 | 0 | KISH-25 | 3 | 5
57 | 361/Netr-6 3rd Bill |  |  |  | 9057764 | [7 empty] | 0 | 0 | 0 | NETR-06 | 3 | 5
58 | 362/kish-12 6th Bill |  |  | 1929546.15 | 1982473.85 | [7 empty] | 0 | 0 | 0 | KISH-12 | 6 | 5
59 | 365/Netr-7 3rd Bill |  |  |  | 15170448 | [7 empty] | 300000 | 42000 | 258000 | NETR-07 | 3 | 5
60 | 367/kish-17 7th Bill | 1581058 |  | 11403081 | [8 empty] | 0 | 0 | 0 | KISH-17 | 7 | 5
61 | 363/Hobi-06 6th Bill |  |  | 25552184 | [8 empty] | 1100000 | 154000 | 946000 | HOBI-06 | 6 | 5
62 | 360/Netr-03 2nd Bill |  |  |  |  | 10190150 | [6 empty] | 0 | 0 | 0 | NETR-03 | 2 | 5
63 | 364(Sunm-2)-02 1st Bill |  |  |  | 15010514 | [7 empty] | 336190 | 47066.6 | 289123.4 | SUNM-02 | 1 | 5
65 | 368/hobi-05 2nd Bill |  |  |  | 6575000 | [7 empty] | 0 | 0 | 0 | HOBI-05 | 2 | 5
66 | 370/kish-09 4th Bill |  |  | 6430088 | [8 empty] | 483525.23 | 67693.5322 | 415831.6978 | KISH-09 | 4 | 6
67 | 379/hobi-01 3rd Bill | [6 empty] | 8404669 |  |  |  |  | 0 | 0 | 0 | HOBI-01 | 3 | 6
68 | 380/hobi-05 2nd Bill |  |  | 1642962 | [8 empty] | 0 | 0 | 0 | HOBI-05 | 2 | 6
69 | 383/kish-06 10th Bill |  |  | 2757459 | [8 empty] | 0 | 0 | 0 | HOBI-06 | 10 | 6
70 | 415/kish-07 8th Bill | [7 empty] | 4689243 |  |  |  | 0 | 0 | 0 | KISH-07 | 8 | 6
71 | 416/hobi-01 4th Bill | [6 empty] | 6240271 |  |  |  |  | 0 | 0 | 0 | HOBI-01 | 4 | 6
72 | 419(Sunm-2)-06 4th Bill |  |  | 13101081 | [8 empty] | 0 | 0 | 0 | SUNM-06 | 4 | 6
73 | 420/hobi-02 2nd Bill | [6 empty] | 16716505 |  |  |  |  | 0 | 0 | 0 | HOBI-02 | 2 | 6
74 | 423/Netr-02 3rd Bill |  |  |  |  | 11206363 | [6 empty] | 182750.37 | 25585.0518 | 157165.3182 | NETR-02 | 3 | 6
75 | 422/Netr-07 4th Bill |  |  |  | 3705998 | [7 empty] | 0 | 0 | 0 | NETR-07 | 4 | 6
79 | 430/kish-06 11th Bill |  |  | 3995166 | [8 empty] | 0 | 0 | 0 | KISH-06 | 11 | 6
80 | 477/kish-05 4th Bill |  |  | 8736715.472 |  |  |  |  | 4715931.82 |  |  |  | 240938.44 | 33731.3816 | 207207.0584 | KISH-05 | 5 | 6
81 | 470(Sunm-1)-03 2nd Bill |  |  | 4436884 | [8 empty] | 0 | 0 | 0 | SUNM-03 | 2 | 6
82 | 476/kish-20 3rd Bill | 491243.985 |  | 19959771.015 | [8 empty] | 0 | 0 | 0 | KISH-20 | 3 | 6
83 | 431(Sunm-2)-01 3rd Bill | 13597054.679 | [6 empty] | 3250310.77 |  |  |  | 0 | 0 | 0 | SUNM-01 | 3 | 6
84 | 474/Netr-01 3rd Bill | [5 empty] | 11681236 | [5 empty] | 0 | 0 | 0 | NETR-01 | 3 | 6
85 | 478/Netr-03 3rd Bill | [6 empty] | 3836480 |  |  |  |  | 0 | 0 | 0 | NETR-03 | 3 | 6
86 | 435/kish-14 7th Bill |  |  | 10766653.29 |  |  |  |  | 5035726.724 |  |  |  | 0 | 0 | 0 | KISH-14 | 7 | 6
87 | 471/kish-28 4th Bill | [9 empty] | 4209533 |  | 0 | 0 | 0 | KISH-28/Lot-1 | 4 | 6
88 | 461/kish-25 4th Bill |  |  | 1092242.61 | 6565980.71 | [7 empty] | 0 | 0 | 0 | KISH-25 | 4 | 6
89 | 450/kish-26 5th Bill |  |  |  | 2772925 | [7 empty] | 0 | 0 | 0 | KISH-25 | 5 | 6
90 | 479/kish-2 6th Bill |  |  | 1865950.84 | 1241270.59 |  |  |  | 22426.7 |  |  |  | 0 | 0 | 0 | KISH-26 | 6 | 6
91 | 475/kish-15 5th Bill | [7 empty] | 5676932 |  |  |  | 0 | 0 | 0 | KISH-15 | 5 | 6
92 | 473/kish-16 8th Bill |  |  | 120705.26 |  |  |  |  | 116300.225 |  |  |  | 0 | 0 | 0 | KISH-16 | 8 | 6
93 | 469/kish-19 5th Bill |  |  |  | 7869228 | [7 empty] | 483525.43 | 67693.5602 | 415831.8698 | KISH-19 | 5 | 6
94 | 472/kish-17 8th Bill | 795781.3 |  | 1039759.708 |  |  |  |  | 5168075.669 |  |  |  | 0 | 0 | 0 | KISH-17 | 8 | 6
77 | 425/hobi-04 4th Bill | [6 empty] | 4828643 |  |  |  |  | 486119.06 | 68056.6684 | 418062.3916 | HOBI-04 | 4 | 6
78 | 426/kish-04 5th Bill | 366417.97 | [5 empty] | 3904887.04 |  |  |  |  | 32269.14 | 4517.6796 | 27751.4604 | KISH-04 | 5 | 6

## Package_wise_cost
PackageNo | IPC1 | IPC2 | IPC3 | IPC4 | IPC5 | IPC6 | IPC7 | IPC8 | IPC9 | IPC10 | IPC11 | IPC12 | IPC13 | IPC14 | IPC15 | IPC16 | IPC17 | IPC18 | IPC19 | IPC20 | Total
KISH-01
KISH-02
KISH-03
KISH-04
KISH-05
KISH-06
KISH-07
KISH-09
KISH-10
KISH-11
KISH-12
KISH-13
KISH-14
KISH-15
KISH-16
KISH-17
KISH-18
KISH-19
KISH-20
KISH-21
KISH-22
KISH-23
KISH-24
KISH-25
KISH-26
KISH-27
KISH-28/Lot-1
KISH-28/Lot-2
KISH-28/Lot-3
KISH-28/Lot-4
HOBI-01
HOBI-02
HOBI-04
HOBI-05
HOBI-06
HOBI-07
HOBI-08
NETR-01
NETR-02
NETR-03
NETR-04
NETR-05
NETR-06
NETR-07
NETR-08
SUNM-01
SUNM-02
SUNM-03
SUNM-04
SUNM-05
SUNM-06
GT-01
GT-02
GT-03

## Monthly_Rpa
PackageNo | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Inlet
Reg_Rehab_Rehab
Reg_CW_Box
Khal_Riv_New
Khal_Riv_Rehab
Full_Emb_Rehab
Sub_Emb_Rehab
Sub_Emb_Const
Reg_Rehab_New
Wmg_Office
Gate_Repair

## Monthly_Gob
PackageNo | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Inlet
Reg_Rehab_Rehab
Reg_CW_Box
Khal_Riv_New
Khal_Riv_Rehab
Full_Emb_Rehab
Sub_Emb_Rehab
Sub_Emb_Const
Reg_Rehab_New
Wmg_Office
Gate_Repair

## InvoiceNo
id | Invoice_no | date | BatchType | Description | Total_amount | document_id | FinancialYear | Month
9545 | 1 | 2016-08-29 | Other | Environment fee | 460000 | 128 | 2 | 8
9546 | 2 | 2016-08-31 | Other | EPRC bill for Jul/16 | 237187 | 128 | 2 | 8
9547 | 3 | 2016-08-31 | Other | Imprest /Aug/16 | 0 | 128 | 2 | 8
9548 | 4 | 2016-08-31 | Other | EPRC bill for Jul/16 | 1399003 | 128 | 2 | 8
9549 | 5 | 2016-08-31 | Other | Asif TRaders bill for Jul/16 | 367364 | 128 | 2 | 8
9550 | 6 | 2016-09-04 | Other | EPRC bill for AUg/16 with bonus | 2159486 | 128 | 2 | 9
9551 | 7 | 2016-09-04 | Other | EPRC bill for AUg/16 with bonus | 366562 | 128 | 2 | 9
9552 | 8 | 2016-09-04 | Other | Nipuna Service bill for Petrol & Lubricant | 126582 | 128 | 2 | 9
9553 | 9 | 2016-09-04 | Other | Asif TRaders bill for Aug/16 with bonus | 592179 | 128 | 2 | 9
9554 | 10 | 2016-09-05 | Other | BCIC office rent bill for Aug/16 | 310726 | 128 | 2 | 9
9555 | 11 | 2016-09-05 | Other | BCIC Water & Electicity bill for Jul/16 | 10861 | 128 | 2 | 9
9556 | 12 | 2016-09-05 | Other | Best Eastern CNG Gus bill | 10861 | 128 | 2 | 9
9557 | 13 | 2016-09-06 | Other | Mun Ent. bill for passbook | 288000 | 128 | 2 | 9
9558 | 14 | 2016-09-06 | Other | TA bill for Fakhrul Abedin | 82700 | 128 | 2 | 9
9559 | 15 | 2016-09-06 | Other | TA bill for Rubol mia | 32842 | 128 | 2 | 9
9560 | 16 | 2016-09-06 | Other | Vehicle repair | 113871 | 128 | 2 | 9
9561 | 17 | 2016-09-07 | Other | Unimart trads bill for Computer Supply | 295000 | 128 | 2 | 9
9562 | 18 | 2016-09-07 | Other | Servey bill | 74100 | 128 | 2 | 9
9563 | 19 | 2016-09-07 | Other | Servey bill | 145920 | 128 | 2 | 9
9564 | 20 | 2016-09-18 | Other | Imprest Sep/16 | 0 | 128 | 2 | 9
9565 | 21 | 2016-09-22 | Other | Financial Express bill for newspaper | 25744 | 128 | 2 | 9
9566 | 22 | 2016-09-22 | Other | Jonokontho bill for newspaper | 43470 | 128 | 2 | 9
9567 | 23 | 2016-09-22 | Other | Best Eastern CNG Gus bill | 9728 | 128 | 2 | 9
9568 | 24 | 2016-09-22 | Other | TA bill for A.K.M sumsul Alam | 53975 | 128 | 2 | 9
9569 | 25 | 2016-09-26 | Other | Ta bill for D. Zahidul ISlam | 57058 | 128 | 2 | 9
9570 | 26 | 2016-09-26 | Other | Casual Lobar bill | 36708 | 128 | 2 | 9
9571 | 27 | 2016-09-26 | Other | TA bill for Alamin | 48975 | 128 | 2 | 9
9574 | 29 | 2016-10-03 | Other | Asif Traders bill for Sep/16 | 442559 | 128 | 2 | 10
9575 | 30 | 2016-10-03 | Other | EPRC bill for Sep/16 65 nos | 1714675 | 128 | 2 | 10
9576 | 31 | 2016-10-03 | Other | EPRC bill for Sep/16 11 nos | 294687 | 128 | 2 | 10
9577 | 32 | 2016-10-09 | Other | Financial Express bill for newspaper | 14710 | 128 | 2 | 10
9578 | 33 | 2016-10-09 | Other | Jonoconto bill for newspaper | 24840 | 128 | 2 | 10
9579 | 34 | 2016-10-09 | Other | BCIC bill for Water & Electicity Aug/16 | 21697 | 128 | 2 | 10
9580 | 35 | 2016-10-09 | Other | Telephone bill for PMO office | 1598 | 128 | 2 | 10
9581 | 36 | 2016-10-10 | Other | SMW Trading bill for Photocopy | 0 | 128 | 2 | 10
9582 | 37 | 2016-10-10 | Other | Imprest bill for Agu/16 | 0 | 128 | 2 | 10
9583 | 38 | 2016-10-16 | Other | Nipuna Service bill for Petrol & Lubricant | 70846 | 128 | 2 | 10
9584 | 39 | 2016-10-16 | Other | Best Eastern CNG Gus bill | 8170 | 128 | 2 | 10
9585 | 40 | 2016-10-16 | Other | M/S Icom Motors bill for Vehicle Repair | 46400 | 128 | 2 | 10
9586 | 41 | 2016-10-17 | Other | BCIC office rent bill for Oct/16 | 310726 | 128 | 2 | 10
9587 | 42 | 2016-10-19 | Other | Jubayar Auto mobile bill for Vehicle repair | 76980 | 128 | 2 | 10
9588 | 43 | 2016-10-19 | Other | Casual Lobar bill | 17615 | 128 | 2 | 10
9589 | 44 | 2016-10-19 | Other | TEC Committee honorarium bill | 12700 | 128 | 2 | 10
9590 | 45 | 2016-10-31 | Other | Servey bill | 118560 | 128 | 2 | 10
9591 | 46 | 2016-10-31 | Other | BCIC water & Electicity bill for Aug/16 | 4821 | 128 | 2 | 10
9592 | 47 | 2016-10-31 | Other | Imprest bill Aug/16 Addi | 0 | 128 | 2 | 10
9593 | 48 | 2016-10-31 | Other | Asif Traders bill for Oct/16 | 443937 | 128 | 2 | 10
9595 | 49 | 2016-11-02 | Other | TEC Committee honorarium bill | 32850 | 128 | 2 | 11
9596 | 50 | 2016-11-02 | Other | Busta Int. bill for Speed boat | 0 | 128 | 2 | 11
9597 | 51 | 2016-11-03 | Other | EPRC bill for Oct/16 65 nos | 1399003 | 128 | 2 | 11
9598 | 52 | 2016-11-03 | Other | EPRC bill for Oct/16 11 nos | 237187 | 128 | 2 | 11
9599 | 53 | 2016-11-06 | Other | Casual Lobar bill | 19572 | 128 | 2 | 11
9600 | 54 | 2016-11-06 | Other | Ayat ali bill for cabinate Supply | 0 | 128 | 2 | 11
9601 | 55 | 2016-11-07 | Other | TA bill for Rubol mia | 35250 | 128 | 2 | 11
9602 | 56 | 2016-11-08 | Other | Said Motors bill for vehicle repair | 17800 | 128 | 2 | 11
9603 | 57 | 2016-11-08 | Other | Nipuna Service bill for Petrol & Lubricant | 59615 | 128 | 2 | 11
9604 | 58 | 2016-11-09 | Other | TA bill for Yousuf Ali | 6594 | 128 | 2 | 11
9605 | 59 | 2016-11-10 | Other | Imprest bii for Nov/16 | 0 | 128 | 2 | 11
9606 | 60 | 2016-11-17 | Other | BCIC Office rent bill for Nov/16 | 310726 | 128 | 2 | 11
9607 | 61 | 2016-11-17 | Other | Said Motors bill for vehicle repair | 17800 | 128 | 2 | 11
9608 | 62 | 2016-11-17 | Other | Best Eastern CNG Gus bill | 8431 | 128 | 2 | 11
9609 | 63 | 2016-11-17 | Other | Land Accusation | 20000000 | 128 | 2 | 11
9610 | 64 | 2016-11-22 | Other | Land Accusation | 20000000 | 128 | 2 | 11
9611 | 65 | 2016-11-22 | Other | Land Accusation | 40000000 | 128 | 2 | 11
9612 | 66 | 2016-11-22 | Other | Land Accusation | 2500000 | 128 | 2 | 11
9613 | 67 | 2016-11-22 | Other | Land Accusation | 5000000 | 128 | 2 | 11
9614 | 68 | 2016-11-22 | Other | Land Accusation | 20000000 | 128 | 2 | 11
9615 | 69 | 2016-11-22 | Other | Land Accusation | 7500000 | 128 | 2 | 11
9616 | 70 | 2016-11-22 | Other | consultancy bill | 0 | 128 | 2 | 11
9617 | 71 | 2016-11-28 | Other | Imprest bill for ov/16 Addi | 0 | 128 | 2 | 11
9618 | 72 | 2016-11-29 | Other | consultancy bill | 0 | 128 | 2 | 11
9619 | 73 | 2016-11-30 | Other | asif Traders bill for Nov/16 | 442539 | 128 | 2 | 11
9620 | 74 | 2016-12-04 | Other | TA bill for Fakhrul Abedin | 59800 | 128 | 2 | 12
9621 | 75 | 2016-12-07 | Other | EPRC bill for Nov/16 65 nos | 1399003 | 128 | 2 | 12
9622 | 76 | 2016-12-07 | Other | EPRC bill for Nov/16 11 nos | 237187 | 128 | 2 | 12
9623 | 77 | 2016-12-07 | Other | TA bill for Yousuf Ali | 10550 | 128 | 2 | 12
9624 | 78 | 2016-12-08 | Other | Nipuna Service bill for Petrol & Lubricant | 65697 | 128 | 2 | 12
9625 | 79 | 2016-12-08 | Other | Casual Lobar bill | 10857 | 128 | 2 | 12
9626 | 80 | 2016-12-12 | Other | imprest bill for Dec/16 | 0 | 128 | 2 | 12
9627 | 81 | 2016-12-18 | Other | Best Eastern CNG Gus bill | 3543 | 128 | 2 | 12
9628 | 82 | 2016-12-20 | Other | consultancy bill | 0 | 128 | 2 | 12
9629 | 83 | 2016-12-20 | Other | consultancy bill | 0 | 128 | 2 | 12
9630 | 84 | 2016-12-27 | Other | M/S Nuzrul bill for Tyre | 47880 | 128 | 2 | 12
9631 | 85 | 2016-12-27 | Other | BCIC Office rent bill for Dec/16 | 310726 | 128 | 2 | 12
9632 | 86 | 2016-12-27 | Other | Jubayar Auto mobile bill for Vehicle repair | 38500 | 128 | 2 | 12
9633 | 87 | 2016-12-28 | Other | Petrol & lubricunt bill | 303752 | 128 | 2 | 12
9634 | 88 | 2016-12-28 | Other | Imprest bill for Dce/addi | 0 | 128 | 2 | 12
9635 | 89 | 2016-12-29 | Other | BCIC Water & electicity bill for Oct/16 | 21706 | 128 | 2 | 12
9636 | 90 | 2017-01-03 | Other | EPRC bill for Dec/16 65 nos | 1399003 | 128 | 2 | 1
9637 | 91 | 2017-01-03 | Other | EPRC bill for Dec/16 11 nos | 237187 | 128 | 2 | 1
9638 | 92 | 2017-01-03 | Other | Asif traders bill for Dec/16 | 453886 | 128 | 2 | 1
9639 | 93 | 2017-01-04 | Other | Telephone bill for PMO office | 2319 | 128 | 2 | 1
9640 | 94 | 2017-01-04 | Other | Midia trads bill for passbook | 199800 | 128 | 2 | 1
9641 | 95 | 2017-01-09 | Other | Nipuna Service bill for Petrol & Lubricant | 44510 | 128 | 2 | 1
9642 | 96 | 2017-01-11 | Other | Imprest bill for Jan/16 | 0 | 128 | 2 | 1
9643 | 97 | 2017-01-18 | Other | Maple computer bill for Photocier | 96700 | 128 | 2 | 1
9644 | 98 | 2017-01-18 | Other | Unimart trads bill for Computer Supply | 322500 | 128 | 2 | 1
9645 | 99 | 2017-01-23 | Other | TA bill for Rubol mia | 35658 | 128 | 2 | 1
9646 | 100 | 2017-01-23 | Other | TA bill for A.K.M sumsul Alam | 75112 | 128 | 2 | 1
9647 | 101 | 2017-01-23 | Other | TA bill for Alamin | 43625 | 128 | 2 | 1
9648 | 102 | 2017-01-24 | Other | Imprest bill for Jan/16 Addi | 0 | 128 | 2 | 1
9649 | 103 | 2017-01-30 | Other | TEC Committee honorarium bill | 46500 | 128 | 2 | 1
9650 | 104 | 2017-01-30 | Other | Shohag Tyre bill for Tyre | 21546 | 128 | 2 | 1
9651 | 105 | 2017-02-01 | Other | Asif traders bill for Jau/17 | 0 | 128 | 2 | 1
9652 | 106 | 2017-02-01 | Other | BCIC Water & electicity bill for Oct/16 | 0 | 128 | 2 | 1
9653 | 107 | 2017-02-01 | Other | M/S Nuzrul bill for Tyre | 41146 | 128 | 2 | 2
9654 | 108 | 2017-02-02 | Other | BCIC office rent Jau/17 | 310726 | 128 | 2 | 2
9655 | 109 | 2017-02-02 | Other | Petrol & lubricunt bill | 506848 | 128 | 2 | 2
9656 | 110 | 2017-02-06 | Other | EPRC bill for Jan/17 11 nos | 258626 | 128 | 2 | 2
9657 | 111 | 2017-02-06 | Other | EPRC bill for Jan/17 65 nos | 1399003 | 128 | 2 | 2
9658 | 112 | 2017-02-07 | Other | Imprest bill for feb/17 | 0 | 128 | 2 | 2
9659 | 113 | 2017-02-08 | Other | TA bill for Masud Rana | 6000 | 128 | 2 | 2
9660 | 114 | 2017-02-08 | Other | TEC Committee honorarium bill | 30600 | 128 | 2 | 2
9661 | 115 | 2017-02-08 | Other | Ayat ali bill for Stationay Supply | 103637 | 128 | 2 | 2
9662 | 116 | 2017-02-13 | Other | consultancy bill | 0 | 128 | 2 | 2
9663 | 117 | 2017-02-14 | Other | Shohag Tyre bill for Tyre | 21546 | 128 | 2 | 2
9664 | 118 | 2017-02-15 | Other | M/S samat Eng. bill for motorecycle | 166200 | 128 | 2 | 2
9665 | 119 | 2017-02-15 | Other | pritom Int. bill for motorecycle | 166200 | 128 | 2 | 2
9666 | 120 | 2017-02-16 | Other | Land Accusation | 120000000 | 128 | 2 | 2
9667 | 121 | 2017-02-19 | Other | Gate Installment | 360000 | 128 | 2 | 2
9668 | 122 | 2017-02-26 | Other | M/S M & Hai bill for Gus and Fuel | 33583 | 128 | 2 | 2
9669 | 123 | 2017-02-26 | Other | Nipuna Service bill for Petrol & Lubricant | 72689 | 128 | 2 | 2
9670 | 124 | 2017-02-26 | Other | BCIC office rent bill for feb/17 | 310726 | 128 | 2 | 2
9671 | 125 | 2017-02-26 | Other | BCIC Water & electicity bill | 12293 | 128 | 2 | 2
9672 | 126 | 2017-02-26 | Civil | PW-02 1st bill | 0 | 128 | 2 | 2
9673 | 127 | 2017-02-27 | Other | M/S Hidroland bill for Electronic purchase | 0 | 128 | 2 | 2
9674 | 128 | 2017-02-27 | Other | Imprest bill for Feb/17 Addi | 0 | 128 | 2 | 2
9675 | 129 | 2017-02-28 | Other | TA bill for maraz | 21210 | 128 | 2 | 2
9676 | 130 | 2017-02-28 | Other | TA bill for Yousuf Ali | 17600 | 128 | 2 | 2
9677 | 131 | 2017-02-28 | Other | Sri mongal Motors bill for vehicle repair | 50000 | 128 | 2 | 2
9678 | 132 | 2017-02-28 | Other | Sri mongal Motors bill for vehicle repair | 69750 | 128 | 2 | 2
9679 | 133 | 2017-02-28 | Other | Asif traders bill for Feb/17 | 487928 | 128 | 2 | 2
9680 | 134 | 2017-02-28 | Other | consultancy bill | 0 | 128 | 2 | 2
9681 | 135 | 2017-03-02 | Other | EPRC bill for feb/17 65 nos | 1399003 | 128 | 2 | 3
9682 | 136 | 2017-03-02 | Other | EPRC bill for feb/17 11 nos | 237312 | 128 | 2 | 3
9683 | 137 | 2017-03-02 | Other | Jubayar Auto mobile bill for Vehicle repair | 35430 | 128 | 2 | 3
9684 | 138 | 2017-03-07 | Other | Best Eastern CNG Gus bill | 11308 | 128 | 2 | 3
9685 | 139 | 2017-03-14 | Other | BCIC water & electicity bill for | 19135 | 128 | 2 | 3
9686 | 140 | 2017-03-14 | Other | Imprest bill for Mar/17 | 0 | 128 | 2 | 3
9687 | 141 | 2017-03-14 | Other | TA bill for Fakhrul Abedin | 99395 | 128 | 2 | 3
9688 | 142 | 2017-03-15 | Other | BCIC office rent Muarch/17 | 310726 | 128 | 2 | 3
9689 | 143 | 2017-03-15 | Other | Nipuna Service bill for Petrol & Lubricant | 51820 | 128 | 2 | 3
9690 | 144 | 2017-03-20 | Other | Servey bill | 22050 | 128 | 2 | 3
9691 | 145 | 2017-03-20 | Other | Servey bill | 22050 | 128 | 2 | 3
9692 | 146 | 2017-03-20 | Other | Jubayar Auto mobile bill for Vehicle repair | 18100 | 128 | 2 | 3
9693 | 147 | 2017-03-20 | Other | Jubayar Auto mobile bill for Vehicle repair | 22000 | 128 | 2 | 3
9694 | 148 | 2017-03-21 | Other | Best Eastern CNG Gus bill | 10681 | 128 | 2 | 3
9695 | 149 | 2017-03-23 | Civil | KISH/HFMLIP/PW-07 1st bill | 9580757 | 128 | 2 | 3
9696 | 150 | 2017-03-23 | Other | consultancy bill | 0 | 128 | 2 | 3
9697 | 151 | 2017-03-28 | Other | BCIC water & electicity bill for Feb/17 | 10763 | 128 | 2 | 3
9698 | 152 | 2017-03-30 | Civil | KISH/HFMLIP/PW-03 1st bill | 14079558 | 128 | 2 | 3
9699 | 153 | 2017-03-30 | Other | TA bill for A.K.M sumsul Alam | 67370 | 128 | 2 | 3
9700 | 154 | 2017-03-30 | Other | Ta bill for D. Zahidul ISlam | 61593 | 128 | 2 | 3
9701 | 155 | 2017-03-30 | Other | TA bill for Rubol mia | 28660 | 128 | 2 | 3
9702 | 156 | 2017-03-30 | Other | TA bill for Alamin | 64725 | 128 | 2 | 3
9703 | 157 | 2017-03-30 | Other | TA bill for Azizur alam | 2660 | 128 | 2 | 3
9704 | 158 | 2017-03-30 | Other | TA bill for Dhaka rac | 40796 | 128 | 2 | 3
9705 | 159 | 2017-04-02 | Other | Imprest bill for April | 0 | 128 | 2 | 4
9706 | 160 | 2017-04-04 | Other | TA bill for Fakhrul Abedin | 58600 | 128 | 2 | 4
9707 | 161 | 2017-04-04 | Other | Asir traders bill for mur/17 with bonus | 553883 | 128 | 2 | 4
9708 | 162 | 2017-04-05 | Other | consultancy bill | 0 | 128 | 2 | 4
9709 | 163 | 2017-04-09 | Other | Jubayar Auto mobile bill for Vehicle repair | 49400 | 128 | 2 | 4
9710 | 164 | 2017-04-09 | Other | TA bill for Polash chandro | 22285 | 128 | 2 | 4
9711 | 165 | 2017-04-11 | Other | Nipuna Service bill for Petrol & Lubricant | 67645 | 128 | 2 | 4
9712 | 166 | 2017-04-11 | Other | Telephone bill for PMO office | 2408 | 128 | 2 | 4
9713 | 167 | 2017-04-12 | Other | Ent. Office bill for toner | 45036 | 128 | 2 | 4
9714 | 168 | 2017-04-16 | Other | Casual Lobar bill | 22208 | 128 | 2 | 4
9715 | 169 | 2017-04-16 | Other | Casual Lobar bill | 11633 | 128 | 2 | 4
9716 | 170 | 2017-04-17 | Other | EPRC 65 nos bill for mur/17 | 263367 | 128 | 2 | 4
9717 | 171 | 2017-04-17 | Other | EPRC 11 nos bill for mur/17 | 1555003 | 128 | 2 | 4
9718 | 172 | 2017-04-17 | Other | Land Accusation | 159000000 | 128 | 2 | 4
9719 | 173 | 2017-04-18 | Other | consultancy bill | 0 | 128 | 2 | 4
9720 | 174 | 2017-04-18 | Other | consultancy bill | 0 | 128 | 2 | 4
9721 | 175 | 2017-04-18 | Other | M/S murad bill for petrol & lubricunt | 160038 | 128 | 2 | 4
9722 | 176 | 2017-04-18 | Civil | KISH/HFMLIP/PW-13 1st bill | 14259856 | 128 | 2 | 4
9723 | 177 | 2017-04-20 | Other | TA bill for maraz | 20490 | 128 | 2 | 4
9724 | 178 | 2017-04-25 | Other | BCIC office rent bill for mur/17 | 310726 | 128 | 2 | 4
9725 | 179 | 2017-04-30 | Other | Ta bill for D. Zahidul ISlam | 93549 | 128 | 2 | 4
9726 | 180 | 2017-04-30 | Other | Casual Lobar bill | 12018 | 128 | 2 | 4
9727 | 181 | 2017-04-30 | Other | Casual Lobar bill | 9237 | 128 | 2 | 4
9728 | 182 | 2017-04-30 | Other | M/s Nuzrul bill for Stationary | 99630 | 128 | 2 | 4
9729 | 183 | 2017-05-02 | Other | M/S Padma Traders bill for printing & publication | 67265 | 128 | 2 | 5
9730 | 184 | 2017-05-02 | Other | Asif traders bill for Apr/17 | 487928 | 128 | 2 | 5
9731 | 185 | 2017-05-03 | Other | Imprest bill for may/17 | 0 | 128 | 2 | 5
9732 | 186 | 2017-05-03 | Other | TA bill for Fakhrul Abedin | 27450 | 128 | 2 | 5
9733 | 187 | 2017-05-08 | Other | Azad Ent. bill for toner | 99666 | 128 | 2 | 5
9736 | 189 | 2017-05-14 | Other | Nipuna Service bill for Petrol & Lubricant | 70351 | 128 | 2 | 5
9737 | 190 | 2017-05-15 | Other | Unifide business bill for Leptop | 0 | 128 | 2 | 5
9738 | 191 | 2017-05-15 | Other | Servey bill | 240834 | 128 | 2 | 5
9739 | 192 | 2017-05-16 | Other | Casual Lobar bill | 11471 | 128 | 2 | 5
9740 | 193 | 2017-05-16 | Other | Best Eastern CNG Gus bill | 23890 | 128 | 2 | 5
9741 | 194 | 2017-05-17 | Other | Mayar doya Motors bill for battery | 9450 | 128 | 2 | 5
9742 | 195 | 2017-05-17 | Other | Centel Autos bill for vehicle repair | 24500 | 128 | 2 | 5
9743 | 196 | 2017-05-17 | Other | BCIC water & electicity bill for mur/17 | 8494 | 128 | 2 | 5
9744 | 197 | 2017-05-24 | Civil | BWDB/KISH/HFMLIP/PW-14 1st bill | 4144654 | 128 | 2 | 5
9745 | 198 | 2017-05-25 | Civil | BWDB/KISH/HFMLIP/PW-05 1st bill | 9280540 | 128 | 2 | 5
9746 | 199 | 2017-05-25 | Other | BCIC office rent bill for may/17 | 327831 | 128 | 2 | 5
9747 | 200 | 2017-05-25 | Other | TA bill for rubel mia | 28234 | 128 | 2 | 5
9748 | 201 | 2017-05-28 | Civil | BWDB/KISH/HFMLIP/PW-06 1st bill | 10328339.98 | 128 | 2 | 5
9749 | 202 | 2017-05-28 | Other | TA bill for D. zahidul islam | 57375 | 128 | 2 | 5
9750 | 203 | 2017-05-28 | Other | TA bill for a.k.m sumsul Alam | 46162 | 128 | 2 | 5
9751 | 204 | 2017-05-28 | Other | TA bill for Alamin | 42400 | 128 | 2 | 5
9752 | 205 | 2017-05-28 | Other | M/S M hai & cong bill for Gus & Fuel | 38172 | 128 | 2 | 5
9753 | 206 | 2017-05-29 | Other | Bill for grain moisture mitre | 21900 | 128 | 2 | 5
9754 | 207 | 2017-05-29 | Other | TA bill for masud rana | 42143 | 128 | 2 | 5
9755 | 208 | 2017-05-31 | Other | SWM trading bill for training bag | 0 | 128 | 2 | 5
9756 | 209 | 2017-05-31 | Other | Asif traders bill for may/17 | 476580 | 128 | 2 | 5
9757 | 210 | 2017-05-31 | Other | Ayat ali bill for stationary | 149960 | 128 | 2 | 5
9758 | 211 | 2017-05-31 | Other | M/S Padma traders bill for form | 74340 | 128 | 2 | 5
9759 | 212 | 2017-06-01 | Other | TA bill for Fakhrul Abedin | 33087 | 128 | 2 | 6
9760 | 213 | 2017-06-04 | Other | EPRC 11 nos bill for may/17 | 237187 | 128 | 2 | 6
9761 | 214 | 2017-06-04 | Other | EPRC 65 nos bill for may/17 | 1399003 | 128 | 2 | 6
9762 | 215 | 2017-06-06 | Other | Imprest bill for June/17 | 0 | 128 | 2 | 6
9763 | 216 | 2017-06-06 | Other | TEC committee honorarium | 24600 | 128 | 2 | 6
9764 | 217 | 2017-06-06 | Other | TA bill for Juzrul ISlam | 74250 | 128 | 2 | 6
9765 | 218 | 2017-06-06 | Other | Telephone bill for PMO Office | 1441 | 128 | 2 | 6
9766 | 219 | 2017-06-11 | Other | Mihad machinary bill for petrol & lubricunt | 72510 | 128 | 2 | 6
9767 | 220 | 2017-06-11 | Other | nipuna service bill for petrol & lubricunt | 78440 | 128 | 2 | 6
9768 | 221 | 2017-06-13 | Other | Asif traders bill for june/17 | 771606 | 128 | 2 | 6
9769 | 222 | 2017-06-13 | Other | best eastern CNG bill for Gus & fuel | 11928 | 128 | 2 | 6
9770 | 223 | 2017-06-13 | Other | casual labur bill | 18630 | 128 | 2 | 6
9771 | 224 | 2017-06-13 | Other | EPRC 65 nos bill for june/17 | 2245579 | 128 | 2 | 6
9772 | 225 | 2017-06-13 | Other | EPRC 11 nos bill for june/17 | 352188 | 128 | 2 | 6
9773 | 226 | 2017-06-15 | Other | jubayar Auto Mobile bill for vehicle repair | 99040 | 128 | 2 | 6
9774 | 227 | 2017-06-15 | Civil | BWDB/KISH/HFMLIP/PW-02 2nd bill | 0 | 128 | 2 | 6
9775 | 228 | 2017-06-18 | Civil | KISH/HFMLIP/PW-4 1st bill | 0 | 128 | 2 | 6
9776 | 229 | 2017-06-18 | Other | Ayat ali bill for partition wall | 141864 | 128 | 2 | 6
9777 | 230 | 2017-06-18 | Other | Unimart trads bill for computer consumable | 0 | 128 | 2 | 6
9778 | 231 | 2017-06-18 | Civil | BWDB//HFMLIP/Motorcycle/Hobi-5 1st bill | 170000 | 128 | 2 | 6
9779 | 232 | 2017-06-18 | Civil | BWDB//HFMLIP/Air con/Hobi-7 1st bill | 0 | 128 | 2 | 6
9780 | 233 | 2017-06-18 | Other | M/S shohan bill for motorecycle | 169500 | 128 | 2 | 6
9781 | 234 | 2017-06-19 | Civil | KISH/HFMLIP/PW-13 2nd bill | 2555298.55 | 128 | 2 | 6
9782 | 235 | 2017-06-19 | Other | M/S Padma traders bill for form | 47084 | 128 | 2 | 6
9783 | 236 | 2017-06-19 | Other | BM Traders bill for pass book | 540000 | 128 | 2 | 6
9784 | 237 | 2017-06-19 | Other | jubayar Auto Mobile bill for vehicle repair | 23900 | 128 | 2 | 6
9785 | 238 | 2017-06-19 | Other | Hidroland solution bill Electronic total Station | 499500 | 128 | 2 | 6
9786 | 239 | 2017-06-20 | Other | casual labur bill | 33207 | 128 | 2 | 6
9787 | 240 | 2017-06-20 | Other | TEC committee honorarium | 0 | 128 | 2 | 6
9788 | 241 | 2017-06-20 | Civil | KISH/HFMLIP/PW-07 2nd bill | 967951 | 128 | 2 | 6
9789 | 242 | 2017-06-21 | Civil | KISH/HFMLIP/PW-03 1st bill | 5287457.98 | 128 | 2 | 6
9790 | 243 | 2017-06-21 | Other | Jus Dhaka bill for gate Instalation | 356392 | 128 | 2 | 6
9791 | 244 | 2017-06-22 | Other | Land Accusation | 20800000 | 128 | 2 | 6
9792 | 245 | 2017-06-22 | Other | Land Accusation | 50165000 | 128 | 2 | 6
9793 | 246 | 2017-06-28 | Other | Levatas bill for air condition | 0 | 128 | 2 | 6
9794 | 247 | 2017-06-28 | Other | servey bill | 388396 | 128 | 2 | 6
9795 | 248 | 2017-06-28 | Other | servey bill | 194198 | 128 | 2 | 6
9796 | 249 | 2017-06-28 | Other | servey bill | 97099 | 128 | 2 | 6
9797 | 250 | 2017-06-28 | Other | M/S R.H Construction bill for motorecycle | 0 | 128 | 2 | 6
9798 | 251 | 2017-06-28 | Other | Uttom Kumar Shingh bill for motorecycle | 0 | 128 | 2 | 6
9799 | 252 | 2017-06-28 | Other | Telephone bill for PMO Office | 590 | 128 | 2 | 6
9800 | 253 | 2017-06-28 | Other | Maple Cmputer bill for Stationary | 199332 | 128 | 2 | 6
9801 | 254 | 2017-06-28 | Other | casual labur bill | 27945 | 128 | 2 | 6
9802 | 255 | 2017-06-28 | Other | Ayat ali bill for printer & pendrive | 53100 | 128 | 2 | 6
9803 | 256 | 2017-06-28 | Other | TEC committee honorarium | 0 | 128 | 2 | 6
9804 | 257 | 2017-06-28 | Other | BCIC water & Electicity bill Apr,may/17 | 60184 | 128 | 2 | 6
9805 | 258 | 2017-06-28 | Other | BCIC office rent bill for June/17 | 0 | 128 | 2 | 6
9806 | 259 | 2017-06-28 | Other | Imprest bill for June/17 addl | 0 | 128 | 2 | 6
9807 | 260 | 2017-06-29 | Other | M/S murad & cong bill for petrol | 48355 | 128 | 2 | 6
9808 | 261 | 2017-06-29 | Other | book purchase | 1595 | 128 | 2 | 6
9809 | 262 | 2017-06-29 | Other | nipuna service bill for petrol & lubricunt | 57626 | 128 | 2 | 6
9810 | 263 | 2017-06-29 | Other | Golden fiber bill for speed boat | 0 | 128 | 2 | 6
9811 | 264 | 2017-06-29 | Other | consultancy bill | 0 | 128 | 2 | 6
9812 | 265 | 2017-06-29 | Other | Telephone purchase | 15000 | 128 | 2 | 6
9813 | 266 | 2017-06-29 | Other | Cookeries purchase | 15177 | 128 | 2 | 6
9814 | 267 | 2017-06-29 | Other | jubayar Auto Mobile bill for vehicle repair | 48500 | 128 | 2 | 6
9815 | 268 | 2017-06-29 | Other | servey bill | 199200 | 128 | 2 | 6
9816 | 269 | 2017-06-29 | Other | servey bill | 439057 | 128 | 2 | 6
9817 | 270 | 2017-06-29 | Other | Neef WiFi bill | 9105 | 128 | 2 | 6
9818 | 271 | 2017-06-29 | Other | Umbrella purchase | 1000 | 128 | 2 | 6
9819 | 272 | 2017-06-29 | Other | TEC committee honorarium | 0 | 128 | 2 | 6
9820 | 273 | 2017-06-29 | Other | Ayat Ali bill for computer consumable | 0 | 128 | 2 | 6
9821 | 274 | 2017-06-29 | Other | M/S Icon Motors Bill for vehicle repair | 24700 | 128 | 2 | 6
9822 | 275 | 2017-06-29 | Other | casual labur bill | 3780 | 128 | 2 | 6
9823 | 276 | 2017-06-29 | Other | M/S murad & cong bill for petrol | 22475 | 128 | 2 | 6
9824 | 277 | 2017-06-29 | Other | consultancy bill | 0 | 128 | 2 | 6
9825 | 278 | 2017-06-29 | Other | M/S murad & cong bill for petrol | 10243 | 128 | 2 | 6
9826 | 279 | 2017-06-29 | Other | RPA | 0 | 128 | 2 | 6
9545 | 1 | 2016-08-29 | Other | Environment fee | 460000 | 128 | 2 | 8
9546 | 2 | 2016-08-31 | Other | EPRC bill for Jul/16 | 237187 | 128 | 2 | 8
9547 | 3 | 2016-08-31 | Other | Imprest /Aug/16 | 0 | 128 | 2 | 8
9548 | 4 | 2016-08-31 | Other | EPRC bill for Jul/16 | 1399003 | 128 | 2 | 8
9549 | 5 | 2016-08-31 | Other | Asif TRaders bill for Jul/16 | 367364 | 128 | 2 | 8
9550 | 6 | 2016-09-04 | Other | EPRC bill for AUg/16 with bonus | 2159486 | 128 | 2 | 9
9551 | 7 | 2016-09-04 | Other | EPRC bill for AUg/16 with bonus | 366562 | 128 | 2 | 9
9552 | 8 | 2016-09-04 | Other | Nipuna Service bill for Petrol & Lubricant | 126582 | 128 | 2 | 9
9553 | 9 | 2016-09-04 | Other | Asif TRaders bill for Aug/16 with bonus | 592179 | 128 | 2 | 9
9554 | 10 | 2016-09-05 | Other | BCIC office rent bill for Aug/16 | 310726 | 128 | 2 | 9
9555 | 11 | 2016-09-05 | Other | BCIC Water & Electicity bill for Jul/16 | 10861 | 128 | 2 | 9
9556 | 12 | 2016-09-05 | Other | Best Eastern CNG Gus bill | 10861 | 128 | 2 | 9
9557 | 13 | 2016-09-06 | Other | Mun Ent. bill for passbook | 288000 | 128 | 2 | 9
9558 | 14 | 2016-09-06 | Other | TA bill for Fakhrul Abedin | 82700 | 128 | 2 | 9
9559 | 15 | 2016-09-06 | Other | TA bill for Rubol mia | 32842 | 128 | 2 | 9
9560 | 16 | 2016-09-06 | Other | Vehicle repair | 113871 | 128 | 2 | 9
9561 | 17 | 2016-09-07 | Other | Unimart trads bill for Computer Supply | 295000 | 128 | 2 | 9
9562 | 18 | 2016-09-07 | Other | Servey bill | 74100 | 128 | 2 | 9
9563 | 19 | 2016-09-07 | Other | Servey bill | 145920 | 128 | 2 | 9
9564 | 20 | 2016-09-18 | Other | Imprest Sep/16 | 0 | 128 | 2 | 9
9565 | 21 | 2016-09-22 | Other | Financial Express bill for newspaper | 25744 | 128 | 2 | 9
9566 | 22 | 2016-09-22 | Other | Jonokontho bill for newspaper | 43470 | 128 | 2 | 9
9567 | 23 | 2016-09-22 | Other | Best Eastern CNG Gus bill | 9728 | 128 | 2 | 9
9568 | 24 | 2016-09-22 | Other | TA bill for A.K.M sumsul Alam | 53975 | 128 | 2 | 9
9569 | 25 | 2016-09-26 | Other | Ta bill for D. Zahidul ISlam | 57058 | 128 | 2 | 9
9570 | 26 | 2016-09-26 | Other | Casual Lobar bill | 36708 | 128 | 2 | 9
9571 | 27 | 2016-09-26 | Other | TA bill for Alamin | 48975 | 128 | 2 | 9
9574 | 29 | 2016-10-03 | Other | Asif Traders bill for Sep/16 | 442559 | 128 | 2 | 10
9575 | 30 | 2016-10-03 | Other | EPRC bill for Sep/16 65 nos | 1714675 | 128 | 2 | 10
9576 | 31 | 2016-10-03 | Other | EPRC bill for Sep/16 11 nos | 294687 | 128 | 2 | 10
9577 | 32 | 2016-10-09 | Other | Financial Express bill for newspaper | 14710 | 128 | 2 | 10
9578 | 33 | 2016-10-09 | Other | Jonoconto bill for newspaper | 24840 | 128 | 2 | 10
9579 | 34 | 2016-10-09 | Other | BCIC bill for Water & Electicity Aug/16 | 21697 | 128 | 2 | 10
9580 | 35 | 2016-10-09 | Other | Telephone bill for PMO office | 1598 | 128 | 2 | 10
9581 | 36 | 2016-10-10 | Other | SMW Trading bill for Photocopy | 0 | 128 | 2 | 10
9582 | 37 | 2016-10-10 | Other | Imprest bill for Agu/16 | 0 | 128 | 2 | 10
9583 | 38 | 2016-10-16 | Other | Nipuna Service bill for Petrol & Lubricant | 70846 | 128 | 2 | 10
9584 | 39 | 2016-10-16 | Other | Best Eastern CNG Gus bill | 8170 | 128 | 2 | 10
9585 | 40 | 2016-10-16 | Other | M/S Icom Motors bill for Vehicle Repair | 46400 | 128 | 2 | 10
9586 | 41 | 2016-10-17 | Other | BCIC office rent bill for Oct/16 | 310726 | 128 | 2 | 10
9587 | 42 | 2016-10-19 | Other | Jubayar Auto mobile bill for Vehicle repair | 76980 | 128 | 2 | 10
9588 | 43 | 2016-10-19 | Other | Casual Lobar bill | 17615 | 128 | 2 | 10
9589 | 44 | 2016-10-19 | Other | TEC Committee honorarium bill | 12700 | 128 | 2 | 10
9590 | 45 | 2016-10-31 | Other | Servey bill | 118560 | 128 | 2 | 10
9591 | 46 | 2016-10-31 | Other | BCIC water & Electicity bill for Aug/16 | 4821 | 128 | 2 | 10
9592 | 47 | 2016-10-31 | Other | Imprest bill Aug/16 Addi | 0 | 128 | 2 | 10
9593 | 48 | 2016-10-31 | Other | Asif Traders bill for Oct/16 | 443937 | 128 | 2 | 10
9595 | 49 | 2016-11-02 | Other | TEC Committee honorarium bill | 32850 | 128 | 2 | 11
9596 | 50 | 2016-11-02 | Other | Busta Int. bill for Speed boat | 0 | 128 | 2 | 11
9597 | 51 | 2016-11-03 | Other | EPRC bill for Oct/16 65 nos | 1399003 | 128 | 2 | 11
9598 | 52 | 2016-11-03 | Other | EPRC bill for Oct/16 11 nos | 237187 | 128 | 2 | 11
9599 | 53 | 2016-11-06 | Other | Casual Lobar bill | 19572 | 128 | 2 | 11
9600 | 54 | 2016-11-06 | Other | Ayat ali bill for cabinate Supply | 0 | 128 | 2 | 11
9601 | 55 | 2016-11-07 | Other | TA bill for Rubol mia | 35250 | 128 | 2 | 11
9602 | 56 | 2016-11-08 | Other | Said Motors bill for vehicle repair | 17800 | 128 | 2 | 11
9603 | 57 | 2016-11-08 | Other | Nipuna Service bill for Petrol & Lubricant | 59615 | 128 | 2 | 11
9604 | 58 | 2016-11-09 | Other | TA bill for Yousuf Ali | 6594 | 128 | 2 | 11
9605 | 59 | 2016-11-10 | Other | Imprest bii for Nov/16 | 0 | 128 | 2 | 11
9606 | 60 | 2016-11-17 | Other | BCIC Office rent bill for Nov/16 | 310726 | 128 | 2 | 11
9607 | 61 | 2016-11-17 | Other | Said Motors bill for vehicle repair | 17800 | 128 | 2 | 11
9608 | 62 | 2016-11-17 | Other | Best Eastern CNG Gus bill | 8431 | 128 | 2 | 11
9609 | 63 | 2016-11-17 | Other | Land Accusation | 20000000 | 128 | 2 | 11
9610 | 64 | 2016-11-22 | Other | Land Accusation | 20000000 | 128 | 2 | 11
9611 | 65 | 2016-11-22 | Other | Land Accusation | 40000000 | 128 | 2 | 11
9612 | 66 | 2016-11-22 | Other | Land Accusation | 2500000 | 128 | 2 | 11
9613 | 67 | 2016-11-22 | Other | Land Accusation | 5000000 | 128 | 2 | 11
9614 | 68 | 2016-11-22 | Other | Land Accusation | 20000000 | 128 | 2 | 11
9615 | 69 | 2016-11-22 | Other | Land Accusation | 7500000 | 128 | 2 | 11
9616 | 70 | 2016-11-22 | Other | consultancy bill | 0 | 128 | 2 | 11
9617 | 71 | 2016-11-28 | Other | Imprest bill for ov/16 Addi | 0 | 128 | 2 | 11
9618 | 72 | 2016-11-29 | Other | consultancy bill | 0 | 128 | 2 | 11
9619 | 73 | 2016-11-30 | Other | asif Traders bill for Nov/16 | 442539 | 128 | 2 | 11
9620 | 74 | 2016-12-04 | Other | TA bill for Fakhrul Abedin | 59800 | 128 | 2 | 12
9621 | 75 | 2016-12-07 | Other | EPRC bill for Nov/16 65 nos | 1399003 | 128 | 2 | 12
9622 | 76 | 2016-12-07 | Other | EPRC bill for Nov/16 11 nos | 237187 | 128 | 2 | 12
9623 | 77 | 2016-12-07 | Other | TA bill for Yousuf Ali | 10550 | 128 | 2 | 12
9624 | 78 | 2016-12-08 | Other | Nipuna Service bill for Petrol & Lubricant | 65697 | 128 | 2 | 12
9625 | 79 | 2016-12-08 | Other | Casual Lobar bill | 10857 | 128 | 2 | 12
9626 | 80 | 2016-12-12 | Other | imprest bill for Dec/16 | 0 | 128 | 2 | 12
9627 | 81 | 2016-12-18 | Other | Best Eastern CNG Gus bill | 3543 | 128 | 2 | 12
9628 | 82 | 2016-12-20 | Other | consultancy bill | 0 | 128 | 2 | 12
9629 | 83 | 2016-12-20 | Other | consultancy bill | 0 | 128 | 2 | 12
9630 | 84 | 2016-12-27 | Other | M/S Nuzrul bill for Tyre | 47880 | 128 | 2 | 12
9631 | 85 | 2016-12-27 | Other | BCIC Office rent bill for Dec/16 | 310726 | 128 | 2 | 12
9632 | 86 | 2016-12-27 | Other | Jubayar Auto mobile bill for Vehicle repair | 38500 | 128 | 2 | 12
9633 | 87 | 2016-12-28 | Other | Petrol & lubricunt bill | 303752 | 128 | 2 | 12
9634 | 88 | 2016-12-28 | Other | Imprest bill for Dce/addi | 0 | 128 | 2 | 12
9635 | 89 | 2016-12-29 | Other | BCIC Water & electicity bill for Oct/16 | 21706 | 128 | 2 | 12
9636 | 90 | 2017-01-03 | Other | EPRC bill for Dec/16 65 nos | 1399003 | 128 | 2 | 1
9637 | 91 | 2017-01-03 | Other | EPRC bill for Dec/16 11 nos | 237187 | 128 | 2 | 1
9638 | 92 | 2017-01-03 | Other | Asif traders bill for Dec/16 | 453886 | 128 | 2 | 1
9639 | 93 | 2017-01-04 | Other | Telephone bill for PMO office | 2319 | 128 | 2 | 1
9640 | 94 | 2017-01-04 | Other | Midia trads bill for passbook | 199800 | 128 | 2 | 1
9641 | 95 | 2017-01-09 | Other | Nipuna Service bill for Petrol & Lubricant | 44510 | 128 | 2 | 1
9642 | 96 | 2017-01-11 | Other | Imprest bill for Jan/16 | 0 | 128 | 2 | 1
9643 | 97 | 2017-01-18 | Other | Maple computer bill for Photocier | 96700 | 128 | 2 | 1
9644 | 98 | 2017-01-18 | Other | Unimart trads bill for Computer Supply | 322500 | 128 | 2 | 1
9645 | 99 | 2017-01-23 | Other | TA bill for Rubol mia | 35658 | 128 | 2 | 1
9646 | 100 | 2017-01-23 | Other | TA bill for A.K.M sumsul Alam | 75112 | 128 | 2 | 1
9647 | 101 | 2017-01-23 | Other | TA bill for Alamin | 43625 | 128 | 2 | 1
9648 | 102 | 2017-01-24 | Other | Imprest bill for Jan/16 Addi | 0 | 128 | 2 | 1
9649 | 103 | 2017-01-30 | Other | TEC Committee honorarium bill | 46500 | 128 | 2 | 1
9650 | 104 | 2017-01-30 | Other | Shohag Tyre bill for Tyre | 21546 | 128 | 2 | 1
9651 | 105 | 2017-02-01 | Other | Asif traders bill for Jau/17 | 0 | 128 | 2 | 1
9652 | 106 | 2017-02-01 | Other | BCIC Water & electicity bill for Oct/16 | 0 | 128 | 2 | 1
9653 | 107 | 2017-02-01 | Other | M/S Nuzrul bill for Tyre | 41146 | 128 | 2 | 2
9654 | 108 | 2017-02-02 | Other | BCIC office rent Jau/17 | 310726 | 128 | 2 | 2
9655 | 109 | 2017-02-02 | Other | Petrol & lubricunt bill | 506848 | 128 | 2 | 2
9656 | 110 | 2017-02-06 | Other | EPRC bill for Jan/17 11 nos | 258626 | 128 | 2 | 2
9657 | 111 | 2017-02-06 | Other | EPRC bill for Jan/17 65 nos | 1399003 | 128 | 2 | 2
9658 | 112 | 2017-02-07 | Other | Imprest bill for feb/17 | 0 | 128 | 2 | 2
9659 | 113 | 2017-02-08 | Other | TA bill for Masud Rana | 6000 | 128 | 2 | 2
9660 | 114 | 2017-02-08 | Other | TEC Committee honorarium bill | 30600 | 128 | 2 | 2
9661 | 115 | 2017-02-08 | Other | Ayat ali bill for Stationay Supply | 103637 | 128 | 2 | 2
9662 | 116 | 2017-02-13 | Other | consultancy bill | 0 | 128 | 2 | 2
9663 | 117 | 2017-02-14 | Other | Shohag Tyre bill for Tyre | 21546 | 128 | 2 | 2
9664 | 118 | 2017-02-15 | Other | M/S samat Eng. bill for motorecycle | 166200 | 128 | 2 | 2
9665 | 119 | 2017-02-15 | Other | pritom Int. bill for motorecycle | 166200 | 128 | 2 | 2
9666 | 120 | 2017-02-16 | Other | Land Accusation | 120000000 | 128 | 2 | 2
9667 | 121 | 2017-02-19 | Other | Gate Installment | 360000 | 128 | 2 | 2
9668 | 122 | 2017-02-26 | Other | M/S M & Hai bill for Gus and Fuel | 33583 | 128 | 2 | 2
9669 | 123 | 2017-02-26 | Other | Nipuna Service bill for Petrol & Lubricant | 72689 | 128 | 2 | 2
9670 | 124 | 2017-02-26 | Other | BCIC office rent bill for feb/17 | 310726 | 128 | 2 | 2
9671 | 125 | 2017-02-26 | Other | BCIC Water & electicity bill | 12293 | 128 | 2 | 2
9672 | 126 | 2017-02-26 | Civil | PW-02 1st bill | 0 | 128 | 2 | 2
9673 | 127 | 2017-02-27 | Other | M/S Hidroland bill for Electronic purchase | 0 | 128 | 2 | 2
9674 | 128 | 2017-02-27 | Other | Imprest bill for Feb/17 Addi | 0 | 128 | 2 | 2
9675 | 129 | 2017-02-28 | Other | TA bill for maraz | 21210 | 128 | 2 | 2
9676 | 130 | 2017-02-28 | Other | TA bill for Yousuf Ali | 17600 | 128 | 2 | 2
9677 | 131 | 2017-02-28 | Other | Sri mongal Motors bill for vehicle repair | 50000 | 128 | 2 | 2
9678 | 132 | 2017-02-28 | Other | Sri mongal Motors bill for vehicle repair | 69750 | 128 | 2 | 2
9679 | 133 | 2017-02-28 | Other | Asif traders bill for Feb/17 | 487928 | 128 | 2 | 2
9680 | 134 | 2017-02-28 | Other | consultancy bill | 0 | 128 | 2 | 2
9681 | 135 | 2017-03-02 | Other | EPRC bill for feb/17 65 nos | 1399003 | 128 | 2 | 3
9682 | 136 | 2017-03-02 | Other | EPRC bill for feb/17 11 nos | 237312 | 128 | 2 | 3
9683 | 137 | 2017-03-02 | Other | Jubayar Auto mobile bill for Vehicle repair | 35430 | 128 | 2 | 3
9684 | 138 | 2017-03-07 | Other | Best Eastern CNG Gus bill | 11308 | 128 | 2 | 3
9685 | 139 | 2017-03-14 | Other | BCIC water & electicity bill for | 19135 | 128 | 2 | 3
9686 | 140 | 2017-03-14 | Other | Imprest bill for Mar/17 | 0 | 128 | 2 | 3
9687 | 141 | 2017-03-14 | Other | TA bill for Fakhrul Abedin | 99395 | 128 | 2 | 3
9688 | 142 | 2017-03-15 | Other | BCIC office rent Muarch/17 | 310726 | 128 | 2 | 3
9689 | 143 | 2017-03-15 | Other | Nipuna Service bill for Petrol & Lubricant | 51820 | 128 | 2 | 3
9690 | 144 | 2017-03-20 | Other | Servey bill | 22050 | 128 | 2 | 3
9691 | 145 | 2017-03-20 | Other | Servey bill | 22050 | 128 | 2 | 3
9692 | 146 | 2017-03-20 | Other | Jubayar Auto mobile bill for Vehicle repair | 18100 | 128 | 2 | 3
9693 | 147 | 2017-03-20 | Other | Jubayar Auto mobile bill for Vehicle repair | 22000 | 128 | 2 | 3
9694 | 148 | 2017-03-21 | Other | Best Eastern CNG Gus bill | 10681 | 128 | 2 | 3
9695 | 149 | 2017-03-23 | Civil | KISH/HFMLIP/PW-07 1st bill | 9580757 | 128 | 2 | 3
9696 | 150 | 2017-03-23 | Other | consultancy bill | 0 | 128 | 2 | 3
9697 | 151 | 2017-03-28 | Other | BCIC water & electicity bill for Feb/17 | 10763 | 128 | 2 | 3
9698 | 152 | 2017-03-30 | Civil | KISH/HFMLIP/PW-03 1st bill | 14079558 | 128 | 2 | 3
9699 | 153 | 2017-03-30 | Other | TA bill for A.K.M sumsul Alam | 67370 | 128 | 2 | 3
9700 | 154 | 2017-03-30 | Other | Ta bill for D. Zahidul ISlam | 61593 | 128 | 2 | 3
9701 | 155 | 2017-03-30 | Other | TA bill for Rubol mia | 28660 | 128 | 2 | 3
9702 | 156 | 2017-03-30 | Other | TA bill for Alamin | 64725 | 128 | 2 | 3
9703 | 157 | 2017-03-30 | Other | TA bill for Azizur alam | 2660 | 128 | 2 | 3
9704 | 158 | 2017-03-30 | Other | TA bill for Dhaka rac | 40796 | 128 | 2 | 3
9705 | 159 | 2017-04-02 | Other | Imprest bill for April | 0 | 128 | 2 | 4
9706 | 160 | 2017-04-04 | Other | TA bill for Fakhrul Abedin | 58600 | 128 | 2 | 4
9707 | 161 | 2017-04-04 | Other | Asir traders bill for mur/17 with bonus | 553883 | 128 | 2 | 4
9708 | 162 | 2017-04-05 | Other | consultancy bill | 0 | 128 | 2 | 4
9709 | 163 | 2017-04-09 | Other | Jubayar Auto mobile bill for Vehicle repair | 49400 | 128 | 2 | 4
9710 | 164 | 2017-04-09 | Other | TA bill for Polash chandro | 22285 | 128 | 2 | 4
9711 | 165 | 2017-04-11 | Other | Nipuna Service bill for Petrol & Lubricant | 67645 | 128 | 2 | 4
9712 | 166 | 2017-04-11 | Other | Telephone bill for PMO office | 2408 | 128 | 2 | 4
9713 | 167 | 2017-04-12 | Other | Ent. Office bill for toner | 45036 | 128 | 2 | 4
9714 | 168 | 2017-04-16 | Other | Casual Lobar bill | 22208 | 128 | 2 | 4
9715 | 169 | 2017-04-16 | Other | Casual Lobar bill | 11633 | 128 | 2 | 4
9716 | 170 | 2017-04-17 | Other | EPRC 65 nos bill for mur/17 | 263367 | 128 | 2 | 4
9717 | 171 | 2017-04-17 | Other | EPRC 11 nos bill for mur/17 | 1555003 | 128 | 2 | 4
9718 | 172 | 2017-04-17 | Other | Land Accusation | 159000000 | 128 | 2 | 4
9719 | 173 | 2017-04-18 | Other | consultancy bill | 0 | 128 | 2 | 4
9720 | 174 | 2017-04-18 | Other | consultancy bill | 0 | 128 | 2 | 4
9721 | 175 | 2017-04-18 | Other | M/S murad bill for petrol & lubricunt | 160038 | 128 | 2 | 4
9722 | 176 | 2017-04-18 | Civil | KISH/HFMLIP/PW-13 1st bill | 14259856 | 128 | 2 | 4
9723 | 177 | 2017-04-20 | Other | TA bill for maraz | 20490 | 128 | 2 | 4
9724 | 178 | 2017-04-25 | Other | BCIC office rent bill for mur/17 | 310726 | 128 | 2 | 4
9725 | 179 | 2017-04-30 | Other | Ta bill for D. Zahidul ISlam | 93549 | 128 | 2 | 4
9726 | 180 | 2017-04-30 | Other | Casual Lobar bill | 12018 | 128 | 2 | 4
9727 | 181 | 2017-04-30 | Other | Casual Lobar bill | 9237 | 128 | 2 | 4
9728 | 182 | 2017-04-30 | Other | M/s Nuzrul bill for Stationary | 99630 | 128 | 2 | 4
9729 | 183 | 2017-05-02 | Other | M/S Padma Traders bill for printing & publication | 67265 | 128 | 2 | 5
9730 | 184 | 2017-05-02 | Other | Asif traders bill for Apr/17 | 487928 | 128 | 2 | 5
9731 | 185 | 2017-05-03 | Other | Imprest bill for may/17 | 0 | 128 | 2 | 5
9732 | 186 | 2017-05-03 | Other | TA bill for Fakhrul Abedin | 27450 | 128 | 2 | 5
9733 | 187 | 2017-05-08 | Other | Azad Ent. bill for toner | 99666 | 128 | 2 | 5
9736 | 189 | 2017-05-14 | Other | Nipuna Service bill for Petrol & Lubricant | 70351 | 128 | 2 | 5
9737 | 190 | 2017-05-15 | Other | Unifide business bill for Leptop | 0 | 128 | 2 | 5
9738 | 191 | 2017-05-15 | Other | Servey bill | 240834 | 128 | 2 | 5
9739 | 192 | 2017-05-16 | Other | Casual Lobar bill | 11471 | 128 | 2 | 5
9740 | 193 | 2017-05-16 | Other | Best Eastern CNG Gus bill | 23890 | 128 | 2 | 5
9741 | 194 | 2017-05-17 | Other | Mayar doya Motors bill for battery | 9450 | 128 | 2 | 5
9742 | 195 | 2017-05-17 | Other | Centel Autos bill for vehicle repair | 24500 | 128 | 2 | 5
9743 | 196 | 2017-05-17 | Other | BCIC water & electicity bill for mur/17 | 8494 | 128 | 2 | 5
9744 | 197 | 2017-05-24 | Civil | BWDB/KISH/HFMLIP/PW-14 1st bill | 4144654 | 128 | 2 | 5
9745 | 198 | 2017-05-25 | Civil | BWDB/KISH/HFMLIP/PW-05 1st bill | 9280540 | 128 | 2 | 5
9746 | 199 | 2017-05-25 | Other | BCIC office rent bill for may/17 | 327831 | 128 | 2 | 5
9747 | 200 | 2017-05-25 | Other | TA bill for rubel mia | 28234 | 128 | 2 | 5
9748 | 201 | 2017-05-28 | Civil | BWDB/KISH/HFMLIP/PW-06 1st bill | 10328339.98 | 128 | 2 | 5
9749 | 202 | 2017-05-28 | Other | TA bill for D. zahidul islam | 57375 | 128 | 2 | 5
9750 | 203 | 2017-05-28 | Other | TA bill for a.k.m sumsul Alam | 46162 | 128 | 2 | 5
9751 | 204 | 2017-05-28 | Other | TA bill for Alamin | 42400 | 128 | 2 | 5
9752 | 205 | 2017-05-28 | Other | M/S M hai & cong bill for Gus & Fuel | 38172 | 128 | 2 | 5
9753 | 206 | 2017-05-29 | Other | Bill for grain moisture mitre | 21900 | 128 | 2 | 5
9754 | 207 | 2017-05-29 | Other | TA bill for masud rana | 42143 | 128 | 2 | 5
9755 | 208 | 2017-05-31 | Other | SWM trading bill for training bag | 0 | 128 | 2 | 5
9756 | 209 | 2017-05-31 | Other | Asif traders bill for may/17 | 476580 | 128 | 2 | 5
9757 | 210 | 2017-05-31 | Other | Ayat ali bill for stationary | 149960 | 128 | 2 | 5
9758 | 211 | 2017-05-31 | Other | M/S Padma traders bill for form | 74340 | 128 | 2 | 5
9759 | 212 | 2017-06-01 | Other | TA bill for Fakhrul Abedin | 33087 | 128 | 2 | 6
9760 | 213 | 2017-06-04 | Other | EPRC 11 nos bill for may/17 | 237187 | 128 | 2 | 6
9761 | 214 | 2017-06-04 | Other | EPRC 65 nos bill for may/17 | 1399003 | 128 | 2 | 6
9762 | 215 | 2017-06-06 | Other | Imprest bill for June/17 | 0 | 128 | 2 | 6
9763 | 216 | 2017-06-06 | Other | TEC committee honorarium | 24600 | 128 | 2 | 6
9764 | 217 | 2017-06-06 | Other | TA bill for Juzrul ISlam | 74250 | 128 | 2 | 6
9765 | 218 | 2017-06-06 | Other | Telephone bill for PMO Office | 1441 | 128 | 2 | 6
9766 | 219 | 2017-06-11 | Other | Mihad machinary bill for petrol & lubricunt | 72510 | 128 | 2 | 6
9767 | 220 | 2017-06-11 | Other | nipuna service bill for petrol & lubricunt | 78440 | 128 | 2 | 6
9768 | 221 | 2017-06-13 | Other | Asif traders bill for june/17 | 771606 | 128 | 2 | 6
9769 | 222 | 2017-06-13 | Other | best eastern CNG bill for Gus & fuel | 11928 | 128 | 2 | 6
9770 | 223 | 2017-06-13 | Other | casual labur bill | 18630 | 128 | 2 | 6
9771 | 224 | 2017-06-13 | Other | EPRC 65 nos bill for june/17 | 2245579 | 128 | 2 | 6
9772 | 225 | 2017-06-13 | Other | EPRC 11 nos bill for june/17 | 352188 | 128 | 2 | 6
9773 | 226 | 2017-06-15 | Other | jubayar Auto Mobile bill for vehicle repair | 99040 | 128 | 2 | 6
9774 | 227 | 2017-06-15 | Civil | BWDB/KISH/HFMLIP/PW-02 2nd bill | 0 | 128 | 2 | 6
9775 | 228 | 2017-06-18 | Civil | KISH/HFMLIP/PW-4 1st bill | 0 | 128 | 2 | 6
9776 | 229 | 2017-06-18 | Other | Ayat ali bill for partition wall | 141864 | 128 | 2 | 6
9777 | 230 | 2017-06-18 | Other | Unimart trads bill for computer consumable | 0 | 128 | 2 | 6
9778 | 231 | 2017-06-18 | Civil | BWDB//HFMLIP/Motorcycle/Hobi-5 1st bill | 170000 | 128 | 2 | 6
9779 | 232 | 2017-06-18 | Civil | BWDB//HFMLIP/Air con/Hobi-7 1st bill | 0 | 128 | 2 | 6
9780 | 233 | 2017-06-18 | Other | M/S shohan bill for motorecycle | 169500 | 128 | 2 | 6
9781 | 234 | 2017-06-19 | Civil | KISH/HFMLIP/PW-13 2nd bill | 2555298.55 | 128 | 2 | 6
9782 | 235 | 2017-06-19 | Other | M/S Padma traders bill for form | 47084 | 128 | 2 | 6
9783 | 236 | 2017-06-19 | Other | BM Traders bill for pass book | 540000 | 128 | 2 | 6
9784 | 237 | 2017-06-19 | Other | jubayar Auto Mobile bill for vehicle repair | 23900 | 128 | 2 | 6
9785 | 238 | 2017-06-19 | Other | Hidroland solution bill Electronic total Station | 499500 | 128 | 2 | 6
9786 | 239 | 2017-06-20 | Other | casual labur bill | 33207 | 128 | 2 | 6
9787 | 240 | 2017-06-20 | Other | TEC committee honorarium | 0 | 128 | 2 | 6
9788 | 241 | 2017-06-20 | Civil | KISH/HFMLIP/PW-07 2nd bill | 967951 | 128 | 2 | 6
9789 | 242 | 2017-06-21 | Civil | KISH/HFMLIP/PW-03 1st bill | 5287457.98 | 128 | 2 | 6
9790 | 243 | 2017-06-21 | Other | Jus Dhaka bill for gate Instalation | 356392 | 128 | 2 | 6
9791 | 244 | 2017-06-22 | Other | Land Accusation | 20800000 | 128 | 2 | 6
9792 | 245 | 2017-06-22 | Other | Land Accusation | 50165000 | 128 | 2 | 6
9793 | 246 | 2017-06-28 | Other | Levatas bill for air condition | 0 | 128 | 2 | 6
9794 | 247 | 2017-06-28 | Other | servey bill | 388396 | 128 | 2 | 6
9795 | 248 | 2017-06-28 | Other | servey bill | 194198 | 128 | 2 | 6
9796 | 249 | 2017-06-28 | Other | servey bill | 97099 | 128 | 2 | 6
9797 | 250 | 2017-06-28 | Other | M/S R.H Construction bill for motorecycle | 0 | 128 | 2 | 6
9798 | 251 | 2017-06-28 | Other | Uttom Kumar Shingh bill for motorecycle | 0 | 128 | 2 | 6
9799 | 252 | 2017-06-28 | Other | Telephone bill for PMO Office | 590 | 128 | 2 | 6
9800 | 253 | 2017-06-28 | Other | Maple Cmputer bill for Stationary | 199332 | 128 | 2 | 6
9801 | 254 | 2017-06-28 | Other | casual labur bill | 27945 | 128 | 2 | 6
9802 | 255 | 2017-06-28 | Other | Ayat ali bill for printer & pendrive | 53100 | 128 | 2 | 6
9803 | 256 | 2017-06-28 | Other | TEC committee honorarium | 0 | 128 | 2 | 6
9804 | 257 | 2017-06-28 | Other | BCIC water & Electicity bill Apr,may/17 | 60184 | 128 | 2 | 6
9805 | 258 | 2017-06-28 | Other | BCIC office rent bill for June/17 | 0 | 128 | 2 | 6
9806 | 259 | 2017-06-28 | Other | Imprest bill for June/17 addl | 0 | 128 | 2 | 6
9807 | 260 | 2017-06-29 | Other | M/S murad & cong bill for petrol | 48355 | 128 | 2 | 6
9808 | 261 | 2017-06-29 | Other | book purchase | 1595 | 128 | 2 | 6
9809 | 262 | 2017-06-29 | Other | nipuna service bill for petrol & lubricunt | 57626 | 128 | 2 | 6
9810 | 263 | 2017-06-29 | Other | Golden fiber bill for speed boat | 0 | 128 | 2 | 6
9811 | 264 | 2017-06-29 | Other | consultancy bill | 0 | 128 | 2 | 6
9812 | 265 | 2017-06-29 | Other | Telephone purchase | 15000 | 128 | 2 | 6
9813 | 266 | 2017-06-29 | Other | Cookeries purchase | 15177 | 128 | 2 | 6
9814 | 267 | 2017-06-29 | Other | jubayar Auto Mobile bill for vehicle repair | 48500 | 128 | 2 | 6
9815 | 268 | 2017-06-29 | Other | servey bill | 199200 | 128 | 2 | 6
9816 | 269 | 2017-06-29 | Other | servey bill | 439057 | 128 | 2 | 6
9817 | 270 | 2017-06-29 | Other | Neef WiFi bill | 9105 | 128 | 2 | 6
9818 | 271 | 2017-06-29 | Other | Umbrella purchase | 1000 | 128 | 2 | 6
9819 | 272 | 2017-06-29 | Other | TEC committee honorarium | 0 | 128 | 2 | 6
9820 | 273 | 2017-06-29 | Other | Ayat Ali bill for computer consumable | 0 | 128 | 2 | 6
9821 | 274 | 2017-06-29 | Other | M/S Icon Motors Bill for vehicle repair | 24700 | 128 | 2 | 6
9822 | 275 | 2017-06-29 | Other | casual labur bill | 3780 | 128 | 2 | 6
9823 | 276 | 2017-06-29 | Other | M/S murad & cong bill for petrol | 22475 | 128 | 2 | 6
9824 | 277 | 2017-06-29 | Other | consultancy bill | 0 | 128 | 2 | 6
9825 | 278 | 2017-06-29 | Other | M/S murad & cong bill for petrol | 10243 | 128 | 2 | 6
9826 | 279 | 2017-06-29 | Other | RPA | 0 | 128 | 2 | 6
9734 | 188 (k) | 2017-05-08 | Other | EPRC 65 nos bill for Apr/17 | 237188 | 128 | 2 | 5
9735 | 188 (kho) | 2017-05-08 | Other | EPRC 11 nos bill for Apr/17 | 1399003 | 128 | 2 | 5
9572 | 28(K) | 2016-09-27 | Other | BCIC office rent bill for Sep/16 | 310726 | 128 | 2 | 9
9573 | 28(Kho) | 2016-09-27 | Other | Imprest bill for Sep/16 Addi | 0 | 128 | 2 | 9
9594 | 48(Kho) | 2016-10-31 | Other | Imprest bill Aug/16 | 0 | 128 | 2 | 10

## Budget_Allocation
DPP_Allocation | dpp_id | Budget_Allocation
Irrigation Inlet | 57 | 678
Regulaor Reinstallation Rehab Haor | 58 | 679
Reg/CW/Bridge/Box outlet | 59 | 680
Re-excavation of Khal New Haor | 60 | 681
Re-excavation of Khal Rehab Haor | 61 | 682
Full Embnk Reahab (Rehab Haor) | 62 | 683
Submersible Embnk Reahab (Rehab Haor) | 63 | 684
Submersible Embnk construction | 64 | 685
Regulaor Reinstallation New Haor | 65 | 686
Const:WMG Office | 66 | 687
Regulator Gate Repair | 39 | 660

## Fy
id | startDate | finishDate
1 | 2015-07-01 | 2016-06-30
2 | 2016-07-01 | 2017-06-30
3 | 2017-07-01 | 2018-06-30
4 | 2018-07-01 | 2019-06-30
5 | 2019-07-01 | 2020-06-30
6 | 2020-07-01 | 2021-06-30
7 | 2021-07-01 | 2022-06-30