## Annex-II
Annexture-II: List of Site where works stopped due to Land Acquisition
Contract Package Name | Structure Name | Did Progress Hampered by Land Acquition Problems/Other Problems due to Employer (Yes/No) | Detail Description of the Problems
HOBI/PW-01 | Cnstruction of 2-Vent Regulator | Yes | Land Ownesr obstructed Mobilization of the Contractor Before Reciept of Land Payment
| Consruction of 4.00 m wide causeway | Yes | Land Owners obstructed Mobilization of the Contractor Before Reciept of Land Payment
| Re-excavation of Matikata Khal from km 0.000 to 2.295 | No
| Re-excavation of Bashira River in between km 0.000 to 20.000=17.400 | No
| Resectioning of Submersible Embankment along the left bank of Bashira River in between km 2.420 to km 9.760=7.00 Km | No
| Construction of New Embankment along the left bank of Bitangal khal in between km 10.000 to 17.000 =7.000 | No
HOBI/PW-02 | 4m Causeway-1 | No
| Satmukha Khal from Km 0.000 to Km 1.790 | No
| Kairdhala Khal from Km 0.000to 1.695 | Yes | Land Ownesr obstructed Mobilization of the Contractor Before Reciept of Land Payment
| Singar Beel Khal from Km 0.000 to Km 2.720 | No
| Construction of new retired embankment between Km 0.000 to Km 26.500=6.894 km | No
| Construction of New embankment from Km 22.850 to 32.210=8.360 Km | No
| Resectiong of Submersible Embankment along left bank of Khoai River from Km 0.000 to Km 16.020=16.020 Km | No
| Resectioning ofSubmesible Embankment along left bank of Kushiyara River in bnetween Km 0.000 to Km 26.000= 7.230 km | No
HOBI/PW-04 | Submersible Embankment at Mokhar Haor in between km 31.600 to 81.749=23.815 | Yes | Due to LAND acquiition problems site posession could not be give at different location
HOBI/PW-05 | 1-Vent Regulator at Km51.58 in Mokhar Haor Project | Yes | Site poseesion could not be give due to LA
| Islampur 1-Vent Regulator at Km35.97 in Mokhar Haor Project | No
| Soyabil 4-Vent Regulator at Km7.61 in Mokhar Haor Project | No
| 2-Vent Regulator at Km81.2 in Mokhar Haor Project | Yes | Site poseesion could not be give due to LA
| 1-Vent Regulator at Km65.45 in Mokhar Haor Project | Yes | Site poseesion could not be give due to LA
| 1-Vent Regulator at Km72.66 in Mokhar Haor Project | Yes | Site poseesion could not be give due to LA
| Chargoar 1-Vent Regulator at Km46.9 in Mokhar Haor Project | No
HOBI/PW-06 | Irrigation Inlet No-90 in Mokhar Haor Project | No
| Irrigation Inlet No-99 in Mokhar Haor Project | No
| Irrigation Inlet No-100 in Mokhar Haor Project | No
| Irrigation Inlet No-101 in Mokhar Haor Project | No
| Irrigation Inlet No-96 in Mokhar Haor Project | No
| Irrigation Inlet No-95 in Mokhar Haor Project | No
| Irrigation Inlet No-94 in Mokhar Haor Project | No
| Irrigation Inlet No-91 in Mokhar Haor Project | No
| Irrigation Inlet No-92 in Mokhar Haor Project | No
| Irrigation Inlet No-87 in Mokhar Haor Project | No
| Irrigation Inlet No-89 in Mokhar Haor Project | No
| Irrigation Inlet No-88 in Mokhar Haor Project | No
| Irrigation Inlet No-97 in Mokhar Haor Project | No
| Irrigation Inlet No-98 in Mokhar Haor Project | No
| Irrigation Inlet No-93 in Mokhar Haor Project | No
| 6m causeway at km 70.6 in Mokhar Haor Project | No
| 6m causeway at km 69.7 in Mokhar Haor Project | No
| 4m causeway at km 17.28 in Mokhar Haor Project | No
| 4m causeway at km 42.78 in Mokhar Haor Project | No
| Box Sluice at Km63.25 in Mokhar Haor Project | No
| Box Sluice at Km70.5 in Mokhar Haor Project | No
| Box Sluice at Km76.38 in Mokhar Haor Project | No
| Box Sluice at Km79.24 in Mokhar Haor Project | No
| Box Sluice at Km77.61 in Mokhar Haor Project | No
| Box Sluice at Km79.75 in Mokhar Haor Project | No
| Box Sluice at Km81.03 in Mokhar Haor Project | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
| Box Sluice at Km50.01 in Mokhar Haor Project | No
| Box Sluice at Km60.35 in Mokhar Haor Project | No
HOBI/PW-07 | Chatal beel Khal | Yes | Site poseesion could not be give due to LA
| Chargaowdair Khal | No
| Purohogun khal | No
| Soay beel khal | No
| Rajendrapur Khal | No
| Islampur Khal | Yes | Site poseesion could not be give due to LA
| Salukadar Khal | No
| Chhotokatari Khal | No
| Sutki River | No
| Ratna River | No
KISH/PW-01 | katakhali khal from km 0.000 to km 1.550=1.550 km | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
| Ganakkhali khal from km 0.000 to km 5.625=5.625 km | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
| Betal Doba from km1.315 to km 3.466 =2.151 km | No
| Alalia-bahadia Khal from km 1.325 to km 2.545=1.220 km | No
| Kali Khal from km 0.00 to km 1.00=1.000 km. | No
KISH/PW-02 | Construction of 2-vent Bata Khal Regulator at 12.09 km | No
| Bata khal from km, 0.000 to km. 2.790 km | Yes | Site poseesion could not be give due to LA
| GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | No
| Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | No
| Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | No
| Diakul Khal from km 1.710 to m 4.690=2.980 | No
| Submersible Embankment from 11.95 to 12.33=0.315 Km | No
KISH/PW-03 | Constriction of Kata Khali Khal Regulator 1-V (1.5m x 1.8m ) at km 23.846 (Part-A) | No
| Submersible Embankment from 7.366 to 17.749 Part-A | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
KISH/PW-04 | Construction of Southern Depression Regulator 1-Vent (1.50mx1.80m) at km. 6.20 (Part- B) | No
| Construction of Northern Depression Regulator 1-Vent (1.50mx1.80m) at km. 2.62 (Part- B) | No
| SamarbariKhal Regulator 4-Vent (1.50mx1.80m) at km. 0.78 (Part- C) | No
| Submersible Embankment from 0.007 to 6.541 Part-B | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
KISH/PW-05 | Construction of Kata Khal Regulator 3-Vent (1.50mx1.80m) at km. 15.30 | No
| Submersible Embankment from 0 to 19.377 Part-C | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
KISH/PW-06 | Construction of Mahindra Khal Regulator (4V-1.5 x 1.80m) at km 12.18. | No
| Kata Khal | Yes
| Mahinhandra Khal | No
| Samarbari Khal | No
| Kata Khali Khal | No
| Kurigai Gang | No
| Beri Gang | No
KISH/PW-07 | Dampara Khal | No
| Hajirkhali Khal | No
| Suti Khal | No
| Baniajan Khal | No
| Karpasha Khal | No
| Old Singua River | Yes | Site poseesion could not be give due to LA
| Diga Nadi | Yes | Work Extension.Design changed and approval process from competent authorty
| Construction of Submersible embnakment In between km. 0.000to km. 56.949) =3.879 km. | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
KISH/PW-09 | 6.0m Causeway at Samarbari of Nunnir Haor. | No
| 6m Dampara at km 33.3 in Boro Haor Project | No
| 4m Karpasha at km 27 in Boro Haor Project | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
| 2- vent box drainage outlet of Mohorkona of Nunnir haor. | No
KISH/PW-10 | 1-vent 1.50X1.80 Regulator at Jalalpur 22.64 km | Yes
| 6m Gazipur Causeway at Km 12.34 | Yes
| Submersible embankment in between km 0.020 to km 12.400=11.750 | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
KISH/PW-11 | 2-Vent Lalpur Khal Regulator at Km16.13 in Noapara Haor Project | No
| Construction of Submersible Embankment in between km 12.400 to km 23.260 | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
KISH/PW-12 | 4-Vent Mohorkona Regulator at Km 1.64 in Noapara Haor Project | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
| 3-Vent Naluar Khal Regulator at Km 4.77 in Noapara Haor Project | No
| Lalpurkhal km 0.410 to km 4.40 = 3.900 km, | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
| NabinpurKhal km 4.000 to km 6.800= 2.800 km | No
| MaherkonaKhal km 0.300 to km 3.300 = 3.00 km, | No
| NaluarKhal km 0.200 to km 0.800 = 0.600 km | No
KISH/PW-13 | 2-Vent Bera Khal Regulator at Km 4.07 in Naogaon Haor Project | No
| 3-Vent Pangair Dair Khal Regulator at Km 2.09 in Naogaon Haor Project | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
| Submersible Embankment from KM 0.00 0to KM 10.000 (Part-A)) | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
KISH/PW-14 | 2-Vent Regulator Gokhra at Km 6.04 in Naogaon Haor Project | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
| Submergible Embankment from KM 10.000 to 28.900=16.900 KM (Part-A) | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
KISH/PW-15 | 2-Vent Khayer Khal Regulator at Km 5.56 in Naogaon Haor Project | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
| Submersible Embankment from 0.000 to 9.00-(Part-B) | No
KISH/PW-16 | 2-Vent Markhali Khal Regulator at Km 33.8 in Naogaon Haor Project | Yes | Work Delayed due to long negotiation with Land Owners for permission to start work before receiving Land Compensation
| Submergible Embankment from KM 9.000 to KM 30.420=14.120 KM (Part-B) | No
KISH/PW-17 | Irrigation Inlet No-40 in Naogaon Haor Project | No
| Irrigation Inlet No-42 in Naogaon Haor Project | No
| Irrigation Inlet No-43 in Naogaon Haor Project | No
| Irrigation Inlet No-39 in Naogaon Haor Project | No
| Irrigation Inlet No-41 in Naogaon Haor Project | No
| Irrigation Inlet No-53 in Naogaon Haor Project | No
| Irrigation Inlet No-52 in Naogaon Haor Project | No
| Irrigation Inlet No-51 in Naogaon Haor Project | No
| Irrigation Inlet No-50 in Naogaon Haor Project | No
| Irrigation Inlet No-49 in Naogaon Haor Project | No
| Irrigation Inlet No-48 in Naogaon Haor Project | No
| Irrigation Inlet No-47 in Naogaon Haor Project | No
| Irrigation Inlet No-46 in Naogaon Haor Project | No
| Irrigation Inlet No-45 in Naogaon Haor Project | No
| Irrigation Inlet No-44 in Naogaon Haor Project | No
| Irrigation Inlet No-38 in Naogaon Haor Project | No
| Irrigation Inlet No-37 in Naogaon Haor Project | No
| Irrigation Inlet No-59 in Naogaon Haor Project | No
| Irrigation Inlet No-58 in Naogaon Haor Project | No
| Irrigation Inlet No-60 in Naogaon Haor Project | No
| Irrigation Inlet No-61 in Naogaon Haor Project | No
| Irrigation Inlet No-54 in Naogaon Haor Project | No
| Irrigation Inlet No-57 in Naogaon Haor Project | No
| Irrigation Inlet No-56 in Naogaon Haor Project | No
| Irrigation Inlet No-55 in Naogaon Haor Project | No
| 1-Vent Bagadia Khal Regulator at Km 14.52 in Naogaon Haor Project | No
| 4-Vent Neora Khal Regulator at Km 44.230 in Naogaon Haor Project | Yes | Structure was partially damaged due to faulty assumption during planning which was reflected in design
| Box Sluice at Km13.7 in Naogaon Haor Project | No
| Box Sluice at Km9.39 in Naogaon Haor Project | No
| Box Sluice at Km6.65 in Naogaon Haor Project | No
| Box Sluice at Km18.24 in Naogaon Haor Project | No
| Box Sluice at Km11.21 in Naogaon Haor Project | No
| Submersible Embankment from 30.420 to 44.200=13.170 KM-(Part-B) | No
KISH/PW-18 | MarkhaliKhal 6.6 m causeway at km 39.07 in Naogaon Haor Project | Yes
| KhaiyarKhal 4m causeway at km 24.06 in Naogaon Haor Project | Yes
| DheuhalKhal 4m causeway at km 12.44 in Naogaon Haor Project | Yes
| NeoraKhal 4m causeway at km 44.2 in Naogaon Haor Project | Yes
| NandirKhal from KM 0.00 to KM 5.985=5.985 | Yes
| MarkhaliKha l from KM 1.01 to KM 4.120=3.11 KM | Yes
| PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM | Yes
| BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Yes
| Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM | Yes
| NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Yes
| KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM | Yes
KISH/PW-19 | Re-excavation of Atoplal River from KM 0.000 to KM 7.113 | Yes
| Re-excavation of Berachapra River from KM 0.000 to KM 15.820 | Yes
KISH/PW-20 | Irrigation Inlet No-32 in Noapara Haor Project | Yes
| Irrigation Inlet No-33 in Noapara Haor Project | Yes
| 4m Dipjurikhal Causeway at Km 27.000 | Yes
| 4m Sudhikhal Causeway at Km 33.300 | Yes
| Construction of 4m Chhitra Khal causeway at km 21.77 in Nunnir Haor Project | Yes
| 4m Nabinpur Khal Causeway at Km 23.380 | Yes
| Boxsluice Singhpurkhal at Km 11.170 in Noapa Haor | Yes
| Box Sluice near Nasir at 7.740 of Nunnir Haor Project | Yes
| Box Sluice Chagaliakhal at Km 10.480 | Yes
| Boxsluice Gorucharakhal at Km 10.000 in Noapara Haor | Yes
KISH/PW-21 | Construction of Kursi Khal Regulatior 2-vent 1.50m x 1.80m at km 16.10 | Yes
| Construction of Chouganga Khal Regulatior 1-vent 1.50m x 1.80m at km 24.40 | Yes
| Sub-Mergible Emabankment from km 2.565 to km 12.059=9.494 km | Yes
KISH/PW-22 | Irrigation Inlet No-65 in Badla Haor Project | Yes
| Irrigation Inlet No-63 in Badla Haor Project | Yes
| Irrigation Inlet No-67 in Badla Haor Project | Yes
| Irrigation Inlet No-64 in Badla Haor Project | Yes
| Irrigation Inlet No-62 in Badla Haor Project | Yes
| Irrigation Inlet No-66 in Badla Haor Project | Yes
| 4m Kalnakhal causeway at km 7.500 in Badla Haor Project | Yes
| Box Sluice at Km23.6 in Badla Haor Project | Yes
| Box Sluice at Km22.3 in Badla Haor Project | Yes
| Box Sluice at Km19.5 in Badla Haor Project | Yes
| Burimara Khal from km. 0.000 to km. 0.439 | Yes
| Maora Khal from km. 0.000 to km. 1.700 | Yes
| Kursi Khal from km. 0.000 to km. 2.900 | Yes
| Chouganga Khal from km. 1.700 to 1.900 km | Yes
| Kanala Khal from km. 0.000 to km. 0.584 | Yes
| Baduti Khal from km. 0.000 to km. 1.000 | Yes
| Bamuna Khal from km. 0.000 to km. 1.400 | Yes
| Sajna Khal from km. 0.000 to km. 1.000 | Yes
| Chandpur Khal from km. 0.000 to km. 0.700 | Yes
| Submersible Embankment from 12.059 to 26.998 Total Length 10.463 | Yes
KISH/PW-23 | Irrigation Inlet No-69 in Chatal Haor Project | Yes
| Irrigation Inlet No-71 in Chatal Haor Project | Yes
| Irrigation Inlet No-70 in Chatal Haor Project | Yes
| Irrigation Inlet No-68 in Chatal Haor Project | Yes
| 2-Vent Mozila Khal Regulator at Km 12.250 in Chatal Haor Project | Yes
| 2-Vent NoaparakhaliKhal Regulator at Km 5.73 in Chatal Haor Project | Yes
| Box Sluice Mogarkhal at Km2.74 in Chatal Haor Project | Yes
| Re-excavation of Mogar Khal from Km 0.000 to 0.150 | Yes
| Re-excavation of Mozilla Khal from Km 0.000 to 1.775 | Yes
| Submersible Embankment from 2.469 to 6.979=4.510 | Yes
KISH/PW-24 | Submersible Embankment from Km 0.000 to Km 33.520 | Yes
KISH/PW-25 | Irrigation Inlet No-86 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-72 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-85 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-84 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-83 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-82 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-81 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-80 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-79 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-78 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-77 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-76 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-75 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-74 in Dakhshiner Haor Project | Yes
| Irrigation Inlet No-73 in Dakhshiner Haor Project | Yes
| 5-Vent Regulator at Km 23.19 in Dakhshiner Haor Project | Yes
| 6m causeway at km 12.38 in Dakhshiner Haor Project | Yes
| 4m causeway at km 0.02 in Dakhshiner Haor Project | Yes
| 6m causeway at km 23.46 in Dakhshiner Haor Project | Yes
| Box Sluice at Km24.23 in Dakhshiner Haor Project | Yes
| Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Yes
| Bantai river from km 0.000 to km 1.650 | Yes
KISH/PW-26 | Phulesswari khal (New) from km 0.000 to km 4.715 = 4.715 km | Yes
| Phulesswari khal (Old) from km 3.250 to km 3.760 = 0.510 km | Yes
| KalnaKhal from km 14.200 to km 17.200 = 1.140 km | Yes
| Suti Nadi from km 2.200 to km 17.700= 15.500 km | Yes
| Construction of Submersible Embankment in between Km 8.200 to 18.030=0.540 | Yes
KISH/PW-27 | Constration of 1vent (1.80m x 1.50 m) Phulesgwari Regulator at km 8.241 | Yes
| Constration of 1 vent (1.80m x 1.50 ) kalna regulatior at km 16.170 1 no. | Yes
| 6m Suti causeway | Yes
| 4mchonati causeway | Yes
| Drainage box outlet at km 17.74 | Yes
| Drainage box outlet at km | Yes
NETR/PW-01 | Re-sectioning of full embankment of Dampara Water Management project in between km 0.00 to km 41.771= 35.828 km, Volume- 515681.07 cum | Yes
| Singer Beel full embankment scheme in between km 0.911 to km 11.60=10.69km, Volume- 87873.05 cum (Total length = 46.21km), | Yes
NETR/PW-02 | DudkuraKhal From km 0.170 to km.5.570=5.40 km | Yes
| AndaKhal From km 0.055 to km.7.247=7.192 km | Yes
| DhalaiKhal in between km 0.00 to km 15.016=7.37 | Yes
| BaliaKhal from km 0.00 to km 5.896=5.896km | Yes
| DupikhaliKhal from km 0.00 to km.3.66=3.66 km, km 10.80 to km.15.857=5.057 km | Yes
| KurikuniaKhal from km 0.00 to km.1.903=1.903 km | Yes
| DighjanKhal From km 3.62 to km.7.94=4.32 km | Yes
| TutnirKhal in between km 0.00 to km.3.45=3.15km | Yes
| KamalpurKhal from km 0.00 to km.2.983=2.983km | Yes
NETR/PW-03 | Re-Installation of Regulator 5Vent (1.8m x 1.5m)= 1 no (Dampara) | Yes
| Re-sectioning of full embankment (Kangsha-20.90km, volume-297422.656 cum), | Yes
| Re-sectioning of submersible embankment (Singer bee-3.56km, volume-14852.987 cum), | Yes
NETR/PW-04 | Jhalokhali khal from km 0.00 to km 6.7 6.70 km | Yes
| Feni khal from km 0.00 to 1.903 1.93 km | Yes
| Putia khal From km.0.00 to km. 5.235 5.235 km | Yes
| Naiyori Khal from km 0.00 to km 7.565 5.27 km | Yes
| Re-excavation of Piyan River from km 0.075 to km 5.00 4.925 km | Yes
| Resectioning of Submersible Embankment in between 0.000 to 48.350 total 9.75 km | Yes
NETR/PW-05 | Construction of 1 vent 1.80 m x1.50 m Ukra Regulator at km 18.02 | Yes
| Construction of 4-vent Regulator over Boilara khal at km. 7.61 | Yes
| Construction of 1 vent 1.80 m x1.50 m Ichamati Regulator at km 29.670 | Yes
| Construction of 1 vent 1.80 m x1.50 m Chapri Regulator at km 27.270 | Yes
| Construction of submersible embankment of Ganesh Haor Sub-project in between Km 6.8 to km 24.855 Total Length 3.071 km | Yes
NETR/PW-06 | Construction of Irrigation Inlet at Km 0.60 | Yes
| Construction of Irrigation Inlet at Km 7.8 | Yes
| Construction of Box Drainage Outlet of Box Sluice at Km24.58 in Ganesh Haor Project | Yes
| Construction of Box Drainage Outlet Box Sluice at Km15.16 in Ganesh Haor Project | Yes
| Chapri khal from km 0.280 to 2.590=2.310 km | Yes
| Boilara khal From km. 8.550 to km.8.900 =0.35 | Yes
| Ichamati khal from km 0.072 to km 1.250 1.178 | Yes
| Ukhra Khal from km 0.110 to km 2.043=1.933 km, | Yes
| Narsua River from km 0.00 to km 6.225=6.226 km | Yes
| Rehabilitation of Existing 4 vent regulator at KM 20.11over the Nasir khal | Yes
NETR/PW-07 | Lower Kangsha river from km 54.42 to km 69.42= km15.00. | Yes
| Gunai river From km.0.00 to km.9.00 = km.9.00 (Total=24.00km) | Yes
NETR/PW-08 | Irrigation Inlet No-116 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-105 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-113 in Dharmapasha Rui Beel Project | Yes
| Agunia Regulator 2-vent -1.5m x 1.8m at km 47.31 | Yes
| Dharam Beel Regulator 2-vent- 1.5m x 1.8m at km 54.42 = 2 nos. | Yes
| Box Sluice at Km40.66 in Dharmapasha Rui Beel Project | Yes
| Box Sluice at Km33.08 in Dharmapasha Rui Beel Project | Yes
| Box Sluice at Km7.8 in Dharmapasha Rui Beel Project | Yes
| Box Sluice at Km48.05 in Dharmapasha Rui Beel Project | Yes
| Box Sluice at Km43.13 in Dharmapasha Rui Beel Project | Yes
SUNM/PW-01 | Irrigation Inlet No-127 in Dhakua Haor Project | Yes
| Irrigation Inlet No-131 in Dhakua Haor Project | Yes
| Irrigation Inlet No-130 in Dhakua Haor Project | Yes
| Irrigation Inlet No-128 in Dhakua Haor Project | Yes
| Irrigation Inlet No-129 in Dhakua Haor Project | Yes
| Irrigation Inlet No-123 in Dhakua Haor Project | Yes
| Irrigation Inlet No-124 in Dhakua Haor Project | Yes
| Irrigation Inlet No-125 in Dhakua Haor Project | Yes
| Irrigation Inlet No-126 in Dhakua Haor Project | Yes
| Box Sluice No-5 at Km19.93 in Dhakua Haor Project | Yes
| Box Sluice No-6 at Km14.72 in Dhakua Haor Project | Yes
| Box Sluice No-7 at Km14.72 in Dhakua Haor Project | Yes
| Box Sluice No-1 at Km55.4 in Dhakua Haor Project | Yes
| Box Sluice No-2 at Km53.78 in Dhakua Haor Project | Yes
| Box Sluice No-3 at Km50.74 in Dhakua Haor Project | Yes
| Box Sluice No-4 at Km28.2 in Dhakua Haor Project | Yes
| Juringa Khal | Yes
| Dariabaz Khal | Yes
| Puknarai Khal | Yes
| Muktakhai Khal | Yes
| Submersible Embankment in between 10.600 to 49.426 total 33.849 km | Yes
SUNM/PW-02 | Re-excavation of Piyan River from Km 19.000 to 55.575 total 36.575 | Yes
SUNM/PW-03 | 1-Vent Regulator at Km26.45 in Dhakua Haor Project No-1 | Yes
| 2-Vent Regulator at Km27.51 in Dhakua Haor Project | Yes
| 6m causeway at km 18.56 in Dhakua Haor Project | Yes
| 4m causeway at km 16.33 in Dhakua Haor Project No-1 | Yes
| 4m causeway at km 16.33 in Dhakua Haor Project No-2 | Yes
| 4m causeway at km 16.33 in Dhakua Haor Project No-3 | Yes
| 4m causeway at km 16.33 in Dhakua Haor Project No-4 | Yes
| 4m causeway at km 16.33 in Dhakua Haor Project No-5 | Yes
SUNM/PW-04 | Submersible Embankment -34.94 km | Yes
SUNM/PW-05 | Dahar 4-Vent Regulator at Km2.07 in Dharmapasha Rui Beel Project | Yes
| Deola 2-Vent Regulator at Km54.42 in Dharmapasha Rui Beel Project | Yes
| Manai 6m causeway at km 38.74 in Dharmapasha Rui Beel Project | Yes
| Dahar 4m causeway at km 27.77 in Dharmapasha Rui Beel Project | Yes
| Dharagang 4m causeway at km 26.98 in Dharmapasha Rui Beel Project | Yes
| Chandrasona Thal 4m causeway at km 22.27 in Dharmapasha Rui Beel Project | Yes
SUNM/PW-06 | Irrigation Inlet No-117 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-118 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-115 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-114 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-112 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-111 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-110 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-109 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-108 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-104 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-107 in Dharmapasha Rui Beel Project | Yes
| Irrigation Inlet No-106 in Dharmapasha Rui Beel Project | Yes
| Box Sluice at Km1.75 in Dharmapasha Rui Beel Project No-1 | Yes
| Agunia Khal | Yes
| Dagar Khal | Yes
| Kolma Khal | Yes
| Baraia Khal | Yes
| Rajapur Khal | Yes
| Khurma Khal | Yes
| Undani Khal | Yes
| Rui Beel Khal | Yes
| Saitan Khal | Yes
| Gobra Khal | Yes
| Bir Khal | Yes
| Banni Khal-2 | Yes
| Banni Khal-1 | Yes
| Banni Link Khal | Yes
| Islam Beel Khal | Yes
| Dharam khal | Yes
| Dahar Gang | Yes

## Annex-IV
Annex-IV:Contractors Claims and Their Settlement
Contract Package Name | Name of the Contractor | Contract Value (Lakh) | Amount of Calim as per GCC 69.1(a) |  | Claim Settlement 69.2
|  |  | Cost (Lakh) | Time (Days) | Cost (Lakh) | Time (Days)
HOBI/PW-01 |  |  |  |  | 0
HOBI/PW-02 |  |  |  |  | 0
HOBI/PW-04 |  |  |  |  | 0
HOBI/PW-05 |  |  |  |  | 0
HOBI/PW-06 |  |  |  |  | 0
HOBI/PW-07 |  |  |  |  | 0
KISH/PW-01 |  |  |  |  | 0
KISH/PW-02 |  |  |  |  | 0
KISH/PW-03 |  |  |  |  | 0
KISH/PW-04 |  |  |  |  | 0
KISH/PW-05 |  |  |  |  | 0
KISH/PW-06 |  |  |  |  | 0
KISH/PW-07 |  |  |  |  | 0
KISH/PW-09 |  |  |  |  | 0
KISH/PW-10 |  |  |  |  | 0
KISH/PW-11 |  |  |  |  | 0
KISH/PW-12 |  |  |  |  | 0
KISH/PW-13 |  |  |  |  | 0
KISH/PW-14 |  |  |  |  | 0
KISH/PW-15 |  |  |  |  | 0
KISH/PW-16 |  |  |  |  | 0
KISH/PW-17 |  |  |  |  | 0
KISH/PW-18 |  |  |  |  | 0
KISH/PW-19 |  |  |  |  | 0
KISH/PW-20 |  |  |  |  | 0
KISH/PW-21 |  |  |  |  | 0
KISH/PW-22 |  |  |  |  | 0
KISH/PW-23 |  |  |  |  | 0
KISH/PW-24 |  |  |  |  | 0
KISH/PW-25 |  |  |  |  | 0
KISH/PW-26 |  |  |  |  | 0
KISH/PW-27 |  |  |  |  | 0
KISH/PW-28 |  |  |  |  | 0
NETR/PW-01 |  |  |  |  | 0
NETR/PW-02 |  |  |  |  | 0
NETR/PW-03 |  |  |  |  | 0
NETR/PW-04 |  |  |  |  | 0
NETR/PW-05 |  |  |  |  | 0
NETR/PW-06 |  |  |  |  | 0
NETR/PW-07 |  |  |  |  | 0
NETR/PW-08 |  |  |  |  | 0
SUNM/PW-01 |  |  |  |  | 0
SUNM/PW-02 |  |  |  |  | 0
SUNM/PW-03 |  |  |  |  | 0
SUNM/PW-04 |  |  |  |  | 0
SUNM/PW-05 |  |  |  |  | 0
SUNM/PW-06 |  |  |  |  | 0