## completed
| StructureName | Unit | As Per 2nd RDPP | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
0 | Construction of Irrigation Inlet | Nos | 116 | 0 | 0 | 0 | 0 | 17 | 45 | 95 | 116
1 | Regulator Re-installation (Rehablitation Sub-project) | Nos | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 5
2 | Construction of Regulator/ Causeway/Drainage Box Outler (New Haor) | Nos | 112 | 0 | 0 | 2 | 19 | 60 | 68 | 98 | 112
3 | Re-excavation of Khal/River (New Haor) | Km | 337.954 | 0 | 0 | 80 | 130 | 210 | 231 | 306 | 337.95
4 | Re-excavation of Khal/River (Rehab Haor) | Km | 108.974 | 0 | 0 | 0 | 0 | 48 | 74 | 108.97 | 108.97
5 | Construction of Full Embankment (Rehab Haor) | Km | 67.11 | 0 | 0 | 0 | 0 | 44 | 60 | 67.11 | 67.11
6 | Construction of Submersible Embankment (Rehab Haor) | Km | 61.21 | 0 | 0 | 0 | 0 | 43 | 53 | 61.21 | 61.31
7 | Construction of Submersible Embankment (New Haor) | Km | 261.653 | 0 | 0 | 28 | 68 | 164 | 188 | 238 | 261.65
8 | Rehablitation of Regulator (New Haor) | Nos | 7 | 0 | 0 | 0 | 0 | 1 | 3 | 7 | 7
9 | Construction of WMG office | Nos | 30 | 0 | 0 | 0 | 0 | 3 | 6 | 19 | 30
10 | Construction of Threshing Floor | Nos | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5
11 | Replecement of Gate (Netrokona & Kishoregonj) | Nos | 86 | 0 | 0 | 26 | 52 | 53 | 54 | 73 | 86

## remaining
| StructureName | Unit | As Per 2nd RDPP | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
0 | Construction of Irrigation Inlet | Nos | 116 | 116 | 116 | 116 | 116 | 99 | 71 | 21 | 0
1 | Regulator Re-installation (Rehablitation Sub-project) | Nos | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 1 | 0
2 | Construction of Regulator/ Causeway/Drainage Box Outler (New Haor) | Nos | 112 | 112 | 112 | 110 | 93 | 52 | 44 | 14 | 0
3 | Re-excavation of Khal/River (New Haor) | Km | 337.954 | 337.954 | 337.954 | 257.954 | 207.954 | 127.954 | 106.954 | 31.954 | 0.004
4 | Re-excavation of Khal/River (Rehab Haor) | Km | 108.974 | 108.974 | 108.974 | 108.974 | 108.974 | 60.974 | 34.974 | 0.004 | 0.004
5 | Construction of Full Embankment (Rehab Haor) | Km | 67.11 | 67.11 | 67.11 | 67.11 | 67.11 | 23.11 | 7.11 | 0 | 0
6 | Construction of Submersible Embankment (Rehab Haor) | Km | 61.21 | 61.21 | 61.21 | 61.21 | 61.21 | 18.21 | 8.21 | 0 | -0.1
7 | Construction of Submersible Embankment (New Haor) | Km | 261.653 | 261.653 | 261.653 | 233.653 | 193.653 | 97.653 | 73.653 | 23.653 | 0.003
8 | Rehablitation of Regulator (New Haor) | Nos | 7 | 7 | 7 | 7 | 7 | 6 | 4 | 0 | 0
9 | Construction of WMG office | Nos | 30 | 30 | 30 | 30 | 30 | 27 | 24 | 11 | 0
10 | Construction of Threshing Floor | Nos | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0
11 | Replecement of Gate (Netrokona & Kishoregonj) | Nos | 86 | 86 | 86 | 60 | 34 | 33 | 32 | 13 | 0

## Current_month
| StructureName | Unit | As Per 2nd RDPP | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
0 | Construction of Irrigation Inlet | Nos | 116 | 0 | 0 | 0 | 0 | 17 | 28 | 50 | 21
1 | Regulator Re-installation (Rehablitation Sub-project) | Nos | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 1
2 | Construction of Regulator/ Causeway/Drainage Box Outler (New Haor) | Nos | 112 | 0 | 0 | 2 | 17 | 41 | 8 | 30 | 14
3 | Re-excavation of Khal/River (New Haor) | Km | 337.954 | 0 | 0 | 80 | 50 | 80 | 21 | 75 | 31.95
4 | Re-excavation of Khal/River (Rehab Haor) | Km | 108.974 | 0 | 0 | 0 | 0 | 48 | 26 | 34.97 | 0
5 | Construction of Full Embankment (Rehab Haor) | Km | 67.11 | 0 | 0 | 0 | 0 | 44 | 16 | 7.11 | 0
6 | Construction of Submersible Embankment (Rehab Haor) | Km | 61.21 | 0 | 0 | 0 | 0 | 43 | 10 | 8.21 | 0.1
7 | Construction of Submersible Embankment (New Haor) | Km | 261.653 | 0 | 0 | 28 | 40 | 96 | 24 | 50 | 23.65
8 | Rehablitation of Regulator (New Haor) | Nos | 7 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 0
9 | Construction of WMG office | Nos | 30 | 0 | 0 | 0 | 0 | 3 | 3 | 13 | 11
10 | Construction of Threshing Floor | Nos | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2
11 | Replecement of Gate (Netrokona & Kishoregonj) | Nos | 86 | 0 | 0 | 26 | 26 | 1 | 1 | 19 | 13

## Prev_cum
| StructureName | Unit | As Per 2nd RDPP | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
0 | Construction of Irrigation Inlet | Nos | 116 | 0 | 0 | 0 | 0 | 0 | 17 | 45 | 95
1 | Regulator Re-installation (Rehablitation Sub-project) | Nos | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4
2 | Construction of Regulator/ Causeway/Drainage Box Outler (New Haor) | Nos | 112 | 0 | 0 | 0 | 2 | 19 | 60 | 68 | 98
3 | Re-excavation of Khal/River (New Haor) | Km | 337.954 | 0 | 0 | 0 | 80 | 130 | 210 | 231 | 306
4 | Re-excavation of Khal/River (Rehab Haor) | Km | 108.974 | 0 | 0 | 0 | 0 | 0 | 48 | 74 | 108.97
5 | Construction of Full Embankment (Rehab Haor) | Km | 67.11 | 0 | 0 | 0 | 0 | 0 | 44 | 60 | 67.11
6 | Construction of Submersible Embankment (Rehab Haor) | Km | 61.21 | 0 | 0 | 0 | 0 | 0 | 43 | 53 | 61.21
7 | Construction of Submersible Embankment (New Haor) | Km | 261.653 | 0 | 0 | 0 | 28 | 68 | 164 | 188 | 238
8 | Rehablitation of Regulator (New Haor) | Nos | 7 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 7
9 | Construction of WMG office | Nos | 30 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 19
10 | Construction of Threshing Floor | Nos | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
11 | Replecement of Gate (Netrokona & Kishoregonj) | Nos | 86 | 0 | 0 | 0 | 26 | 52 | 53 | 54 | 73