## Лист1
Task Name | Unit | TaskCode | Type_A_60M_M1240_TO_M1300 | Type_A_905M_M1600_TO_M2505 | Type_A_125M_M23437_TO_M23562
|  |  | 60 | 905 | 125
Mobilization and Site Preparation | Percent | NS101
CC Block Manufacture(30X30X30) | Nos | 40-190-50 | 1980 | 29865 | 4125
CC Block Manufacture(40X40X20) | Nos | 40-190-40 | 6691 | 100914 | 9218
Curing CC Block | Percent | NS105
Embankment Construction | Cum | 16-240 | 768 | 11584 | 913
Placing Sand Filter | Cum | 40-550-10 | 113 | 1700 | 133
Placing Geotextile Filter | sqm | 40-500-40 | 1235 | 18625 | 1553
Placing Pea Gravel Filter | Cum | 40-530-30 | 124 | 1863 | 156
Placing CC Block | Nos | NS106 | 8671 | 130779 | 13343
Ancilary Work for Site Completion | Percent | NS102
|  |  | 8671 | 130779 | 13343 | 0
|  |  | 8671 | 130779 | 13343 | 0 | 152793
Type D
Task Name | Unit | TaskCode | Type_D_360M_M880_TO_M31240 | Type_D_300M_M1300_TO_M1600 | Type_D_495M_M2505_TO_M3000
|  |  | 360 | 300 | 495
Mobilization and Site Preparation | percent | NS101
Embankment Construction | Cum | 16-240 | 5699 | 4749 | 7836
Placing Geotextile Filter | sqm | 40-500-40 | 7625 | 6354 | 10485
Sand-Cement Gunny Bag | Nos | 40-670-30 | 38880 | 32400 | 53460
Ancilary Work for Site Completion | Percent | NS102
|  |  | 38880 | 32400 | 53460 | 0 | 0
|  |  | 38880 | 32400 | 53460 | 0 | 0
Name | Unit | TaskCode | Task Volume
Mobilization and Site Preparation | percent | NS101
CC Block Manufacture(50X50X50) | Nos | 40-190-15 | 2787
CC Block Manufacture(50X50X30) | Nos | 40-190-05 | 5557
CC Block Manufacture(40X40X40) | Nos | 40-190-35 | 3563
CC Block Manufacture(40X40X20) | Nos | 40-190-40 | 1349
Curing | percent | NS105
Ring Bundh construction | Cum | 40-450 | 0 |  |  |  | `
Excavation | Cum | 16-510 | 2665
Embankment Construction | Cum | 16-240 | 2838
Placing Sand Filter | Cum | 40-550-10 | 362
Placing Geotextile Filter | sqm | 40-500-40 | 2467
Placing Pea Gravel Filter | Cum | 40-530-30 | 483
Geo Bag Placing(175) Kg | Nos | 40-380-20 | 3071
Placing CC Block | Nos | NS106 | 13256
Ring Bundh Removal | percent | 16-470 | 0
Ancilary Work for Site Completion | Percent | NS102