## Revised_2nd
8.0 Economic code wise comparison of cost summary between the 1st Revised DPP and proposed 2nd Revised DPP | [27 empty] | (BDT in Lakh)
Economic Code | Economic Sub-Code | Sub-Code wise component description | approved 1st Revised DPP | [8 empty] | Proposed 2nd Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3111327 | Overtime Allowance |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3111338 | Other Allowance |  | 1 Item | 140 | 140 |  | 0 | 0 |  |  |  | 1 Item | 140 | 140 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Supplies and Services
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) |  | 1 Item | 100 | 100 |  | 0 | 0 |  |  |  | 1 Item | 120 | 120 |  | 0 | 0 |  |  |  |  | 20 | 20 |  | 0 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | 1 Item | 245 | 245 |  | 0 | 0 |  |  |  | 1 Item | 245 | 245 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | 1 Item | 2596.27 | 2596.27 |  | 0 | 0 |  |  |  | 1 Item | 2874.35 | 2874.35 |  | 0 | 0 |  |  |  |  | 278.08 | 278.08 |  | 0 | 0
| 3211119 | Postage |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -20 | -20 |  | 0 | 0
| 3211120 | Telephones/Telegram/Teleprinter |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -20 | -20 |  | 0 | 0
| 3211117 | Telex/Fax/Internet |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -20 | -20 |  | 0 | 0
| 3221104 | Registration Fee (Vehicles) |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  | 1 Item | 20 | 20 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3211115 | Water |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 5 | 5 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3211113 | Electricity |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  | 1 Item | 20 | 20 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3243102 | Gas & Fuel |  | 1 Item | 200 | 200 |  | 0 | 0 |  |  |  | 1 Item | 40 | 40 |  | 0 | 0 |  |  |  |  | -160 | -160 |  | 0 | 0
| 3243101 | Petrol and Lubricant |  | 1 Item | 150 | 150 |  | 0 | 0 |  |  |  | 1 Item | 170 | 170 |  | 0 | 0 |  |  |  |  | 20 | 20 |  | 0 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) |  | 1 Item | 3 | 3 |  | 0 | 0 |  |  |  | 1 Item | 3 | 3 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3255102 | Printing & Binding |  | 1 Item | 35 | 35 |  | 0 | 0 |  |  |  | 1 Item | 50 | 50 |  | 0 | 0 |  |  |  |  | 15 | 15 |  | 0 | 0
| 3255104 | Stationery, Seals & Stamps |  | 1 Item | 150 | 150 |  | 0 | 0 |  |  |  | 1 Item | 120 | 120 |  | 0 | 0 |  |  |  |  | -30 | -30 |  | 0 | 0
| 3211127 | Books & Periodicals |  | 1 Item | 2 | 2 |  | 0 | 0 |  |  |  | 1 Item | 2 | 2 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 1 Item | 238.54 | 0 |  | 238.54 | 0 |  |  |  | 1 Item | 119 | 0 |  | 119 | 0 |  |  |  |  | -119.54 | 0 |  | -119.54 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | 1 Item | 398.41 | 47.81 |  | 350.6 | 0 |  |  |  | 1 Item | 536.7 | 64.4 |  | 472.3 | 0 |  |  |  |  | 138.29 | 16.59 |  | 121.7 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  | 1 Item | 2533.34 | 304 |  | 2229.34 | 0 |  |  |  | 1 Item | 3130.1 | 373.9 |  | 2756.2 | 0 |  |  |  |  | 596.76 | 69.9 |  | 526.86 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  | 1 Item | 1321.68 | 158.6 |  | 1163.08 | 0 |  |  |  | 1 Item | 1331.2 | 159.7 |  | 1171.5 | 0 |  |  |  |  | 9.52 | 1.1 |  | 8.42 | 0
| 3211109 | Casual labour/Job worker |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  | 1 Item | 22 | 22 |  | 0 | 0 |  |  |  |  | 7 | 7 |  | 0 | 0
| 3256103 | Consumable Stores |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 15 | 15 |  | 0 | 0 |  |  |  |  | -10 | -10 |  | 0 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | MM | 71+234 | 7901.4 | 0 |  | 0 | 7901.4 |  |  | MM | 56+532 | 7901.4 | 0 |  | 0 | 7901.4 |  |  | MM |  | 0 | 0 |  | 0 | 0
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) |  | 1 Item | 25 | 25 |  | 0 | 0 |  |  |  | 1 Item | 30 | 30 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3111332 | b) Interim Evaluation |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3111332 | c) Progress Monitoring |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  | 1 Item | 10 | 10 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3257104 | Survey |  | 1 Item | 162 | 162 |  | 0 | 0 |  |  |  | 1 Item | 162 | 162 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 3255101 | Computer Consumables |  | 1 Item | 50 | 50 |  | 0 | 0 |  |  |  | 1 Item | 60 | 60 |  | 0 | 0 |  |  |  |  | 10 | 10 |  | 0 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing |  | 1 Item | 1700 | 1700 |  | 0 | 0 |  |  |  | 1 Item | 1700 | 1700 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Repair, Maintenance & Rehabilitation
| 3258101 | Motor Vehicles |  | L.S. | 100 | 100 |  | 0 | 0 |  |  |  | L.S. | 125 | 125 |  | 0 | 0 |  |  |  |  | 25 | 25 |  | 0 | 0
| 3258102 | Furnitures & Fixtures |  | L.S. | 15 | 15 |  | 0 | 0 |  |  |  | L.S. | 10 | 10 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3258103 | Computers & office equipments |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 15 | 15 |  | 0 | 0 |  |  |  |  | -10 | -10 |  | 0 | 0
| 3258105 | Machineries & Equipments |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 10 | 10 |  | 0 | 0 |  |  |  |  | -15 | -15 |  | 0 | 0
| 3258107 | Office Building : Repair & Maintenance |  | L.S. | 20 | 20 |  | 0 | 0 |  |  |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  |  | 5 | 5 |  | 0 | 0
| 3258106 | Residential Building : Repair & Maintenance |  | L.S. | 20 | 20 |  | 0 | 0 |  |  |  | L.S. | 40 | 40 |  | 0 | 0 |  |  |  |  | 20 | 20 |  | 0 | 0
| 3258105 | Engineering Equipments |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 20 | 20 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) |  | 104 | 362.5 | 43.5 |  | 319 | 0 |  |  |  | 86 | 405.55 | 56.777 |  | 348.773 | 0 |  |  |  |  | 43.05 | 13.277 |  | 29.773 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) |  | L.S. | 10 | 10 |  | 0 | 0 |  |  |  | L.S. | 5 | 5 |  | 0 | 0 |  |  |  |  | -5 | -5 |  | 0 | 0
| 3258107 | Others : Repair & Maintenance |  | L.S. | 25 | 25 |  | 0 | 0 |  |  |  | L.S. | 40 | 40 |  | 0 | 0 |  |  |  |  | 15 | 15 |  | 0 | 0
Sub-total : (a) Revenue Component:
Economic Code | Economic Sub-Code | Sub-Code wise component description | approved 1st Revised DPP | [8 empty] | Proposed 2nd Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos | 10 | 702.5 | 702.5 |  | 0 | 0 |  |  | Nos | 10 | 702.5 | 702.5 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos | 35 | 68.25 | 68.25 |  | 0 | 0 |  |  | Nos | 45 | 68.25 | 68.25 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos | 6 | 100 | 100 |  | 0 | 0 |  |  | Nos | 5 | 90 | 90 |  | 0 | 0 |  |  | Nos |  | -10 | -10 |  | 0 | 0
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos | 7 | 8.97 | 8.97 |  | 0 | 0 |  |  | Nos | 7 | 8.97 | 8.97 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos | 7 | 5 | 5 |  | 0 | 0 |  |  | Nos | 2 | 1 | 1 |  | 0 | 0 |  |  | Nos |  | -4 | -4 |  | 0 | 0
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos | 17 | 20.5 | 20.5 |  | 0 | 0 |  |  | Nos | 17 | 20.5 | 20.5 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | Nos | 6 | 6 | 6 |  | 0 | 0 |  |  | Nos | 3 | 3 | 3 |  | 0 | 0 |  |  | Nos |  | -3 | -3 |  | 0 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division |  | L.S | 50 | 50 |  | 0 | 0 |  |  |  | L.S | 50 | 50 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos | 30 | 19.5 | 19.5 |  | 0 | 0 |  |  | Nos | 37 | 24.5 | 24.5 |  | 0 | 0 |  |  | Nos |  | 5 | 5 |  | 0 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos | 11 | 13.75 | 13.75 |  | 0 | 0 |  |  | Nos | 11 | 13.75 | 13.75 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | Nos | 2 | 1.5 | 1.5 |  | 0 | 0 |  |  | Nos | 2 | 1.5 | 1.5 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos | 11 | 5.25 | 5.25 |  | 0 | 0 |  |  | Nos | 17 | 5.25 | 5.25 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0
| 4112314 | Furnitures & Fixtures |  | LS | 50 | 50 |  | 0 | 0 |  |  |  | LS | 50 | 50 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 4112303 | Aircooler | Nos | 15 | 15 | 15 |  | 0 | 0 |  |  | Nos | 15 | 15 | 15 |  | 0 | 0 |  |  | Nos |  | 0 | 0 |  | 0 | 0 |  |  |  | Ori |  | Pro | Diff
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) | ha | 470 | 24000 | 24000 |  | 0 | 0 |  |  | ha | 470 | 18386.72 | 18386.72 |  | 0 | 0 |  |  | ha |  | -5613.28 | -5613.28 |  | 0 | 0 |  |  |  |  | 50 | 371
Construction and Works:
|  | Irrigation Infrastructures : | [27 empty] | 46.5 | 895.5 | 161 | 1182
| 4111306 | Construction of Irrigation Inlet (New Haors) | Nos | 131 | 1261 | 151.32 |  | 1109.68 | 0 |  |  | Nos | 119 | 1220.46 | 170.8644 |  | 1049.5956 | 0 |  |  | Nos |  | -40.54 | 19.5444 |  | -60.0844 | 0
|  | Drainage Structures : | [27 empty] | 46.5 | 895.5 | 161 | 1182
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | Nos | 7(2+5) | 1515 | 181.8 |  | 1333.2 | 0 |  |  | Nos | 5 | 1172.62 | 164.1668 |  | 1008.4532 | 0 |  |  | Nos |  | -342.38 | -17.6332 |  | -324.7468 | 0 |  |  | 978.5 | 18871.5 | 3398 | 24917
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos | 137(57+35+14) | 20311 | 2437.32 |  | 17873.68 | 0 |  |  | Nos | 111 | 18421.37 | 2578.9918 |  | 15842.3782 | 0 |  |  | Nos |  | -1889.63 | 141.6718 |  | -2031.3018 | 0 |  |  | 131 | 2528 | 455 | 3337
| 4111307 | Re-excavation of Khal/River (New Haors) | Km | 318 | 9729 | 1167.48 |  | 8561.52 | 0 |  |  | Km | 336.214 | 10184.13 | 1425.7782 |  | 8758.3518 | 0 |  |  | Km |  | 455.13 | 258.2982 |  | 196.8318 | 0
|  | Others | [27 empty] | 18 | 360 | 65 | 475.36
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | Km | 143 | 2515 | 301.8 |  | 2213.2 | 0 |  |  | Km | 108.974 | 3398.89 | 475.8446 |  | 2923.0454 | 0 |  |  | Km |  | 883.89 | 174.0446 |  | 709.8454 | 0 |  |  | 3 | 60 | 11 | 80
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | Km | 84.31 | 2550 | 306 |  | 2244 | 0 |  |  | Km | 67.11 | 2035.43 | 284.9602 |  | 1750.4698 | 0 |  |  | Km |  | -514.57 | -21.0398 |  | -493.5302 | 0 |  |  | 8.25 | 170.25 | 31 | 225
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | Km | 87.03 | 1785 | 214.2 |  | 1570.8 | 0 |  |  | Km | 62.662 | 1748.43 | 244.7802 |  | 1503.6498 | 0 |  |  | Km |  | -36.57 | 30.5802 |  | -67.1502 | 0
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km | 263.24 | 11952.5 | 1434.3 |  | 10518.2 | 0 |  |  | Km | 261.238 | 21445.23 | 9315.3802 |  | 12129.8498 | 0 |  |  | Km |  | 9492.73 | 7881.0802 |  | 1611.6498 | 0
| 4111201 | Rehabilitation of Regulator (New Haors) | Nos | 8 | 166 | 19.92 |  | 146.08 | 0 |  |  | Nos | 7 | 146.69 | 20.5366 |  | 126.1534 | 0 |  |  | Nos |  | -19.31 | 0.6166 |  | -19.9266 | 0 |  |  | 8.25 | 170.25 | 31 | 225
| 4111201 | Threshing Floor Construction | Nos |  | 0 | 0 |  | 0 | 0 |  |  | Nos | 5 | 225 | 31.5 |  | 193.5 | 0 |  |  | Nos |  | 225 | 31.5 |  | 193.5 | 0
| 4111201 | Construction of WMG Office | Nos | 60 | 1380 | 165.6 |  | 1214.4 | 0 |  |  | Nos | 55 | 1618 | 226.52 |  | 1391.48 | 0 |  |  | Nos |  | 238 | 60.92 |  | 177.08 | 0 |  |  | 726.6 | 14031.95 | 2526 | 18527
| 4111201 | O&M During Construction | Iten | L.S | 200 | 200 |  | 0 | 0 |  |  | Iten | 1 | 120 | 120 |  | 0 | 0 |  |  | Iten |  | -80 | -80 |  | 0 | 0
Sub-total : (b) Capital Component:
Total Cost (a+b) :
| 0 | (c) Physical Contingency ( Lump sum): | Item | L.S. | 258 | 100 |  | 158 | 0 |  |  | Item | L.S. | 30.51 | 30.51 |  | 0 | 0 |  |  | Item |  | -227.49 | -69.49 |  | -158 | 0
| 0 | (d) Price Contingency (Lump sum): | Item | L.S. | 402.14 | 100.76 |  | 301.38 | 0 |  |  | Item | L.S. | 10 | 10 |  | 0 | 0 |  |  | Item |  | -392.14 | -90.76 |  | -301.38 | 0
Grand Total : (a)+(b)+(c)+(d):
* DOSA, CONTASA, SAFE, IMPREST etc.
c+d
|  |  |  | Phy.Works | [8 empty] | Phy.Works | [8 empty] | Phy.Works
c+d+works
other
[9 empty] | Reh | [7 empty] | Reh
[9 empty] | New | [7 empty] | New
|  | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km | 263.24 | 11952.5 | 1434.3 |  | 10518.2 | 0 |  |  | Km | 254.207 | 16526.21 | 4527.399 |  | 11998.811 | 0 |  |  | Km | -9.033 | 4573.71 | 3093.099 |  | 1480.611 | 0

## 9.Detil Phasing
9.0 Item wise Cumulative Progress and Year wise Breakdown of Revised Quantity and Cost to be Incurred. | [18 empty] | Taka in Lac
Economic Code | Economic Sub-Code | Sub-Code wise component description | Cumulative Progress Upto June 2019 (Year 1 to Year-5) † | [9 empty] | FY: 2019-2020 (Year-6) | [9 empty] | FY: 2020-21 (Year-7) | [9 empty] | FY: 2021-2022 (Year-8)
|  |  | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance |  | Part | 1.01 | 1.01 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 2.0242 | 2.0242 |  | 0 | 0 |  |  |  |  | Part | 1.4658 | 1.4658 |  | 0 | 0
| 3111327 | Overtime Allowance |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 6.3 | 6.3 |  | 0 | 0 |  |  |  |  | Part | 3.7 | 3.7 |  | 0 | 0
| 3111338 | Other Allowance |  |  | 36.61 | 36.61 |  | 0 | 0 |  |  |  |  | Part | 14 | 14 |  | 0 | 0 |  |  |  |  | Part | 53.634 | 53.634 |  | 0 | 0 |  |  |  |  | Part | 35.756 | 35.756 |  | 0 | 0
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) |  | Part | 58.54 | 58.54 |  | 0 | 0 |  |  |  |  | Part | 14.97 | 14.97 |  | 0 | 0 |  |  |  |  | Part | 28.8176 | 28.8176 |  | 0 | 0 |  |  |  |  | Part | 17.6624 | 17.6624 |  | 0 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | Part | 116.67 | 116.67 |  | 0 | 0 |  |  |  |  | Part | 34.21 | 34.21 |  | 0 | 0 |  |  |  |  | Part | 58.3544 | 58.3544 |  | 0 | 0 |  |  |  |  | Part | 35.7656 | 35.7656 |  | 0 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | Part | 1603.18 | 1603.18 |  | 0 | 0 |  |  |  |  | Part | 177.18 | 177.18 |  | 0 | 0 |  |  |  |  | Part | 634.52 | 634.52 |  | 0 | 0 |  |  |  |  | Part | 459.48 | 459.48 |  | 0 | 0
| 3211119 | Postage |  | Part | 0.77 | 0.77 |  | 0 | 0 |  |  |  |  | Part | 0.48 | 0.48 |  | 0 | 0 |  |  |  |  | Part | 2.175 | 2.175 |  | 0 | 0 |  |  |  |  | Part | 1.575 | 1.575 |  | 0 | 0
| 3211120 | Telephones/Telegram/Teleprinter |  | Part | 0.97 | 0.97 |  | 0 | 0 |  |  |  |  | Part | 0.07 | 0.07 |  | 0 | 0 |  |  |  |  | Part | 2.4156 | 2.4156 |  | 0 | 0 |  |  |  |  | Part | 1.5444 | 1.5444 |  | 0 | 0
| 3211117 | Telex/Fax/Internet |  | Part | 0.44 | 0.44 |  | 0 | 0 |  |  |  |  | Part | 0.1 | 0.1 |  | 0 | 0 |  |  |  |  | Part | 2.497 | 2.497 |  | 0 | 0 |  |  |  |  | Part | 1.962 | 1.962 |  | 0 | 0
| 3221104 | Registration Fee (Vehicles) |  | Part | 11.92 | 11.92 |  | 0 | 0 | [5 empty] | 0.17 | 0.17 |  | 0 | 0 | [5 empty] | 4.9833 | 4.9833 |  | 0 | 0 | [5 empty] | 2.9267 | 2.9267 |  | 0 | 0
| 3211115 | Water |  | Part | 1.11 | 1.11 |  | 0 | 0 |  |  |  |  | Part | 0.55 | 0.55 |  | 0 | 0 |  |  |  |  | Part | 2.0313 | 2.0313 |  | 0 | 0 |  |  |  |  | Part | 1.2987 | 1.2987 |  | 0 | 0
| 3211113 | Electricity |  | Part | 8.74 | 8.74 |  | 0 | 0 |  |  |  |  | Part | 2.89 | 2.89 |  | 0 | 0 |  |  |  |  | Part | 4.609 | 4.609 |  | 0 | 0 |  |  |  |  | Part | 3.771 | 3.771 |  | 0 | 0
| 3243102 | Gas & Fuel |  | Part | 17.52 | 17.52 |  | 0 | 0 |  |  |  |  | Part | 4.02 | 4.02 |  | 0 | 0 |  |  |  |  | Part | 11.2545 | 11.2545 |  | 0 | 0 |  |  |  |  | Part | 7.1955 | 7.1955 |  | 0 | 0
| 3243101 | Petrol and Lubricant |  | Part | 64.59 | 64.59 |  | 0 | 0 |  |  |  |  | Part | 24.18 | 24.18 |  | 0 | 0 |  |  |  |  | Part | 46.3068 | 46.3068 |  | 0 | 0 |  |  |  |  | Part | 34.9332 | 34.9332 |  | 0 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) |  | Part | 1.16 | 1.16 |  | 0 | 0 |  |  |  |  | Part | 0.91 | 0.91 |  | 0 | 0 |  |  |  |  | Part | 0.51205 | 0.51205 |  | 0 | 0 | [5 empty] | 0.41895 | 0.41895 |  | 0 | 0
| 3255102 | Printing & Binding |  | Part | 34.16 | 34.16 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 9.355 | 9.355 |  | 0 | 0 |  |  |  |  | Part | 5.981 | 5.981 |  | 0 | 0
| 3255104 | Stationery, Seals & Stamps |  | Part | 49.91 | 49.91 |  | 0 | 0 |  |  |  |  | Part | 19.95 | 19.95 |  | 0 | 0 |  |  |  |  | Part | 31.5869 | 31.5869 |  | 0 | 0 |  |  |  |  | Part | 18.5511 | 18.5511 |  | 0 | 0
| 3211127 | Books & Periodicals |  | Part | 0.28 | 0.28 |  | 0 | 0 |  |  |  |  | Part | 0.2 | 0.2 |  | 0 | 0 |  |  |  |  | Part | 0.8816 | 0.8816 |  | 0 | 0 |  |  |  |  | Part | 0.6384 | 0.6384 |  | 0 | 0
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 119 | 0 |  | 119 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | Part | 301.5 | 22.54 |  | 278.96 | 0 |  |  |  |  | Part | 22.21 | 2.3809 |  | 19.8291 | 0 |  |  |  |  | Part | 127.794 | 13.6995 |  | 114.0945 | 0 |  |  |  |  | Part | 85.196 | 9.133 |  | 76.063 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  |  | 1346.63 | 80.34 |  | 1266.29 | 0 |  |  |  |  | Part | 338.12 | 36.2465 |  | 301.8735 | 0 |  |  |  |  | Part | 910.5705 | 97.6132 |  | 812.9573 | 0 |  |  |  |  | Part | 534.7795 | 57.3284 |  | 477.4511 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  |  | 578.2 | 35.47 |  | 542.73 | 0 |  |  |  |  | Part | 82.97 | 8.8944 |  | 74.0756 | 0 |  |  |  |  | Part | 368.5165 | 39.505 |  | 329.0115 | 0 |  |  |  |  | Part | 301.5135 | 32.3222 |  | 269.1913 | 0
| 3211109 | Casual labour/Job worker |  | Part | 10.96 | 10.96 |  | 0 | 0 |  |  |  |  | Part | 3.49 | 3.49 |  | 0 | 0 |  |  |  |  | Part | 4.681 | 4.681 |  | 0 | 0 |  |  |  |  | Part | 2.869 | 2.869 |  | 0 | 0
| 3256103 | Consumable Stores |  | Part | 3.74 | 3.74 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 4.7908 | 4.7908 |  | 0 | 0 |  |  |  |  | Part | 3.4692 | 3.4692 |  | 0 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) |  | Part | 5168.01 | 0 |  | 0 | 5168.01 |  |  |  | MM | Part | 450 | 0 |  | 0 | 450 |  |  |  | MM | Part | 1374.571 | 0 |  | 0 | 1374.571 |  |  |  | MM | Part | 878.824 | 0 |  | 0 | 878.824
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) |  | Part | 12.73 | 12.73 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 8.2766 | 8.2766 |  | 0 | 0 |  |  |  |  | Part | 5.9934 | 5.9934 |  | 0 | 0
| 3111332 | b) Interim Evaluation |  |  | 1.29 | 1.29 |  | 0 | 0 |  |  |  |  | Part | 0.41 | 0.41 |  | 0 | 0 | [5 empty] | 8.3 | 8.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3111332 | c) Progress Monitoring |  |  | 1.3 | 1.3 |  | 0 | 0 |  |  |  |  | Part | 0.41 | 0.41 |  | 0 | 0 |  |  |  |  | Part | 4.145 | 4.145 |  | 0 | 0 |  |  |  |  | Part | 4.145 | 4.145 |  | 0 | 0
| 3257104 | Survey |  | Part | 85.02 | 85.02 |  | 0 | 0 |  |  |  |  | Part | 30 | 30 |  | 0 | 0 |  |  |  |  | Part | 26.7786 | 26.7786 |  | 0 | 0 |  |  |  |  | Part | 20.2014 | 20.2014 |  | 0 | 0
| 3255101 | Computer Consumables |  | Part | 20.47 | 20.47 |  | 0 | 0 |  |  |  |  | Part | 10 | 10 |  | 0 | 0 |  |  |  |  | Part | 16.242 | 16.242 |  | 0 | 0 |  |  |  |  | Part | 13.2889 | 13.2889 |  | 0 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing |  | Part | 875.46 | 875.46 |  | 0 | 0 |  |  |  |  | Part | 299.96 | 299.96 |  | 0 | 0 |  |  |  |  | Part | 299.0163 | 299.0163 |  | 0 | 0 |  |  |  |  | Part | 225.5737 | 225.5737 |  | 0 | 0
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles |  | Part | 61.4 | 61.4 |  | 0 | 0 |  |  |  |  | Part | 14.97 | 14.97 |  | 0 | 0 |  |  |  |  | Part | 26.7481 | 26.7481 |  | 0 | 0 |  |  |  |  | Part | 21.8849 | 21.8849 |  | 0 | 0
| 3258102 | Furnitures & Fixtures |  | Part | 3.2 | 3.2 |  | 0 | 0 |  |  |  |  | Part | 1.11 | 1.11 |  | 0 | 0 |  |  |  |  | Part | 3.414 | 3.414 |  | 0 | 0 |  |  |  |  | Part | 2.276 | 2.276 |  | 0 | 0
| 3258103 | Computers & office equipments |  | Part | 5.34 | 5.34 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 3.9294 | 3.9294 |  | 0 | 0 |  |  |  |  | Part | 2.7306 | 2.7306 |  | 0 | 0
| 3258105 | Machineries & Equipments |  | Part | 1.22 | 1.22 |  | 0 | 0 |  |  |  |  | Part | 1.99 | 1.99 |  | 0 | 0 |  |  |  |  | Part | 4.1358 | 4.1358 |  | 0 | 0 |  |  |  |  | Part | 2.6442 | 2.6442 |  | 0 | 0
| 3258107 | Office Building : Repair & Maintenance |  |  | 19.98 | 19.98 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 2.9618 | 2.9618 |  | 0 | 0 |  |  |  |  | Part | 2.0582 | 2.0582 |  | 0 | 0
| 3258106 | Residential Building : Repair & Maintenance |  |  | 14.53 | 14.53 |  | 0 | 0 |  |  |  |  | Part | 4.95 | 4.95 |  | 0 | 0 |  |  |  |  | Part | 11.9016 | 11.9016 |  | 0 | 0 |  |  |  |  | Part | 8.6184 | 8.6184 |  | 0 | 0
| 3258105 | Engineering Equipments |  | Part | 1.39 | 1.39 |  | 0 | 0 |  |  |  |  | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 9.1355 | 9.1355 |  | 0 | 0 |  |  |  |  | Part | 7.4745 | 7.4745 |  | 0 | 0
Drainage Structures :
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | Part | 95.03 | 10.83 |  | 84.2 | 0 |  |  |  | Nos. | Part | 33.17 | 4.8826 |  | 28.2874 | 0 |  |  |  | Nos. | Part | 174.7305 | 25.7203 |  | 149.0102 | 0 | [5 empty] | 102.6195 | 15.1056 |  | 87.5139 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) | Nos. | Part | 2.39 | 2.39 |  | 0 | 0 |  |  |  | Nos. | Part | 0.38 | 0.38 |  | 0 | 0 |  |  |  | Nos. | Part | 1.3603 | 1.3603 |  | 0 | 0 |  |  |  | Nos. | Part | 0.8697 | 0.8697 |  | 0 | 0
| 3258107 | Others : Repair & Maintenance |  |  | 7.48 | 7.48 |  | 0 | 0 |  |  |  |  | Part | 1.49 | 1.49 |  | 0 | 0 |  |  |  |  | Part | 17.3768 | 17.3768 |  | 0 | 0 |  |  |  |  | Part | 13.6532 | 13.6532 |  | 0 | 0
(a) Sub-total Revenue Component:
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 7 nos. | 606.9 | 606.9 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 95.6 | 95.6 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos. | 30 nos | 50.22 | 50.22 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 18.03 | 18.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 3 nos | 61.29 | 61.29 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 28.71 | 28.71 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Mechinary & Other Equipment
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 nos. | 8.97 | 8.97 |  | 0 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos. | 2 nos. | 1 | 1 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0.21 | 0.21 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 11 nos. | 20.5 | 20.5 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) |  |  | 3 | 3 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division |  |  | 9.49 | 9.49 |  | 0 | 0 | [5 empty] | 5 | 5 |  | 0 | 0 | [5 empty] | 35.51 | 35.51 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos. | 27 nos. | 19.47 | 19.47 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 5.03 | 5.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 7 nos. | 9.88 | 9.88 |  | 0 | 0 |  |  |  | Nos. | 4 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 3.87 | 3.87 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | Nos. | 1 no. | 0.2 | 0.2 |  | 0 | 0 |  |  |  | No. | 1 no. | 0 | 0 |  | 0 | 0 | [5 empty] | 1.3 | 1.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 nos. | 4.08 | 4.08 |  | 0 | 0 |  |  |  | Nos. | 4 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 1.17 | 1.17 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112314 | Furnitures & Fixtures |  | Part | 45.32 | 45.32 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 2.8954 | 2.8954 |  | 0 | 0 |  |  |  |  | Part | 1.7746 | 1.7746 |  | 0 | 0
| 4112303 | Aircooler | Nos. | 4 nos. | 9.73 | 9.73 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 2.99 | 2.99 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 1.3908 | 1.3908 |  | 0 | 0 | [5 empty] | 0.8892 | 0.8892 |  | 0 | 0
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) |  |  | 14323.6 | 14323.6 |  | 0 | 0 |  |  |  | ha. | Part | 1000 | 1000 |  | 0 | 0 |  |  |  | ha. | Part | 1531.56 | 1531.56 |  | 0 | 0 |  |  |  | ha. |  | 1531.56 | 1531.56 |  | 0 | 0
Construction and Works:
Irrigation Infrastructurs :
| 4111306 | Construction of Irrigation Inlet (New Haors) |  |  | 116.72 | 16.34 |  | 100.38 | 0 | [5 empty] | 192.22 | 26.9108 |  | 165.3092 | 0 |  |  |  | Nos. | 131 | 528.6816 | 74.0154 |  | 454.6662 | 0 | [5 empty] | 382.8384 | 53.5974 |  | 329.241 | 0
Drainage Structures :
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) |  |  | 0 | 0 |  | 0 | 0 |  |  |  | No. | Part | 0 | 0 |  | 0 | 0 |  |  |  | No. | Part | 668.3934 | 93.5751 |  | 574.8183 | 0 | [5 empty] | 504.2266 | 70.5917 |  | 433.6349 | 0
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) |  |  | 6143.66 | 889.49 |  | 5254.17 | 0 |  |  |  | Nos. | Part | 4075.22 | 570.5308 |  | 3504.6892 | 0 |  |  |  | Nos. | Part | 4347.3197 | 608.6248 |  | 3738.6949 | 0 |  |  |  | Nos. | Part | 3855.1703 | 539.7238 |  | 3315.4465 | 0
| 4111307 | Re-excavation of Khal/River (New Haors) |  |  | 6011.48 | 791.08 |  | 5220.4 | 0 |  |  |  | Km. | Part | 2673.22 | 374.2508 |  | 2298.9692 | 0 |  |  |  | Km. | Part | 839.6808 | 117.5553 |  | 722.1255 | 0 |  |  |  | Km. | Part | 659.7492 | 92.3649 |  | 567.3843 | 0
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) |  |  | 455.04 | 64.36 |  | 390.68 | 0 |  |  |  | Km. | Part | 726.54 | 101.7156 |  | 624.8244 | 0 |  |  |  | Km. | Part | 1219.5205 | 170.7329 |  | 1048.7876 | 0 | [5 empty] | 997.7895 | 139.6905 |  | 858.099 | 0
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) |  |  | 452.46 | 63.49 |  | 388.97 | 0 |  |  |  | Km. | Part | 253.65 | 35.511 |  | 218.139 | 0 |  |  |  | Km. | Part | 771.0056 | 107.9408 |  | 663.0648 | 0 | [5 empty] | 558.3144 | 78.164 |  | 480.1504 | 0
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) |  |  | 341.85 | 48.84 |  | 293.01 | 0 |  |  |  | Km. | Part | 179.68 | 25.1552 |  | 154.5248 | 0 |  |  |  | Km. | Part | 674.795 | 94.4713 |  | 580.3237 | 0 | [5 empty] | 552.105 | 77.2947 |  | 474.8103 | 0
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) |  |  | 6127.06 | 779.02 |  | 5348.04 | 0 |  |  |  | Km. | Part | 2923.61 | 409.3054 |  | 2514.3046 | 0 |  |  |  | Km. | Part | 7188.8448 | 1006.4383 |  | 6182.4065 | 0 |  |  |  | Km. |  | 5205.7152 | 728.8001 |  | 4476.9151 | 0
| 4111201 | Rehabilitation of Regulator (New Haors) |  |  | 73.26 | 9.77 |  | 63.49 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 |  |  |  | Nos. |  | 40.3865 | 5.6541 |  | 34.7324 | 0 |  |  |  | Nos. |  | 33.0435 | 4.6261 |  | 28.4174 | 0
| 4111201 | Threshing Floor Construction |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 123.75 | 17.325 |  | 106.425 | 0 | [5 empty] | 101.25 | 14.175 |  | 87.075 | 0
| 4111201 | Construction of WMG Office |  |  | 42.09 | 5.47 |  | 36.62 | 0 |  |  |  | Nos. | Part | 93.33 | 13.0662 |  | 80.2638 | 0 |  |  |  | Nos. |  | 845.0706 | 118.3099 |  | 726.7607 | 0 |  |  |  | Nos. |  | 637.5094 | 89.2513 |  | 548.2581 | 0
| 4111201 | O&M During Construction |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 66 | 9.24 |  | 56.76 | 0 | [5 empty] | 54 | 7.56 |  | 46.44 | 0
(b)Sub-total Capital Component:
Total Cost (a+b) :
| 0 | (c) Physical Contingency ( Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 16.1703 | 16.1703 |  | 0 | 0 | [5 empty] | 14.3397 | 14.3397 |  | 0 | 0
| 0 | (d) Price Contingency (Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 5.4 | 5.4 |  | 0 | 0 | [5 empty] | 4.6 | 4.6 |  | 0 | 0
Grand Total (a+b+c+d) :
† Year 1 is FY 2014-15, Year 2 is FY 2015-16 and Year 3 is FY 2016-17

## 9.Detil Phasing_2
9.0 Item wise Cumulative Progress and Year wise Breakdown of Revised Quantity and Cost to be Incurred. | [18 empty] | Taka in Lac
Economic Code | Economic Sub-Code | Sub-Code wise component description | Cumulative Progress Upto June 2020 (Year 1 to Year-6) † | [9 empty] | FY: 2020-2021 (Year-7) | [9 empty] | FY: 2021-22 (Year-8)
|  |  | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance |  | Part | 1.51 | 1.51 |  | 0 | 0 |  |  |  |  | Part | 2.0242 | 2.0242 |  | 0 | 0 |  |  |  |  | Part | 1.4658 | 1.4658 |  | 0 | 0
| 3111327 | Overtime Allowance |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 6.3 | 6.3 |  | 0 | 0 |  |  |  |  | Part | 3.7 | 3.7 |  | 0 | 0
| 3111338 | Other Allowance |  |  | 50.61 | 50.61 |  | 0 | 0 |  |  |  |  | Part | 53.634 | 53.634 |  | 0 | 0 |  |  |  |  | Part | 35.756 | 35.756 |  | 0 | 0
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) |  | Part | 73.523 | 73.523 |  | 0 | 0 |  |  |  |  | Part | 28.8176 | 28.8176 |  | 0 | 0 |  |  |  |  | Part | 17.6624 | 17.6624 |  | 0 | 0
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | Part | 150.88 | 150.88 |  | 0 | 0 |  |  |  |  | Part | 58.3544 | 58.3544 |  | 0 | 0 |  |  |  |  | Part | 35.7656 | 35.7656 |  | 0 | 0
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | Part | 1780.35 | 1780.35 |  | 0 | 0 |  |  |  |  | Part | 634.52 | 634.52 |  | 0 | 0 |  |  |  |  | Part | 459.48 | 459.48 |  | 0 | 0
| 3211119 | Postage |  | Part | 1.25 | 1.25 |  | 0 | 0 |  |  |  |  | Part | 2.175 | 2.175 |  | 0 | 0 |  |  |  |  | Part | 1.575 | 1.575 |  | 0 | 0
| 3211120 | Telephones/Telegram/Teleprinter |  | Part | 1.04 | 1.04 |  | 0 | 0 |  |  |  |  | Part | 2.4156 | 2.4156 |  | 0 | 0 |  |  |  |  | Part | 1.5444 | 1.5444 |  | 0 | 0
| 3211117 | Telex/Fax/Internet |  | Part | 0.541 | 0.541 |  | 0 | 0 |  |  |  |  | Part | 2.497 | 2.497 |  | 0 | 0 |  |  |  |  | Part | 1.962 | 1.962 |  | 0 | 0
| 3221104 | Registration Fee (Vehicles) |  | Part | 12.09 | 12.09 |  | 0 | 0 | [5 empty] | 4.9833 | 4.9833 |  | 0 | 0 | [5 empty] | 2.9267 | 2.9267 |  | 0 | 0
| 3211115 | Water |  | Part | 1.67 | 1.67 |  | 0 | 0 |  |  |  |  | Part | 2.0313 | 2.0313 |  | 0 | 0 |  |  |  |  | Part | 1.2987 | 1.2987 |  | 0 | 0
| 3211113 | Electricity |  | Part | 11.62 | 11.62 |  | 0 | 0 |  |  |  |  | Part | 4.609 | 4.609 |  | 0 | 0 |  |  |  |  | Part | 3.771 | 3.771 |  | 0 | 0
| 3243102 | Gas & Fuel |  | Part | 21.55 | 21.55 |  | 0 | 0 |  |  |  |  | Part | 11.2545 | 11.2545 |  | 0 | 0 |  |  |  |  | Part | 7.1955 | 7.1955 |  | 0 | 0
| 3243101 | Petrol and Lubricant |  | Part | 88.76 | 88.76 |  | 0 | 0 |  |  |  |  | Part | 46.3068 | 46.3068 |  | 0 | 0 |  |  |  |  | Part | 34.9332 | 34.9332 |  | 0 | 0
| 3221108 | Insurance/Bank Charges (including Vehicles) |  | Part | 2.07 | 2.07 |  | 0 | 0 |  |  |  |  | Part | 0.51205 | 0.51205 |  | 0 | 0 |  |  |  |  | Part | 0.41895 | 0.41895 |  | 0 | 0
| 3255102 | Printing & Binding |  | Part | 34.664 | 34.664 |  | 0 | 0 |  |  |  |  | Part | 9.355 | 9.355 |  | 0 | 0 |  |  |  |  | Part | 5.981 | 5.981 |  | 0 | 0
| 3255104 | Stationery, Seals & Stamps |  | Part | 69.862 | 69.862 |  | 0 | 0 |  |  |  |  | Part | 31.5869 | 31.5869 |  | 0 | 0 |  |  |  |  | Part | 18.5511 | 18.5511 |  | 0 | 0
| 3211127 | Books & Periodicals |  | Part | 0.48 | 0.48 |  | 0 | 0 |  |  |  |  | Part | 0.8816 | 0.8816 |  | 0 | 0 |  |  |  |  | Part | 0.6384 | 0.6384 |  | 0 | 0
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 119 | 0 |  | 119 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | Part | 323.71 | 25.25 |  | 298.46 | 0 |  |  |  |  | Part | 127.794 | 23.4885 |  | 104.3055 | 0 |  |  |  |  | Part | 85.196 | 15.659 |  | 69.537 | 0
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  |  | 1684.75 | 114.81 |  | 1569.94 | 0 |  |  |  |  | Part | 910.5705 | 163.2653 |  | 747.3052 | 0 |  |  |  |  | Part | 534.7795 | 95.886 |  | 438.8935 | 0
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  |  | 661.17 | 42.58 |  | 618.59 | 0 |  |  |  |  | Part | 368.5165 | 64.4167 |  | 304.0998 | 0 |  |  |  |  | Part | 301.5135 | 52.7046 |  | 248.8089 | 0
| 3211109 | Casual labour/Job worker |  | Part | 14.45 | 14.45 |  | 0 | 0 |  |  |  |  | Part | 4.681 | 4.681 |  | 0 | 0 |  |  |  |  | Part | 2.869 | 2.869 |  | 0 | 0
| 3256103 | Consumable Stores |  | Part | 6.74 | 6.74 |  | 0 | 0 |  |  |  |  | Part | 4.7908 | 4.7908 |  | 0 | 0 |  |  |  |  | Part | 3.4692 | 3.4692 |  | 0 | 0
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) |  | Part | 5648.005 | 0 |  | 0 | 5648.005 |  |  |  | MM | Part | 1374.571 | 0 |  | 0 | 1374.571 |  |  |  | MM | Part | 878.824 | 0 |  | 0 | 878.824
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) |  | Part | 15.73 | 15.73 |  | 0 | 0 |  |  |  |  | Part | 8.2766 | 8.2766 |  | 0 | 0 |  |  |  |  | Part | 5.9934 | 5.9934 |  | 0 | 0
| 3111332 | b) Interim Evaluation |  |  | 1.7 | 1.7 |  | 0 | 0 |  |  |  |  | Part | 8.3 | 8.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 3111332 | c) Progress Monitoring |  |  | 1.71 | 1.71 |  | 0 | 0 |  |  |  |  | Part | 4.145 | 4.145 |  | 0 | 0 |  |  |  |  | Part | 4.145 | 4.145 |  | 0 | 0
| 3257104 | Survey |  | Part | 115.02 | 115.02 |  | 0 | 0 |  |  |  |  | Part | 26.7786 | 26.7786 |  | 0 | 0 |  |  |  |  | Part | 20.2014 | 20.2014 |  | 0 | 0
| 3255101 | Computer Consumables |  | Part | 30.469 | 30.469 |  | 0 | 0 |  |  |  |  | Part | 16.242 | 16.242 |  | 0 | 0 |  |  |  |  | Part | 13.2889 | 13.2889 |  | 0 | 0
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing |  | Part | 1175.41 | 1175.41 |  | 0 | 0 |  |  |  |  | Part | 299.0163 | 299.0163 |  | 0 | 0 |  |  |  |  | Part | 225.5737 | 225.5737 |  | 0 | 0
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles |  | Part | 76.367 | 76.367 |  | 0 | 0 |  |  |  |  | Part | 26.7481 | 26.7481 |  | 0 | 0 |  |  |  |  | Part | 21.8849 | 21.8849 |  | 0 | 0
| 3258102 | Furnitures & Fixtures |  | Part | 4.31 | 4.31 |  | 0 | 0 |  |  |  |  | Part | 3.414 | 3.414 |  | 0 | 0 |  |  |  |  | Part | 2.276 | 2.276 |  | 0 | 0
| 3258103 | Computers & office equipments |  | Part | 8.34 | 8.34 |  | 0 | 0 |  |  |  |  | Part | 3.9294 | 3.9294 |  | 0 | 0 |  |  |  |  | Part | 2.7306 | 2.7306 |  | 0 | 0
| 3258105 | Machineries & Equipments |  | Part | 3.22 | 3.22 |  | 0 | 0 |  |  |  |  | Part | 4.1358 | 4.1358 |  | 0 | 0 |  |  |  |  | Part | 2.6442 | 2.6442 |  | 0 | 0
| 3258107 | Office Building : Repair & Maintenance |  |  | 19.98 | 19.98 |  | 0 | 0 |  |  |  |  | Part | 2.9618 | 2.9618 |  | 0 | 0 |  |  |  |  | Part | 2.0582 | 2.0582 |  | 0 | 0
| 3258106 | Residential Building : Repair & Maintenance |  |  | 19.48 | 19.48 |  | 0 | 0 |  |  |  |  | Part | 11.9016 | 11.9016 |  | 0 | 0 |  |  |  |  | Part | 8.6184 | 8.6184 |  | 0 | 0
| 3258105 | Engineering Equipments |  | Part | 3.39 | 3.39 |  | 0 | 0 |  |  |  |  | Part | 9.1355 | 9.1355 |  | 0 | 0 |  |  |  |  | Part | 7.4745 | 7.4745 |  | 0 | 0
Drainage Structures :
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | Part | 128.2 | 14.98 |  | 113.22 | 0 |  |  |  | Nos. | Part | 174.7305 | 26.3319 |  | 148.3986 | 0 |  |  |  | Nos. | Part | 102.6195 | 15.4648 |  | 87.1547 | 0
| 3258128 | Water Transport : Repair of Speedboat(s) | Nos. | Part | 2.77 | 2.77 |  | 0 | 0 |  |  |  | Nos. | Part | 1.3603 | 1.3603 |  | 0 | 0 |  |  |  | Nos. | Part | 0.8697 | 0.8697 |  | 0 | 0
| 3258107 | Others : Repair & Maintenance |  |  | 8.97 | 8.97 |  | 0 | 0 |  |  |  |  | Part | 17.3768 | 17.3768 |  | 0 | 0 |  |  |  |  | Part | 13.6532 | 13.6532 |  | 0 | 0
(a) Sub-total Revenue Component:
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 7 nos. | 606.9 | 606.9 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 95.6 | 95.6 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos. | 30 nos | 50.22 | 50.22 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 18.03 | 18.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 3 nos | 61.29 | 61.29 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 28.71 | 28.71 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Mechinary & Other Equipment
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 nos. | 8.97 | 8.97 |  | 0 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos. | 2 nos. | 0.79 | 0.79 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0.21 | 0.21 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 11 nos. | 20.5 | 20.5 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) |  |  | 3 | 3 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division |  |  | 14.49 | 14.49 |  | 0 | 0 | [5 empty] | 35.51 | 35.51 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos. | 27 nos. | 19.47 | 19.47 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 5.03 | 5.03 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 7 nos. | 9.88 | 9.88 |  | 0 | 0 |  |  |  | Nos. | 4 nos. | 3.87 | 3.87 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | Nos. | 1 no. | 0.2 | 0.2 |  | 0 | 0 |  |  |  | No. | 1 no. | 1.3 | 1.3 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 nos. | 4.08 | 4.08 |  | 0 | 0 |  |  |  | Nos. | 4 nos. | 1.17 | 1.17 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
| 4112314 | Furnitures & Fixtures |  | Part | 45.33 | 45.33 |  | 0 | 0 |  |  |  |  | Part | 2.8954 | 2.8954 |  | 0 | 0 |  |  |  |  | Part | 1.7746 | 1.7746 |  | 0 | 0
| 4112303 | Aircooler | Nos. | 4 nos. | 12.72 | 12.72 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 1.3908 | 1.3908 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0.8892 | 0.8892 |  | 0 | 0
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) |  |  | 15323.6 | 15323.6 |  | 0 | 0 |  |  |  | ha. | Part | 1531.56 | 1531.56 |  | 0 | 0 |  |  |  | ha. | Part | 1531.56 | 1531.56 |  | 0 | 0
Construction and Works:
Irrigation Infrastructurs :
| 4111306 | Construction of Irrigation Inlet (New Haors) |  |  | 308.94 | 40.42 |  | 268.52 | 0 | [5 empty] | 528.6816 | 75.6543 |  | 453.0273 | 0 |  |  |  | Nos. | 131 | 382.8384 | 54.7842 |  | 328.0542 | 0
Drainage Structures :
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) |  |  | 0 | 0 |  | 0 | 0 |  |  |  | No. | Part | 668.3934 | 93.5751 |  | 574.8183 | 0 |  |  |  | No. | Part | 504.2266 | 70.5917 |  | 433.6349 | 0
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) |  |  | 10218.88 | 1398.89 |  | 8819.99 | 0 |  |  |  | Nos. | Part | 4347.3197 | 625.5793 |  | 3721.7404 | 0 |  |  |  | Nos. | Part | 3855.1703 | 554.759 |  | 3300.4113 | 0
| 4111307 | Re-excavation of Khal/River (New Haors) |  |  | 8684.7 | 1125.23 |  | 7559.47 | 0 |  |  |  | Km. | Part | 839.6808 | 168.272 |  | 671.4088 | 0 |  |  |  | Km. | Part | 659.7492 | 132.2137 |  | 527.5355 | 0
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) |  |  | 1181.58 | 155.18 |  | 1026.4 | 0 |  |  |  | Km. | Part | 1219.5205 | 176.3427 |  | 1043.1778 | 0 |  |  |  | Km. | Part | 997.7895 | 144.2804 |  | 853.5091 | 0
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) |  |  | 706.11 | 95.2 |  | 610.91 | 0 |  |  |  | Km. | Part | 771.0056 | 110.0225 |  | 660.9831 | 0 |  |  |  | Km. | Part | 558.3144 | 79.6715 |  | 478.6429 | 0
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) |  |  | 521.53 | 71.3 |  | 450.23 | 0 |  |  |  | Km. | Part | 674.795 | 95.416 |  | 579.379 | 0 |  |  |  | Km. | Part | 552.105 | 78.0676 |  | 474.0374 | 0
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) |  |  | 9050.67 | 1144.47 |  | 7906.2 | 0 |  |  |  | Km. | Part | 7188.8448 | 4738.8865 |  | 2449.9583 | 0 |  |  |  | Km. | Part | 5205.7152 | 3431.6075 |  | 1774.1077 | 0
| 4111201 | Rehabilitation of Regulator (New Haors) |  |  | 73.26 | 9.77 |  | 63.49 | 0 |  |  |  | Nos. |  | 40.3865 | 5.9207 |  | 34.4658 | 0 |  |  |  | Nos. |  | 33.0435 | 4.8442 |  | 28.1993 | 0
| 4111201 | Threshing Floor Construction |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 123.75 | 17.325 |  | 106.425 | 0 | [5 empty] | 101.25 | 14.175 |  | 87.075 | 0
| 4111201 | Construction of WMG Office |  |  | 135.42 | 17.14 |  | 118.28 | 0 |  |  |  | Nos. | Part | 845.0706 | 119.324 |  | 725.7466 | 0 |  |  |  | Nos. |  | 637.5094 | 90.0163 |  | 547.4931 | 0
| 4111201 | O&M During Construction |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 66 | 66 |  | 0 | 0 |  |  |  |  | Part | 54 | 54 |  | 0 | 0
(b)Sub-total Capital Component:
Total Cost (a+b) :
| 0 | (c) Physical Contingency ( Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 16.1703 | 16.1703 |  | 0 | 0 | [5 empty] | 14.3397 | 14.3397 |  | 0 | 0
| 0 | (d) Price Contingency (Lump sum): |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 5.4 | 5.4 |  | 0 | 0 | [5 empty] | 4.6 | 4.6 |  | 0 | 0
Grand Total (a+b+c+d) :
[5 empty] | 59318.897 | [11 empty] | 23.1682
† Year 1 is FY 2014-15, Year 2 is FY 2015-16 and Year 3 is FY 2016-17
59318.897

## Sheet3
1.51 | 1.51 | 0 | 0
0 | 0 | 0 | 0
50.61 | 50.61 | 0 | 0
73.53 | 73.523 | 0 | 0
150.88 | 150.88 | 0 | 0
1780.35 | 1780.35 | 0 | 0
1.25 | 1.25 | 0 | 0
1.04 | 1.04 | 0 | 0
0.541 | 0.541 | 0 | 0
12.09 | 12.09 | 0 | 0
1.67 | 1.67 | 0 | 0
11.62 | 11.62 | 0 | 0
21.55 | 21.55 | 0 | 0
88.76 | 88.76 | 0 | 0
2.069 | 2.07 | 0 | 0
34.664 | 34.664 | 0 | 0
69.862 | 69.862 | 0 | 0
0.48 | 0.48 | 0 | 0
0 | 0 | 0 | 0
323.71 | 25.25 | 298.46 | 0
1684.75 | 114.81 | 1569.94 | 0
661.17 | 42.58 | 618.59 | 0
14.45 | 14.45 | 0 | 0
6.74 | 6.74 | 0 | 0
5648.005 | 0 | 0 | 5648.005
15.73 | 15.73 | 0 | 0
1.7 | 1.7 | 0 | 0
1.71 | 1.71 | 0 | 0
115.02 | 115.02 | 0 | 0
30.469 | 30.469 | 0 | 0
1175.41 | 1175.41 | 0 | 0

## Annex-II
Year wise Financial and Physical Target Plan | [16 empty] | Annexure-II | [11 empty] | Annexure-II
Name of the Project : Haor Flood Management and Livelihood Improvement Project.(BWDB Part)
Name of agency/Division/Ministry: Bangladesh Water Development Board / Ministry of Water Resources
Economic Code | Economic Sub-Code (In detail) | Sub Code Description (In detail) | Total Physical & Financial Target |  |  |  |  | FY: 2014-15 (Year-1) |  |  | FY: 2015-16 (Year-2) |  |  | FY: 2016-17 (Year-3) |  |  | FY: 2017-18 (Year-4) |  |  | FY: 2018-19 (Year-5) |  |  | FY: 2019-20 (Year-6) |  |  | FY: 2020-21 (Year-7) |  |  | FY: 2021-22 (Year-8)
|  |  | Unit | Unit Cost | Quantity | Total Cost (Taka in Lac) | Weight | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical
[9 empty] | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance | Item | 5 | 1 Item | 5 | 5e-05 | 0 |  |  | 0.3 |  |  | 0.13 |  |  | 0.28 |  |  | 0.3 |  |  | 0.5 |  |  | 2.0242 |  |  | 1.4658
| 3111327 | Overtime Allowance | Item | 10 | 1 Item | 10 | 0.0001 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 6.3 |  |  | 3.7
| 3111338 | Other Allowance | Item | 140 | 1 Item | 140 | 0.00139 | 0 |  |  | 0 |  |  | 0 |  |  | 25 |  |  | 11.61 |  |  | 14 |  |  | 53.634 |  |  | 35.756
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) | Item | 120 | 1 Item | 120 | 0.00119 | 0.99 |  |  | 11.92 |  |  | 14.98 |  |  | 17.96 |  |  | 12.7 |  |  | 14.97 |  |  | 28.8176 |  |  | 17.6624
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | Months | 245 | 1 Item | 245 | 0.00243 | 0 |  |  | 16.25 |  |  | 31.35 |  |  | 34.86 |  |  | 34.21 |  |  | 34.21 |  |  | 58.3544 |  |  | 35.7656
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | Item | 2874.35 | 1 Item | 2874.35 | 0.02852 | 223.75 |  |  | 464.64 |  |  | 327.7 |  |  | 337.33 |  |  | 249.75 |  |  | 177.18 |  |  | 634.52 |  |  | 459.48
| 3211119 | Postage | Item | 5 | 1 Item | 5 | 5e-05 | 0 |  |  | 0.05 |  |  | 0.13 |  |  | 0.22 |  |  | 0.37 |  |  | 0.48 |  |  | 2.175 |  |  | 1.575
| 3211120 | Telephones/Telegram/Teleprinter | Item | 5 | 1 Item | 5 | 5e-05 | 0.21 |  |  | 0.24 |  |  | 0.29 |  |  | 0.15 |  |  | 0.08 |  |  | 0.07 |  |  | 2.4156 |  |  | 1.5444
| 3211117 | Telex/Fax/Internet | Item | 5 | 1 Item | 5 | 5e-05 | 0.25 |  |  | 0.001 |  |  | 0.09 |  |  | 0.05 |  |  | 0.05 |  |  | 0.1 |  |  | 2.497 |  |  | 1.962
| 3221104 | Registration Fee (Vehicles) | Item | 20 | 1 Item | 20 | 0.0002 | 1.1 |  |  | 8.37 |  |  | 0.08 |  |  | 0 |  |  | 2.37 |  |  | 0.17 |  |  | 4.9833 |  |  | 2.9267
| 3211115 | Water | Item | 5 | 1 Item | 5 | 5e-05 | 0 |  |  | 0.12 |  |  | 0.23 |  |  | 0.37 |  |  | 0.4 |  |  | 0.55 |  |  | 2.0313 |  |  | 1.2987
| 3211113 | Electricity | Item | 20 | 1 Item | 20 | 0.0002 | 0.19 |  |  | 1.67 |  |  | 1.78 |  |  | 2.31 |  |  | 2.78 |  |  | 2.89 |  |  | 4.609 |  |  | 3.771
| 3243102 | Gas & Fuel | Item | 40 | 1 Item | 40 | 0.0004 | 0.94 |  |  | 3.7 |  |  | 3 |  |  | 4 |  |  | 5.89 |  |  | 4.02 |  |  | 11.2545 |  |  | 7.1955
| 3243101 | Petrol and Lubricant | Item | 170 | 1 Item | 170 | 0.00169 | 0.62 |  |  | 6.99 |  |  | 18.97 |  |  | 18 |  |  | 20 |  |  | 24.18 |  |  | 46.3068 |  |  | 34.9332
| 3221108 | Insurance/Bank Charges (including Vehicles) | Item | 3 | 1 Item | 3 | 3e-05 | 0.08 |  |  | 0.749 |  |  | 0.01 |  |  | 0.22 |  |  | 0.1 |  |  | 0.91 |  |  | 0.51205 |  |  | 0.41895
| 3255102 | Printing & Binding | Item | 50 | 1 Item | 50 | 0.0005 | 0.2 |  |  | 6.994 |  |  | 16.99 |  |  | 6 |  |  | 3.98 |  |  | 0.5 |  |  | 9.355 |  |  | 5.981
| 3255104 | Stationery, Seals & Stamps | Item | 120 | 1 Item | 120 | 0.00119 | 0.97 |  |  | 6.972 |  |  | 11.2 |  |  | 12.79 |  |  | 17.98 |  |  | 19.95 |  |  | 31.5869 |  |  | 18.5511
| 3211127 | Books & Periodicals | Item | 2 | 1 Item | 2 | 2e-05 | 0 |  |  | 0.1 |  |  | 0.03 |  |  | 0.05 |  |  | 0.1 |  |  | 0.2 |  |  | 0.8816 |  |  | 0.6384
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | Item | 119 | 1 Item | 119 | 0.00118 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 119 |  |  | 0
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | 536.7 | 1 Item | 536.7 | 0.00533 | 0 |  |  | 9.22 |  |  | 29.86 |  |  | 86.55 |  |  | 175.87 |  |  | 22.21 |  |  | 127.794 |  |  | 85.196
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  | 3130.1 | 1 Item | 3130.1 | 0.03106 | 0 |  |  | 0 |  |  | 199.49 |  |  | 524.89 |  |  | 622.25 |  |  | 338.12 |  |  | 910.5705 |  |  | 534.7795
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  | 1331.2 | 1 Item | 1331.2 | 0.01321 | 0 |  |  | 0 |  |  | 119.7 |  |  | 224.29 |  |  | 234.21 |  |  | 82.97 |  |  | 368.5165 |  |  | 301.5135
| 3211109 | Casual labour/Job worker | MM | 22 | 1 Item | 22 | 0.00022 | 0.25 |  |  | 2.11 |  |  | 2.35 |  |  | 2 |  |  | 4.25 |  |  | 3.49 |  |  | 4.681 |  |  | 2.869
| 3256103 | Consumable Stores |  | 15 | 1 Item | 15 | 0.00015 | 0 |  |  | 0.99 |  |  | 0.75 |  |  | 1 |  |  | 1 |  |  | 3 |  |  | 4.7908 |  |  | 3.4692
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | MM | 0 | 56+532 | 7901.4 | 0.0784 | 849.67 |  |  | 1849.425 |  |  | 1123.15 |  |  | 689.33 |  |  | 686.43 |  |  | 450 |  |  | 1374.571 |  |  | 878.824
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | item | 30 | 1 Item | 30 | 0.0003 | 0.4 |  |  | 1.33 |  |  | 1.5 |  |  | 4.5 |  |  | 5 |  |  | 3 |  |  | 8.2766 |  |  | 5.9934
| 3111332 | b) Interim Evaluation | item | 10 | 1 Item | 10 | 0.0001 | 0 |  |  | 0 |  |  | 0.27 |  |  | 0.25 |  |  | 0.77 |  |  | 0.41 |  |  | 8.3 |  |  | 0
| 3111332 | c) Progress Monitoring | item | 10 | 1 Item | 10 | 0.0001 | 0 |  |  | 0 |  |  | 0.3 |  |  | 0.25 |  |  | 0.75 |  |  | 0.41 |  |  | 4.145 |  |  | 4.145
| 3257104 | Survey | item | 162 | 1 Item | 162 | 0.00161 | 0 |  |  | 7.62 |  |  | 17.47 |  |  | 30 |  |  | 29.93 |  |  | 30 |  |  | 26.7786 |  |  | 20.2014
| 3255101 | Computer Consumables | item | 60 | 1 Item | 60 | 0.0006 | 0.49 |  |  | 1.499 |  |  | 4.5 |  |  | 6.48 |  |  | 7.5 |  |  | 10 |  |  | 16.242 |  |  | 13.2889
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing | item | 1700 | 1 Item | 1700 | 0.01687 | 0 |  |  | 84.31 |  |  | 227.97 |  |  | 263.24 |  |  | 299.93 |  |  | 299.96 |  |  | 299.0163 |  |  | 225.5737
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles |  | 125 | L.S. | 125 | 0.00124 | 0.98 |  |  | 5.967 |  |  | 12 |  |  | 21.99 |  |  | 20.46 |  |  | 14.97 |  |  | 26.7481 |  |  | 21.8849
| 3258102 | Furnitures & Fixtures |  | 10 | L.S. | 10 | 0.0001 | 0 |  |  | 0.49 |  |  | 0.74 |  |  | 0.98 |  |  | 0.99 |  |  | 1.11 |  |  | 3.414 |  |  | 2.276
| 3258103 | Computers & office equipments |  | 15 | L.S. | 15 | 0.00015 | 0 |  |  | 0.5 |  |  | 0.85 |  |  | 2 |  |  | 1.99 |  |  | 3 |  |  | 3.9294 |  |  | 2.7306
| 3258105 | Machineries & Equipments |  | 10 | L.S. | 10 | 0.0001 | 0 |  |  | 0.22 |  |  | 0.01 |  |  | 0.5 |  |  | 0.5 |  |  | 1.99 |  |  | 4.1358 |  |  | 2.6442
| 3258107 | Office Building : Repair & Maintenance |  | 25 | L.S. | 25 | 0.00025 | 0 |  |  | 0 |  |  | 0 |  |  | 9.98 |  |  | 10 |  |  | 0 |  |  | 2.9618 |  |  | 2.0582
| 3258106 | Residential Building : Repair & Maintenance |  | 40 | L.S. | 40 | 0.0004 | 0 |  |  | 0 |  |  | 0 |  |  | 8.95 |  |  | 5.58 |  |  | 4.95 |  |  | 11.9016 |  |  | 8.6184
| 3258105 | Engineering Equipments |  | 20 | L.S. | 20 | 0.0002 | 0 |  |  | 0.09 |  |  | 0.3 |  |  | 0.5 |  |  | 0.5 |  |  | 2 |  |  | 9.1355 |  |  | 7.4745
Drainage Structures :
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | 405.55 | 86 | 405.55 | 0.00402 | 0 |  |  | 0 |  |  | 59.7 |  |  | 24.34 |  |  | 10.99 |  |  | 33.17 |  |  | 174.7305 |  |  | 102.6195
| 3258128 | Water Transport : Repair of Speedboat(s) | Nos. | 5 | L.S. | 5 | 5e-05 | 0 |  |  | 0.9 |  |  | 0 |  |  | 0.75 |  |  | 0.74 |  |  | 0.38 |  |  | 1.3603 |  |  | 0.8697
| 3258107 | Others : Repair & Maintenance |  | 40 | L.S. | 40 | 0.0004 | 0 |  |  | 0 |  |  | 0 |  |  | 2.5 |  |  | 4.98 |  |  | 1.49 |  |  | 17.3768 |  |  | 13.6532
(a)Sub-total Revenue Component:
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 70.25 | 10 | 702.5 | 0.00697 | 346.3 |  |  | 138.6 |  |  | 0 |  |  | 122 |  |  | 0 |  |  | 0 |  |  | 95.6 |  |  | 0
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | Nos. | 1.52 | 45 | 68.25 | 0.00068 | 5.83 |  |  | 26.31 |  |  | 10.08 |  |  | 8 |  |  | 0 |  |  | 0 |  |  | 18.03 |  |  | 0
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 18 | 5 | 90 | 0.00089 | 0 |  |  | 0 |  |  | 40.29 |  |  | 21 |  |  | 0 |  |  | 0 |  |  | 28.71 |  |  | 0
Mechinary & Other Equipment
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 1.28 | 7 | 8.97 | 9e-05 | 3.73 |  |  | 2.74 |  |  | 2.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 4112316 | Fax -2 nos (PMO 2 Nos.). | Nos. | 0.5 | 2 | 1 | 1e-05 | 0.79 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0.21 |  |  | 0
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Sets | 20.5 | 17 | 20.5 | 0.0002 | 0 |  |  | 5.55 |  |  | 11.15 |  |  | 3.8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | Nos. | 1 | 3 | 3 | 3e-05 | 0 |  |  | 0 |  |  | 0 |  |  | 3 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | Nos. | 0 | L.S | 50 | 0.0005 | 0 |  |  | 0 |  |  | 0 |  |  | 7.89 |  |  | 1.6 |  |  | 5 |  |  | 35.51 |  |  | 0
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | Nos. | 0.66 | 37 | 24.5 | 0.00024 | 3.88 |  |  | 7.14 |  |  | 6.18 |  |  | 2.27 |  |  | 0 |  |  | 0 |  |  | 5.03 |  |  | 0
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 1.25 | 11 | 13.75 | 0.00014 | 3.744 |  |  | 0 |  |  | 2.986 |  |  | 3.15 |  |  | 0 |  |  | 0 |  |  | 3.87 |  |  | 0
| 4112202 | A3 Combo Printer 2 no ( PMO) | No. | 0.75 | 2 | 1.5 | 1e-05 | 0 |  |  | 0.2 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1.3 |  |  | 0
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 0.31 | 17 | 5.25 | 5e-05 | 2.97 |  |  | 0.2 |  |  | 0 |  |  | 0.91 |  |  | 0 |  |  | 0 |  |  | 1.17 |  |  | 0
| 4112314 | Furnitures & Fixtures | item | 50 | LS | 50 | 0.0005 | 7.96 |  |  | 8.45 |  |  | 8.99 |  |  | 9.96 |  |  | 9.97 |  |  | 0 |  |  | 2.8954 |  |  | 1.7746
| 4112303 | Aircooler | Nos. | 1 | 15 | 15 | 0.00015 | 0 |  |  | 0 |  |  | 3.77 |  |  | 2 |  |  | 3.96 |  |  | 2.99 |  |  | 1.3908 |  |  | 0.8892
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) | ha | 39.12 | 470 | 18386.72 | 0.18244 | 0 |  |  | 0 |  |  | 4649.65 |  |  | 5794.05 |  |  | 3879.9 |  |  | 1000 |  |  | 1531.56 |  |  | 1531.56
Construction and Works:
Irrigation Infrastructurs :
| 4111306 | Construction of Irrigation Inlet (New Haors) | Nos. | 10.26 | 119 | 1220.46 | 0.01211 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 116.72 |  |  | 192.22 |  |  | 528.6816 |  |  | 382.8384
Drainage Structures :
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | Nos. | 234.52 | 5 | 1172.62 | 0.01164 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 668.3934 |  |  | 504.2266
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos. | 165.96 | 111 | 18421.37 | 0.18279 | 0 |  |  | 0 |  |  | 293.15 |  |  | 2773.9 |  |  | 3076.61 |  |  | 4075.22 |  |  | 4347.3197 |  |  | 3855.1703
| 4111307 | Re-excavation of Khal/River (New Haors) | km | 30.29 | 336.214 | 10184.13 | 0.10105 | 0 |  |  | 0 |  |  | 349.16 |  |  | 840.8 |  |  | 4821.52 |  |  | 2673.22 |  |  | 839.6808 |  |  | 659.7492
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | km | 31.19 | 108.974 | 3398.89 | 0.03373 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 455.04 |  |  | 726.54 |  |  | 1219.5205 |  |  | 997.7895
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | km | 30.33 | 67.11 | 2035.43 | 0.0202 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 452.46 |  |  | 253.65 |  |  | 771.0056 |  |  | 558.3144
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | km | 27.9 | 62.662 | 1748.43 | 0.01735 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 341.85 |  |  | 179.68 |  |  | 674.795 |  |  | 552.105
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | km | 0 | 261.238 | 21445.23 | 0.21275 | 0 |  |  | 0 |  |  | 336.91 |  |  | 3910 |  |  | 1880.15 |  |  | 2923.61 |  |  | 7188.8448 |  |  | 5205.7152
| 4111201 | Rehabilitation of Regulator (New Haors) | Nos. | 20.96 | 7 | 146.69 | 0.00146 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 73.26 |  |  | 0 |  |  | 40.3865 |  |  | 33.0435
| 4111201 | Threshing Floor Construction | Nos. | 45 | 5 | 225 | 0.00223 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 123.75 |  |  | 101.25
| 4111201 | Construction of WMG Office | Nos. | 29.42 | 55 | 1618 | 0.01605 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 42.09 |  |  | 93.33 |  |  | 845.0706 |  |  | 637.5094
| 4111201 | O&M During Construction | item | 0 | 1 | 120 | 0.00119 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 66 |  |  | 54
(b) Sub-total Capital Component:
Total Cost (a+b) :
| 0 | (c) Physical Contingency ( Lump sum): | item | 0 | L.S. | 30.51 | 0.0003 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 16.1703 |  |  | 14.3397
| 0 | (d) Price Contingency (Lump sum): | item | 0 | L.S. | 10 | 0.0001 | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 5.4 |  |  | 4.6
Grand Total (a+b+c+d) :
# Weight of each item = |  | (Est. cost of each respective item)
(Total cost of all Physical items)
# Physical Percentage of item = |  | Quantity/number targeted in each year |  |  |  |  | x 100
Total quantity/number of respective item for whole project period
# Physical % of total Project = |  | Weight of each item x % of item

## Inves._Cost
Investment Cost
Name of the Project : |  |  | Haor Flood Management and Livelihood Improvement Project.(BWDB Part)(Revised)
Name of agency/Division/Ministry : |  |  | Bangladesh Water Development Board / Ministry of Water Resources
(In Lakh Taka)
Budget Head | Economic Code/ Sub Code | Code/Sub Code Description | Total Project Cost | Financial | [7 empty] | CF | Economic
|  |  |  | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6 | Year-7 | Year-8 |  | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6 | Year-7 | Year-8
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance | 5 | 0 | 0.3 | 0.13 | 0.28 | 0.3 | 0.5 | 2.0242 | 1.4658 | 0.902
| 3111327 | Overtime Allowance | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 3.7 | 0.902
| 3111338 | Other Allowance | 140 | 0 | 0 | 0 | 25 | 11.61 | 14 | 53.634 | 35.756 | 0.902
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 120 | 0.99 | 11.92 | 14.98 | 17.96 | 12.7 | 14.97 | 28.8176 | 17.6624 | 0.902
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 245 | 0 | 16.25 | 31.35 | 34.86 | 34.21 | 34.21 | 58.3544 | 35.7656 | 0.812
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 2874.35 | 223.75 | 464.64 | 327.7 | 337.33 | 249.75 | 177.18 | 634.52 | 459.48 | 0.812
| 3211119 | Postage | 5 | 0 | 0.05 | 0.13 | 0.22 | 0.37 | 0.48 | 2.175 | 1.575 | 0.812
| 3211120 | Telephones/Telegram/Teleprinter | 5 | 0.21 | 0.24 | 0.29 | 0.15 | 0.08 | 0.07 | 2.4156 | 1.5444 | 0.812
| 3211117 | Telex/Fax/Internet | 5 | 0.25 | 0.001 | 0.09 | 0.05 | 0.05 | 0.1 | 2.497 | 1.962 | 0.812
| 3221104 | Registration Fee (Vehicles) | 20 | 1.1 | 8.37 | 0.08 | 0 | 2.37 | 0.17 | 4.9833 | 2.9267 | 0.812
| 3211115 | Water | 5 | 0 | 0.12 | 0.23 | 0.37 | 0.4 | 0.55 | 2.0313 | 1.2987 | 0.812
| 3211113 | Electricity | 20 | 0.19 | 1.67 | 1.78 | 2.31 | 2.78 | 2.89 | 4.609 | 3.771 | 0.812
| 3243102 | Gas & Fuel | 40 | 0.94 | 3.7 | 3 | 4 | 5.89 | 4.02 | 11.2545 | 7.1955 | 0.812
| 3243101 | Petrol and Lubricant | 170 | 0.62 | 6.99 | 18.97 | 18 | 20 | 24.18 | 46.3068 | 34.9332 | 0.72
| 3221108 | Insurance/Bank Charges (including Vehicles) | 3 | 0.08 | 0.749 | 0.01 | 0.22 | 0.1 | 0.91 | 0.51205 | 0.41895 | 0.902
| 3255102 | Printing & Binding | 50 | 0.2 | 6.994 | 16.99 | 6 | 3.98 | 0.5 | 9.355 | 5.981 | 0.812
| 3255104 | Stationery, Seals & Stamps | 120 | 0.97 | 6.972 | 11.2 | 12.79 | 17.98 | 19.95 | 31.5869 | 18.5511 | 0.812
| 3211127 | Books & Periodicals | 2 | 0 | 0.1 | 0.03 | 0.05 | 0.1 | 0.2 | 0.8816 | 0.6384 | 0.812
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 0.902
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 536.7 | 0 | 9.22 | 29.86 | 86.55 | 175.87 | 22.21 | 127.794 | 85.196 | 0.902
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 3130.1 | 0 | 0 | 199.49 | 524.89 | 622.25 | 338.12 | 910.5705 | 534.7795 | 0.902
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 1331.2 | 0 | 0 | 119.7 | 224.29 | 234.21 | 82.97 | 368.5165 | 301.5135 | 0.902
| 3211109 | Casual labour/Job worker | 22 | 0.25 | 2.11 | 2.35 | 2 | 4.25 | 3.49 | 4.681 | 2.869 | 0.902
| 3256103 | Consumable Stores | 15 | 0 | 0.99 | 0.75 | 1 | 1 | 3 | 4.7908 | 3.4692 | 0.812
| 3257101 | Consultancy : International - 56 M/M(Detail in Appendix-E of original approved DPP) National - 532 M/M (Detail in Appendix-E of original approved DPP) | 7901.4 | 849.67 | 1849.425 | 1123.15 | 689.33 | 686.43 | 450 | 1374.571 | 878.824 | 0.902
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 30 | 0.4 | 1.33 | 1.5 | 4.5 | 5 | 3 | 8.2766 | 5.9934 | 0.902
| 3111332 | b) Interim Evaluation | 10 | 0 | 0 | 0.27 | 0.25 | 0.77 | 0.41 | 8.3 | 0 | 0.902
| 3111332 | c) Progress Monitoring | 10 | 0 | 0 | 0.3 | 0.25 | 0.75 | 0.41 | 4.145 | 4.145 | 0.902
| 3257104 | Survey | 162 | 0 | 7.62 | 17.47 | 30 | 29.93 | 30 | 26.7786 | 20.2014 | 0.902
| 3255101 | Computer Consumables | 60 | 0.49 | 1.499 | 4.5 | 6.48 | 7.5 | 10 | 16.242 | 13.2889 | 0.902
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 1700 | 0 | 84.31 | 227.97 | 263.24 | 299.93 | 299.96 | 299.0163 | 225.5737 | 0.86
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles | 125 | 0.98 | 5.967 | 12 | 21.99 | 20.46 | 14.97 | 26.7481 | 21.8849 | 0.86
| 3258102 | Furnitures & Fixtures | 10 | 0 | 0.49 | 0.74 | 0.98 | 0.99 | 1.11 | 3.414 | 2.276 | 0.86
| 3258103 | Computers & office equipments | 15 | 0 | 0.5 | 0.85 | 2 | 1.99 | 3 | 3.9294 | 2.7306 | 0.86
| 3258105 | Machineries & Equipments | 10 | 0 | 0.22 | 0.01 | 0.5 | 0.5 | 1.99 | 4.1358 | 2.6442 | 0.86
| 3258107 | Office Building : Repair & Maintenance | 25 | 0 | 0 | 0 | 9.98 | 10 | 0 | 2.9618 | 2.0582 | 0.765
| 3258106 | Residential Building : Repair & Maintenance | 40 | 0 | 0 | 0 | 8.95 | 5.58 | 4.95 | 11.9016 | 8.6184 | 0.765
| 3258105 | Engineering Equipments | 20 | 0 | 0.09 | 0.3 | 0.5 | 0.5 | 2 | 9.1355 | 7.4745 | 0.86
Drainage Structures :
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 405.55 | 0 | 0 | 59.7 | 24.34 | 10.99 | 33.17 | 174.7305 | 102.6195 | 0.812
| 3258128 | Water Transport : Repair of Speedboat(s) | 5 | 0 | 0.9 | 0 | 0.75 | 0.74 | 0.38 | 1.3603 | 0.8697 | 0.812
| 3258107 | Others : Repair & Maintenance | 40 | 0 | 0 | 0 | 2.5 | 4.98 | 1.49 | 17.3768 | 13.6532 | 0.902
(a)Sub-total Revenue Component:
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 702.5 | 346.3 | 138.6 | 0 | 122 | 0 | 0 | 95.6 | 0 | 0.68
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 15 Nos., Netrokona 8 Nos., Sunamganj 8 Nos., Habiganj 8 Nos.& Brahmanbaria 4 Nos). | 68.25 | 5.83 | 26.31 | 10.08 | 8 | 0 | 0 | 18.03 | 0 | 0.68
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | 90 | 0 | 0 | 40.29 | 21 | 0 | 0 | 28.71 | 0 | 0.68
Mechinary & Other Equipment
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 8.97 | 3.73 | 2.74 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0.812
| 4112316 | Fax -2 nos (PMO 2 Nos.). | 1 | 0.79 | 0 | 0 | 0 | 0 | 0 | 0.21 | 0 | 0.812
Engineering Equipments
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 20.5 | 0 | 5.55 | 11.15 | 3.8 | 0 | 0 | 0 | 0 | 0.68
| 4112304 | Networking Equipment- 3 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., ) | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0.68
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | 50 | 0 | 0 | 0 | 7.89 | 1.6 | 5 | 35.51 | 0 | 0.68
Computers & Accessories
| 4112202 | Desktop Computer- 37 nos. (Project Management Office 11 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 4 Nos., Netrokona 3 Nos., Sunamganj 3 Nos., Habiganj 3 Nos.& Brahmanbaria 3 Nos.) | 24.5 | 3.88 | 7.14 | 6.18 | 2.27 | 0 | 0 | 5.03 | 0 | 0.812
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 13.75 | 3.744 | 0 | 2.986 | 3.15 | 0 | 0 | 3.87 | 0 | 0.812
| 4112202 | A3 Combo Printer 2 no ( PMO) | 1.5 | 0 | 0.2 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0.812
| 4112202 | Laser Printer- 17 nos. (PMO 9 Nos.,Kishoreganj 2 No., Netrokona 2 No., Sunamganj 2 No., Habiganj 1No.& Brahmanbaria 1 No.) | 5.25 | 2.97 | 0.2 | 0 | 0.91 | 0 | 0 | 1.17 | 0 | 0.812
| 4112314 | Furnitures & Fixtures | 50 | 7.96 | 8.45 | 8.99 | 9.96 | 9.97 | 0 | 2.8954 | 1.7746 | 0.812
| 4112303 | Aircooler | 15 | 0 | 0 | 3.77 | 2 | 3.96 | 2.99 | 1.3908 | 0.8892 | 0.812
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) | 18386.72 | 0 | 0 | 4649.65 | 5794.05 | 3879.9 | 1000 | 1531.56 | 1531.56 | 0.902
Construction and Works:
Irrigation Infrastructurs :
| 4111306 | Construction of Irrigation Inlet (New Haors) | 1220.46 | 0 | 0 | 0 | 0 | 116.72 | 192.22 | 528.6816 | 382.8384 | 0.902 | [8 empty] | 1310 | 996.91 | 0.761 | 996.91
Drainage Structures :
| 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 1172.62 | 0 | 0 | 0 | 0 | 0 | 0 | 668.3934 | 504.2266 | 0.765
| 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 18421.37 | 0 | 0 | 293.15 | 2773.9 | 3076.61 | 4075.22 | 4347.3197 | 3855.1703 | 0.765
| 4111307 | Re-excavation of Khal/River (New Haors) | 10184.13 | 0 | 0 | 349.16 | 840.8 | 4821.52 | 2673.22 | 839.6808 | 659.7492 | 0.761
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 3398.89 | 0 | 0 | 0 | 0 | 455.04 | 726.54 | 1219.5205 | 997.7895 | 0.761
| 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 2035.43 | 0 | 0 | 0 | 0 | 452.46 | 253.65 | 771.0056 | 558.3144 | 0.761
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 1748.43 | 0 | 0 | 0 | 0 | 341.85 | 179.68 | 674.795 | 552.105 | 0.761
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 21445.23 | 0 | 0 | 336.91 | 3910 | 1880.15 | 2923.61 | 7188.8448 | 5205.7152 | 0.761
| 4111201 | Rehabilitation of Regulator (New Haors) | 146.69 | 0 | 0 | 0 | 0 | 73.26 | 0 | 40.3865 | 33.0435 | 0.761
| 4111201 | Threshing Floor Construction | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 123.75 | 101.25 | 2.761
| 4111201 | Construction of WMG Office | 1618 | 0 | 0 | 0 | 0 | 42.09 | 93.33 | 845.0706 | 637.5094 | 0.765
| 4111201 | O&M During Construction | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 54 | 0.761
(b) Sub-total Capital Component:
Total Cost (a+b) :
| 0 | (c) Physical Contingency ( Lump sum): | 30.51 | 0 | 0 | 0 | 0 | 0 | 0 | 16.1703 | 14.3397 | 0.765
| 0 | (d) Price Contingency (Lump sum): | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 4.6 | 0
Grand Total (a+b+c+d) :

## Crop. Pattern
Area,Yield and Gross Production Value
Gross Area = 185475 ha.& Net Cultivable Area = 156392 ha.
PRE - PROJECT CONDITION
Sl. |  | Area | Yield | Total | Unit Rate (Tk./mt.) |  | Gross Prod. Value(Lakh Tk.)
No. | Crops | (ha.) | (mt./ha.) | Prod. (mt.) | Financial | Economic | Financial | Economic | ML | Seed | Urea | TSP | MP
1. | Boro (L) | 47000 | 3.5 |  | 10000
2. | Boro (HYV) | 125000 | 4 |  | 11000
| Total : |  | - | - | - | -
Cropping Intensity =
|  | Total Paddy Production = |  |  |  | mt.
Area,Yield and Gross Production Value
Gross Area = 185475 ha.& Net Cultivable Area = 156392 ha.
POST - PROJECT CONDITION
Sl. |  | Area | Yield | Total | Unit Rate (Tk./mt.) |  | Gross Prod. Value(Lakh Tk.)
No. | Crops | (ha.) | (mt./ha.) | Prod. (mt.) | Financial | Economic | Financial | Economic
1. | Boro (HYV) | 280500 | 5.5 |  | 10000
| Total : |  | - | - | - | -
|  | Cropping Intensity = |  |  | %
|  | Total Paddy Production = |  |  |  | mt.
|  | Incremental Paddy Production = |  |  |  | mt.
Variable Cost of Cultivation
PRE - PROJECT CONDITION
Sl. | Items | Unit | Quantity | Unit Rate (Taka) |  | Total cost (Lakh Taka)
No. |  |  |  | Financial | Economic | Financial | Economic
1. | Manual Labour | Man-day |  | 100 | 75
2. | Power Tiller | - | - | - | -
3. | Seed/Seedlings
a) | Paddy | mt. |  | 30000
b) | Wheat | mt. | 0 | 30000
d) | Mustard | mt. | 0 | 50000
4. | Fertilizers
a) | Urea | mt. |  | 8000
b) | T.S.P. | mt. |  | 22000
c) | M.P. | mt. |  | 18000
5. | Insecticide | - | - | - | - | 200
6. | Irrigation Cost | - | - | - | - | 500
| Total | - | - | - | -
POST - PROJECT CONDITION
Sl. | Items | Unit | Quantity | Unit Rate (Taka) |  | Total cost (Lakh Taka)
No. |  |  |  | Financial | Economic | Financial | Economic
1. | Manual Labour | Man-day |  | 100 | 75
2. | Power Tiller | - | - | - | -
3. | Seed/Seedlings
a) | Paddy | mt. |  | 30000
b) | Wheat | mt. | 0 | 30000
c) | Onion | mt. | 0 | 50000
d) | Jute | mt. | 0 | 50000
e) | Vegetables | mt. | 0 | 20000
4. | Fertilizers
a) | Urea | mt. |  | 8000
|  | mt. | 34.61 | 22000
b) | T.S.P. | mt. |  | 22000
|  | mt. | 34.61 | 200
c) | M.P. | mt. |  | 18000
|  |  | 0 | - | -
0
5. | Insecticide | - | - | - | - | 500
6. | Irrigation Cost | - | - | - | - | 1000
| Total | - | - | -
| Incremental Farm Labour = |  |  | mandays
FIXED COST
A. | PRE - PROJECT CONDITION
Sl. | Items |  |  | Financial |  |  | Economic
No.
1. | Rent & rates
2. | Up-keep of stock
3. | Interest on credit
4. | Others
Total per hectare(Taka)
Total for the project (Lakh Taka)
(Net Area= 240578 ha.)
B. | POST - PROJECT CONDITION
Sl. | Items |  |  | Financial |  |  | Economic
No.
1. | Rent & rates
2. | Up-keep of stock
3. | Interest on credit
4. | Others
Total per hectare(Taka)
Total for the project (Lakh Taka)
(Net Area= 240578 ha.)
SUMMARY OF BENEFIT
A. | POST - PROJECT CONDITION
|  |  |  | Financial |  |  | Economic
1. | Gross Production Value
2. | Cost of cultivation
i) Variable Cost
ii) Fixed Cost
3. | Net Benefit (A1-A2)
B. | PRE - PROJECT CONDITION
1. | Gross Production Value
2. | Cost of cultivation
i) Variable Cost
ii) Fixed Cost
3. | Net Benefit (B1-B2)
C. | Net Incremental Benefit from Agriculture (A3-B3)

## FIRR
Computation of Internal Rate of Return
(Financial)
(BDT In Lakh)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1456.294 | 0 |  | 0 | 0
| 2682.927 | 0 |  | 0 | 0
| 7942.686 | 0 |  | 0 | 0
| 15867.59 | 0 |  | 0 | 0
| 17642.42 | 0 |  | 0 | 0
| 13726.97 | 0 |  |  | 0
| 23490.9294 | 0 |  |  | 0
| 17970.1836 | 0 |  |  | 0
|  | 670 |  |  | 0
|  |  |  | 43664.3166 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
NPV @12%
All calculations are based on project period of 30 years
FIRR base case
Benefit Cost Ratio
NPV @12%

## EIRR
Computation of Internal Rate of Return
(Economic)
(In Lakh Taka)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1212.6888 | 0 |  | 0 | 0
| 2329.3642 | 0 |  | 0 | 0
| 6957.1397 | 0 |  | 0 | 0
| 13168.0538 | 0 |  | 0 | 0
| 14304.0085 | 0 |  | 0 | 0
| 10812.9973 | 0 |  |  | 0
| 18935.0014 |  |  |  | 0
| 14492.7013 |  |  |  | 0
|  | 604.34 |  |  | 0
|  | 604.34 |  | 42547.8856 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
NPV @12%
All calculations are based on project period of 30 years
EIRR base case
Benefit Cost Ratio
NPV @12% |  |  | 110049.79

## Annex-IV
Annexure-IV
Revised Amortization Schedule
Name of Project |  | : Haor Flood Management & Livelihood Improvement Project (BWDB Part)
Total Investment |  | : BDT 102234.00 Lakh |  |  |  | 102234
Loan Portion |  | : BDT 59529.60 Lakh
Loan Period |  | : 40 Years Including 10 Uears grace Period
Trate of Investment |  | : 0.01% per annum
(Taka in Lac)
Year | Beginning Principal Amount | Yearly Fixed Amount to be Paid (Principal) | Yearly Interes to be Paid | Total Payment (Principal + Interest) | Ending Principal Balance |  |  | 2014-15
1 | 2 | 3 | 4 | 5= (3+4) | 6=(2-3) |  |  | GoB | RPA | DPA | Total
11 | 59529.6 | [5 empty] | Rev | 231.42 |  | 849.67
12 | [6 empty] | Cap | 375.2
13 | [6 empty] | Total
14
15 | [7 empty] | 2015-16
16 | [7 empty] | GoB | RPA | DPA | Total
17 | [6 empty] | Rev | 635.09 | 9.22 | 1849.43
18 | [6 empty] | Cap | 189.19
19 | [6 empty] | Total
20 | [6 empty] | Cum
21
22
23 | [7 empty] | 2016-17
24 | [7 empty] | GoB | RPA | DPA | Total
25 | [6 empty] | Rev | 703.95 | 401.59 | 1093.15
26 | [6 empty] | Cap | 4854.6 | 860.19
27 | [6 empty] | Total
28 | [6 empty] | Cum
29
30 | [6 empty] | ADP | 2017-18
31 | [7 empty] | GoB | RPA | DPA | Total
32 | [6 empty] | Rev | 700 | 800 | 800
33 | [6 empty] | Cap | 10300 | 7400
34 | [6 empty] | Total
35
36 | [7 empty] | July2016-Mar17
37 | [7 empty] | GoB | RPA | DPA | Total
38 | [6 empty] | Rev
39 | [6 empty] | Cap
40 | [6 empty] | Total
Total
Apr2017-June17
[8 empty] | GoB | RPA | DPA | Total
Rev
Cap
Total

## FIRR_Backup
Computation of Internal Rate of Return
(Financial)
(BDT In Lakh)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1456.29 | 0 |  | 0 | 0
| 2652.93 | 0 |  | 0 | 0
| 7942.666 | 0 |  | 0 | 0
| 15866.4 | 0 |  | 0 | 0
| 17642.414 | 0 |  | 0 | 0
| 24717.06 | 0 |  |  | 0
| 18586.3447 | 0 |  |  | 0
| 12971.6853 | 0 |  |  | 0
|  | 670 |  |  | 0
|  |  |  | 43664.3166 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
NPV @12%
All calculations are based on project period of 30 years
FIRR base case
Benefit Cost Ratio
NPV @12%

## Package_wise_quantity
Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
KISH/PW-01 | [19 empty] | 2
KISH/PW-02 | [19 empty] | 3
KISH/PW-03 | [19 empty] | 4
KISH/PW-04 | [19 empty] | 5
KISH/PW-05 | [19 empty] | 6
KISH/PW-06 | [19 empty] | 7
KISH/PW-07 | [19 empty] | 8
KISH/PW-09 | [19 empty] | 9
KISH/PW-10 | [19 empty] | 10
KISH/PW-11 | [19 empty] | 11
KISH/PW-12 | [19 empty] | 12
KISH/PW-13 | [19 empty] | 13
KISH/PW-14 | [19 empty] | 14
KISH/PW-15 | [19 empty] | 15
KISH/PW-16 | [19 empty] | 16
KISH/PW-17 | [19 empty] | 17
KISH/PW-18 | [19 empty] | 18
KISH/PW-19 | [19 empty] | 19
KISH/PW-20 | [19 empty] | 20
KISH/PW-21 | [19 empty] | 21
KISH/PW-22 | [19 empty] | 22
KISH/PW-23 | [19 empty] | 23
KISH/PW-24 | [19 empty] | 24
KISH/PW-25 | [19 empty] | 25
KISH/PW-26 | [19 empty] | 26
KISH/PW-27 | [19 empty] | 27
KISH/PW-28 | [19 empty] | 28
KISH/PW-29 | [19 empty] | 29
KISH/PW-30 | [19 empty] | 30
KISH/PW-31 | [19 empty] | 31
KISH/PW-32 | [19 empty] | 32
KISH/PW-33 | [19 empty] | 33
HOBI/PW-01 | [19 empty] | 34
HOBI/PW-02 | [19 empty] | 35
HOBI/PW-04 | [19 empty] | 36
HOBI/PW-05 | [19 empty] | 37
HOBI/PW-06 | [19 empty] | 38
HOBI/PW-07 | [19 empty] | 39
HOBI/PW-08 | [19 empty] | 40
NETR/PW-01 | [19 empty] | 41
NETR/PW-02 | [19 empty] | 42
NETR/PW-03 | [19 empty] | 43
NETR/PW-04 | [19 empty] | 44
NETR/PW-05 | [19 empty] | 45
NETR/PW-06 | [19 empty] | 46
NETR/PW-07 | [19 empty] | 47
NETR/PW-08 | [19 empty] | 48
SUNM/PW-01 | [19 empty] | 49
SUNM/PW-02 | [19 empty] | 50
SUNM/PW-03 | [19 empty] | 51
SUNM/PW-04 | [19 empty] | 52
SUNM/PW-05 | [19 empty] | 53
SUNM/PW-06 | [19 empty] | 54
SUNM/PW-07 | [19 empty] | 55
BRAH/PW-01 | [19 empty] | 56
Total

## Package_wise_cost
Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
KISH/PW-01 | [19 empty] | 2
KISH/PW-02 | [19 empty] | 3
KISH/PW-03 | [19 empty] | 4
KISH/PW-04 | [19 empty] | 5
KISH/PW-05 | [19 empty] | 6
KISH/PW-06 | [19 empty] | 7
KISH/PW-07 | [19 empty] | 8
KISH/PW-09 | [19 empty] | 9
KISH/PW-10 | [19 empty] | 10
KISH/PW-11 | [19 empty] | 11
KISH/PW-12 | [19 empty] | 12
KISH/PW-13 | [19 empty] | 13
KISH/PW-14 | [19 empty] | 14
KISH/PW-15 | [19 empty] | 15
KISH/PW-16 | [19 empty] | 16
KISH/PW-17 | [19 empty] | 17
KISH/PW-18 | [19 empty] | 18
KISH/PW-19 | [19 empty] | 19
KISH/PW-20 | [19 empty] | 20
KISH/PW-21 | [19 empty] | 21
KISH/PW-22 | [19 empty] | 22
KISH/PW-23 | [19 empty] | 23
KISH/PW-24 | [19 empty] | 24
KISH/PW-25 | [19 empty] | 25
KISH/PW-26 | [19 empty] | 26
KISH/PW-27 | [19 empty] | 27
KISH/PW-28 | [19 empty] | 28
KISH/PW-29 | [19 empty] | 29
KISH/PW-30 | [19 empty] | 30
KISH/PW-31 | [19 empty] | 31
KISH/PW-32 | [19 empty] | 32
KISH/PW-33 | [19 empty] | 33
HOBI/PW-01 | [19 empty] | 34
HOBI/PW-02 | [19 empty] | 35
HOBI/PW-04 | [19 empty] | 36
HOBI/PW-05 | [19 empty] | 37
HOBI/PW-06 | [19 empty] | 38
HOBI/PW-07 | [19 empty] | 39
HOBI/PW-08 | [19 empty] | 40
NETR/PW-01 | [19 empty] | 41
NETR/PW-02 | [19 empty] | 42
NETR/PW-03 | [19 empty] | 43
NETR/PW-04 | [19 empty] | 44
NETR/PW-05 | [19 empty] | 45
NETR/PW-06 | [19 empty] | 46
NETR/PW-07 | [19 empty] | 47
NETR/PW-08 | [19 empty] | 48
SUNM/PW-01 | [19 empty] | 49
SUNM/PW-02 | [19 empty] | 50
SUNM/PW-03 | [19 empty] | 51
SUNM/PW-04 | [19 empty] | 52
SUNM/PW-05 | [19 empty] | 53
SUNM/PW-06 | [19 empty] | 54
SUNM/PW-07 | [19 empty] | 55
BRAH/PW-01 | [19 empty] | 56
Total

## Haor_wise_quantity
Name | Sub-Project No | Construction of Irrigation Inlet | Rehab Regulator Rehab Haor | Regulator | Box Drainage Outlet | Causeway | Bridge | Khal_River Reexcavation(New Haor) | Khal_River Reexcavation(Rehab Haor) | Embankment Rehablitation | Submersible Embankment Rehabilitation | Submersible Embankment Construction | Rehab Regulator New Haor | Embankment Slope Protection | Thrashing Floor Construction | Construction of WMG | ME Gate Repair | O&M During Construction | Total | index
Chandpur Haor Sub-Project | N-1 | 0 | 0 | 1 | 0 | 0 | 0 | 11.095 | 0 | 0 | 0 | 0.315 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2
Nunnir Haor Sub-Project | N-2 | 15 | 0 | 6 | 3 | 2 | 0 | 20 | 0 | 0 | 0 | 29.418 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3
Boro Haor Sub-Project | N-3 | 7 | 0 | 0 | 0 | 4 | 0 | 25.7 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4
Noapara Haor Sub-Project | N-4 | 14 | 0 | 4 | 2 | 2 | 0 | 10.757 | 0 | 0 | 0 | 23.29 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5
Naogaon Haor Sub-Project | N-5 | 25 | 0 | 6 | 5 | 3 | 0 | 48.968 | 0 | 0 | 0 | 70.395 | 0 | 0 | 20 | 0 | 0 | 0 |  | 6
Badla Haor Sub-Project | N-6 | 6 | 0 | 2 | 3 | 1 | 0 | 9.92 | 0 | 0 | 0 | 21 | 5 | 0 | 0 | 0 | 0 | 0 |  | 7
Chatal Haor Sub-Project | N-7 | 4 | 0 | 2 | 1 | 0 | 0 | 1.925 | 0 | 0 | 0 | 4.51 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8
Dakhshiner Haor Sub-Project | N-8 | 15 | 0 | 1 | 1 | 3 | 0 | 11 | 0 | 0 | 0 | 22.048 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
Suniar Haor Sub-Project | N-9 | 0 | 0 | 2 | 4 | 2 | 0 | 22.7 | 0 | 0 | 0 | 0.54 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10
Mokhar Haor Sub-Project | N-10 | 15 | 0 | 6 | 9 | 5 | 0 | 30.058 | 0 | 0 | 0 | 23.815 | 1 | 0 | 0 | 0 | 0 | 0 |  | 11
Ganesh Haor Sub-Project | N-11 | 2 | 0 | 3 | 2 | 0 | 0 | 11.97 | 0 | 0 | 0 | 3.071 | 1 | 0 | 0 | 0 | 0 | 0 |  | 12
Dharmapasha Rui Beel Sub-Project | N-12 | 15 | 0 | 4 | 6 | 4 | 0 | 87.983 | 0 | 0 | 0 | 38.465 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13
Jaliar Haor Sub-Project | N-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14
Dhakua Haor Sub-Project | N-14 | 9 | 0 | 2 | 7 | 6 | 0 | 50.508 | 0 | 0 | 0 | 16.54 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15
Alalia-Bahadia Sub-Project | R-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 16
Modkhola-Bairagir Char Sub-Project | R-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 17
Ganakkhali Sub-Project | R-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 18
Boraikhali Khal Sub-Project | R-4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 19
Koirdahla Ratna Sub-Project | R-5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 20
Guingajuri Sub-Project | R-6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 21
Aralia Khal Sub-Project | R-7 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3.312 | 0 | 26.952 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 22
Bashira River Re-excavation Sub-Project | R-8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 19.695 | 0 | 22.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23
Dampara Water Management Scheme | R-9 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13.27 | 35.52 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 24
Kangsha River Scheme | R-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.98 | 20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 25
Singer Beel Sub-Project | R-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.133 | 10.69 | 3.56 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 26
Khaliajuri FCD Polder-2 | R-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.195 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 27
Khaliajuri FCD Polder-4 | R-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 28
Chandal Beel Sub-Project | R-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 29
Satdona Beel Scheme | R-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 30
All Haors | A-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 2 |  | 31
Total

## distribution_of_cost
Item | costcode | rindex | 1st Revised | 2nd revised | difference
Office Administration | 1 | 2 | 5403.27 | 5360.27
Fuel & Lubricant | 2 | 3 | 350 | 210
Training and Livelihood | 3 | 4 | 4491.97 | 5236.54
Consulatantcy | 4 | 5 | 7901.4 | 7901.4
Repair & Maintenance | 5 | 6 | 265 | 290
Vehicle & Equipments | 6 | 7 | 1066.22 | 1054.22
Land Acquisition | 7 | 8 | 24000 | 20000
Civilworks | 8 | 9 | 53727 | 60687.03
contingency | 9 | 10 | 660.14 | 40
Total
0 | Office Administration | 1 | 2 | 5403.27 | 5360.27 | -43
1 | Fuel & Lubricant | 2 | 3 | 350 | 210 | -140
2 | Training and Livelihood | 3 | 4 | 4491.97 | 5236.54 | 744.57
3 | Consulatantcy | 4 | 5 | 7901.4 | 7901.4 | 0
4 | Repair & Maintenance | 5 | 6 | 265 | 290 | 25
5 | Vehicle & Equipments | 6 | 7 | 1066.22 | 1054.22 | -12
6 | Land Acquisition | 7 | 8 | 24000 | 20000 | -4000
7 | Civilworks | 8 | 9 | 53727 | 60687.03 | 6960.03
8 | contingency | 9 | 10 | 660.14 | 40 | -620.14