## Resource_List
Code | Name | Unit
101 | Mixture Machine | Nos
102 | Excavator | Nos
103 | Compaction Ruller | Nos
104 | Form Work | Nos
201 | Cement | Bag
202 | Sand 1.5 FM | cum
203 | Stone Chips | cum
204 | Geotextile Filter | sqm
205 | Filter Sand | cum
206 | Peagravel | cum
207 | CC Block | Nos
301 | Labor | m-day
401 | Labor payment | BDT Lac

## Allocation
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05
CC Block Manufacture(30X30X30) | 8 | 25 | 16 | 3 | 0 | 0 | 2500 | 350 | 36 | 80 | 0 | 0 | 0 | 0 | 120 | 0.3
CC Block Manufacture(40X40X20) | 8 | 25 | 16 | 2 | 0 | 0 | 500 | 90 | 8 | 18 | 0 | 0 | 0 | 0 | 30 | 0.075
Embankment Construction | 8 | 41 | 34 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05
Placing Sand Filter | 41 | 50 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 30 | 0.075
Placing Geotextile Filter | 51 | 60 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 30 | 0.075
Placing Pea Gravel Filter | 61 | 70 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 30 | 0.075
Placing CC Block | 71 | 80 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 150 | 0.375
Ancilary Work for Site Completion | 81 | 87 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05

## Main
Name | Start | Finish | Allocation_Sheet_Name
TYPE_A_281_M_R | 1 | 87 | TYPE_A_281_M
FF_30M_at_KM_1_R | 1 | 87 | FF_30M_at_KM_1

## TYPE_A_281_M
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05
CC Block Manufacture(30X30X30) | 8 | 25 | 16 | 3 | 0 | 0 | 2500 | 350 | 36 | 80 | 0 | 0 | 0 | 0 | 120 | 0.3
CC Block Manufacture(40X40X20) | 8 | 25 | 16 | 2 | 0 | 0 | 500 | 90 | 8 | 18 | 0 | 0 | 0 | 0 | 30 | 0.075
Embankment Construction | 8 | 41 | 34 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05
Placing Sand Filter | 41 | 50 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 30 | 0.075
Placing Geotextile Filter | 51 | 60 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 30 | 0.075
Placing Pea Gravel Filter | 61 | 70 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 30 | 0.075
Placing CC Block | 71 | 80 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 150 | 0.375
Ancilary Work for Site Completion | 81 | 87 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05

## FF_30M_at_KM_1
Name | Start | Finish | Duration | 101 | 102 | 103 | 104 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 301 | 401
Mobilization and Site Preparation | 1 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05
CC Block Manufacture(30X30X30) | 8 | 25 | 16 | 3 | 0 | 0 | 2500 | 350 | 36 | 80 | 0 | 0 | 0 | 0 | 120 | 0.3
CC Block Manufacture(40X40X20) | 8 | 25 | 16 | 2 | 0 | 0 | 500 | 90 | 8 | 18 | 0 | 0 | 0 | 0 | 30 | 0.075
Embankment Construction | 8 | 41 | 34 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05
Placing Sand Filter | 41 | 50 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 30 | 0.075
Placing Geotextile Filter | 51 | 60 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 30 | 0.075
Placing Pea Gravel Filter | 61 | 70 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 30 | 0.075
Placing CC Block | 71 | 80 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 150 | 0.375
Ancilary Work for Site Completion | 81 | 87 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0.05