## Submergible_Embankment
Package No. 10
Time Schedule/Bar-Chart for Construction of Sub mersible embankment in between km.0.00 to km. 33.520 = 19.843 km in Dakshiner Haor under Flood Management & Livelihood Improvement Project (HFM&LIP) during the year 2017-18 & 2018-19.
Sl. No. | Name of Work | Nov-17 |  | 2017-12-17 |  |  |  | Jan-18 |  |  |  | Feb-18 |  |  |  | Mar-18 |  |  |  | Apr-18 |  |  | Nov-18 |  | Dec-18 |  |  |  | Jan-19 |  |  |  | Feb-19 |  |  |  | Mar-19 |  |  |  | Apr-19 |  |  |  | May-19
|  | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd |  | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd
1 | Mobilization (Construction of site office with furniture, Godown,Toilet & Tube-well and also stackyard for soil stockpiling) | [20 empty] | Off Period (16 May, 2018 to 15 Nov,2018)
2 | Equipment deployment at site
1. Excavator = 6 nos.(0.7m³ each)
2. Dumptruck = 3 no. (5-6m³)
3. Sheep foot roller= 2 nos.
4. Bull Dozers = 3 Nos.
5. Motorized Vibratory Compactor = 1 Nos.
6. Generator = 1 Nos.
3 | Manufacturing and Supplying RCC(1:2:4) BM Pillar
4 | Fixing in position BM Pillar
5 | Site Preparation dug bailing, Stripping or Ploughing, removing roots and stumps of trees as per direction of engineer in charge.
6 | Earth Work by carried earth by truck/boat or any other (Constructing/ resectioning of the embankment/Canal bank/ road etc).
7 | Earth Work by manual Labour (Constructing/ resectioning of the embankment/Canal bank/ road etc).
8 | Construction of submergible embankment Execavating earth by mechanical excavator and placing and compaction layer by layer as per direction of Engineering incharge.
9 | Compaction of earth in Constructing/ resectioning of the embankment/ Canal bank/ road/river slope etc.
10 | Biological protection of bare earth surface by Dholkalmi
11 | Turfing with 75mm thick durba or charkata sods of size 200mm x 200mm as per direction of engineer in charge.
12 | Earth work in Box Cutting
13 | Manufacturing of C.C. Blocks in different size.
14 | Construction of improved road sub-grade in 98% compaction & Road Construction.
15 | De-mobilization, Site clearence & handover the site
[20 empty] | 3/ | 1
Signature of Executive Engineer
Signature of Sub-Divitional Engineer
Signature of Sectional Officer
Signature of Contractor