## WBS3
TaskNo | Name | Duration | Predecessor | order
0 | Contract | 0 | 4,5
1 | Mobilization and Site Preparation | 7 | 3,4 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 5 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 2 | 6
4 | Embankment Construction | 34 | -1 | 2
5 | Placing Sand Filter | 10 | -1 | 3

## WBS
TaskNo | Name | Duration | Predecessor | order
1 | Mobilization and Site Preparation | 7 | -1 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 1 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 1 | 6
4 | Embankment Construction | 34 | 1 | 2
5 | Placing Sand Filter | 10 | 4 | 3
6 | Placing Geotextile Filter | 10 | 5 | 4
7 | Placing Pea Gravel Filter | 10 | 6 | 5
8 | Placing CC Block | 10 | 2,3,7 | 8
9 | Ancilary Work for Site Completion | 7 | 8 | 9

## Main
Name | Start | Finish | Allocation_Sheet_Name | Site Name
Type_A_211M_724_To_935_S | 1 | 87 | Type_A_211M_724_To_935_S | Type A slope protection work of the Dharmapasha Ruibeel Submergible Embankment from M724 to M935=211M under HFMLIP
Type_A_50M_965_TO_1015_S | 1 | 87 | Type_A_50M_965_TO_1015_S | Type A slope protection work of the Dharmapasha Ruibeel Submergible Embankment from M965 to M1015=50M under HFMLIP
Type_A_40M_4500_TO_4570_S | 1 | 87 | Type_A_40M_4500_TO_4570_S | Type A slope protection work of the Dharmapasha Ruibeel Submergible Embankment in between M4500 to M4570=40M under HFMLIP
Type_A_40M_35020_TO_35100_S | 1 | 87 | Type_A_40M_35020_TO_35100_S | Type A slope protection work of the Dharmapasha Ruibeel Submergible Embankment in between M35020 to M35100=40M
FF_30M_at_KM_1000_S | 1 | 87 | FF_30M_at_KM_1000_S | Construction of 30M Flood Fuse on Submersible Embankment M1000 to M1030 of Dharmapasha Ruibeel Project under HFMLIP
FF_15M_at_KM_4520_S | 1 | 87 | FF_15M_at_KM_4520_S | Construction of 15M Flood Fuse on Submersible Embankment M4520 of Dharmapasha Ruibeel Project under HFMLIP
FF_15M_at_KM_35050_S | 1 | 87 | FF_15M_at_KM_35050_S | Construction of 15M Flood Fuse on Submersible Embankment M35050 of Dharmapasha Ruibeel Project under HFMLIP
T_B5_724M_M0_TO_M724_S | 1 | 87 | T_B5_724M_M0_TO_M724_S | Type B5 slope protection work of the Dharmapasha Ruibeel Submergible Embankment from M0 to M724=724M under HFMLIP
T_B5_1165M_1015_TO_2180_S | 1 | 87 | T_B5_1165M_1015_TO_2180_S | Type B5 slope protection work of the Dharmapasha Ruibeel Submergible Embankment from M1015 to M2180=1165M under HFMLIP
T_B5_1150M_9200_TO_10350_S | 1 | 87 | T_B5_1150M_9200_TO_10350_S | Type B5 slope protection work of the Dharmapasha Ruibeel Submergible Embankment from M9200 to M10350=1150M under HFMLIP
RS_850M_4600_TO_7800_S |  |  | RS_850M_4600_TO_7800_S | Resentioning of the Dharmapasha Ruibeel Submergible Embankment in between M4600 to M7800=850M under HFMLIP
RS_3850M_M25200_TO_M36630_S |  |  | RS_3850M_M25200_TO_M36630_S | Resentioning of the Dharmapasha Ruibeel Submergible Embankment in between M4600 to M7800=850M under HFMLIP

## Type_A_211M_724_To_935_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100
2 | CC Block Manufacture(30X30X30) | 16 | 1 | Nos | 33338
3 | CC Block Manufacture(40X40X20) | 8 | 1 | Nos | 5012
4 | Curing CC Block | 21 | 2,3 | Percent | 100
5 | Embankment Construction | 34 | 1 | Cum | 6974
6 | Placing Sand Filter | 10 | 5,4 | Cum | 560
7 | Placing Geotextile Filter | 10 | 5,4 | sqm | 6098
8 | Placing Pea Gravel Filter | 10 | 5,4 | Cum | 560
9 | Placing CC Block | 10 | 5,4 | Nos | 38350
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100

## Type_A_50M_965_TO_1015_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 1188
3 | CC Block Manufacture(40X40X20) | 6 | 1 | Nos | 7900
4 | Curing | 21 | 2,3 | Percent | 100
5 | Embankment Construction | 7 | 1 | Cum | 1653
6 | Placing Sand Filter | 5 | 5 | Cum | 133
7 | Placing Geotextile Filter | 5 | 6 | sqm | 1445
8 | Placing Pea Gravel Filter | 5 | 7 | Cum | 133
9 | Placing CC Block | 5 | 4,8 | Nos | 328
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100

## Type_A_40M_4500_TO_4570_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 950
3 | CC Block Manufacture(40X40X20) | 6 | 1 | Nos | 4151
4 | Curing | 21 | 2,3 | Percent | 100
5 | Embankment Construction | 7 | 1 | Cum | 330
6 | Placing Sand Filter | 5 | 5 | Cum | 68
7 | Placing Geotextile Filter | 5 | 6 | sqm | 770
8 | Placing Pea Gravel Filter | 5 | 7 | Cum | 68
9 | Placing CC Block | 5 | 4,8 | Nos | 193
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100

## Type_A_40M_35020_TO_35100_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 950
3 | CC Block Manufacture(40X40X20) | 6 | 1 | Nos | 4151
4 | Curing | 21 | 2,3 | Percent | 100
5 | Embankment Construction | 7 | 1 | Cum | 330
6 | Placing Sand Filter | 5 | 5 | Cum | 68
7 | Placing Geotextile Filter | 5 | 6 | sqm | 770
8 | Placing Pea Gravel Filter | 5 | 7 | Cum | 68
9 | Placing CC Block | 5 | 4,8 | Nos | 193
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100

## FF_30M_at_KM_1000_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | CC Block Manufacture(50X50X50) | 17 | 1 | Nos | 2670
3 | CC Block Manufacture(50X50X30) | 18 | 1 | Nos | 4795
4 | CC Block Manufacture(40X40X40) | 12 | 1 | Nos | 3563
5 | CC Block Manufacture(40X40X20) | 6 | 1 | Nos | 2655
6 | Curing | 21 | 2,3,4,5 | percent | 100
7 | Ring Bundh construction | 7 | 1 | Cum | 2052
8 | Excavation | 9 | 6 | Cum | 2524
9 | Embankment Construction | 15 | 6 | Cum | 1751
10 | Placing Sand Filter | 7 | 8 | Cum | 361
11 | Placing Geotextile Filter | 7 | 9 | sqm | 2457
12 | Placing Pea Gravel Filter | 7 | 10 | Cum | 480
13 | Geo Bag Placing(175) Kg | 7 | 12 | Nos | 4021
14 | Placing CC Block | 7 | 6,12 | Nos | 13683
15 | Ring Bundh Removal | 7 | 14 | percent | 1641
16 | Ancilary Work for Site Completion | 7 | 15 | Percent | 100

## FF_15M_at_KM_4520_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | CC Block Manufacture(50X50X50) | 9 | 1 | Nos | 1356
3 | CC Block Manufacture(50X50X30) | 11 | 1 | Nos | 2951
4 | CC Block Manufacture(40X40X40) | 6 | 1 | Nos | 1781
5 | CC Block Manufacture(40X40X20) | 7 | 1 | Nos | 3917
6 | Curing | 21 | 2,3,4,5 | percent | 100
7 | Ring Bundh construction | 5 | 1 | Cum | 1482
8 | Excavation | 4 | 1 | Cum | 1193
9 | Embankment Construction | 15 | 7 | Cum | 1022
10 | Placing Sand Filter | 5 | 9 | Cum | 268
11 | Placing Geotextile Filter | 5 | 10 | sqm | 1837
12 | Placing Pea Gravel Filter | 5 | 11 | Cum | 358
13 | Geo Bag Placing(175) Kg | 5 | 12 | Nos | 1851
14 | Placing CC Block | 5 | 6,12 | Nos | 10005
15 | Ring Bundh Removal | 5 | 14 | percent | 1185
16 | Ancilary Work for Site Completion | 7 | 15 | Percent | 100

## FF_15M_at_KM_35050_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | CC Block Manufacture(50X50X50) | 9 | 1 | Nos | 1270
3 | CC Block Manufacture(50X50X30) | 11 | 1 | Nos | 2390
4 | CC Block Manufacture(40X40X40) | 6 | 1 | Nos | 1781
5 | CC Block Manufacture(40X40X20) | 7 | 1 | Nos | 3917
6 | Curing | 21 | 2,3,4,5 | percent | 100
7 | Ring Bundh construction | 5 | 1 | Cum | 1482
8 | Excavation | 4 | 1 | Cum | 1123
9 | Embankment Construction | 15 | 7 | Cum | 670
10 | Placing Sand Filter | 5 | 9 | Cum | 242
11 | Placing Geotextile Filter | 5 | 10 | sqm | 1668
12 | Placing Pea Gravel Filter | 5 | 11 | Cum | 322
13 | Placing CC Block | 5 | 6,11 | Nos | 9358
14 | Ring Bundh Removal | 5 | 13 | percent | 1185
15 | Ancilary Work for Site Completion | 7 | 14 | Percent | 100

## T_B5_724M_M0_TO_M724_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | Embankment Construction | 15 | 1 | Cum | 3495
3 | Placing Geotextile Filter | 15 | 2 | sqm | 11251
4 | Geo Bag Placing(125 Kg) | 15 | 2 | Nos | 3388
5 | Close Turfing | 25 | 4 | percent | 9842
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100

## T_B5_1165M_1015_TO_2180_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | Embankment Construction | 30 | 1 | Cum | 5623
3 | Placing Geotextile Filter | 20 | 2 | sqm | 18105
4 | Geo Bag Placing(125 Kg) | 20 | 2 | Nos | 5451
5 | Close Turfing | 30 | 4 | percent | 15836
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100

## T_B5_1150M_9200_TO_10350_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | Embankment Construction | 15 | 1 | Cum | 5551
3 | Placing Geotextile Filter | 20 | 2 | sqm | 17871
4 | Geo Bag Placing(125 Kg) | 20 | 2 | Nos | 5380
5 | Close Turfing | 25 | 4 | percent | 15632
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100

## RS_850M_4600_TO_7800_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | Embankment Construction | 15 | 1 | Cum | 3366
3 | Close Turfing | 30 | 2 | percent | 11722
4 | Ancilary Work for Site Completion | 7 | 3 | Percent | 100

## RS_3850M_M25200_TO_M36630_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | Embankment Construction | 30 | 1 | Cum | 15246
3 | Close Turfing | 40 | 2 | percent | 53092
4 | Ancilary Work for Site Completion | 7 | 3 | Percent | 100

## Equipment Production Rate
50X50X50 | 162
50X50X30 | 270
40X40X40 | 317
40X40X20 | 634
Equipment | Daily Prod(8hrs)
Excavator | 300
Roller | 760
Mixuture Machie | 17

## Block Placing Production Rate
1 Group | 20 Labour
Dayliy Placing Including Bed Preparation for 40X40X20 CC Block | 1400 | Nos
unit area of block | 0.16 | sqm
Bed Area | 224 | sqm
Sand Filter 100mm thick | 22.4 | cum
Geo Textile Filter | 224 | sqm
Gravel Filter | 22.4 | cum