## Resource_List
Code | Name | Unit
101 | Mixture Machine | Nos
102 | Excavator | Nos
103 | Compaction Ruller | Nos
104 | Form Work | Nos
201 | Cement | Bag
202 | Sand 1.5 FM | cum
203 | Stone Chips | cum
204 | Geotextile Filter | sqm
205 | Filter Sand | cum
206 | Peagravel | cum
207 | CC Block | Nos
301 | Labor | m-day
401 | Labor payment | BDT Lac

## Resources_Consumption
Code | Name | Unit | NS101 | 40-190-05 | 40-190-15 | 40-190-35 | 40-190-40 | 40-190-50 | NS105 | 16-240 | 40-550-10 | 40-500-40 | 40-530-30 | NS106 | NS102
101 | Mixture Machine | Nos | 0 | 0.0037037 | 0.0061728 | 0.0031546 | 0.0015798 | 0.0013333 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | Excavator | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0033 | 0 | 0 | 0 | 0 | 0
103 | Compaction Ruller | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | Form Work | Nos | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | Cement | Bag | 0 | 0.38448 | 0.6408 | 0.32809 | 0.16404 | 0.13841 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | Sand 1.5 FM | cum | 0 | 0.033375 | 0.055625 | 0.02848 | 0.01424 | 0.012015 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | Stone Chips | cum | 0 | 0.073209 | 0.12202 | 0.062472 | 0.031236 | 0.026355 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | Filter Sand | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
205 | Geotextile Filter | sqm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
206 | Peagravel | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
207 | CC Block | Nos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
301 | Labor | m-day | 0.7 | 0.11111 | 0.18519 | 0.094637 | 0.047393 | 0.04 | 0 | 0 | 0.18 | 0.18 | 0.18 | 0.36 | 0.7
401 | Labor payment | BDT Lac | 210 | 33 | 56 | 29 | 14 | 12 | 0 | 60 | 53 | 53 | 53 | 106 | 210

## WBS3
TaskNo | Name | Duration | Predecessor | order
0 | Contract | 0 | 4,5
1 | Mobilization and Site Preparation | 7 | 3,4 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 5 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 2 | 6
4 | Embankment Construction | 34 | -1 | 2
5 | Placing Sand Filter | 10 | -1 | 3

## WBS
TaskNo | Name | Duration | Predecessor | order
1 | Mobilization and Site Preparation | 7 | -1 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 1 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 1 | 6
4 | Embankment Construction | 34 | 1 | 2
5 | Placing Sand Filter | 10 | 4 | 3
6 | Placing Geotextile Filter | 10 | 5 | 4
7 | Placing Pea Gravel Filter | 10 | 6 | 5
8 | Placing CC Block | 10 | 2,3,7 | 8
9 | Ancilary Work for Site Completion | 7 | 8 | 9

## Main
Name | Start | Finish | Allocation_Sheet_Name | Site Name
Type_A_211M_724_To_935_S | 1 | 87 | Type_A_211M_724_To_935_S | Type A slope protection work of the Dharmapasha Ruibeel Submergible Embankment from M724 to M935=211M under HFMLIP

## Type_A_211M_724_To_935_S
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 14 | 1 | Nos | 33338 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 8 | 1 | Nos | 5012 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 40 | 1 | Cum | 6974 | 16-240
6 | Placing Sand Filter | 17 | 4,5 | Cum | 560 | 40-550-10
7 | Placing Geotextile Filter | 17 | 4,5 | sqm | 6098 | 40-500-40
8 | Placing Pea Gravel Filter | 17 | 4,5 | Cum | 560 | 40-530-30
9 | Placing CC Block | 17 | 4,5 | Nos | 38350 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## Type_A_50M_965_TO_1015_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 1188
3 | CC Block Manufacture(40X40X20) | 6 | 1 | Nos | 7900
4 | Curing | 21 | 2,3 | Percent | 100
5 | Embankment Construction | 7 | 1 | Cum | 1653
6 | Placing Sand Filter | 5 | 5 | Cum | 133
7 | Placing Geotextile Filter | 5 | 6 | sqm | 1445
8 | Placing Pea Gravel Filter | 5 | 7 | Cum | 133
9 | Placing CC Block | 5 | 4,8 | Nos | 328
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100

## Type_A_40M_4500_TO_4570_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 950
3 | CC Block Manufacture(40X40X20) | 6 | 1 | Nos | 4151
4 | Curing | 21 | 2,3 | Percent | 100
5 | Embankment Construction | 7 | 1 | Cum | 330
6 | Placing Sand Filter | 5 | 5 | Cum | 68
7 | Placing Geotextile Filter | 5 | 6 | sqm | 770
8 | Placing Pea Gravel Filter | 5 | 7 | Cum | 68
9 | Placing CC Block | 5 | 4,8 | Nos | 193
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100

## Type_A_40M_35020_TO_35100_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 950
3 | CC Block Manufacture(40X40X20) | 6 | 1 | Nos | 4151
4 | Curing | 21 | 2,3 | Percent | 100
5 | Embankment Construction | 7 | 1 | Cum | 330
6 | Placing Sand Filter | 5 | 5 | Cum | 68
7 | Placing Geotextile Filter | 5 | 6 | sqm | 770
8 | Placing Pea Gravel Filter | 5 | 7 | Cum | 68
9 | Placing CC Block | 5 | 4,8 | Nos | 193
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100

## FF_30M_at_KM_1000_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | CC Block Manufacture(50X50X50) | 17 | 1 | Nos | 2670
3 | CC Block Manufacture(50X50X30) | 18 | 1 | Nos | 4795
4 | CC Block Manufacture(40X40X40) | 12 | 1 | Nos | 3563
5 | CC Block Manufacture(40X40X20) | 6 | 1 | Nos | 2655
6 | Curing | 21 | 2,3,4,5 | percent | 100
7 | Ring Bundh construction | 7 | 1 | Cum | 2052
8 | Excavation | 9 | 6 | Cum | 2524
9 | Embankment Construction | 15 | 6 | Cum | 1751
10 | Placing Sand Filter | 7 | 8 | Cum | 361
11 | Placing Geotextile Filter | 7 | 9 | sqm | 2457
12 | Placing Pea Gravel Filter | 7 | 10 | Cum | 480
13 | Geo Bag Placing(175) Kg | 7 | 12 | Nos | 4021
14 | Placing CC Block | 7 | 6,12 | Nos | 13683
15 | Ring Bundh Removal | 7 | 14 | percent | 1641
16 | Ancilary Work for Site Completion | 7 | 15 | Percent | 100

## FF_15M_at_KM_4520_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | CC Block Manufacture(50X50X50) | 9 | 1 | Nos | 1356
3 | CC Block Manufacture(50X50X30) | 11 | 1 | Nos | 2951
4 | CC Block Manufacture(40X40X40) | 6 | 1 | Nos | 1781
5 | CC Block Manufacture(40X40X20) | 7 | 1 | Nos | 3917
6 | Curing | 21 | 2,3,4,5 | percent | 100
7 | Ring Bundh construction | 5 | 1 | Cum | 1482
8 | Excavation | 4 | 1 | Cum | 1193
9 | Embankment Construction | 15 | 7 | Cum | 1022
10 | Placing Sand Filter | 5 | 9 | Cum | 268
11 | Placing Geotextile Filter | 5 | 10 | sqm | 1837
12 | Placing Pea Gravel Filter | 5 | 11 | Cum | 358
13 | Geo Bag Placing(175) Kg | 5 | 12 | Nos | 1851
14 | Placing CC Block | 5 | 6,12 | Nos | 10005
15 | Ring Bundh Removal | 5 | 14 | percent | 1185
16 | Ancilary Work for Site Completion | 7 | 15 | Percent | 100

## FF_15M_at_KM_35050_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | CC Block Manufacture(50X50X50) | 9 | 1 | Nos | 1270
3 | CC Block Manufacture(50X50X30) | 11 | 1 | Nos | 2390
4 | CC Block Manufacture(40X40X40) | 6 | 1 | Nos | 1781
5 | CC Block Manufacture(40X40X20) | 7 | 1 | Nos | 3917
6 | Curing | 21 | 2,3,4,5 | percent | 100
7 | Ring Bundh construction | 5 | 1 | Cum | 1482
8 | Excavation | 4 | 1 | Cum | 1123
9 | Embankment Construction | 15 | 7 | Cum | 670
10 | Placing Sand Filter | 5 | 9 | Cum | 242
11 | Placing Geotextile Filter | 5 | 10 | sqm | 1668
12 | Placing Pea Gravel Filter | 5 | 11 | Cum | 322
13 | Placing CC Block | 5 | 6,11 | Nos | 9358
14 | Ring Bundh Removal | 5 | 13 | percent | 1185
15 | Ancilary Work for Site Completion | 7 | 14 | Percent | 100

## T_B5_724M_M0_TO_M724_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | Embankment Construction | 15 | 1 | Cum | 3495
3 | Placing Geotextile Filter | 15 | 2 | sqm | 11251
4 | Geo Bag Placing(125 Kg) | 15 | 2 | Nos | 3388
5 | Close Turfing | 25 | 4 | percent | 9842
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100

## T_B5_1165M_1015_TO_2180_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | Embankment Construction | 30 | 1 | Cum | 5623
3 | Placing Geotextile Filter | 20 | 2 | sqm | 18105
4 | Geo Bag Placing(125 Kg) | 20 | 2 | Nos | 5451
5 | Close Turfing | 30 | 4 | percent | 15836
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100

## T_B5_1150M_9200_TO_10350_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | Embankment Construction | 15 | 1 | Cum | 5551
3 | Placing Geotextile Filter | 20 | 2 | sqm | 17871
4 | Geo Bag Placing(125 Kg) | 20 | 2 | Nos | 5380
5 | Close Turfing | 25 | 4 | percent | 15632
6 | Ancilary Work for Site Completion | 7 | 5 | Percent | 100

## RS_850M_4600_TO_7800_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | Embankment Construction | 15 | 1 | Cum | 3366
3 | Close Turfing | 30 | 2 | percent | 11722
4 | Ancilary Work for Site Completion | 7 | 3 | Percent | 100

## RS_3850M_M25200_TO_M36630_S
TaskNo | Name | Duration | Predecessor | Unit | Volume
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100
2 | Embankment Construction | 30 | 1 | Cum | 15246
3 | Close Turfing | 40 | 2 | percent | 53092
4 | Ancilary Work for Site Completion | 7 | 3 | Percent | 100

## Equipment Production Rate
CC Bock | L | B | H | Relative Size wrt 30X30X30 | Standard Production Rate | Block/machine |  | code
50X50X50 | 50 | 50 | 50 | 4.6296 | 750 | 162 | 0.0061728 | 40-190-15
50X50X30 | 50 | 50 | 30 | 2.7778 | 750 | 270 | 0.0037037 | 40-190-05
40X40X40 | 40 | 40 | 40 | 2.3704 | 750 | 317 | 0.0031546 | 40-190-35
40X40X20 | 40 | 40 | 20 | 1.1852 | 750 | 633 | 0.0015798 | 40-190-40
30X30X30 | 30 | 30 | 30 | 1 | 750 | 750 | 0.0013333 | 40-190-50
|  |  |  | Equipment |  | Daily Prod(8hrs)
|  |  |  | Excavator |  | 300
|  |  |  | Roller |  | 760
|  |  |  | Mixuture Machie |  | 17
CC Block Placing
Block Size | L | B | H | Realtive Area | Standard Prod/Day | Daily Production
50X50X30 | 50 | 50 | 30 | 1.5625 | 1400 | 896
50X50X20 | 50 | 50 | 20 | 1.5625 | 1400 | 896
30X30X30 | 30 | 30 | 30 | 0.5625 | 1400 | 2489

## Block Placing Production Rate
1 Group | 20 Labour
Dayliy Placing Including Bed Preparation for 40X40X20 CC Block | 1400 | Nos
unit area of block | 0.16 | sqm
Bed Area | 224 | sqm
Sand Filter 100mm thick | 22.4 | cum
Geo Textile Filter | 224 | sqm
Gravel Filter | 22.4 | cum