## 9.Detil Phasing
9.0 Item wise Cumulative Progress and Year wise Breakdown of Revised Quantity and Cost to be Incurred. | [18 empty] | Taka in Lac
Economic Code | Economic Sub-Code | Sub-Code wise component description | Cumulative Progress Upto June 2019 (Year 1 to Year-5) † | [9 empty] | FY: 2019-2020 (Year-6) | [9 empty] | FY: 2020-21 (Year-7) | [9 empty] | FY: 2021-2022 (Year-8)
|  |  | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
(a) Revenue Component:
| 4700 | Allowances
| 4765 | Conveyance Allowance |  | Part | 1.01 | 1.01 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 2.0242 | 2.0242 |  | 0 | 0 |  |  |  |  | Part | 1.4658 | 1.4658 |  | 0 | 0
| 4769 | Overtime Allowance |  |  | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 6.3 | 6.3 |  | 0 | 0 |  |  |  |  | Part | 3.7 | 3.7 |  | 0 | 0
| 4795 | Other Allowance |  |  | 36.61 | 36.61 |  | 0 | 0 |  |  |  |  | Part | 14 | 14 |  | 0 | 0 |  |  |  |  | Part | 53.634 | 53.634 |  | 0 | 0 |  |  |  |  | Part | 35.756 | 35.756 |  | 0 | 0
| 4800 | Supplies and services:
| 4801 | Travel Expenses (TA & DA for PMO & PIU) |  | Part | 58.54 | 58.54 |  | 0 | 0 |  |  |  |  | Part | 15 | 15 |  | 0 | 0 |  |  |  |  | Part | 28.8052 | 28.8052 |  | 0 | 0 |  |  |  |  | Part | 17.6548 | 17.6548 |  | 0 | 0
| 4806 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | Part | 116.67 | 116.67 |  | 0 | 0 |  |  |  |  | Part | 34.25 | 34.25 |  | 0 | 0 |  |  |  |  | Part | 58.3296 | 58.3296 |  | 0 | 0 |  |  |  |  | Part | 35.7504 | 35.7504 |  | 0 | 0
| 4814 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | Part | 1603.18 | 1603.18 |  | 0 | 0 |  |  |  |  | Part | 359.08 | 359.08 |  | 0 | 0 |  |  |  |  | Part | 367.7258 | 367.7258 |  | 0 | 0 |  |  |  |  | Part | 266.2842 | 266.2842 |  | 0 | 0
| 4815 | Postage |  | Part | 0.77 | 0.77 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 2.1634 | 2.1634 |  | 0 | 0 |  |  |  |  | Part | 1.5666 | 1.5666 |  | 0 | 0
| 4816 | Telephones/Telegram/Teleprinter |  | Part | 0.97 | 0.97 |  | 0 | 0 |  |  |  |  | Part | 0.2 | 0.2 |  | 0 | 0 |  |  |  |  | Part | 2.3363 | 2.3363 |  | 0 | 0 |  |  |  |  | Part | 1.4937 | 1.4937 |  | 0 | 0
| 4817 | Telex/Fax/Internet |  | Part | 0.44 | 0.44 |  | 0 | 0 |  |  |  |  | Part | 0.2 | 0.2 |  | 0 | 0 |  |  |  |  | Part | 2.4416 | 2.4416 |  | 0 | 0 |  |  |  |  | Part | 1.9184 | 1.9184 |  | 0 | 0
| 4818 | Registration Fee (Vehicles) |  | Part | 11.92 | 11.92 |  | 0 | 0 | [5 empty] | 1 | 1 |  | 0 | 0 | [5 empty] | 4.4604 | 4.4604 |  | 0 | 0 | [5 empty] | 2.6196 | 2.6196 |  | 0 | 0
| 4819 | Water |  | Part | 1.11 | 1.11 |  | 0 | 0 |  |  |  |  | Part | 0.45 | 0.45 |  | 0 | 0 |  |  |  |  | Part | 2.0984 | 2.0984 |  | 0 | 0 |  |  |  |  | Part | 1.3416 | 1.3416 |  | 0 | 0
| 4821 | Electricity |  | Part | 8.74 | 8.74 |  | 0 | 0 |  |  |  |  | Part | 3.5 | 3.5 |  | 0 | 0 |  |  |  |  | Part | 4.268 | 4.268 |  | 0 | 0 |  |  |  |  | Part | 3.492 | 3.492 |  | 0 | 0
| 4822 | Gas & Fuel |  | Part | 17.52 | 17.52 |  | 0 | 0 |  |  |  |  | Part | 6 | 6 |  | 0 | 0 |  |  |  |  | Part | 46.6528 | 46.6528 |  | 0 | 0 |  |  |  |  | Part | 29.8272 | 29.8272 |  | 0 | 0
| 4823 | Petrol and Lubricant |  | Part | 64.59 | 64.59 |  | 0 | 0 |  |  |  |  | Part | 20 | 20 |  | 0 | 0 |  |  |  |  | Part | 65.7837 | 65.7837 |  | 0 | 0 |  |  |  |  | Part | 49.6263 | 49.6263 |  | 0 | 0
| 4824 | Insurance/Bank Charges (including Vehicles) |  | Part | 1.16 | 1.16 |  | 0 | 0 |  |  |  |  | Part | 0.15 | 0.15 |  | 0 | 0 |  |  |  |  | Part | 0.9295 | 0.9295 |  | 0 | 0 | [5 empty] | 0.7605 | 0.7605 |  | 0 | 0
| 4827 | Printing & Binding |  | Part | 34.16 | 34.16 |  | 0 | 0 |  |  |  |  | Part | 0.5 | 0.5 |  | 0 | 0 |  |  |  |  | Part | 9.3574 | 9.3574 |  | 0 | 0 |  |  |  |  | Part | 5.9826 | 5.9826 |  | 0 | 0
| 4828 | Stationery, Seals & Stamps |  | Part | 49.91 | 49.91 |  | 0 | 0 |  |  |  |  | Part | 20 | 20 |  | 0 | 0 |  |  |  |  | Part | 31.5567 | 31.5567 |  | 0 | 0 |  |  |  |  | Part | 18.5333 | 18.5333 |  | 0 | 0
| 4831 | Books & Periodicals |  | Part | 0.28 | 0.28 |  | 0 | 0 |  |  |  |  | Part | 0.2 | 0.2 |  | 0 | 0 |  |  |  |  | Part | 0.8816 | 0.8816 |  | 0 | 0 |  |  |  |  | Part | 0.6384 | 0.6384 |  | 0 | 0
| 4840 | Training Expenditure
|  | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 138.3532 | 0 |  | 138.3532 | 0 | [5 empty] | 100.1868 | 0 |  | 100.1868 | 0
|  | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | Part | 301.5 | 22.54 |  | 278.96 | 0 |  |  |  |  | Part | 196.17 | 21.0294 |  | 175.1406 | 0 |  |  |  |  | Part | 23.346 | 2.5027 |  | 20.8433 | 0 |  |  |  |  | Part | 15.564 | 1.6685 |  | 13.8955 | 0
|  | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  |  | 1346.63 | 80.34 |  | 1266.29 | 0 |  |  |  |  | Part | 677.14 | 72.5894 |  | 604.5506 | 0 |  |  |  |  | Part | 703.0989 | 75.3722 |  | 627.7267 | 0 |  |  |  |  | Part | 412.9311 | 44.2662 |  | 368.6649 | 0
|  | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  |  | 578.2 | 35.47 |  | 542.73 | 0 |  |  |  |  | Part | 246.66 | 26.442 |  | 220.218 | 0 |  |  |  |  | Part | 273.251 | 29.2925 |  | 243.9585 | 0 |  |  |  |  | Part | 223.569 | 23.9666 |  | 199.6024 | 0
| 4851 | Casual labour/Job worker |  | Part | 10.96 | 10.96 |  | 0 | 0 |  |  |  |  | Part | 3.5 | 3.5 |  | 0 | 0 |  |  |  |  | Part | 4.6748 | 4.6748 |  | 0 | 0 |  |  |  |  | Part | 2.8652 | 2.8652 |  | 0 | 0
| 4854 | Consumable Stores |  | Part | 3.74 | 3.74 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 4.7908 | 4.7908 |  | 0 | 0 |  |  |  |  | Part | 3.4692 | 3.4692 |  | 0 | 0
| 4874 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) |  | Part | 5168.01 | 0 |  | 0 | 5168.01 |  |  |  | MM | Part | 500 | 0 |  | 0 | 500 |  |  |  | MM | Part | 1362.3679 | 0 |  | 0 | 1362.3679 |  |  |  | MM | Part | 871.0221 | 0 |  | 0 | 871.0221
| 4883 | a) Honorarium/Fees/Remuneration (for different Committee) |  | Part | 12.73 | 12.73 |  | 0 | 0 |  |  |  |  | Part | 5 | 5 |  | 0 | 0 |  |  |  |  | Part | 7.1166 | 7.1166 |  | 0 | 0 |  |  |  |  | Part | 5.1534 | 5.1534 |  | 0 | 0
|  | b) Interim Evaluation |  |  | 1.29 | 1.29 |  | 0 | 0 |  |  |  |  | Part | 1 | 1 |  | 0 | 0 | [5 empty] | 4.3176 | 4.3176 |  | 0 | 0 | [5 empty] | 3.3924 | 3.3924 |  | 0 | 0
|  | c) Progress Monitoring |  |  | 1.3 | 1.3 |  | 0 | 0 |  |  |  |  | Part | 1 | 1 |  | 0 | 0 |  |  |  |  | Part | 4.774 | 4.774 |  | 0 | 0 |  |  |  |  | Part | 2.926 | 2.926 |  | 0 | 0
| 4884 | Survey |  | Part | 85.02 | 85.02 |  | 0 | 0 |  |  |  |  | Part | 50 | 50 |  | 0 | 0 |  |  |  |  | Part | 37.0386 | 37.0386 |  | 0 | 0 |  |  |  |  | Part | 27.9414 | 27.9414 |  | 0 | 0
| 4888 | Computer Consumables |  | Part | 20.47 | 20.47 |  | 0 | 0 |  |  |  |  | Part | 10 | 10 |  | 0 | 0 |  |  |  |  | Part | 16.2415 | 16.2415 |  | 0 | 0 |  |  |  |  | Part | 13.2885 | 13.2885 |  | 0 | 0
| 4899 | Other Expenses: Salary of Manpower through Outsourcing |  | Part | 875.46 | 875.46 |  | 0 | 0 |  |  |  |  | Part | 300 | 300 |  | 0 | 0 |  |  |  |  | Part | 355.9878 | 355.9878 |  | 0 | 0 |  |  |  |  | Part | 268.5522 | 268.5522 |  | 0 | 0
| 4900 | Repair, Maintenance & Rehabilitation:
| 4901 | Motor Vehicles |  | Part | 61.4 | 61.4 |  | 0 | 0 |  |  |  |  | Part | 15 | 15 |  | 0 | 0 |  |  |  |  | Part | 26.73 | 26.73 |  | 0 | 0 |  |  |  |  | Part | 21.87 | 21.87 |  | 0 | 0
| 4906 | Furnitures & Fixtures |  | Part | 3.2 | 3.2 |  | 0 | 0 |  |  |  |  | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 2.88 | 2.88 |  | 0 | 0 |  |  |  |  | Part | 1.92 | 1.92 |  | 0 | 0
| 4911 | Computers & office equipments |  | Part | 5.34 | 5.34 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 3.9294 | 3.9294 |  | 0 | 0 |  |  |  |  | Part | 2.7306 | 2.7306 |  | 0 | 0
| 4916 | Machineries & Equipments |  | Part | 1.22 | 1.22 |  | 0 | 0 |  |  |  |  | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 4.1358 | 4.1358 |  | 0 | 0 |  |  |  |  | Part | 2.6442 | 2.6442 |  | 0 | 0
| 4921 | Office Building : Repair & Maintenance |  |  | 19.98 | 19.98 |  | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 2.9618 | 2.9618 |  | 0 | 0 |  |  |  |  | Part | 2.0582 | 2.0582 |  | 0 | 0
| 4923 | Residential Building : Repair & Maintenance |  |  | 14.53 | 14.53 |  | 0 | 0 |  |  |  |  | Part | 5 | 5 |  | 0 | 0 |  |  |  |  | Part | 11.8726 | 11.8726 |  | 0 | 0 |  |  |  |  | Part | 8.5974 | 8.5974 |  | 0 | 0
| 4932 | Engineering Equipments |  | Part | 1.39 | 1.39 |  | 0 | 0 |  |  |  |  | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 9.1355 | 9.1355 |  | 0 | 0 |  |  |  |  | Part | 7.4745 | 7.4745 |  | 0 | 0
| 4947 | Drainage Structures : | [12 empty] | 0
|  | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | Part | 95.03 | 10.83 |  | 84.2 | 0 |  |  |  | Nos. | Part | 58.25 | 8.5744 |  | 49.6756 | 0 |  |  |  | Nos. | Part | 131.8086 | 19.4022 |  | 112.4064 | 0 | [5 empty] | 77.4114 | 11.395 |  | 66.0164 | 0
| 4976 | Water Transport : Repair of Speedboat(s) | Nos. | Part | 2.39 | 2.39 |  | 0 | 0 |  |  |  | Nos. | Part | 0.75 | 0.75 |  | 0 | 0 |  |  |  | Nos. | Part | 1.1346 | 1.1346 |  | 0 | 0 |  |  |  | Nos. | Part | 0.7254 | 0.7254 |  | 0 | 0
| 4991 | Others : Repair & Maintenance |  |  | 7.48 | 7.48 |  | 0 | 0 |  |  |  |  | Part | 3 | 3 |  | 0 | 0 |  |  |  |  | Part | 16.5312 | 16.5312 |  | 0 | 0 |  |  |  |  | Part | 12.9888 | 12.9888 |  | 0 | 0
(a) Sub-total Revenue Component: |  |  |  |  | 10624.85 | 3284.66 |  | 2172.18 | 5168.01 | [5 empty] | 2560 | 1010.4152 |  | 1049.5848 | 500 | [5 empty] | 3836.2268 | 1330.5708 |  | 1143.2881 | 1362.3679 | [5 empty] | 2567.6932 | 948.305 |  | 748.3661 | 871.0221
(b) Capital Component:
| 6800 | Acquisition of Assets:
| 6807 | Motor Vehicle :
|  | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 7 nos. | 606.9 | 606.9 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 95.6 | 95.6 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0
|  | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | Nos. | 30 nos | 50.22 | 50.22 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 10.0968 | 10.0968 |  | 0 | 0 | [5 empty] | 7.9332 | 7.9332 |  | 0 | 0
| 6809 | Water Transport :
|  | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | Nos. | 3 nos | 61.29 | 61.29 |  | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 22.8389 | 22.8389 |  | 0 | 0 | [5 empty] | 15.8711 | 15.8711 |  | 0 | 0
| 6813 | Mechinary & Other Equipment
|  | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 nos. | 8.95 | 8.95 |  | 0 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 | [5 empty] | 0.0114 | 0.0114 |  | 0 | 0 | [5 empty] | 0.0086 | 0.0086 |  | 0 | 0
|  | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 2 nos. | 0.796 | 0.796 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 2.4418 | 2.4418 |  | 0 | 0 | [5 empty] | 1.7682 | 1.7682 |  | 0 | 0
| 6814 | Engineering Equipments
|  | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 11 nos. | 20.18 | 20.18 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0.1824 | 0.1824 |  | 0 | 0 | [5 empty] | 0.1376 | 0.1376 |  | 0 | 0
|  | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) |  |  | 2.13 | 2.13 |  | 0 | 0 |  |  |  | Nos. | 6 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 2.4381 | 2.4381 |  | 0 | 0 | [5 empty] | 1.4319 | 1.4319 |  | 0 | 0
|  | Engineering Laboratory Equipments for Kishoregonj WD Division |  |  | 9.49 | 9.49 | 70 | 0 | 0 | [5 empty] | 5 | 5 |  | 0 | 0 | [5 empty] | 19.5305 | 19.5305 |  | 0 | 0 | [5 empty] | 15.9795 | 15.9795 |  | 0 | 0
| 6815 | Computers & Accessories
|  | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | Nos. | 27 nos. | 19.47 | 19.47 | 72 | 0 | 0 |  |  |  | Nos. | 3 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0.018 | 0.018 |  | 0 | 0 | [5 empty] | 0.012 | 0.012 |  | 0 | 0
|  | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 7 nos. | 9.88 | 9.88 | 73 | 0 | 0 |  |  |  | Nos. | 4 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 2.3994 | 2.3994 |  | 0 | 0 | [5 empty] | 1.4706 | 1.4706 |  | 0 | 0
|  | A3 Combo Printer 2 nos ( PMO) | Nos. | 1 no. | 0.2 | 0.2 | 74 | 0 | 0 |  |  |  | No. | 1 no. | 0 | 0 |  | 0 | 0 | [5 empty] | 0.715 | 0.715 |  | 0 | 0 | [5 empty] | 0.585 | 0.585 |  | 0 | 0
|  | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 nos. | 4.08 | 4.08 | 75 | 0 | 0 |  |  |  | Nos. | 4 nos. | 0 | 0 |  | 0 | 0 | [5 empty] | 0.6552 | 0.6552 |  | 0 | 0 | [5 empty] | 0.5148 | 0.5148 |  | 0 | 0
| 6821 | Furnitures & Fixtures |  | Part | 45.32 | 45.32 | 76 | 0 | 0 |  |  |  |  | Part | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 2.9016 | 2.9016 |  | 0 | 0 |  |  |  |  | Part | 1.7784 | 1.7784 |  | 0 | 0
| 6869 | Aircooler | Nos. | 4 nos. | 9.73 | 9.73 | 77 | 0 | 0 |  |  |  | Nos. | 6 nos. | 4 | 4 |  | 0 | 0 |  |  |  | Nos. | 5 nos. | 0.7747 | 0.7747 |  | 0 | 0 | [5 empty] | 0.4953 | 0.4953 |  | 0 | 0
| 6900 | Acquisition/Purchase of lands and landed properties of Assets:
| 6901 | Land Acquisition ( 470 hectare) |  |  | 14323.6 | 14323.6 | 79 | 0 | 0 |  |  |  | ha. | Part | 2049.42 | 2049.42 |  | 0 | 0 |  |  |  | ha. | Part | 4499.9182 | 4499.9182 |  | 0 | 0 |  |  |  | ha. |  | 3127.0618 | 3127.0618 |  | 0 | 0
| 7000 | Construction and Works:
| 7036 | Irrigation Infrastructurs :
|  | Construction of Irrigation Inlet (New Haors) |  |  | 116.72 | 16.34 | 82 | 100.38 | 0 | [5 empty] | 490.33 | 68.6462 |  | 421.6838 | 0 |  |  |  | Nos. | 131 | 350.075 | 49.0105 |  | 301.0645 | 0 | [5 empty] | 286.425 | 40.0995 |  | 246.3255 | 0
| 7041 | Drainage Structures :
|  | Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) |  |  | 0 | 0 | 84 | 0 | 0 |  |  |  | No. | Part | 0 | 0 |  | 0 | 0 |  |  |  | No. | Part | 281.5882 | 39.4223 |  | 242.1659 | 0 | [5 empty] | 180.0318 | 25.2045 |  | 154.8273 | 0
|  | Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) |  |  | 6143.66 | 889.49 | 85 | 5254.17 | 0 |  |  |  | Nos. | Part | 8105.58 | 1134.7812 |  | 6970.7988 | 0 |  |  |  | Nos. | Part | 2949.1731 | 412.8842 |  | 2536.2889 | 0 |  |  |  | Nos. | Part | 1885.5369 | 263.9752 |  | 1621.5617 | 0
|  | Re-excavation of Khal/River (New Haors) (Earth Volume: 68.97 Lakh cum) |  |  | 6011.48 | 791.08 | 86 | 5220.4 | 0 |  |  |  | Km. | Part | 3936.68 | 551.1352 |  | 3385.5448 | 0 |  |  |  | Km. | Part | 0 | 0 |  | 0 | 0 |  |  |  | Km. | Part | 0 | 0 |  | 0 | 0
| 7081 | Others:
|  | Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 28.01 Lakh cum) |  |  | 455.04 | 64.36 | 88 | 390.68 | 0 |  |  |  | Km. | Part | 900.73 | 126.1022 |  | 774.6278 | 0 |  |  |  | Km. | Part | 1033.1022 | 144.6343 |  | 888.4679 | 0 | [5 empty] | 779.3578 | 109.1101 |  | 670.2477 | 0
|  | Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) |  |  | 452.46 | 63.49 | 89 | 388.97 | 0 |  |  |  | Km. | Part | 913.26 | 127.8564 |  | 785.4036 | 0 |  |  |  | Km. | Part | 220.1853 | 30.8259 |  | 189.3594 | 0 | [5 empty] | 166.1047 | 23.2547 |  | 142.85 | 0
|  | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 7.43 lakh cum) |  |  | 341.85 | 48.84 | 90 | 293.01 | 0 |  |  |  | Km. | Part | 657.55 | 92.057 |  | 565.493 | 0 |  |  |  | Km. | Part | 320.8968 | 44.9256 |  | 275.9712 | 0 | [5 empty] | 188.4632 | 26.3848 |  | 162.0784 | 0
|  | Construction of Submersible Embankment (New Haors) (Earth Volume: 25.68 lakh cum) |  |  | 6127.06 | 779.02 | 91 | 5348.04 | 0 |  |  |  | Km. | Part | 4650.77 | 651.1078 |  | 3999.6622 | 0 |  |  |  | Km. | Part | 0 | 0 |  | 0 | 0 |  |  |  | Km. |  | 0 | 0 |  | 0 | 0
|  | Rehabilitation of Regulator (New Haors) |  |  | 73.26 | 9.77 | 92 | 63.49 | 0 |  |  |  | Nos. |  | 0 | 0 |  | 0 | 0 |  |  |  | Nos. |  | 50.1332 | 7.0186 |  | 43.1146 | 0 |  |  |  | Nos. |  | 30.7268 | 4.3018 |  | 26.425 | 0
|  | Embankment Slope Protection Work |  |  | 0 | 0 | 93 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 2924.5608 | 409.4385 |  | 2515.1223 | 0 | [5 empty] | 2297.8692 | 321.7017 |  | 1976.1675 | 0
|  | Threshing Floor Construction |  |  | 0 | 0 | 94 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 549 | 76.86 |  | 472.14 | 0 | [5 empty] | 351 | 49.14 |  | 301.86 | 0
|  | Construction of WMG Office |  |  | 42.09 | 5.47 | 95 | 36.62 | 0 |  |  |  | Nos. | Part | 348.14 | 48.7396 |  | 299.4004 | 0 |  |  |  | Nos. |  | 1008.7643 | 141.227 |  | 867.5373 | 0 |  |  |  | Nos. |  | 701.0057 | 98.1408 |  | 602.8649 | 0
|  | O & M during Construction |  |  | 0 | 0 | 96 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 |  |  |  |  | Part | 114 | 114 |  | 0 | 0 | [5 empty] | 86 | 86 |  | 0 | 0
(b)Sub-total Capital Component: |  |  |  |  | 34935.856 | 17840.096 |  | 17095.76 | 0 | [5 empty] | 22157.06 | 4954.4456 |  | 17202.6144 | 0 | [5 empty] | 14366.4009 | 6035.169 |  | 8331.2319 | 0 | [5 empty] | 10127.5691 | 4222.361 |  | 5905.2081 | 0
Total Cost (a+b) : |  |  |  |  | 45560.706 | 21124.756 |  | 19267.94 | 5168.01 | [5 empty] | 24717.06 | 5964.8608 |  | 18252.1992 | 500 | [5 empty] | 18202.6277 | 7365.7399 |  | 9474.5199 | 1362.3679 | [5 empty] | 12695.2623 | 5170.666 |  | 6653.5742 | 871.0221
(c) Physical Contingency ( Lump sum): |  |  |  |  | 0 | 0 | 99 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 162.54 | 162.54 |  | 0 | 0 | [5 empty] | 95.46 | 95.46 |  | 0 | 0
(d) Price Contingency (Lump sum): |  |  |  |  | 0 | 0 | 100 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | [5 empty] | 221.177 | 221.177 |  | 0 | 0 | [5 empty] | 180.963 | 180.963 |  | 0 | 0
Grand Total (a+b+c+d) : |  |  |  | 16% | 45560.706 | 21124.756 |  | 19267.94 | 5168.01 | [5 empty] | 24717.06 | 5964.8608 |  | 18252.1992 | 500 | [5 empty] | 18586.3447 | 7749.4569 |  | 9474.5199 | 1362.3679 | [5 empty] | 12971.6853 | 5447.089 |  | 6653.5742 | 871.0221
† Year 1 is FY 2014-15, Year 2 is FY 2015-16 and Year 3 is FY 2016-17

## Annex-II
Year wise Financial and Physical Target Plan | [16 empty] | Annexure-II | [11 empty] | Annexure-II
Name of the Project : Haor Flood Management and Livelihood Improvement Project.(BWDB Part)
Name of agency/Division/Ministry: Bangladesh Water Development Board / Ministry of Water Resources
Economic Code | Economic Sub-Code (In detail) | Sub Code Description (In detail) | Total Physical & Financial Target |  |  |  |  | FY: 2014-15 (Year-1) |  |  | FY: 2015-16 (Year-2) |  |  | FY: 2016-17 (Year-3) |  |  | FY: 2017-18 (Year-4) |  |  | FY: 2018-19 (Year-5) |  |  | FY: 2019-20 (Year-6) |  |  | FY: 2020-21 (Year-7) |  |  | FY: 2021-22 (Year-8)
|  |  | Unit | Unit Cost | Quantity | Total Cost (Taka in Lac) | Weight | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical |  | Financial Amount (Taka in Lac) | Physical
[9 empty] | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
(a) Revenue Component:
Allowances
| 3111302 | Conveyance Allowance | Item | 5 | 0 | 5 | 4.9099e-05 | 0 | 0 | 0 | 0.3 | 6 | 0.00029459 | 0.13 | 2.6 | 0.00012766 | 0.28 | 5.6 | 0.00027495 | 0.3 | 6 | 0.00029459 | 0.5 | 10 | 0.00049099 | 2.0242 | 40.484 | 0.0019877 | 1.4658 | 29.316 | 0.0014394 | 100 | 0.0049099 | 10
| 3111327 | Overtime Allowance | Item | 10 | 0 | 10 | 9.8197e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 63 | 0.0061864 | 3.7 | 37 | 0.0036333 | 100 | 0.0098197 | 11
| 3111338 | Other Allowance | Item | 140 | 0 | 140 | 0.0013748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 17.8571 | 0.024549 | 11.61 | 8.2929 | 0.011401 | 14 | 10 | 0.013748 | 53.634 | 38.31 | 0.052667 | 35.756 | 25.54 | 0.035111 | 100 | 0.13748 | 12
Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) | Item | 120 | 0 | 120 | 0.0011784 | 0.991 | 0.82583 | 0.00097314 | 11.909 | 9.9242 | 0.011694 | 14.98 | 12.4833 | 0.01471 | 17.96 | 14.9667 | 0.017636 | 12.7 | 10.5833 | 0.012471 | 15 | 12.5 | 0.01473 | 28.8052 | 24.0043 | 0.028286 | 17.6548 | 14.7123 | 0.017337 | 100 | 0.11686 | 14
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | Months | 245 | 0 | 245 | 0.0024058 | 0 | 0 | 0 | 16.25 | 6.6327 | 0.015957 | 31.35 | 12.7959 | 0.030785 | 34.86 | 14.2286 | 0.034232 | 34.21 | 13.9633 | 0.033593 | 34.25 | 13.9796 | 0.033633 | 58.3296 | 23.808 | 0.057278 | 35.7504 | 14.592 | 0.035106 | 100 | 0.24058 | 15 | 245 | 100
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | Item | 2596.27 | 0 | 2596.27 | 0.025495 | 223.746 | 8.618 | 0.21971 | 464.654 | 17.897 | 0.45628 | 327.7 | 12.622 | 0.32179 | 337.33 | 12.9929 | 0.33125 | 249.75 | 9.6196 | 0.24525 | 359.08 | 13.8306 | 0.35261 | 367.7258 | 14.1636 | 0.3611 | 266.2842 | 10.2564 | 0.26148 | 100 | 2.3298 | 16
| 3211119 | Postage | Item | 5 | 0 | 5 | 4.9099e-05 | 0 | 0 | 0 | 0.05 | 1 | 4.9099e-05 | 0.13 | 2.6 | 0.00012766 | 0.22 | 4.4 | 0.00021603 | 0.37 | 7.4 | 0.00036333 | 0.5 | 10 | 0.00049099 | 2.1634 | 43.268 | 0.0021244 | 1.5666 | 31.332 | 0.0015384 | 100 | 0.0049099 | 17
| 3211120 | Telephones/Telegram/Teleprinter | Item | 5 | 0 | 5 | 4.9099e-05 | 0.21 | 4.2 | 0.00020621 | 0.24 | 4.8 | 0.00023567 | 0.29 | 5.8 | 0.00028477 | 0.15 | 3 | 0.0001473 | 0.08 | 1.6 | 7.8558e-05 | 0.2 | 4 | 0.00019639 | 2.3363 | 46.726 | 0.0022942 | 1.4937 | 29.874 | 0.0014668 | 100 | 0.0047037 | 18
| 3211117 | Telex/Fax/Internet | Item | 5 | 0 | 5 | 4.9099e-05 | 0.249 | 4.98 | 0.00024451 | 0.001 | 0.02 | 9.8197e-07 | 0.09 | 1.8 | 8.8378e-05 | 0.05 | 1 | 4.9099e-05 | 0.05 | 1 | 4.9099e-05 | 0.2 | 4 | 0.00019639 | 2.4416 | 48.832 | 0.0023976 | 1.9184 | 38.368 | 0.0018838 | 100 | 0.0046654 | 19
| 3221104 | Registration Fee (Vehicles) | Item | 20 | 0 | 20 | 0.00019639 | 1.1 | 5.5 | 0.0010802 | 8.37 | 41.85 | 0.0082191 | 0.08 | 0.4 | 7.8558e-05 | 0 | 0 | 0 | 2.37 | 11.85 | 0.0023273 | 1 | 5 | 0.00098197 | 4.4604 | 22.302 | 0.00438 | 2.6196 | 13.098 | 0.0025724 | 100 | 0.018559 | 20
| 3211115 | Water | Item | 5 | 0 | 5 | 4.9099e-05 | 0 | 0 | 0 | 0.11 | 2.2 | 0.00010802 | 0.23 | 4.6 | 0.00022585 | 0.37 | 7.4 | 0.00036333 | 0.4 | 8 | 0.00039279 | 0.45 | 9 | 0.00044189 | 2.0984 | 41.968 | 0.0020606 | 1.3416 | 26.832 | 0.0013174 | 100 | 0.0049099 | 21
| 3211113 | Electricity | Item | 20 | 0 | 20 | 0.00019639 | 0.187 | 0.935 | 0.00018363 | 1.683 | 8.415 | 0.0016527 | 1.78 | 8.9 | 0.0017479 | 2.31 | 11.55 | 0.0022684 | 2.78 | 13.9 | 0.0027299 | 3.5 | 17.5 | 0.0034369 | 4.268 | 21.34 | 0.0041911 | 3.492 | 17.46 | 0.003429 | 100 | 0.019456 | 22
| 3243102 | Gas & Fuel | Item | 100 | 0 | 100 | 0.00098197 | 0.938 | 0.938 | 0.00092109 | 3.692 | 3.692 | 0.0036254 | 3 | 3 | 0.0029459 | 4 | 4 | 0.0039279 | 5.89 | 5.89 | 0.0057838 | 6 | 6 | 0.0058918 | 46.6528 | 46.6528 | 0.045812 | 29.8272 | 29.8272 | 0.02929 | 100 | 0.097276 | 23
| 3243101 | Petrol and Lubricant | Item | 200 | 0 | 200 | 0.0019639 | 0.625 | 0.3125 | 0.00061373 | 6.995 | 3.4975 | 0.0068689 | 18.97 | 9.485 | 0.018628 | 18 | 9 | 0.017676 | 20 | 10 | 0.019639 | 20 | 10 | 0.019639 | 65.7837 | 32.8918 | 0.064598 | 49.6263 | 24.8132 | 0.048732 | 100 | 0.19578 | 24
| 3221108 | Insurance/Bank Charges (including Vehicles) | Item | 3 | 0 | 3 | 2.9459e-05 | 0.081 | 2.7 | 7.954e-05 | 0.749 | 24.9667 | 0.0007355 | 0.01 | 0.33333 | 9.8197e-06 | 0.22 | 7.3333 | 0.00021603 | 0.1 | 3.3333 | 9.8197e-05 | 0.15 | 5 | 0.0001473 | 0.9295 | 30.9833 | 0.00091274 | 0.7605 | 25.35 | 0.00074679 | 100 | 0.0028664 | 25
| 3255102 | Printing & Binding | Item | 50 | 0 | 50 | 0.00049099 | 0.196 | 0.392 | 0.00019247 | 6.994 | 13.988 | 0.0068679 | 16.99 | 33.98 | 0.016684 | 6 | 12 | 0.0058918 | 3.98 | 7.96 | 0.0039083 | 0.5 | 1 | 0.00049099 | 9.3574 | 18.7148 | 0.0091887 | 5.9826 | 11.9652 | 0.0058748 | 100 | 0.048906 | 26
| 3255104 | Stationery, Seals & Stamps | Item | 120 | 0 | 120 | 0.0011784 | 0.968 | 0.80667 | 0.00095055 | 6.972 | 5.81 | 0.0068463 | 11.2 | 9.3333 | 0.010998 | 12.79 | 10.6583 | 0.012559 | 17.98 | 14.9833 | 0.017656 | 20 | 16.6667 | 0.019639 | 31.5567 | 26.2972 | 0.030988 | 18.5333 | 15.4444 | 0.018199 | 100 | 0.11689 | 27
| 3211127 | Books & Periodicals | Item | 2 | 0 | 2 | 1.9639e-05 | 0 | 0 | 0 | 0.1 | 5 | 9.8197e-05 | 0.03 | 1.5 | 2.9459e-05 | 0.05 | 2.5 | 4.9099e-05 | 0.1 | 5 | 9.8197e-05 | 0.2 | 10 | 0.00019639 | 0.8816 | 44.08 | 0.00086571 | 0.6384 | 31.92 | 0.00062689 | 100 | 0.0019639 | 28
Training Expenditure
| 3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | Item | 238.54 | 0 | 238.54 | 0.0023424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138.3532 | 58 | 0.13586 | 100.1868 | 42 | 0.098381 | 100 | 0.23424 | 30
| 3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | 536.58 | 0 | 536.58 | 0.0052691 | 0 | 0 | 0 | 9.22 | 1.7183 | 0.0090538 | 29.86 | 5.5649 | 0.029322 | 86.55 | 16.1299 | 0.08499 | 175.87 | 32.7761 | 0.1727 | 196.17 | 36.5593 | 0.19263 | 23.346 | 4.3509 | 0.022925 | 15.564 | 2.9006 | 0.015283 | 100 | 0.52691 | 31
| 3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  | 3139.8 | 0 | 3139.8 | 0.030832 | 0 | 0 | 0 | 0 | 0 | 0 | 199.49 | 6.3536 | 0.19589 | 524.89 | 16.7173 | 0.51543 | 622.25 | 19.8181 | 0.61103 | 677.14 | 21.5663 | 0.66493 | 703.0989 | 22.3931 | 0.69042 | 412.9311 | 13.1515 | 0.40549 | 100 | 3.0832 | 32
| 3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  | 1321.68 | 0 | 1321.68 | 0.012979 | 0 | 0 | 0 | 0 | 0 | 0 | 119.7 | 9.0567 | 0.11754 | 224.29 | 16.9701 | 0.22025 | 234.21 | 17.7206 | 0.22999 | 246.66 | 18.6626 | 0.24221 | 273.251 | 20.6745 | 0.26833 | 223.569 | 16.9155 | 0.21954 | 100 | 1.2979 | 33
| 3211109 | Casual labour/Job worker | MM | 22 | 0 | 22 | 0.00021603 | 0.25 | 1.1364 | 0.00024549 | 2.11 | 9.5909 | 0.002072 | 2.35 | 10.6818 | 0.0023076 | 2 | 9.0909 | 0.0019639 | 4.25 | 19.3182 | 0.0041734 | 3.5 | 15.9091 | 0.0034369 | 4.6748 | 21.2491 | 0.0045905 | 2.8652 | 13.0236 | 0.0028135 | 100 | 0.021358 | 34
| 3256103 | Consumable Stores |  | 15 | 0 | 15 | 0.0001473 | 0 | 0 | 0 | 0.99 | 6.6 | 0.00097215 | 0.75 | 5 | 0.00073648 | 1 | 6.6667 | 0.00098197 | 1 | 6.6667 | 0.00098197 | 3 | 20 | 0.0029459 | 4.7908 | 31.9387 | 0.0047044 | 3.4692 | 23.128 | 0.0034067 | 100 | 0.01473 | 35
| 3257101 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) | MM | - | 71+234 | 7901.4 | 0.07759 | 849.675 | 10.7535 | 0.83436 | 1819.425 | 23.0266 | 1.7866 | 1123.15 | 14.2146 | 1.1029 | 689.33 | 8.7242 | 0.6769 | 686.43 | 8.6874 | 0.67406 | 500 | 6.328 | 0.49099 | 1362.3679 | 17.2421 | 1.3378 | 871.0221 | 11.0236 | 0.85532 | 100 | 6.9246 | 36
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | item | 30 | 0 | 30 | 0.00029459 | 0.4 | 1.3333 | 0.00039279 | 1.33 | 4.4333 | 0.001306 | 1.5 | 5 | 0.001473 | 4.5 | 15 | 0.0044189 | 5 | 16.6667 | 0.0049099 | 5 | 16.6667 | 0.0049099 | 7.1166 | 23.722 | 0.0069883 | 5.1534 | 17.178 | 0.0050605 | 100 | 0.029066 | 37
| 3111332 | b) Interim Evaluation | item | 10 | 0 | 10 | 9.8197e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27 | 2.7 | 0.00026513 | 0.25 | 2.5 | 0.00024549 | 0.77 | 7.7 | 0.00075612 | 1 | 10 | 0.00098197 | 4.3176 | 43.176 | 0.0042398 | 3.3924 | 33.924 | 0.0033312 | 100 | 0.0098197 | 38
| 3111332 | c) Progress Monitoring | item | 10 | 0 | 10 | 9.8197e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 3 | 0.00029459 | 0.25 | 2.5 | 0.00024549 | 0.75 | 7.5 | 0.00073648 | 1 | 10 | 0.00098197 | 4.774 | 47.74 | 0.0046879 | 2.926 | 29.26 | 0.0028733 | 100 | 0.0098197 | 39
| 3257104 | Survey | item | 200 | 0 | 200 | 0.0019639 | 0 | 0 | 0 | 7.62 | 3.81 | 0.0074826 | 17.47 | 8.735 | 0.017155 | 30 | 15 | 0.029459 | 29.93 | 14.965 | 0.02939 | 50 | 25 | 0.049099 | 37.0386 | 18.5193 | 0.036371 | 27.9414 | 13.9707 | 0.027438 | 100 | 0.19639 | 40
| 3255101 | Computer Consumables | item | 60 | 0 | 60 | 0.00058918 | 0.491 | 0.81833 | 0.00048215 | 1.499 | 2.4983 | 0.001472 | 4.5 | 7.5 | 0.0044189 | 6.48 | 10.8 | 0.0063632 | 7.5 | 12.5 | 0.0073648 | 10 | 16.6667 | 0.0098197 | 16.2415 | 27.0692 | 0.015949 | 13.2885 | 22.1475 | 0.013049 | 100 | 0.058436 | 41
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing | item | 1800 | 0 | 1800 | 0.017676 | 0 | 0 | 0 | 84.32 | 4.6844 | 0.0828 | 227.97 | 12.665 | 0.22386 | 263.24 | 14.6244 | 0.25849 | 299.93 | 16.6628 | 0.29452 | 300 | 16.6667 | 0.29459 | 355.9878 | 19.7771 | 0.34957 | 268.5522 | 14.9196 | 0.26371 | 100 | 1.7676 | 42
Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles |  | - | 0 | 125 | 0.0012275 | 0.983 | 0.7864 | 0.00096528 | 5.967 | 4.7736 | 0.0058594 | 12 | 9.6 | 0.011784 | 21.99 | 17.592 | 0.021594 | 20.46 | 16.368 | 0.020091 | 15 | 12 | 0.01473 | 26.73 | 21.384 | 0.026248 | 21.87 | 17.496 | 0.021476 | 100 | 0.12178 | 44
| 3258102 | Furnitures & Fixtures |  | - | 0 | 10 | 9.8197e-05 | 0 | 0 | 0 | 0.49 | 4.9 | 0.00048117 | 0.74 | 7.4 | 0.00072666 | 0.98 | 9.8 | 0.00096233 | 0.99 | 9.9 | 0.00097215 | 2 | 20 | 0.0019639 | 2.88 | 28.8 | 0.0028281 | 1.92 | 19.2 | 0.0018854 | 100 | 0.0098197 | 45
| 3258103 | Computers & office equipments |  | - | 0 | 15 | 0.0001473 | 0 | 0 | 0 | 0.5 | 3.3333 | 0.00049099 | 0.85 | 5.6667 | 0.00083468 | 2 | 13.3333 | 0.0019639 | 1.99 | 13.2667 | 0.0019541 | 3 | 20 | 0.0029459 | 3.9294 | 26.196 | 0.0038586 | 2.7306 | 18.204 | 0.0026814 | 100 | 0.01473 | 46
| 3258105 | Machineries & Equipments |  | - | 0 | 10 | 9.8197e-05 | 0 | 0 | 0 | 0.21 | 2.1 | 0.00020621 | 0.01 | 0.1 | 9.8197e-06 | 0.5 | 5 | 0.00049099 | 0.5 | 5 | 0.00049099 | 2 | 20 | 0.0019639 | 4.1358 | 41.358 | 0.0040612 | 2.6442 | 26.442 | 0.0025965 | 100 | 0.0098197 | 47
| 3258107 | Office Building : Repair & Maintenance |  | 25 | 0 | 25 | 0.00024549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.98 | 39.92 | 0.0098001 | 10 | 40 | 0.0098197 | 0 | 0 | 0 | 2.9618 | 11.8472 | 0.0029084 | 2.0582 | 8.2328 | 0.0020211 | 100 | 0.024549 | 48
| 3258106 | Residential Building : Repair & Maintenance |  | - | 0 | 40 | 0.00039279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.95 | 22.375 | 0.0087887 | 5.58 | 13.95 | 0.0054794 | 5 | 12.5 | 0.0049099 | 11.8726 | 29.6815 | 0.011659 | 8.5974 | 21.4935 | 0.0084424 | 100 | 0.039279 | 49
| 3258105 | Engineering Equipments |  | - | 0 | 20 | 0.00019639 | 0 | 0 | 0 | 0.09 | 0.45 | 8.8378e-05 | 0.3 | 1.5 | 0.00029459 | 0.5 | 2.5 | 0.00049099 | 0.5 | 2.5 | 0.00049099 | 2 | 10 | 0.0019639 | 9.1355 | 45.6775 | 0.0089708 | 7.4745 | 37.3725 | 0.0073398 | 100 | 0.019639 | 50
|  | Drainage Structures : | [31 empty] | 51
| 3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | - | 0 | 362.5 | 0.0035597 | 0 | 0 | 0 | 0 | 0 | 0 | 59.7 | 16.469 | 0.058624 | 24.34 | 6.7145 | 0.023901 | 10.99 | 3.0317 | 0.010792 | 58.25 | 16.069 | 0.0572 | 131.8086 | 36.361 | 0.12943 | 77.4114 | 21.3549 | 0.076016 | 100 | 0.35597 | 52
| 3258128 | Water Transport : Repair of Speedboat(s) | Nos. | - | 0 | 5 | 4.9099e-05 | 0 | 0 | 0 | 0.9 | 18 | 0.00088378 | 0 | 0 | 0 | 0.75 | 15 | 0.00073648 | 0.74 | 14.8 | 0.00072666 | 0.75 | 15 | 0.00073648 | 1.1346 | 22.692 | 0.0011141 | 0.7254 | 14.508 | 0.00071232 | 100 | 0.0049099 | 53
| 3258107 | Others : Repair & Maintenance |  | - | 0 | 40 | 0.00039279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 6.25 | 0.0024549 | 4.98 | 12.45 | 0.0048902 | 3 | 7.5 | 0.0029459 | 16.5312 | 41.328 | 0.016233 | 12.9888 | 32.472 | 0.012755 | 100 | 0.039279 | 54
(a)Sub-total Revenue Component: | [5 empty] | 19588.77 | 0.19236 | 1081.09 |  | 1.0616 | 2463.74 |  | 2.4193 | 2227.87 |  | 2.1877 | 2364.86 |  | 2.3222 | 2487.29 |  | 2.4425 | 2560 |  | 2.5139 | 3836.2268 |  | 3.7671 | 2567.6932 |  | 2.5214 |  |  | 55
(b) Capital Component:
Acquisition of Assets:
Motor Vehicle :
| 4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 70.25 | 10 | 702.5 | 0.0068984 | 346.3 | 49.2954 | 0.34006 | 138.6 | 19.7295 | 0.1361 | 0 | 0 | 0 | 122 | 17.3665 | 0.1198 | 0 | 0 | 0 | 95.6 | 13.6085 | 0.093877 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0.34978 | 59
| 4112101 | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | Nos. | 1.36 | 50 | 68.25 | 0.0006702 | 5.825 | 8.5348 | 0.00572 | 26.315 | 38.5568 | 0.025841 | 10.08 | 14.7692 | 0.0098983 | 8 | 11.7216 | 0.0078558 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0968 | 14.7938 | 0.0099148 | 7.9332 | 11.6237 | 0.0077902 | 100 | 0.0613 | 60
Water Transport :
| 4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | Nos. | 16.67 | 6 | 100 | 0.00098197 | 0 | 0 | 0 | 0 | 0 | 0 | 40.29 | 40.29 | 0.039564 | 21 | 21 | 0.020621 | 0 | 0 | 0 | 0 | 0 | 0 | 22.8389 | 22.8389 | 0.022427 | 15.8711 | 15.8711 | 0.015585 | 100 | 0.098197 | 62
|  | Mechinary & Other Equipment | [30 empty] | 0 | 63
| 4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 1.28 | 7 | 8.97 | 8.8083e-05 | 3.726 | 41.5385 | 0.0036588 | 2.744 | 30.5909 | 0.0026945 | 2.48 | 27.6477 | 0.0024353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0114 | 0.12709 | 1.1194e-05 | 0.0086 | 0.095875 | 8.445e-06 | 100 | 0.0051495 | 64
| 4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 0.71 | 7 | 5 | 4.9099e-05 | 0.796 | 15.92 | 0.00078165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.006 | -0.12 | -5.8918e-06 | 0 | 0 | 0 | 2.4418 | 48.836 | 0.0023978 | 1.7682 | 35.364 | 0.0017363 | 100 | 0.0041282 | 65
|  | Engineering Equipments | [31 empty] | 66
| 4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Sets | 1.21 | 17 | 20.5 | 0.0002013 | 0 | 0 | 0 | 5.55 | 27.0732 | 0.00545 | 11.15 | 54.3902 | 0.010949 | 3.48 | 16.9756 | 0.0034173 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1824 | 0.88976 | 0.00017911 | 0.1376 | 0.67122 | 0.00013512 | 100 | 0.02013 | 67
| 4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 1 | 6 | 6 | 5.8918e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.13 | 35.5 | 0.0020916 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4381 | 40.635 | 0.0023941 | 1.4319 | 23.865 | 0.0014061 | 100 | 0.0058918 | 68
| 4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | Nos. | 50 | L.S | 50 | 0.00049099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.89 | 15.78 | 0.0077478 | 1.6 | 3.2 | 0.0015712 | 5 | 10 | 0.0049099 | 19.5305 | 39.061 | 0.019178 | 15.9795 | 31.959 | 0.015691 | 100 | 0.049099 | 69
Computers & Accessories
| 4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | Nos. | 0.65 | 30 | 19.5 | 0.00019148 | 3.879 | 19.8923 | 0.0038091 | 7.141 | 36.6205 | 0.0070123 | 6.18 | 31.6923 | 0.0060686 | 2.27 | 11.641 | 0.0022291 | 0 | 0 | 0 | 0 | 0 | 0 | 0.018 | 0.092308 | 1.7676e-05 | 0.012 | 0.061538 | 1.1784e-05 | 100 | 0.015339 | 71
| 4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 1.25 | 11 | 13.75 | 0.00013502 | 3.744 | 27.2291 | 0.0036765 | 0 | 0 | 0 | 2.986 | 21.7164 | 0.0029322 | 3.15 | 22.9091 | 0.0030932 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3994 | 17.4502 | 0.0023561 | 1.4706 | 10.6953 | 0.0014441 | 100 | 0.0098256 | 72
| 4112202 | A3 Combo Printer 2 nos ( PMO) | No. | 0.75 | 2 | 1.5 | 1.473e-05 | 0 | 0 | 0 | 0.2 | 13.3333 | 0.00019639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.715 | 47.6667 | 0.00070211 | 0.585 | 39 | 0.00057445 | 100 | 0.001473 | 73
| 4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 0.48 | 11 | 5.25 | 5.1554e-05 | 2.97 | 56.5714 | 0.0029165 | 0.2 | 3.8095 | 0.00019639 | 0 | 0 | 0 | 0.91 | 17.3333 | 0.0008936 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6552 | 12.48 | 0.00064339 | 0.5148 | 9.8057 | 0.00050552 | 100 | 0.0022389 | 74
| 4112314 | Furnitures & Fixtures | item | 50 | LS | 50 | 0.00049099 | 7.96 | 15.92 | 0.0078165 | 8.44 | 16.88 | 0.0082879 | 8.99 | 17.98 | 0.0088279 | 9.96 | 19.92 | 0.0097805 | 9.97 | 19.94 | 0.0097903 | 0 | 0 | 0 | 2.9016 | 5.8032 | 0.0028493 | 1.7784 | 3.5568 | 0.0017463 | 100 | 0.041282 | 75
| 4112303 | Aircooler | Nos. | 1 | 15 | 15 | 0.0001473 | 0 | 0 | 0 | 0 | 0 | 0 | 3.77 | 25.1333 | 0.003702 | 2 | 13.3333 | 0.0019639 | 3.96 | 26.4 | 0.0038886 | 4 | 26.6667 | 0.0039279 | 0.7747 | 5.1647 | 0.00076073 | 0.4953 | 3.302 | 0.00048637 | 100 | 0.01473 | 76
Acquisition/Purchase of lands and landed properties of Assets:
| 4141101 | Land Acquisition ( 470 hectare) | ha | 51.06 | 470 | 24000 | 0.23567 | 0 | 0 | 0 | 0 | 0 | 0 | 4649.65 | 19.3735 | 4.5658 | 5794.05 | 24.1419 | 5.6896 | 3879.9 | 16.1663 | 3.81 | 2049.42 | 8.5392 | 2.0125 | 4499.9182 | 18.7497 | 4.4188 | 3127.0618 | 13.0294 | 3.0707 | 100 | 23.5674 | 78
Construction and Works:
| 7036 | Irrigation Infrastructurs :
| 4111306 | Construction of Irrigation Inlet (New Haors) | Nos. | 9.5658 | 130 | 1243.55 | 0.012211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 116.72 | 9.386 | 0.11462 | 490.33 | 39.4299 | 0.48149 | 350.075 | 28.1513 | 0.34376 | 286.425 | 23.0328 | 0.28126 | 100 | 1.2211 | 81
Drainage Structures :
| 4111307 | Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | Nos. | 153.8733 | 3 | 461.62 | 0.004533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281.5882 | 61 | 0.27651 | 180.0318 | 39 | 0.17679 | 100 | 0.4533 | 83
| 4111307 | Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos. | 159.0329 | 120 | 19083.95 | 0.1874 | 0 | 0 | 0 | 0 | 0 | 0 | 293.15 | 1.5361 | 0.28787 | 2773.9 | 14.5353 | 2.7239 | 3076.61 | 16.1215 | 3.0211 | 8105.58 | 42.4733 | 7.9595 | 2949.1731 | 15.4537 | 2.896 | 1885.5369 | 9.8802 | 1.8515 | 100 | 18.7399 | 84
| 4111307 | Re-excavation of Khal/River (New Haors) (Earth Volume: 68.97 Lakh cum) | km | 29.0368 | 342.605 | 9948.16 | 0.097688 | 0 | 0 | 0 | 0 | 0 | 0 | 349.16 | 3.5098 | 0.34287 | 840.8 | 8.4518 | 0.82564 | 4821.52 | 48.4665 | 4.7346 | 3936.68 | 39.5719 | 3.8657 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 9.7688 | 85
Others:
| 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 28.01 Lakh cum) | km | 29.0746 | 108.969 | 3168.23 | 0.031111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455.04 | 14.3626 | 0.44684 | 900.73 | 28.4301 | 0.88449 | 1033.1022 | 32.6082 | 1.0145 | 779.3578 | 24.5992 | 0.76531 | 100 | 3.1111 | 87
| 4111201 | Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) | km | 26.1065 | 67.11 | 1752.01 | 0.017204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452.46 | 25.8252 | 0.4443 | 913.26 | 52.1264 | 0.8968 | 220.1853 | 12.5676 | 0.21622 | 166.1047 | 9.4808 | 0.16311 | 100 | 1.7204 | 88
| 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 7.43 lakh cum) | km | 25.8917 | 58.272 | 1508.76 | 0.014816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341.85 | 22.6577 | 0.33569 | 657.55 | 43.5821 | 0.6457 | 320.8968 | 21.2689 | 0.31511 | 188.4632 | 12.4913 | 0.18507 | 100 | 1.4816 | 89
| 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 25.68 lakh cum) | km | 44.8195 | 240.472 | 10777.83 | 0.10584 | 0 | 0 | 0 | 0 | 0 | 0 | 336.91 | 3.126 | 0.33084 | 3910 | 36.2782 | 3.8395 | 1880.15 | 17.4446 | 1.8463 | 4650.77 | 43.1513 | 4.5669 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 10.5835 | 90
| 4111201 | Rehabilitation of Regulator (New Haors) | Nos. | 22.0171 | 7 | 154.12 | 0.0015134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 73.26 | 47.5344 | 0.071939 | 0 | 0 | 0 | 50.1332 | 32.5287 | 0.049229 | 30.7268 | 19.9369 | 0.030173 | 100 | 0.15134 | 91
| 4111201 | Embankment Slope Protection Work | Km | 383.2976 | 13.625 | 5222.43 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2924.5608 |  |  | 2297.8692 |  |  |  |  | 92
| 4111201 | Threshing Floor Construction | Nos. | 45 | 20 | 900 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 549 |  |  | 351 |  |  |  |  | 93
| 4111201 | Construction of WMG Office | Nos. | 35 | 60 | 2100 | 0.020621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.09 | 2.0043 | 0.041331 | 348.14 | 16.5781 | 0.34186 | 1008.7643 | 48.0364 | 0.99058 | 701.0057 | 33.3812 | 0.68837 | 100 | 2.0621 | 94
| 4111201 | O & M during Construction | item | 200 | L.S | 200 | 0.0019639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 57 | 0.11194 | 86 | 43 | 0.08445 | 100 | 0.19639 | 95
|  | (b) Sub-total Capital Component: |  |  |  | 81586.88 | 0.74104 | 375.2 |  | 0.36844 | 189.19 |  | 0.18578 | 5714.796 | 261.1646 | 5.6118 | 13501.54 |  | 13.2581 | 15155.124 |  | 14.8819 | 22157.06 |  | 21.7576 | 14366.4009 |  | 10.6965 | 10127.5691 |  | 7.3439 |  |  | 96
|  | Total Cost (a+b) : |  |  |  | 101175.65 | 0.9334 | 1456.29 |  | 1.43 | 2652.93 |  | 2.6051 | 7942.666 | 261.1646 | 7.7995 | 15866.4 |  | 15.5804 | 17642.414 |  | 17.3244 | 24717.06 |  | 24.2715 | 18202.6277 |  | 14.4635 | 12695.2623 |  | 9.8653 |  |  | 97
| 0 | (c) Physical Contingency ( Lump sum): | item | 258 | 0 | 258 | 0.0025335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 162.54 | 63 | 0.15961 | 95.46 | 37 | 0.093739 | 100 | 0.25335 | 98
| 0 | (d) Price Contingency (Lump sum): | item | 402.14 | 0 | 402.14 | 0.0039489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 221.177 | 55 | 0.21719 | 180.963 | 45 | 0.1777 | 100 | 0.39489 | 99
|  | Grand Total (a+b+c+d) : |  |  |  | 101835.79 | 0.93988 | 1456.29 |  | 1.43 | 2652.93 |  | 2.6051 | 7942.666 |  | 7.7995 | 15866.4 |  | 15.5804 | 17642.414 |  | 17.3244 | 24717.06 |  | 24.2715 | 18586.3447 |  | 14.8403 | 12971.6853 |  | 10.1367 |  |  | 100 |  | 92.5579
# Weight of each item = |  | (Est. cost of each respective item)
(Total cost of all Physical items)
# Physical Percentage of item = |  | Quantity/number targeted in each year |  |  |  |  | x 100
Total quantity/number of respective item for whole project period
# Physical % of total Project = |  | Weight of each item x % of item
[10 empty] | 1.43 |  |  | 2.6051 |  |  | 7.7995 |  |  | 15.5804 |  |  | 17.3244 |  |  | 24.2715 |  |  | 18.2513 |  |  | 12.7378 |  | 100

## Inves._Cost
Investment Cost
Name of the Project : |  |  | Haor Flood Management and Livelihood Improvement Project.(BWDB Part)(Revised)
Name of agency/Division/Ministry : |  |  | Bangladesh Water Development Board / Ministry of Water Resources
(In Lakh Taka)
Budget Head | Economic Code/ Sub Code | Code/Sub Code Description | Total Project Cost | Financial | [7 empty] | CF | Economic
|  |  |  | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6 | Year-7 | Year-8 |  | Year-1 | Year-2 | Year-3 | Year-4 | Year-5 | Year-6 | Year-7 | Year-8
(a) Revenue Component:
| 0 | Allowances
| 3111302 | Conveyance Allowance | 5 | 0 | 0.3 | 0.13 | 0.28 | 0.3 | 0.5 | 2.0242 | 1.4658 | 0.902 | 0 | 0.2706 | 0.11726 | 0.25256 | 0.2706 | 0.451 | 1.8258 | 1.3222
| 3111327 | Overtime Allowance | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 3.7 | 0.902 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6826 | 3.3374
| 3111338 | Other Allowance | 140 | 0 | 0 | 0 | 25 | 11.61 | 14 | 53.634 | 35.756 | 0.902 | 0 | 0 | 0 | 22.55 | 10.4722 | 12.628 | 48.3779 | 32.2519
| 0 | Supplies and services:
| 3241101 | Travel Expenses (TA & DA for PMO & PIU) | 120 | 0.991 | 11.909 | 14.98 | 17.96 | 12.7 | 15 | 28.8052 | 17.6548 | 0.902 | 0.89388 | 10.7419 | 13.512 | 16.1999 | 11.4554 | 13.53 | 25.9823 | 15.9246
| 3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | 245 | 0 | 16.25 | 31.35 | 34.86 | 34.21 | 34.25 | 58.3296 | 35.7504 | 0.812 | 0 | 13.195 | 25.4562 | 28.3063 | 27.7785 | 27.811 | 47.3636 | 29.0293
| 3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | 2596.27 | 223.746 | 464.654 | 327.7 | 337.33 | 249.75 | 359.08 | 367.7258 | 266.2842 | 0.812 | 181.6818 | 377.299 | 266.0924 | 273.912 | 202.797 | 291.573 | 298.5933 | 216.2228
| 3211119 | Postage | 5 | 0 | 0.05 | 0.13 | 0.22 | 0.37 | 0.5 | 2.1634 | 1.5666 | 0.812 | 0 | 0.0406 | 0.10556 | 0.17864 | 0.30044 | 0.406 | 1.7567 | 1.2721
| 3211120 | Telephones/Telegram/Teleprinter | 5 | 0.21 | 0.24 | 0.29 | 0.15 | 0.08 | 0.2 | 2.3363 | 1.4937 | 0.812 | 0.17052 | 0.19488 | 0.23548 | 0.1218 | 0.06496 | 0.1624 | 1.8971 | 1.2129
| 3211117 | Telex/Fax/Internet | 5 | 0.249 | 0.001 | 0.09 | 0.05 | 0.05 | 0.2 | 2.4416 | 1.9184 | 0.812 | 0.20219 | 0.000812 | 0.07308 | 0.0406 | 0.0406 | 0.1624 | 1.9826 | 1.5577
| 3221104 | Registration Fee (Vehicles) | 20 | 1.1 | 8.37 | 0.08 | 0 | 2.37 | 1 | 4.4604 | 2.6196 | 0.812 | 0.8932 | 6.7964 | 0.06496 | 0 | 1.9244 | 0.812 | 3.6218 | 2.1271
| 3211115 | Water | 5 | 0 | 0.11 | 0.23 | 0.37 | 0.4 | 0.45 | 2.0984 | 1.3416 | 0.812 | 0 | 0.08932 | 0.18676 | 0.30044 | 0.3248 | 0.3654 | 1.7039 | 1.0894
| 3211113 | Electricity | 20 | 0.187 | 1.683 | 1.78 | 2.31 | 2.78 | 3.5 | 4.268 | 3.492 | 0.812 | 0.15184 | 1.3666 | 1.4454 | 1.8757 | 2.2574 | 2.842 | 3.4656 | 2.8355
| 3243102 | Gas & Fuel | 100 | 0.938 | 3.692 | 3 | 4 | 5.89 | 6 | 46.6528 | 29.8272 | 0.812 | 0.76166 | 2.9979 | 2.436 | 3.248 | 4.7827 | 4.872 | 37.8821 | 24.2197
| 3243101 | Petrol and Lubricant | 200 | 0.625 | 6.995 | 18.97 | 18 | 20 | 20 | 65.7837 | 49.6263 | 0.72 | 0.45 | 5.0364 | 13.6584 | 12.96 | 14.4 | 14.4 | 47.3643 | 35.7309
| 3221108 | Insurance/Bank Charges (including Vehicles) | 3 | 0.081 | 0.749 | 0.01 | 0.22 | 0.1 | 0.15 | 0.9295 | 0.7605 | 0.902 | 0.073062 | 0.6756 | 0.00902 | 0.19844 | 0.0902 | 0.1353 | 0.83841 | 0.68597
| 3255102 | Printing & Binding | 50 | 0.196 | 6.994 | 16.99 | 6 | 3.98 | 0.5 | 9.3574 | 5.9826 | 0.812 | 0.15915 | 5.6791 | 13.7959 | 4.872 | 3.2318 | 0.406 | 7.5982 | 4.8579
| 3255104 | Stationery, Seals & Stamps | 120 | 0.968 | 6.972 | 11.2 | 12.79 | 17.98 | 20 | 31.5567 | 18.5333 | 0.812 | 0.78602 | 5.6613 | 9.0944 | 10.3855 | 14.5998 | 16.24 | 25.624 | 15.049
| 3211127 | Books & Periodicals | 2 | 0 | 0.1 | 0.03 | 0.05 | 0.1 | 0.2 | 0.8816 | 0.6384 | 0.812 | 0 | 0.0812 | 0.02436 | 0.0406 | 0.0812 | 0.1624 | 0.71586 | 0.51838
| 0 | Training Expenditure
|  | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | 238.54 | 0 | 0 | 0 | 0 | 0 | 0 | 138.3532 | 100.1868 | 0.902 | 0 | 0 | 0 | 0 | 0 | 0 | 124.7946 | 90.3685
|  | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | 536.58 | 0 | 9.22 | 29.86 | 86.55 | 175.87 | 196.17 | 23.346 | 15.564 | 0.902 | 0 | 8.3164 | 26.9337 | 78.0681 | 158.6347 | 176.9453 | 21.0581 | 14.0387 | 536.58 | 483.9952 | 0.902 | 483.9952
|  | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | 3139.8 | 0 | 0 | 199.49 | 524.89 | 622.25 | 677.14 | 703.0989 | 412.9311 | 0.902 | 0 | 0 | 179.94 | 473.4508 | 561.2695 | 610.7803 | 634.1952 | 372.4639 | 3139.8 | 2832.0996 | 0.902 | 2832.0996
|  | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | 1321.68 | 0 | 0 | 119.7 | 224.29 | 234.21 | 246.66 | 273.251 | 223.569 | 0.902 | 0 | 0 | 107.9694 | 202.3096 | 211.2574 | 222.4873 | 246.4724 | 201.6592 | 1321.68 | 1192.1554 | 0.902 | 1192.1554
| 3211109 | Casual labour/Job worker | 22 | 0.25 | 2.11 | 2.35 | 2 | 4.25 | 3.5 | 4.6748 | 2.8652 | 0.902 | 0.2255 | 1.9032 | 2.1197 | 1.804 | 3.8335 | 3.157 | 4.2167 | 2.5844
| 3256103 | Consumable Stores | 15 | 0 | 0.99 | 0.75 | 1 | 1 | 3 | 4.7908 | 3.4692 | 0.812 | 0 | 0.80388 | 0.609 | 0.812 | 0.812 | 2.436 | 3.8901 | 2.817 | 15 | 12.18 | 0.812 | 12.18
| 3257101 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) | 7901.4 | 849.675 | 1819.425 | 1123.15 | 689.33 | 686.43 | 500 | 1362.3679 | 871.0221 | 0.902 | 766.4068 | 1641.1213 | 1013.0813 | 621.7757 | 619.1599 | 451 | 1228.8558 | 785.6619 | 7901.4 | 7127.0628 | 0.902 | 7127.0628
| 3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | 30 | 0.4 | 1.33 | 1.5 | 4.5 | 5 | 5 | 7.1166 | 5.1534 | 0.902 | 0.3608 | 1.1997 | 1.353 | 4.059 | 4.51 | 4.51 | 6.4192 | 4.6484 | 30 | 27.06 | 0.902 | 27.06
|  | b) Interim Evaluation | 10 | 0 | 0 | 0.27 | 0.25 | 0.77 | 1 | 4.3176 | 3.3924 | 0.902 | 0 | 0 | 0.24354 | 0.2255 | 0.69454 | 0.902 | 3.8945 | 3.0599
|  | c) Progress Monitoring | 10 | 0 | 0 | 0.3 | 0.25 | 0.75 | 1 | 4.774 | 2.926 | 0.902 | 0 | 0 | 0.2706 | 0.2255 | 0.6765 | 0.902 | 4.3061 | 2.6393
| 4884 | Survey | 200 | 0 | 7.62 | 17.47 | 30 | 29.93 | 50 | 37.0386 | 27.9414 | 0.902 | 0 | 6.8732 | 15.7579 | 27.06 | 26.9969 | 45.1 | 33.4088 | 25.2031
| 3255101 | Computer Consumables | 60 | 0.491 | 1.499 | 4.5 | 6.48 | 7.5 | 10 | 16.2415 | 13.2885 | 0.902 | 0.44288 | 1.3521 | 4.059 | 5.845 | 6.765 | 9.02 | 14.6498 | 11.9862 | 60 | 54.12 | 0.902 | 54.12
| 3256101 | Other Expenses: Salary of Manpower through Outsourcing | 1800 | 0 | 84.32 | 227.97 | 263.24 | 299.93 | 300 | 355.9878 | 268.5522 | 0.86 | 0 | 72.5152 | 196.0542 | 226.3864 | 257.9398 | 258 | 306.1495 | 230.9549 |  | 1548 | 0.86
| 0 | Repair, Maintenance & Rehabilitation:
| 3258101 | Motor Vehicles | 125 | 0.983 | 5.967 | 12 | 21.99 | 20.46 | 15 | 26.73 | 21.87 | 0.86 | 0.84538 | 5.1316 | 10.32 | 18.9114 | 17.5956 | 12.9 | 22.9878 | 18.8082
| 3258102 | Furnitures & Fixtures | 10 | 0 | 0.49 | 0.74 | 0.98 | 0.99 | 2 | 2.88 | 1.92 | 0.86 | 0 | 0.4214 | 0.6364 | 0.8428 | 0.8514 | 1.72 | 2.4768 | 1.6512
| 3258103 | Computers & office equipments | 15 | 0 | 0.5 | 0.85 | 2 | 1.99 | 3 | 3.9294 | 2.7306 | 0.86 | 0 | 0.43 | 0.731 | 1.72 | 1.7114 | 2.58 | 3.3793 | 2.3483
| 3258105 | Machineries & Equipments | 10 | 0 | 0.21 | 0.01 | 0.5 | 0.5 | 2 | 4.1358 | 2.6442 | 0.86 | 0 | 0.1806 | 0.0086 | 0.43 | 0.43 | 1.72 | 3.5568 | 2.274 | 10 | 8.6 | 0.86 | 8.6
| 4921 | Office Building : Repair & Maintenance | 25 | 0 | 0 | 0 | 9.98 | 10 | 0 | 2.9618 | 2.0582 | 0.765 | 0 | 0 | 0 | 7.6347 | 7.65 | 0 | 2.2658 | 1.5745 | 25 | 19.125 | 0.765 | 19.125
| 4923 | Residential Building : Repair & Maintenance | 40 | 0 | 0 | 0 | 8.95 | 5.58 | 5 | 11.8726 | 8.5974 | 0.765 | 0 | 0 | 0 | 6.8467 | 4.2687 | 3.825 | 9.0825 | 6.577 | 40 | 30.6 | 0.765 | 30.6
| 3258105 | Engineering Equipments | 20 | 0 | 0.09 | 0.3 | 0.5 | 0.5 | 2 | 9.1355 | 7.4745 | 0.86 | 0 | 0.0774 | 0.258 | 0.43 | 0.43 | 1.72 | 7.8565 | 6.4281
| 0 | Drainage Structures :
|  | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | 362.5 | 0 | 0 | 59.7 | 24.34 | 10.99 | 58.25 | 131.8086 | 77.4114 | 0.812 | 0 | 0 | 48.4764 | 19.7641 | 8.9239 | 47.299 | 107.0286 | 62.8581 | 362.5 | 294.35 | 0.812 | 294.35
| 4976 | Water Transport : Repair of Speedboat(s) | 5 | 0 | 0.9 | 0 | 0.75 | 0.74 | 0.75 | 1.1346 | 0.7254 | 0.812 | 0 | 0.7308 | 0 | 0.609 | 0.60088 | 0.609 | 0.9213 | 0.58902 | 5 | 4.06 | 0.812 | 4.06
| 4991 | Others : Repair & Maintenance | 40 | 0 | 0 | 0 | 2.5 | 4.98 | 3 | 16.5312 | 12.9888 | 0.902 | 0 | 0 | 0 | 2.255 | 4.492 | 2.706 | 14.9111 | 11.7159 | 40 | 36.08 | 0.902 | 36.08
| (a)Sub-total Revenue Component: |  | 19588.77 | 1081.09 | 2463.74 | 2227.87 | 2364.86 | 2487.29 | 2560 | 3836.2268 | 2567.6932 |  | 954.5047 | 2171.1836 | 1955.1289 | 2076.9077 | 2194.3755 | 2247.2778 | 3369.0536 | 2252.1546 | 19588.77 | 17220.5862 | 0 | 12121.4879
(b) Capital Component:
| 0 | Acquisition of Assets:
| 0 | Motor Vehicle : | [18 empty] | 0 | 0 | 0 | 0
|  | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | 702.5 | 346.3 | 138.6 | 0 | 122 | 0 | 95.6 | 0 | 0 | 0.68 | 235.484 | 94.248 | 0 | 82.96 | 0 | 65.008 | 0 | 0 | 702.5 | 477.7 | 0.68 | 477.7
|  | Motorcycle - 45 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | 68.25 | 5.825 | 26.315 | 10.08 | 8 | 0 | 0 | 10.0968 | 7.9332 | 0.68 | 3.961 | 17.8942 | 6.8544 | 5.44 | 0 | 0 | 6.8658 | 5.3946 | 68.25 | 46.41 | 0.68 | 46.41
| 6809 | Water Transport : |  | Financial Year-1: 0
|  | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | 100 | 0 | 0 | 40.29 | 21 | 0 | 0 | 22.8389 | 15.8711 | 0.68 | 0 | 0 | 27.3972 | 14.28 | 0 | 0 | 15.5305 | 10.7923
| 6813 | Mechinary & Other Equipment |  | Financial Year-1: 0
|  | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 8.97 | 3.726 | 2.744 | 2.48 | 0 | 0 | 0 | 0.0114 | 0.0086 | 0.812 | 3.0255 | 2.2281 | 2.0138 | 0 | 0 | 0 | 0.0092568 | 0.0069832 | 8.97 | 7.2836 | 0.812 | 7.2836
|  | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | 5 | 0.796 | 0 | 0 | 0 | -0.006 | 0 | 2.4418 | 1.7682 | 0.812 | 0.64635 | 0 | 0 | 0 | -0.004872 | 0 | 1.9827 | 1.4358 | 5 | 4.06 | 0.812 | 4.06
| 6814 | Engineering Equipments |  | Financial Year-1: 0
|  | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | 20.5 | 0 | 5.55 | 11.15 | 3.48 | 0 | 0 | 0.1824 | 0.1376 | 0.68 | 0 | 3.774 | 7.582 | 2.3664 | 0 | 0 | 0.12403 | 0.093568 | 20.5 | 13.94 | 0.68 | 13.94
|  | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 6 | 0 | 0 | 0 | 2.13 | 0 | 0 | 2.4381 | 1.4319 | 0.68 | 0 | 0 | 0 | 1.4484 | 0 | 0 | 1.6579 | 0.97369 | 6 | 4.08 | 0.68 | 4.08
|  | Engineering Laboratory Equipments for Kishoregonj WD Division | 50 | 0 | 0 | 0 | 7.89 | 1.6 | 5 | 19.5305 | 15.9795 | 0.68 | 0 | 0 | 0 | 5.3652 | 1.088 | 3.4 | 13.2807 | 10.8661 | 50 | 34 | 0.68 | 34
| 6815 | Computers & Accessories |  | Financial Year-1: 0
|  | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | 19.5 | 3.879 | 7.141 | 6.18 | 2.27 | 0 | 0 | 0.018 | 0.012 | 0.812 | 3.1497 | 5.7985 | 5.0182 | 1.8432 | 0 | 0 | 0.014616 | 0.009744 | 19.5 | 15.834 | 0.812 | 15.834
|  | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | 13.75 | 3.744 | 0 | 2.986 | 3.15 | 0 | 0 | 2.3994 | 1.4706 | 0.812 | 3.0401 | 0 | 2.4246 | 2.5578 | 0 | 0 | 1.9483 | 1.1941 | 13.75 | 11.165 | 0.812 | 11.165
|  | A3 Combo Printer 2 nos ( PMO) | 1.5 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0.715 | 0.585 | 0.812 | 0 | 0.1624 | 0 | 0 | 0 | 0 | 0.58058 | 0.47502 | 1.5 | 1.218 | 0.812 | 1.218
|  | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | 5.25 | 2.97 | 0.2 | 0 | 0.91 | 0 | 0 | 0.6552 | 0.5148 | 0.812 | 2.4116 | 0.1624 | 0 | 0.73892 | 0 | 0 | 0.53202 | 0.41802
| 6821 | Furnitures & Fixtures | 50 | 7.96 | 8.44 | 8.99 | 9.96 | 9.97 | 0 | 2.9016 | 1.7784 | 0.812 | 6.4635 | 6.8533 | 7.2999 | 8.0875 | 8.0956 | 0 | 2.3561 | 1.4441
| 6869 | Aircooler | 15 | 0 | 0 | 3.77 | 2 | 3.96 | 4 | 0.7747 | 0.4953 | 0.812 | 0 | 0 | 3.0612 | 1.624 | 3.2155 | 3.248 | 0.62906 | 0.40218
| 0 | Acquisition/Purchase of lands and landed properties of Assets: |  | Financial Year-1: 0
| 4141101 | Land Acquisition ( 470 hectare) | 24000 | 0 | 0 | 4649.65 | 5794.05 | 3879.9 | 2049.42 | 4499.9182 | 3127.0618 | 0.902 | 0 | 0 | 4193.9843 | 5226.2331 | 3499.6698 | 1848.5768 | 4058.9262 | 2820.6097 | 24000 | 21648 | 0.902 | 21648
| 0 | Construction and Works: |  | Financial Year-1: 0
|  | Irrigation Infrastructurs : |  | Financial Year-1: 0 | [9 empty] | 0 | 0 | 0 | 0
|  | Construction of Irrigation Inlet (New Haors) | 1243.55 | 0 | 0 | 0 | 0 | 116.72 | 490.33 | 350.075 | 286.425 | 0.902 | 0 | 0 | 0 | 0 | 105.2814 | 442.2777 | 315.7677 | 258.3554 | 1310 | 996.91 | 0.761 | 996.91
| 0 | Drainage Structures : |  | Financial Year-1: 0 | [9 empty] | 0 | 0 | 0 | 0
|  | Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | 461.62 | 0 | 0 | 0 | 0 | 0 | 0 | 281.5882 | 180.0318 | 0.765 | 0 | 0 | 0 | 0 | 0 | 0 | 215.415 | 137.7243 | 461.62 | 353.1393 | 0.765 | 353.1393
|  | Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | 19083.95 | 0 | 0 | 293.15 | 2773.9 | 3076.61 | 8105.58 | 2949.1731 | 1885.5369 | 0.765 | 0 | 0 | 224.2597 | 2122.0335 | 2353.6067 | 6200.7687 | 2256.1174 | 1442.4357 | 19083.95 | 14599.2218 | 0.765 | 14599.2217
|  | Re-excavation of Khal/River (New Haors) (Earth Volume: 68.97 Lakh cum) | 9948.16 | 0 | 0 | 349.16 | 840.8 | 4821.52 | 3936.68 | 0 | 0 | 0.761 | 0 | 0 | 265.7108 | 639.8488 | 3669.1767 | 2995.8135 | 0 | 0 | 9948.16 | 7570.5498 | 0.761 | 7570.5498
| 0 | Others: |  | Financial Year-1: 0
|  | Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 28.01 Lakh cum) | 3168.23 | 0 | 0 | 0 | 0 | 455.04 | 900.73 | 1033.1022 | 779.3578 | 0.761 | 0 | 0 | 0 | 0 | 346.2854 | 685.4555 | 786.1908 | 593.0913 | 3168.23 | 2411.023 | 0.761 | 2411.023
|  | Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) | 1752.01 | 0 | 0 | 0 | 0 | 452.46 | 913.26 | 220.1853 | 166.1047 | 0.761 | 0 | 0 | 0 | 0 | 344.3221 | 694.9909 | 167.561 | 126.4057 | 1752.01 | 1333.2796 | 0.761 | 1333.2796
|  | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 7.43 lakh cum) | 1508.76 | 0 | 0 | 0 | 0 | 341.85 | 657.55 | 320.8968 | 188.4632 | 0.761 | 0 | 0 | 0 | 0 | 260.1479 | 500.3955 | 244.2025 | 143.4205 | 1508.76 | 1148.1664 | 0.761 | 1148.1664
|  | Construction of Submersible Embankment (New Haors) (Earth Volume: 25.68 lakh cum) | 10777.83 | 0 | 0 | 336.91 | 3910 | 1880.15 | 4650.77 | 0 | 0 | 0.761 | 0 | 0 | 256.3885 | 2975.51 | 1430.7942 | 3539.236 | 0 | 0 | 10777.83 | 8201.9286 | 0.761 | 8201.9286
|  | Rehabilitation of Regulator (New Haors) | 154.12 | 0 | 0 | 0 | 0 | 73.26 | 0 | 50.1332 | 30.7268 | 0.761 | 0 | 0 | 0 | 0 | 55.7509 | 0 | 38.1514 | 23.3831 | 154.12 | 117.2853 | 0.761 | 117.2853
|  | Construction of WMG Office | 2100 | 0 | 0 | 0 | 0 | 42.09 | 348.14 | 1008.7643 | 701.0057 | 0.765 | 0 | 0 | 0 | 0 | 32.1989 | 266.3271 | 771.7047 | 536.2694 | 2100 | 1606.5 | 0.765 | 1606.5
|  | O & M during Construction | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 86 | 0.761 | 0 | 0 | 0 | 0 | 0 | 0 | 86.754 | 65.446 | 200 | 152.2 | 0.761 | 152.2
(b) Sub-total Capital Component: |  |  | 81586.88 | 375.2 | 189.19 | 5714.796 | 13501.54 | 15155.124 | 22157.06 | 14366.4009 | 10127.5691 |  | 258.1819 | 131.1209 | 5001.9946 | 11090.3369 | 12109.6281 | 17245.4977 | 8986.3022 | 6180.6472
Total Cost (a+b) : |  |  | 101175.65 | 1456.29 | 2652.93 | 7942.666 | 15866.4 | 17642.414 | 24717.06 | 18202.6277 | 12695.2623 |  | 1212.6866 | 2302.3045 | 6957.1235 | 13167.2446 | 14304.0036 | 19492.7755 | 12355.3558 | 8432.8018
(c) Physical Contingency ( Lump sum): |  |  | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 162.54 | 95.46 | 0.765 | 0 | 0 | 0 | 0 | 0 | 0 | 124.3431 | 73.0269
(d) Price Contingency (Lump sum): |  |  | 402.14 | 0 | 0 | 0 | 0 | 0 | 0 | 221.177 | 180.963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total (a+b+c+d) : |  |  | 101835.79 | 1456.29 | 2652.93 | 7942.666 | 15866.4 | 17642.414 | 24717.06 | 18586.3447 | 12971.6853 |  | 1212.6866 | 2302.3045 | 6957.1235 | 13167.2446 | 14304.0036 | 19492.7755 | 12479.6989 | 8505.8287 | 78421.6657 | 101835.79
78421.6657
101835.79

## Crop. Pattern
Area,Yield and Gross Production Value
Gross Area = 185475 ha.& Net Cultivable Area = 156392 ha.
PRE - PROJECT CONDITION
Sl. |  | Area | Yield | Total | Unit Rate (Tk./mt.) |  | Gross Prod. Value(Lakh Tk.)
No. | Crops | (ha.) | (mt./ha.) | Prod. (mt.) | Financial | Economic | Financial | Economic | ML | Seed | Urea | TSP | MP
1. | Boro (L) | 47000 | 3.5 | 164500 | 10000 | 10050 | 16450 | 16532.25 | 5405000 | 1880000 | 9400000 | 7520000 | 4700000
2. | Boro (HYV) | 125000 | 4 | 500000 | 11000 | 11055 | 55000 | 55275 | 18750000 | 5000000 | 37500000 | 30000000 | 18750000
| Total : | 172000 | - | - | - | - | 71450 | 71807.25 | 24155000 | 6880000 | 46900000 | 37520000 | 23450000
|  | Cropping Intensity = |  | 110%
|  | Total Paddy Production = |  |  | 664500 | mt.
Area,Yield and Gross Production Value
Gross Area = 185475 ha.& Net Cultivable Area = 156392 ha.
POST - PROJECT CONDITION
Sl. |  | Area | Yield | Total | Unit Rate (Tk./mt.) |  | Gross Prod. Value(Lakh Tk.)
No. | Crops | (ha.) | (mt./ha.) | Prod. (mt.) | Financial | Economic | Financial | Economic
1. | Boro (HYV) | 280500 | 5.5 | 1542750 | 10000 | 10050 | 154275 | 155046.375 | 43477500 | 11220000 | 84150000 | 67320000 | 42075000
| Total : | 280500 | - | - | - | - | 154275 | 155046.375 | 43477500 | 11220000 | 84150000 | 67320000 | 42075000
|  | Cropping Intensity = |  | 179.357 | %
|  | Total Paddy Production = |  |  | 1542750 | mt.
|  | Incremental Paddy Production = |  |  | 878250 | mt.
Variable Cost of Cultivation
PRE - PROJECT CONDITION
Sl. | Items | Unit | Quantity | Unit Rate (Taka) |  | Total cost (Lakh Taka)
No. |  |  |  | Financial | Economic | Financial | Economic
1. | Manual Labour | Man-day | 24155000 | 100 | 75 | 24155 | 18116.25
2. | Power Tiller | - | - | - | - | 6880 | 6205.76
3. | Seed/Seedlings
a) | Paddy | mt. | 6880 | 30000 | 27060 | 2064 | 1861.728
b) | Wheat | mt. | 0 | 30000 | 27060 | 0 | 0
d) | Mustard | mt. | 0 | 50000 | 45100 | 0 | 0
4. | Fertilizers
a) | Urea | mt. | 46900 | 8000 | 12000 | 3752 | 5628
b) | T.S.P. | mt. | 37520 | 22000 | 33000 | 8254.4 | 12381.6
c) | M.P. | mt. | 23450 | 18000 | 27000 | 4221 | 6331.5
5. | Insecticide | - | - | - | - | 200 | 180.4
6. | Irrigation Cost | - | - | - | - | 500 | 750
| Total | - | - | - | - | 49526.4 | 50705.238
POST - PROJECT CONDITION
Sl. | Items | Unit | Quantity | Unit Rate (Taka) |  | Total cost (Lakh Taka)
No. |  |  |  | Financial | Economic | Financial | Economic
1. | Manual Labour | Man-day | 43477500 | 100 | 75 | 43477.5 | 32608.125
2. | Power Tiller | - | - | - | - | 11220 | 10120.44
3. | Seed/Seedlings
a) | Paddy | mt. | 11220 | 30000 | 27060 | 3366 | 3036.132
b) | Wheat | mt. | 0 | 30000 | 27060 | 0 | 0
c) | Onion | mt. | 0 | 50000 | 45100 | 0 | 0
d) | Jute | mt. | 0 | 50000 | 45100 | 0 | 0
e) | Vegetables | mt. | 0 | 20000 | 18040 | 0 | 0
4. | Fertilizers
a) | Urea | mt. | 84150 | 8000 | 12000 | 6732 | 10098
|  | mt. | 34.61 | 22000 | 19844 | 7.6142 | 6.868
b) | T.S.P. | mt. | 67320 | 22000 | 33000 | 14810.4 | 22215.6
|  | mt. | 34.61 | 200 | 180.4 | 0.06922 | 0.062436
c) | M.P. | mt. | 42075 | 18000 | 27000 | 7573.5 | 11360.25
|  |  | 0 | - | -
|  |  | 0 |  | 0 | 0 | 0
5. | Insecticide | - | - | - | - | 500 | 451
6. | Irrigation Cost | - | - | - | - | 1000 | 1500
| Total | - | - | - |  | 88687.0834 | 91396.4774
| Incremental Farm Labour = |  | 19322500 | mandays
FIXED COST
A. | PRE - PROJECT CONDITION
Sl. | Items |  |  | Financial |  |  | Economic
No.
1. | Rent & rates
2. | Up-keep of stock
3. | Interest on credit
4. | Others
Total per hectare(Taka) |  |  |  | 0 |  |  | 0
Total for the project (Lakh Taka)
| (Net Area= 240578 ha.) |  |  | 0 |  |  | 0
B. | POST - PROJECT CONDITION
Sl. | Items |  |  | Financial |  |  | Economic
No.
1. | Rent & rates
2. | Up-keep of stock
3. | Interest on credit
4. | Others
Total per hectare(Taka) |  |  |  | 0 |  |  | 0
Total for the project (Lakh Taka)
| (Net Area= 240578 ha.) |  |  | 0 |  |  | 0
SUMMARY OF BENEFIT
A. | POST - PROJECT CONDITION
|  |  |  | Financial |  |  | Economic
1. | Gross Production Value |  |  | 154275 |  |  | 155046.375
2. | Cost of cultivation
| i) Variable Cost |  |  | 88687.0834 |  |  | 91396.4774
| ii) Fixed Cost |  |  | 0 |  |  | 0
3. | Net Benefit (A1-A2) |  |  | 65587.9166 |  |  | 63649.8976
B. | PRE - PROJECT CONDITION
1. | Gross Production Value |  |  | 71450 |  |  | 71807.25
2. | Cost of cultivation
| i) Variable Cost |  |  | 49526.4 |  |  | 50705.238
| ii) Fixed Cost |  |  | 0 |  |  | 0
3. | Net Benefit (B1-B2) |  |  | 21923.6 |  |  | 21102.012
C. | Net Incremental Benefit from Agriculture (A3-B3) |  |  | 43664.3166 |  |  | 42547.8856

## FIRR
Computation of Internal Rate of Return
(Financial)
(BDT In Lakh)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1456.29 | 0 | 1456.29 | 0 | 0 | 0 | -1456.29
2 | 2652.93 | 0 | 2652.93 | 0 | 0 | 0 | -2652.93
3 | 7942.666 | 0 | 7942.666 | 0 | 0 | 0 | -7942.666
4 | 15866.4 | 0 | 15866.4 | 0 | 0 | 0 | -15866.4
5 | 17642.414 | 0 | 17642.414 | 0 | 0 | 0 | -17642.414
6 | 24717.06 | 0 | 24717.06 | 21832.1583 | 0 | 21832.1583 | -2884.9017
7 | 18586.3447 | 0 | 18586.3447 | 26198.5899 | 0 | 26198.5899 | 7612.2452
8 | 12971.6853 | 0 | 12971.6853 | 30565.0216 | 0 | 30565.0216 | 17593.3363
9 |  | 670 | 670 | 34931.4533 | 0 | 34931.4533 | 34261.4533
10 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
11 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
12 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
13 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
14 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
15 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
16 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
17 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
18 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
19 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
20 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
21 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
22 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
23 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
24 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
25 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
26 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
27 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
28 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
29 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
30 |  | 670 | 670 | 43664.3166 | 0 | 43664.3166 | 42994.3166
NPV @12% | 55331.7512 | 2068.6546 | 57400.4058 | 166922.8114 | 0 | 166922.8114 | 109522.4056
All calculations are based on project period of 30 years
FIRR base case |  |  | 32.6%
Benefit Cost Ratio |  |  | 2.908
NPV @12% |  |  | 109522.4056

## EIRR
Computation of Internal Rate of Return
(Economic)
(In Lakh Taka)
Year | Invest. Cost | O & M | Total Cost | Benefits from Agriculture | Others Benefits | Total Benefits | Cashflow
1 | 1212.6866 | 0 | 1212.6866 | 0 | 0 | 0 | -1212.6866
2 | 2302.3045 | 0 | 2302.3045 | 0 | 0 | 0 | -2302.3045
3 | 6957.1235 | 0 | 6957.1235 | 0 | 0 | 0 | -6957.1235
4 | 13167.2446 | 0 | 13167.2446 | 0 | 0 | 0 | -13167.2446
5 | 14304.0036 | 0 | 14304.0036 | 0 | 0 | 0 | -14304.0036
6 | 19492.7755 | 0 | 19492.7755 | 21273.9428 | 0 | 21273.9428 | 1781.1673
7 | 12479.6989 | 0 | 12479.6989 | 25528.7313 | 0 | 25528.7313 | 13049.0325
8 | 8505.8287 | 0 | 8505.8287 | 29783.5199 | 0 | 29783.5199 | 21277.6912
9 |  | 604.34 | 604.34 | 34038.3084 | 0 | 34038.3084 | 33433.9684
10 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
11 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
12 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
13 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
14 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
15 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
16 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
17 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
18 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
19 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
20 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
21 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
22 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
23 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
24 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
25 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
26 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
27 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
28 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
29 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
30 |  | 604.34 | 604.34 | 42547.8856 | 0 | 42547.8856 | 41943.5456
NPV @12% | 43310.77 | 1865.9265 | 45176.6964 | 162654.8457 | 0 | 162654.8457 | 117478.1493
All calculations are based on project period of 30 years
EIRR base case |  |  | 37.89%
Benefit Cost Ratio |  |  | 3.6004
NPV @12% |  |  | 117478.1493

## Revised 1st
8.0 Economic code wise comparison of cost summary between the Original DPP and proposed Revised DPP | [27 empty] | (BDT in Lakh)
Economic Code | Economic Sub-Code | Sub-Code wise component description | Original approved DPP | [8 empty] | Proposed 1st Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(a) Revenue Component:
4700 | Allowances
| 4765 | Conveyance Allowance |  | 1 Item | 10 | 10 | [6 empty] | 1 Item | 10 | 10
| 4769 | Overtime Allowance |  | 1 Item | 50 | 50 | [6 empty] | 1 Item | 10 | 10 | [7 empty] | -40 | -40
| 4795 | Other Allowance |  | 1 Item | [8 empty] | 1 Item | 140 | 140 | [7 empty] | 140 | 140
4800 | Supplies and Services
| 4801 | Travel Expenses (TA & DA for PMO & PIU) |  | 1 Item | 100 | 100 | [6 empty] | 1 Item | 100 | 100
| 4806 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | 1 Item | 378 | 378 | [6 empty] | 1 Item | 245 | 245 | [7 empty] | -133 | -133
| 4814 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | 1 Item | 2396.27 | 2396.27 | [6 empty] | 1 Item | 2596.27 | 2596.27 | [7 empty] | 200 | 200
| 4815 | Postage |  | 1 Item | 25 | 25 | [6 empty] | 1 Item | 25 | 25
| 4816 | Telephones/Telegram/Teleprinter |  | 1 Item | 25 | 25 | [6 empty] | 1 Item | 25 | 25
| 4817 | Telex/Fax/Internet |  | 1 Item | 25 | 25 | [6 empty] | 1 Item | 25 | 25
| 4818 | Registration Fee (Vehicles) |  | 1 Item | 10 | 10 | [6 empty] | 1 Item | 15 | 15 | [7 empty] | 5 | 5
| 4819 | Water |  | 1 Item | 10 | 10 | [6 empty] | 1 Item | 10 | 10
| 4821 | Electricity |  | 1 Item | 15 | 15 | [6 empty] | 1 Item | 15 | 15
| 4822 | Gas & Fuel |  | 1 Item | 200 | 200 | [6 empty] | 1 Item | 200 | 200
| 4823 | Petrol and Lubricant |  | 1 Item | 150 | 150 | [6 empty] | 1 Item | 150 | 150
| 4824 | Insurance/Bank Charges (including Vehicles) |  | 1 Item | 3 | 3 | [6 empty] | 1 Item | 3 | 3
| 4827 | Printing & Binding |  | 1 Item | 25 | 25 | [6 empty] | 1 Item | 35 | 35 | [7 empty] | 10 | 10
| 4828 | Stationery, Seals & Stamps |  | 1 Item | 150 | 150 | [6 empty] | 1 Item | 150 | 150
| 4831 | Books & Periodicals |  | 1 Item | 2 | 2 | [6 empty] | 1 Item | 2 | 2
| 4840 | Training Expenditure
|  | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) |  | 1 Item | 238.54 |  |  | 238.54 |  |  |  |  | 1 Item | 238.54 |  |  | 238.54
|  | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  |  | 78 |  |  | 78 | [5 empty] | 398.41 | 47.81 |  | 350.6 | [5 empty] | 320.41 | 47.81 |  | 272.6
|  | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. |  |  | 1815.8 |  |  | 1815.8 | [5 empty] | 2533.34 | 304 |  | 2229.34 | [5 empty] | 717.54 | 304 |  | 413.54
|  | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. |  |  | 298 |  |  | 298 | [5 empty] | 1321.68 | 158.6 |  | 1163.08 | [5 empty] | 1023.68 | 158.6 |  | 865.08
| 4851 | Casual labour/Job worker |  |  | 10 | 10 | [6 empty] | 1 Item | 15 | 15 | [7 empty] | 5 | 5
| 4854 | Consumable Stores |  |  | 25 | 25 | [6 empty] | 1 Item | 25 | 25
| 4874 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) | MM | 71+324 | 7901.4 |  |  | 5904.6 | 1996.8 |  |  | MM | 71+324 | 7901.4 |  |  |  | 7901.4 |  |  |  |  | 0 |  |  | -5904.6 | 5904.6
| 4883 | a) Honorarium/Fees/Remuneration (for different Committee) |  | 1 Item | 25 | 25 | [6 empty] | 1 Item | 25 | 25
|  | b) Interim Evaluation |  | 1 Item | 10 | 10 | [6 empty] | 1 Item | 10 | 10
|  | c) Progress Monitoring |  | 1 Item | 10 | 10 | [6 empty] | 1 Item | 10 | 10
| 4886 | Survey |  | 1 Item | 162 | 162 | [6 empty] | 1 Item | 162 | 162
| 4888 | Computer Consumables |  | 1 Item | 50 | 50 | [6 empty] | 1 Item | 50 | 50
| 4899 | Other Expenses: Salary of Manpower through Outsourcing |  | 1 Item | 912.29 | 912.29 | [6 empty] | 1 Item | 1700 | 1700 | [7 empty] | 787.71 | 787.71
4900 | Repair, Maintenance & Rehabilitation
| 4901 | Motor Vehicles |  | L.S. | 100 | 100 | [6 empty] | L.S. | 100 | 100
| 4906 | Furnitures & Fixtures |  | L.S. | 15 | 15 | [6 empty] | L.S. | 15 | 15
| 4911 | Computers & office equipments |  | L.S. | 25 | 25 | [6 empty] | L.S. | 25 | 25
| 4916 | Machineries & Equipments |  | L.S. | 25 | 25 | [6 empty] | L.S. | 25 | 25
| 4921 | Office Building : Repair & Maintenance |  | L.S. | [8 empty] | L.S. | 20 | 20 | [7 empty] | 20 | 20
| 4923 | Residential Building : Repair & Maintenance |  | L.S. | [8 empty] | L.S. | 20 | 20 | [7 empty] | 20 | 20
| 4932 | Engineering Equipments |  | L.S. | 25 | 25 | [6 empty] | L.S. | 25 | 25
| 4947 | Drainage Structures :
|  | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | 98 | 295.75 | 14.75 |  | 281 |  |  |  | Nos. | 104 | 362.5 | 43.5 |  | 319 | [5 empty] | 66.75 | 28.75 |  | 38
| 4976 | Water Transport : Repair of Speedboat(s) | Nos. | 5 | 10 | 10 | [5 empty] | Nos. | 5 | 10 | 10
| 4991 | Others : Repair & Maintenance | [10 empty] | L.S. | 25 | 25 | [7 empty] | 25 | 25
Sub-total : (a) Revenue Component: |  |  |  |  | 15606.05 | 4993.31 |  | 8615.94 | 1996.8 |  |  |  |  | 18774.14 | 6572.18 |  | 4300.56 | 7901.4 |  |  |  |  | 3168.09 | 1578.87 |  | -4315.38 | 5904.6
Economic Code | Economic Sub-Code | Sub-Code wise component description | Original approved DPP | [8 empty] | Proposed 1st Revised DPP | [8 empty] | Difference
|  |  | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost | [6 empty] | Unit | Qty. | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA | [6 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account* | [7 empty] | Through GOB | Special Account*
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(b) Capital Component:
6800 | Acquisition of Assets:
| 6807 | Motor Vehicle :
|  | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | Nos. | 7 | 702.5 | 702.5 | [5 empty] | Nos. | 10 | 702.5 | 702.5
|  | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | Nos. | 35 | 68.25 | 68.25 | [5 empty] | Nos. | 35 | 68.25 | 68.25
| 6809 | Water Transport :
|  | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | Nos. | 5 | 100 | 100 | [5 empty] | Nos. | 6 | 100 | 100
| 6813 | Mechinary & Other Equipment
|  | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 | 8.97 | 8.97 | [5 empty] | Nos. | 7 | 8.97 | 8.97
|  | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 | 5 | 5 | [5 empty] | Nos. | 7 | 5 | 5
| 6814 | Engineering Equipments
|  | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 17 | 20.5 | 20.5 | [5 empty] | Nos. | 17 | 20.5 | 20.5
|  | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 6 | 6 | 6 | [5 empty] | Nos. | 6 | 6 | 6
|  | Engineering Laboratory Equipments for Kishoregonj WD Division | [10 empty] | L.S. | 50 | 50 | [7 empty] | 50 | 50
| 6815 | Computers & Accessories
|  | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | Nos. | 30 | 19.5 | 19.5 | [5 empty] | Nos. | 30 | 19.5 | 19.5
|  | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 11 | 13.75 | 13.75 | [5 empty] | Nos. | 11 | 13.75 | 13.75
|  | A3 Combo Printer 2 no ( PMO) | Nos. | 1 | 1.5 | 1.5 | [5 empty] | Nos. | 2 | 1.5 | 1.5
|  | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 | 5.25 | 5.25 | [5 empty] | Nos. | 11 | 5.25 | 5.25
| 6821 | Furnitures & Fixtures |  | L.S. | 50 | 50 | [6 empty] | L.S. | 50 | 50
| 6869 | Aircooler |  |  | 15 | 15 | [5 empty] | Nos. | 15 | 15 | 15 | [16 empty] | Ori |  |  | Pro |  | Diff
6900 |  | Acquisition/Purchase of lands and landed properties of Assets:
| 6901 | Land Acquisition ( 408 hectare) | ha. | 408 ha. | 30334.2 | 30334.2 | [5 empty] | ha. | 470 | 24000 | 24000 | [7 empty] | -6334.2 | -6334.2 | [6 empty] | #REF! | #REF! | #REF! | 50 | 371 | 421 | #REF!
7000 |  | Construction and Works:
| 7036 | Irrigation Infrastructures : | [27 empty] | #DIV/0! | 46.5 | 895.5 | 942 | 161 | 1182 | 1343 | 401
|  | Construction of Irrigation Inlet (New Haors) | Nos. | [8 empty] | Nos. | 131 | 1261 | 151.32 |  | 1109.68 | [5 empty] | 1261 | 151.32 |  | 1109.68
| 7041 | Drainage Structures : | [27 empty] | #DIV/0! | 46.5 | 895.5 | 942 | 161 | 1182 | 1343 | 401
|  | Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | Nos. | 5 | 942 | 46.5 |  | 895.5 |  |  |  | Nos. | 7 (2+5) | 1515 | 181.8 |  | 1333.2 | [5 empty] | 573 | 135.3 |  | 437.7 |  |  |  | #DIV/0! | 978.5 | 18871.5 | 19850 | 3398 | 24917 | 28315 | 8465
|  | Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | Nos. | 42 | 19850 | 978.5 |  | 18871.5 |  |  |  | Nos. | 137 (57+35+ 1+44) | 20311 | 2437.32 |  | 17873.68 | [5 empty] | 461 | 1458.82 |  | -997.82 |  |  |  | #DIV/0! | 131 | 2528 | 2659 | 455 | 3337 | 3792 | 1133
|  | Re-excavation of Khal/River (New Haors) (Earth Volume: 76.42 Lakh cum) | Km. | 266 | 2659 | 131 |  | 2528 |  |  |  | Km | 318.2 | 9729 | 1167.48 |  | 8561.52 | [5 empty] | 7070 | 1036.48 |  | 6033.52 |  |  |  | #REF!
| 7081 | Others | [27 empty] | #DIV/0! | 18 | 360 | 378 | 65 | 475.36 | 540.36 | 162.36
|  | Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 20.12 Lakh cum) | Km. | 75.4 | 378 | 18 |  | 360 |  |  |  | Km | 143 | 2515 | 301.8 |  | 2213.2 | [5 empty] | 2137 | 283.8 |  | 1853.2 |  |  |  | #DIV/0! | 3 | 60 | 63 | 11 | 80 | 91 | 28
|  | Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 10.63 lakh cum) | Km. | 1.55 | 63 | 3 |  | 60 |  |  |  | Km | 84.31 | 2550 | 306 |  | 2244 | [5 empty] | 2487 | 303 |  | 2184 |  |  |  | #DIV/0! | 8.25 | 170.25 | 178.5 | 31 | 225 | 256 | 77.5
|  | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 6.44 lakh cum) | Km. | 8.09 | 178.5 | 8.25 |  | 170.25 |  |  |  | Km | 87.03 | 1785 | 214.2 |  | 1570.8 | [5 empty] | 1606.5 | 205.95 |  | 1400.55 |  |  |  | #DIV/0!
|  | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | Km. | 342.3 | 14758.55 | 726.6 |  | 14031.95 |  |  |  | Km | 263.24 | 11952.5 | 1434.3 |  | 10518.2 | [5 empty] | -2806.05 | 707.7 |  | -3513.75 |  |  |  | #REF!
|  | Rehabilitation of Regulator (New Haors) | Nos. | [8 empty] | Nos. | 8 | 166 | 19.92 |  | 146.08 | [5 empty] | 166 | 19.92 |  | 146.08 |  |  |  | #REF! | 8.25 | 170.25 | 178.5 | 31 | 225 | 256 | 77.5
|  | Construction of WMG Office | Nos. | [8 empty] | Nos. | 60 | 1380 | 165.6 |  | 1214.4 | [5 empty] | 1380 | 165.6 |  | 1214.4 |  |  |  |  | 726.6 | 14031.95 | 14758.55 | 2526 | 18527 | 21053 | 6294.45
|  | O & M during Construction |  | L.S. | [8 empty] | L.S. | 200 | 200 | [7 empty] | 200 | 200 | [6 empty] | #REF! | #REF! | #REF! | 6889 | 50521.36 | 57410.36 | #REF!
Sub-total : (b) Capital Component: |  |  |  |  | 70179.47 | 33262.27 |  | 36917.2 | [5 empty] | 78430.72 | 31645.96 |  | 46784.76 | [5 empty] | 8251.25 | -1616.31 |  | 9867.56 | 0
Total Cost (a+b) : |  |  |  |  | 85785.52 | 38255.58 |  | 45533.14 | 1996.8 |  |  |  |  | 97204.86 | 38218.14 |  | 51085.32 | 7901.4 |  |  |  |  | 11419.34 | -37.44 |  | 5552.18 | 5904.6
(c) Physical Contingency ( Lump sum): |  |  |  | L.S. | 2857.84 | 393.04 |  | 2464.8 | [5 empty] | 258 | 100 |  | 158 | [5 empty] | -2599.84 | -293.04 |  | -2306.8
(d) Price Contingency (Lump sum): |  |  |  | L.S. | 10694.36 | 1243 |  | 9451.36 | [5 empty] | 402.14 | 100.76 |  | 301.38 | [5 empty] | -10292.22 | -1142.24 |  | -9149.98
|  | Grand Total : (a)+(b)+(c)+(d): |  |  | 99337.72 | 39891.62 |  | 57449.3 | 1996.8 |  |  |  |  | 97865 | 38418.9 |  | 51544.7 | 7901.4 |  |  |  |  | -1472.72 | -1472.72 |  | -5904.6 | 5904.6
* DOSA, CONTASA, SAFE, IMPREST etc.
|  |  |  | c+d | 39124.8 | 1926.6 |  | 37198.2 | [5 empty] | 53527 | 6423.24 |  | 47103.76 |  |  | 0 |  |  | 14402.2 | 4496.64 |  | 9905.56
|  |  |  | Phy.Works | 39124.8 | 1926.6 |  | 37198.2 |  |  |  |  | Phy.Works | 53727 | 6623.24 |  | 47103.76 |  |  | 0 |  | Phy.Works | 14602.2 | 4696.64 |  | 9905.56
|  |  |  | c+d+works |  | 3853.2 |  | 74396.4 | [6 empty] | 13046.48 |  | 94207.52 |  |  | 0
|  |  |  | other |  | 36038.42 |  | 2430.34 | [8 empty] | 3981.56
[8 empty] | 76826.74 | [8 empty] | 98189.08
[9 empty] | Reh | [7 empty] | Reh | 0
[9 empty] | New | [7 empty] | New | #REF!
[5 empty] | 2191.8 | [8 empty] | 4253.43 |  |  | 3743.02 | 0
#REF!

## Annex-IV
Annexure-IV
Revised Amortization Schedule
Name of Project |  | : Haor Flood Management & Livelihood Improvement Project (BWDB Part)
Total Investment |  | : BDT 97865.00 Lakh
Loan Portion |  | : BDT 59529.60 Lakh
Loan Period |  | : 40 Years Including 10 Uears grace Period
Trate of Investment |  | : 0.01% per annum
(Taka in Lac)
Year | Beginning Principal Amount | Yearly Fixed Amount to be Paid (Principal) | Yearly Interes to be Paid | Total Payment (Principal + Interest) | Ending Principal Balance |  | 2014-15
1 | 2 | 3 | 4 | 5= (3+4) | 6=(2-3) |  | GoB | RPA | DPA | Total
11 | 59529.6 | 1984.32 | 5.953 | 1990.273 | 57545.28 | Rev | 231.42 |  | 849.67 | 1081.09
12 | 57545.28 | 1984.32 | 5.7545 | 1990.0745 | 55560.96 | Cap | 375.2 |  |  | 375.2
13 | 55560.96 | 1984.32 | 5.5561 | 1989.8761 | 53576.64 | Total | 606.62 | 0 | 849.67 | 1456.29
14 | 53576.64 | 1984.32 | 5.3577 | 1989.6777 | 51592.32
15 | 51592.32 | 1984.32 | 5.1592 | 1989.4792 | 49608 |  | 2015-16
16 | 49608 | 1984.32 | 4.9608 | 1989.2808 | 47623.68 |  | GoB | RPA | DPA | Total
17 | 47623.68 | 1984.32 | 4.7624 | 1989.0824 | 45639.36 | Rev | 635.09 | 9.22 | 1849.43 | 2493.74
18 | 45639.36 | 1984.32 | 4.5639 | 1988.8839 | 43655.04 | Cap | 189.19 |  |  | 189.19
19 | 43655.04 | 1984.32 | 4.3655 | 1988.6855 | 41670.72 | Total | 824.28 | 9.22 | 1849.43 | 2682.93
20 | 41670.72 | 1984.32 | 4.1671 | 1988.4871 | 39686.4 | Cum | 1430.9 | 9.22 | 2699.1 | 4139.22
21 | 39686.4 | 1984.32 | 3.9686 | 1988.2886 | 37702.08
22 | 37702.08 | 1984.32 | 3.7702 | 1988.0902 | 35717.76
23 | 35717.76 | 1984.32 | 3.5718 | 1987.8918 | 33733.44 |  | 2016-17
24 | 33733.44 | 1984.32 | 3.3733 | 1987.6933 | 31749.12 |  | GoB | RPA | DPA | Total
25 | 31749.12 | 1984.32 | 3.1749 | 1987.4949 | 29764.8 | Rev | 703.95 | 401.59 | 1093.15 | 2198.69
26 | 29764.8 | 1984.32 | 2.9765 | 1987.2965 | 27780.48 | Cap | 4854.6 | 860.19 |  | 5714.79
27 | 27780.48 | 1984.32 | 2.778 | 1987.098 | 25796.16 | Total | 5558.55 | 1261.78 | 1093.15 | 7913.48
28 | 25796.16 | 1984.32 | 2.5796 | 1986.8996 | 23811.84 | Cum | 6989.45 | 1271 | 3792.25 | 12052.7
29 | 23811.84 | 1984.32 | 2.3812 | 1986.7012 | 21827.52
30 | 21827.52 | 1984.32 | 2.1828 | 1986.5028 | 19843.2 | ADP | 2017-18
31 | 19843.2 | 1984.32 | 1.9843 | 1986.3043 | 17858.88 |  | GoB | RPA | DPA | Total
32 | 17858.88 | 1984.32 | 1.7859 | 1986.1059 | 15874.56 | Rev | 700 | 800 | 800 | 2300
33 | 15874.56 | 1984.32 | 1.5875 | 1985.9075 | 13890.24 | Cap | 10300 | 7400 |  | 17700
34 | 13890.24 | 1984.32 | 1.389 | 1985.709 | 11905.92 | Total | 11000 | 8200 | 800 | 20000
35 | 11905.92 | 1984.32 | 1.1906 | 1985.5106 | 9921.6
36 | 9921.6 | 1984.32 | 0.99216 | 1985.3122 | 7937.28 |  | July2016-Mar17
37 | 7937.28 | 1984.32 | 0.79373 | 1985.1137 | 5952.96 |  | GoB | RPA | DPA | Total
38 | 5952.96 | 1984.32 | 0.5953 | 1984.9153 | 3968.64 | Rev | -166.51 | 790.78 | -1899.1 | -1274.83
39 | 3968.64 | 1984.32 | 0.39686 | 1984.7169 | 1984.32 | Cap | 9735.61 | 7400 | 0 | 17135.61
40 | 1984.32 | 1984.32 | 0.19843 | 1984.5184 | 6.8212e-12 | Total | 9569.1 | 8190.78 | -1899.1 | 15860.78
Total |  | 59529.6 | 92.2709 | 59621.8709
Apr2017-June17
[7 empty] | GoB | RPA | DPA | Total
[6 empty] | Rev | 870.46 | -389.19 | 2992.25 | 3473.52
[6 empty] | Cap | -4881.01 | -6539.81 | 0 | -11420.82
[6 empty] | Total | -4010.55 | -6929 | 2992.25 | -7947.3

## 9.0 Det Ph-Fak
9.0 Item wise Cumulative Progress and Year wise Breakdown of Revised Quantity and Cost to be Incurred. | [18 empty] | Taka in Lac
Economic Code | Economic Sub-Code | Sub-Code wise component description | Cumulative Progress Upto June 15, 2017(Year 1 + Year 2 +Part of Year 3) † | [9 empty] | FY: June 16 to 30, 2017 of 2016-2017 (Remaining Part of Year-3) | [9 empty] | FY: 2017-2018 (Year-4) | [9 empty] | FY: 2018-2019 (Year-5) | [9 empty] | FY: 2019-2020 (Year-6) | [9 empty] | FY: 2020-2021 (Year-7) | [9 empty] | FY: 2021-2022 (Year-8) | [9 empty] | Total
|  |  | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost | [7 empty] | Unit | Quantity (In detail) | Cost
[5 empty] | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  | Total | GOB (FE) | Project Aid |  |  |  | Own Fund | Others |  |  |  | Cost
[7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [7 empty] | RPA |  | DPA | [6 empty] | Total | GOB (FE) | Project Aid |  |  | Own Fund | Others
[7 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [6 empty] | Through GOB | Special Account | Through PD | Through DP | [7 empty] | RPA |  | DPA
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 |  |  |  | 15 | 16 | 17 | 18 | 19 | 20 | 21
(a) Revenue Component:
| 4700 | Allowances
| 4765 | Conveyance Allowance |  | Part | 0.43 | 0.43 | [7 empty] | Part | 0.02 | 0.02 | [7 empty] | Part | 2.4 | 2.4 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 1.15 | 1.15 | [7 empty] | Part | 10 | 10 | [6 empty] | 0 | 0 | 0 | 10 | 10
| 4769 | Overtime Allowance | [21 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 10 | 10 | [6 empty] | 0 | 0 | 0 | 10 | 10
| 4795 | Other Allowance | [21 empty] | Part | 64 | 64 | [7 empty] | Part | 32 | 32 | [7 empty] | Part | 20 | 20 | [7 empty] | Part | 14 | 14 | [7 empty] | Part | 10 | 10 | [7 empty] | Part | 140 | 140 | [6 empty] | -10 | -10 | 0 | 150 | 150
| 4800 | Supplies and services: | [80 empty] | 0 | 0 | 0
| 4801 | Travel Expenses (TA & DA for PMO & PIU) |  | Part | 27.88 | 27.88 | [7 empty] | Part | 0.02 | 1.09 | [7 empty] | Part | 17 | 17 | [7 empty] | Part | 17 | 17 | [7 empty] | Part | 15 | 15 | [7 empty] | Part | 13 | 13 | [7 empty] | Part | 10.1 | 10.1 | [7 empty] | Part | 100 | 101.07 | [6 empty] | 0 | 1.07 | 0 | 100 | 100
| 4806 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years |  | Part | 44.76 | 44.76 | [7 empty] | Part | 2.84 | 2.84 | [7 empty] | Part | 39.4 | 39.4 | [7 empty] | Part | 39.4 | 39.4 | [7 empty] | Part | 39.4 | 39.4 | [7 empty] | Part | 39.6 | 39.6 | [7 empty] | Part | 39.6 | 39.6 | [7 empty] | Part | 245 | 245 | [6 empty] | 0 | 0 | 0 | 245 | 245
| 4814 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) |  | Part | 997.69 | 997.69 | [7 empty] | Part | 18.41 | 30.46 | [7 empty] | Part | 375 | 375 | [7 empty] | Part | 375 | 375 | [7 empty] | Part | 325 | 325 | [7 empty] | Part | 275 | 275 | [7 empty] | Part | 230.17 | 230.17 | [7 empty] | Part | 2596.27 | 2608.32 | [6 empty] | 100 | 112.05 | 0 | 2496.27 | 2496.27
| 4815 | Postage |  | Part | 0.18 | 0.18 | [7 empty] | Part | 0.02 | 0.04 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 4.8 | 4.8 | [7 empty] | Part | 25 | 25.02 | [6 empty] | 0 | 0.02 | 0 | 25 | 25
| 4816 | Telephones/Telegram/Teleprinter |  | Part | 0.59 | 0.59 | [7 empty] | Part | 0.16 | 0.18 | [7 empty] | Part | 6 | 6 | [7 empty] | Part | 6 | 6 | [7 empty] | Part | 4.35 | 4.35 | [7 empty] | Part | 4 | 4 | [7 empty] | Part | 3.9 | 3.9 | [7 empty] | Part | 25 | 25.02 | [6 empty] | 0 | 0.02 | 0 | 25 | 25
| 4817 | Telex/Fax/Internet |  | Part | 0.25 | 0.25 | [7 empty] | Part | 0.1 | 0.1 | [7 empty] | Part | 6 | 6 | [7 empty] | Part | 6 | 6 | [7 empty] | Part | 4.25 | 4.25 | [7 empty] | Part | 4.2 | 4.2 | [7 empty] | Part | 4.2 | 4.2 | [7 empty] | Part | 25 | 25 | [6 empty] | 0 | 0 | 0 | 25 | 25
| 4818 | Registration Fee (Vehicles) |  | Part | 9.55 | 9.55 | [7 empty] | Part | 0.52 | 0.52 | [8 empty] | 2.93 | 2.93 | [48 empty] | 13 | 13 | [6 empty] | 0 | 0 | 0 | 13 | 13
| 4819 | Water |  | Part | 0.3 | 0.3 | [7 empty] | Part | 0.06 | 0.06 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 1.64 | 1.64 | [7 empty] | Part | 10 | 10 | [6 empty] | 0 | 0 | 0 | 10 | 10
| 4821 | Electricity |  | Part | 3.09 | 3.09 | [7 empty] | Part | 0.88 | 0.88 | [7 empty] | Part | 3.13 | 3.13 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 1.9 | 1.9 | [7 empty] | Part | 15 | 15 | [6 empty] | 0 | 0 | 0 | 15 | 15
| 4822 | Gas & Fuel |  | Part | 7.63 | 7.63 | [9 empty] | 0.3 | [7 empty] | Part | 40 | 40 | [7 empty] | Part | 40 | 40 | [7 empty] | Part | 40 | 40 | [7 empty] | Part | 36.37 | 36.37 | [7 empty] | Part | 36 | 36 | [7 empty] | Part | 200 | 200.3 | [6 empty] | 0 | 0.3 | 0 | 200 | 200
| 4823 | Petrol and Lubricant |  | Part | 25.42 | 25.42 | [7 empty] | Part | 1.2 | 2.77 | [7 empty] | Part | 27 | 27 | [7 empty] | Part | 25 | 25 | [7 empty] | Part | 23.38 | 23.38 | [7 empty] | Part | 23 | 23 | [7 empty] | Part | 25 | 25 | [7 empty] | Part | 150 | 151.57 | [6 empty] | 0 | 1.57 | 0 | 150 | 150
| 4824 | Insurance/Bank Charges (including Vehicles) |  | Part | 0.83 | 0.83 | [7 empty] | Part | 0.75 | 0.75 | [7 empty] | Part | 1 | 1 | [7 empty] | Part | 0.42 | 0.42 | [38 empty] | 3 | 3 | [6 empty] | 0 | 0 | 0 | 3 | 3
| 4827 | Printing & Binding |  | Part | 18.3 | 18.3 | [7 empty] | Part | 5.89 | 6.01 | [7 empty] | Part | 4 | 4 | [7 empty] | Part | 2.5 | 2.5 | [7 empty] | Part | 2.31 | 2.31 | [7 empty] | Part | 2 | 2 | [17 empty] | Part | 35 | 35.12 | [6 empty] | 0 | 0.12 | 0 | 35 | 35
| 4828 | Stationery, Seals & Stamps |  | Part | 17.43 | 17.43 | [7 empty] | Part | 2.51 | 2.9 | [7 empty] | Part | 30 | 30 | [7 empty] | Part | 30 | 30 | [7 empty] | Part | 25 | 25 | [7 empty] | Part | 25 | 25 | [7 empty] | Part | 20.06 | 20.06 | [7 empty] | Part | 150 | 150.39 | [6 empty] | 0 | 0.39 | 0 | 150 | 150
| 4831 | Books & Periodicals |  | Part | 0.11 | 0.11 | [7 empty] | Part | 0.02 | 0.03 | [7 empty] | Part | 0.35 | 0.35 | [7 empty] | Part | 0.35 | 0.35 | [7 empty] | Part | 0.35 | 0.35 | [7 empty] | Part | 0.5 | 0.5 | [7 empty] | Part | 0.32 | 0.32 | [7 empty] | Part | 2 | 2.01 | [6 empty] | 0 | 0.01 | 0 | 2 | 2
| 4840 | Training Expenditure | [80 empty] | 0 | 0 | 0
|  | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | [22 empty] | 238.54 |  |  | 238.54 | [46 empty] | 238.54 |  |  | 238.54 |  |  |  |  | 0 | 0 | 0 | 238.54 |  |  | 238.54
|  | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) |  | Part | 34.72 |  |  | 34.72 | [5 empty] | Part | 4.5 |  |  | 4.5 | [5 empty] | Part | 178.45 | 14.45 |  | 164 | [5 empty] | Part | 134.85 | 10.85 |  | 124 | [5 empty] | Part | 126.25 | 10.85 |  | 115.4 | [5 empty] | Part | 228.62 | 21.22 |  | 207.4 | [5 empty] | Part | 107.85 | 7.85 |  | 100 | [5 empty] | Part | 815.24 | 65.22 |  | 750.02 |  |  |  |  | 0 | 0 | 0 | 815.24 | 65.22 |  | 750.02
|  | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme. |  | Part | 196.5 |  |  | 196.5 | [5 empty] | Part | 3 |  |  | 3 | [5 empty] | Part | 459.3 | 34.3 |  | 425 | [5 empty] | Part | 404.34 | 29.34 |  | 375 | [5 empty] | Part | 404.34 | 29.34 |  | 375 | [5 empty] | Part | 376.6 | 42.27 |  | 334.33 | [5 empty] | Part | 337.06 | 39.25 |  | 297.81 | [5 empty] | Part | 2181.14 | 174.5 |  | 2006.64 |  |  |  |  | 0 | 0 | 0 | 2181.14 | 174.5 |  | 2006.64
|  | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme. |  | Part | 118 |  |  | 118 | [5 empty] | Part | 1.7 |  |  | 1.7 | [5 empty] | Part | 193.96 | 15.5 |  | 178.46 | [5 empty] | Part | 185.86 | 14.86 |  | 171 | [5 empty] | Part | 178.23 | 14.26 |  | 163.97 | [5 empty] | Part | 185.17 | 21.05 |  | 164.12 | [5 empty] | Part | 209.21 | 20.1 |  | 189.11 | [5 empty] | Part | 1072.13 | 85.77 |  | 986.36 |  |  |  |  | 0 | 0 | 0 | 1072.13 | 85.77 |  | 986.36
| 4849 | Compensation (Crop etc.) | [21 empty] | Part | 400 | 400 | [7 empty] | Part | 50 | 50 | [8 empty] | 0 | 0 | [8 empty] | 0 | 0 | [8 empty] | 0 | 0 | [8 empty] | 450 | 450 | [6 empty] | 0 | 0 | 0 | 450 | 450
| 4851 | Casual labour/Job worker |  | Part | 3.97 | 3.97 | [7 empty] | Part | 0.74 | 0.74 | [7 empty] | Part | 1.25 | 1.25 | [7 empty] | Part | 1.25 | 1.25 | [7 empty] | Part | 1.25 | 1.25 | [7 empty] | Part | 1.05 | 1.05 |  | 0 | [5 empty] | Part | 0.49 | 0.49 | [7 empty] | Part | 10 | 10 | [6 empty] | 0 | 0 | 0 | 10 | 10
| 4854 | Consumable Stores |  | Part | 1.21 | 1.21 | [7 empty] | Part | 0.53 | 0.53 | [7 empty] | Part | 8 | 8 | [7 empty] | Part | 8 | 8 | [7 empty] | Part | 6 | 6 | [7 empty] | Part | 1.26 | 1.26 |  | 0 | [6 empty] | 0 | 0 |  | 0 | [6 empty] | 25 | 25 | [6 empty] | 0 | 0 | 0 | 25 | 25
| 4874 | Consultancy : International - 71 M/M (Detail in Appendix-E of original approved DPP) National - 324 M/M (Detail in Appendix-E of original approved DPP) | MM | Part | 3793.31 |  |  |  | 3793.31 |  |  |  | MM | Part | 5.79 |  |  |  | 5.79 |  |  |  | MM | Part | 900 | 0 |  |  | 900 |  |  |  | MM | Part | 1000 |  |  |  | 1000 |  |  |  | MM | Part | 1000 | 0 |  |  | 1000 |  |  |  | MM | Part | 1000 | 0 |  | 0 | 1000 |  |  |  | MM | Part | 202.3 | 0 |  | 0 | 202.3 |  |  |  |  | Part | 7901.4 |  |  |  | 7901.4 |  |  |  | 0 | 0 | 0 | 7901.4 |  |  |  | 7901.4
| 4883 | a) Honorarium/Fees/Remuneration (for different Committee) |  | Part | 3.23 | 3.23 | [17 empty] | Part | 4.77 | 4.77 | [7 empty] | Part | 4 | 4 | [7 empty] | Part | 4 | 4 | [7 empty] | Part | 4 | 4 |  | 0 | [5 empty] | Part | 5 | 5 |  | 0 | [5 empty] | Part | 25 | 25 |  | 0 |  |  |  |  | 0 | 0 | 0 | 25 | 25
|  | b) Interim Evaluation | [11 empty] | Part | 0.5 | 0.5 | [7 empty] | Part | 5 | 5 | [8 empty] | 2.5 | 2.5 | [8 empty] | 2 | 2 | [8 empty] | 0 | 0 |  | 0 | [5 empty] | Part |  |  |  | 0 | [5 empty] | Part | 10 | 10 |  | 0 |  |  |  |  | 0 | 0 | 0 | 10 | 10
|  | c) Progress Monitoring | [11 empty] | Part | 0.5 | 0.5 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 | [7 empty] | Part | 2 | 2 |  | 0 | [5 empty] | Part | 1.5 | 1.5 |  | 0 | [5 empty] | Part | 10 | 10 |  | 0 |  |  |  |  | 0 | 0 | 0 | 10 | 10
| 4884 | Survey |  | Part | 13.86 | 13.86 | [7 empty] | Part | 13.76 | 13.76 | [7 empty] | Part | 45 | 45 | [7 empty] | Part | 45 | 45 | [7 empty] | Part | 44.38 | 44.38 | [8 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | [6 empty] | 162 | 162 |  | 0 |  |  |  |  | 0 | 0 | 0 | 162 | 162
| 4888 | Computer Consumables |  | Part | 6.37 | 6.37 | [7 empty] | Part | 0.12 | 0.12 | [7 empty] | Part | 10 | 10 | [7 empty] | Part | 10 | 10 | [7 empty] | Part | 10 | 10 | [7 empty] | Part | 8 | 8 |  | 0 | [5 empty] | Part | 5.51 | 5.51 |  | 0 | [5 empty] | Part | 50 | 50 |  | 0 |  |  |  |  | 0 | 0 | 0 | 50 | 50
| 4899 | Other Expenses: Salary of Manpower through Outsourcing |  | Part | 310.68 | 310.68 | [7 empty] | Part | 1.61 | 1.61 | [7 empty] | Part | 290 | 290 | [7 empty] | Part | 290 | 290 | [7 empty] | Part | 290 | 290 | [7 empty] | Part | 290 | 290 |  | 0 | [5 empty] | Part | 227.71 | 227.71 |  | 0 | [5 empty] | Part | 1700 | 1700 |  | 0 |  |  |  |  | 0 | 0 | 0 | 1700 | 1700
| 4900 | Repair, Maintenance & Rehabilitation: | [80 empty] | 0 | 0 | 0
| 4901 | Motor Vehicles |  | Part | 18.84 | 18.84 | [7 empty] | Part | 0.11 | 0.11 | [7 empty] | Part | 15 | 15 | [7 empty] | Part | 17 | 17 | [7 empty] | Part | 18 | 18 | [7 empty] | Part | 18 | 18 |  | 0 | [5 empty] | Part | 13.05 | 13.05 |  | 0 | [5 empty] | Part | 100 | 100 |  | 0 |  |  |  |  | 0 | 0 | 0 | 100 | 100
| 4906 | Furnitures & Fixtures |  | Part | 1.11 | 1.11 | [7 empty] | Part | 0.13 | 0.13 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 3.76 | 3.76 | [8 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | [6 empty] | 15 | 15 |  | 0 |  |  |  |  | 0 | 0 | 0 | 15 | 15
| 4911 | Computers & office equipments |  | Part | 1.35 | 1.35 | [17 empty] | Part | 3 | 3 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 5 | 5 |  | 0 | [5 empty] | Part | 5.65 | 5.65 |  | 0 | [5 empty] | Part | 25 | 25 |  | 0 |  |  |  |  | 0 | 0 | 0 | 25 | 25
| 4916 | Machineries & Equipments |  | Part | 0.28 | 0.28 | [7 empty] | Part | 0.53 | 0.53 | [7 empty] | Part | 3 | 3 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 5 | 5 |  | 0 | [5 empty] | Part | 6.19 | 6.19 |  | 0 | [5 empty] | Part | 25 | 25 |  | 0 |  |  |  |  | 0 | 0 | 0 | 25 | 25
| 4921 | Office Building : Repair & Maintenance | [21 empty] | Part | 10 | 10 | [7 empty] | Part | 3 | 3 | [7 empty] | Part | 3 | 3 | [7 empty] | Part | 2 | 2 |  | 0 | [5 empty] | Part | 2 | 2 |  | 0 | [5 empty] | Part | 20 | 20 |  | 0 |  |  |  |  | 0 | 0 | 0 | 20 | 20
| 4923 | Residential Building : Repair & Maintenance | [21 empty] | Part | 10 | 10 | [7 empty] | Part | 3 | 3 | [7 empty] | Part | 3 | 3 | [7 empty] | Part | 2 | 2 |  | 0 | [5 empty] | Part | 2 | 2 |  | 0 | [5 empty] | Part | 20 | 20 |  | 0 |  |  |  |  | 0 | 0 | 0 | 20 | 20
| 4932 | Engineering Equipments |  | Part | 0.37 | 0.37 | [7 empty] | Part | 0.02 | 0.02 | [7 empty] | Part | 3 | 3 | [7 empty] | Part | 6 | 6 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 5 | 5 |  | 0 | [5 empty] | Part | 5.61 | 5.61 |  | 0 | [5 empty] | Part | 25 | 25 |  | 0 |  |  |  |  | 0 | 0 | 0 | 25 | 25
| 4947 | Drainage Structures : | [22 empty] | 0 | [57 empty] | 0 | 0 | 0
|  | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | Nos. | Part | 30 | 3.6 |  | 26.4 |  |  |  |  | Nos. |  | 30 | 3.6 |  | 26.4 |  |  |  |  | Nos. | Part | 262 | 32 |  | 230 |  |  |  |  | Nos. | Part | 63 | 7 |  | 56 |  |  |  |  | Nos. | [9 empty] | Nos. | [9 empty] | Nos. | [11 empty] | 385 | 46.2 |  | 338.8 |  |  |  |  | 0 | 0 | 0 | 385 | 46.2 |  | 338.8
| 4976 | Water Transport : Repair of Speedboat(s) | Nos. | Part | 0.9 | 0.9 | [6 empty] | Nos. | Part | 0.75 | 0.75 | [6 empty] | Nos. | Part | 2 | 2 | [6 empty] | Nos. | Part | 2 | 2 | [6 empty] | Nos. | Part | 2 | 2 | [6 empty] | Nos. | Part | 2 | 2 |  | 0 |  |  |  |  | Nos. | Part | 0.35 | 0.35 |  | 0 | [5 empty] | Part | 10 | 10 | [6 empty] | 0 | 0 | 0 | 10 | 10
| 4991 | Others : Repair & Maintenance |  | Part | [9 empty] | Part | [9 empty] | Part | 10 | 10 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 5 | 5 | [7 empty] | Part | 3 | 3 |  | 0 | [5 empty] | Part | 2 | 2 |  | 0 | 0 |  |  |  |  | Part | 25 | 25 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 25 | 25
(a) Sub-total Revenue Component: |  |  |  |  | 5689.14 | 1520.21 |  | 375.62 | 3793.31 | [5 empty] | 97.69 | 71.85 |  | 35.6 | 5.79 | [5 empty] | 3686.48 | 1550.48 |  | 1236 | 900 | [5 empty] | 2838.47 | 1112.47 |  | 726 | 1000 | [5 empty] | 2630.25 | 975.88 |  | 654.37 | 1000 | [5 empty] | 2588.37 | 882.52 | 0 | 705.85 | 1000 | [5 empty] | 1524.32 | 735.1 | 0 | 586.92 | 202.3 | [5 empty] | 19054.72 | 6848.51 | 0 | 4320.36 | 7901.4 |  |  |  | 90 | 105.55 | 0 | 18964.72 | 6742.96 |  | 4320.36 | 7901.4
(b) Capital Component: | [82 empty] | 0 | 0 | 0
| 6800 | Acquisition of Assets: | [80 empty] | 0 | 0 | 0
| 6807 | Motor Vehicle : | [80 empty] | 0 | 0 | 0
|  | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO and Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. (PMO 2 Nos., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No.& Deputy Chief(Extension Officer) 1 No.) | Nos. | 7 nos. | 484.9 | 484.9 | [6 empty] | Nos. | [9 empty] | Nos. | 2 nos | 165.1 | 165.1 | [48 empty] | 650 | 650 | [6 empty] | #REF! | #REF! | #REF! | 385 | 46.2 |  | 338.8
|  | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | Nos. | 26 nos | 35.46 | 35.46 | [6 empty] | Nos. | 9 nos. | 15.68 | 15.68 | [6 empty] | Nos. | - | 17.11 | 17.11 | [48 empty] | 68.25 | 68.25 | [6 empty] | #REF! | #REF! | #REF! | 385 | 46.2 |  | 338.8
| 6809 | Water Transport : | [80 empty] | #REF! | #REF! | #REF!
|  | Speed Boat with Engine and all accessories (75 hp & 5 Nos.) | Nos. | 2 nos. | 27.9 | 27.9 | [6 empty] | Nos. | 1 no. | 17.1 | 17.1 | [6 empty] | Nos. | 2 nos | 30 | 30 | [48 empty] | 75 | 75 | [6 empty] | #REF! | #REF! | #REF! | 385 | 46.2 |  | 338.8
| 6813 | Mechinary & Other Equipment | [80 empty] | #REF! | #REF! | #REF!
|  | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 7 nos. | 8.97 | 8.97 | [16 empty] | Nos. |  | 0 | 0 | [48 empty] | 8.97 | 8.97 | [6 empty] | #REF! | #REF! | #REF! | 385 | 46.2 |  | 338.8
|  | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | Nos. | 2 nos. | 0.79 | 0.79 | [6 empty] | Nos. | 1 no. | 0.5 | 0.5 | [6 empty] | Nos. | 4 nos. | 3.71 | 3.71 | [48 empty] | 5 | 5 | [6 empty] | #REF! | #REF! | #REF! | 385 | 46.2 |  | 338.8
| 6814 | Engineering Equipments | [80 empty] | -385 | -46.2 | -338.8
|  | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | Nos. | 9 nos. | 11.7 | 11.7 | [6 empty] | Nos. | 2 nos. | 5 | 5 | [6 empty] | Nos. | 6 nos. | 3.8 | 3.8 | [48 empty] | 20.5 | 20.5 | [6 empty] | -364.5 | -25.7 | -338.8 | 385 | 46.2 |  | 338.8
|  | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | [20 empty] | Nos. | 6 nos. | 6 | 6 | [48 empty] | 6 | 6 | [6 empty] | -379 | -40.2 | -338.8 | 385 | 46.2 |  | 338.8
|  | Engineering Laboratory Equipment 33 Nos. | [20 empty] | Nos. | 33 nos. | 36 | 36 | [48 empty] | 36 | 36 | [6 empty] | 36 | 36 | 0 | 385 | 46.2 |  | 338.8
| 6815 | Computers & Accessories | [80 empty] | -385 | -46.2 | -338.8
|  | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | Nos. | 27 nos. | 17.2 | 17.2 | [8 empty] | 0.02 | 0.02 | [6 empty] | Nos. | 3 nos. | 2.28 | 2.28 | [48 empty] | 19.5 | 19.5 | [6 empty] | 19.5 | 19.5 | 0 | 385 | 46.2 |  | 338.8
|  | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | Nos. | 7 nos. | 6.75 | 6.75 | [16 empty] | Nos. | 4 nos. | 7 | 7 | [48 empty] | 13.75 | 13.75 | [6 empty] | -371.25 | -32.45 | -338.8 | 385 | 46.2 |  | 338.8
|  | A3 Combo Printer 1 no ( PMO) | No. | 1 no. | 0.2 | 0.2 | [16 empty] | No. | - | 1.3 | 1.3 | [48 empty] | 1.5 | 1.5 | [6 empty] | -383.5 | -44.7 | -338.8 | 385 | 46.2 |  | 338.8
|  | Laser Printer- 7 nos. (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | Nos. | 7 nos. | 3.17 | 3.17 | [16 empty] | Nos. | - | 2.08 | 2.08 | [48 empty] | 5.25 | 5.25 | [6 empty] | 5.25 | 5.25 | 0 | 385 | 46.2 |  | 338.8
| 6821 | Furnitures & Fixtures |  | Part | 21.44 | 21.44 | [7 empty] | Part | 3.96 | 3.96 | [7 empty] | Part | 10 | 10 | [7 empty] | Part | 4.6 | 4.6 | [7 empty] | Part | 10 | 10 | [28 empty] | 50 | 50 | [6 empty] | -335 | 3.8 | -338.8 | 385 | 46.2 |  | 338.8
| 6869 | Aircooler |  |  | 0 | 0 | [7 empty] | Part | 4 | 4 | [7 empty] | Part | 6 | 6 | [7 empty] | Part | 5 | 5 | [38 empty] | 15 | 15 | [6 empty] | -370 | -31.2 | -338.8 | 385 | 46.2 |  | 338.8
| 6900 | Acquisition/Purchase of lands and landed properties of Assets: | [80 empty] | 0 | 0 | 0
| 6901 | Land Acquisition ( 470 hectare) | ha. | Part | 4649 | 4649 | [6 empty] | ha. | Part | 0.65 | 0.65 | [6 empty] | ha. | Part | 10841.26 | 10841.26 | [6 empty] | ha. | Part | 4577.87 | 4577.87 | [6 empty] | ha. |  | 3931.22 | 3931.22 | [28 empty] | 24000 | 24000 |  | 0 |  |  |  |  | 23615 | 23953.8 | -338.8 | 385 | 46.2 |  | 338.8
| 7000 | Construction and Works: | [80 empty] | -385 | -46.2 | -338.8
| 7041 | Drainage Structures : | [80 empty] | -385 | -46.2 | -338.8
|  | Re-installation/Construction of Regulator (Rehabilitation Haors) | [20 empty] | No. | Part | 375 | 45 |  | 330 |  |  |  |  | No. | Part | 190 | 22.8 |  | 167.2 | [36 empty] | 565 | 67.8 |  | 497.2 |  |  |  |  | 180 | 21.6 | 158.4 | 375 | 45 |  | 330
|  | Installation/Construction of New Regulators/Causeway/Bridge (New Haors) | Nos. | Part | 167.62 | 19.69 |  | 147.93 |  |  |  |  | Nos. | Part | 1012.38 | 160.31 |  | 852.07 |  |  |  |  | Nos. | Part | 2840.88 | 340.88 |  | 2500 |  |  |  |  | Nos. | Part | 11233 | 1348 |  | 9885 |  |  |  |  | Nos. | Part | 1527.12 | 144.84 |  | 1382.28 | [26 empty] | 16781 | 2013.72 |  | 14767.28 |  |  |  |  | 16396 | 1967.52 | 14428.48 | 385 | 46.2 |  | 338.8
|  | Re-excavation of Khal/River (New Haors) | Km. | Part | 482.08 | 57.86 |  | 424.22 |  |  |  |  | Km. | Part | 497.92 | 72.14 |  | 425.78 |  |  |  |  | Km. | Part | 2840 | 340 |  | 2500 |  |  |  |  | Km. | Part | 921.06 | 109.7 |  | 811.36 |  |  |  |  | Km. | Part | 3488.05 | 368.54 |  | 3119.51 |  |  |  |  | Km. | Part | 3233.89 | 427.32 |  | 2806.57 | [16 empty] | 11463 | 1375.56 |  | 10087.44 |  |  |  |  | 11078 | 1329.36 | 9748.64 | 385 | 46.2 |  | 338.8
|  | Construction of Pipe Sluice/Culvert (New Haors) | [30 empty] | Nos. | 45 | 1350 | 162 |  | 1188 | [36 empty] | 1350 | 162 |  | 1188 |  |  |  |  | 1350 | 162 | 1188 | 385 | 46.2 |  | 338.8
|  | Construction of Irrigation Inlet (New Haors) | [30 empty] | Nos. | 131 | 1310 | 157.2 |  | 1152.8 | [36 empty] | 1310 | 157.2 |  | 1152.8 |  |  |  |  | 925 | 111 | 814 | 385 | 46.2 |  | 338.8
| 7081 | Others: | [80 empty] | 0 | 0 | 0 | 385 | 46.2 |  | 338.8
|  | Re-excavation of Khal/River (Rehabilitation Haors) | [20 empty] | Km. | Part | 910 | 110 |  | 800 |  |  |  |  | Km. | Part | 1076 | 128.32 |  | 947.68 | [36 empty] | 1986 | 238.32 |  | 1747.68 |  |  |  |  | 1986 | 238.32 | 1747.68 | 385 | 46.2 |  | 338.8
|  | Rehabilitation of Full Embankment (Rehabilitation Haors) | [20 empty] | Km. | Part | 910 | 110 |  | 800 |  |  |  |  | Km. | Part | 1040 | 124 |  | 916 | [36 empty] | 1950 | 234 |  | 1716 |  |  |  |  | 1575 | 189 | 1386 | 385 | 46.2 |  | 338.8
|  | Rehabilitation of Submergible Embankment (Rehabilitation Haors) | [20 empty] | Km. | Part | 568 | 68 |  | 500 |  |  |  |  | Km. | Part | 470 | 56.56 |  | 413.44 | [36 empty] | 1038 | 124.56 |  | 913.44 |  |  |  |  | 653 | 78.36 | 574.64 | 385 | 46.2 |  | 338.8
|  | Construction of Submersible Embankment (New Haors) | Km. | Part | 284.04 | 34.09 |  | 249.95 |  |  |  |  | Km. | Part | 1393.96 | 195.91 |  | 1198.05 |  |  |  |  | Km. | Part | 768 | 68 |  | 700 |  |  |  |  | Km. | Part | 4941 | 588.12 |  | 4352.88 |  |  |  |  | Km. |  | 3829.36 | 379.52 |  | 3449.84 |  |  |  |  | Km. |  | 1664.08 | 246.5 |  | 1417.58 |  |  |  |  | Km. |  | 1451.56 | 207.7 |  | 1243.86 | [6 empty] | 14332 | 1719.84 |  | 12612.16 |  |  |  |  | 13947 | 1673.64 | 12273.36 | 385 | 46.2 |  | 338.8
|  | Rehab./Construction of Closure (New Haors) | [20 empty] | Nos. | [9 empty] | Nos. |  | 88 | 10.56 |  | 77.44 |  |  |  |  | Nos. | [9 empty] | Nos. | [9 empty] | Nos. | [11 empty] | 88 | 10.56 |  | 77.44 |  |  |  |  | -297 | -35.64 | -261.36 | 385 | 46.2 |  | 338.8
|  | Rehabilitation of Regulator (New Haors) | [20 empty] | Nos. | [9 empty] | Nos. |  | 190 | 22.8 |  | 167.2 |  |  |  |  | Nos. | [9 empty] | Nos. | [9 empty] | Nos. | [11 empty] | 190 | 22.8 |  | 167.2 |  |  |  |  | -195 | -23.4 | -171.6 | 385 | 46.2 |  | 338.8
|  | Construction of WMG Office | [20 empty] | Nos. | Part | 1970 | 236 |  | 1734 |  |  |  |  | Nos. |  | 130 | 16 |  | 114 |  |  |  |  | Nos. | [9 empty] | Nos. | [9 empty] | Nos. | [11 empty] | 2100 | 252 |  | 1848 |  |  |  |  | 1715 | 205.8 | 1509.2 | 385 | 46.2 |  | 338.8
|  | O & M during Construction | L.S. | [30 empty] | Part | 400 | 400 | [8 empty] | 400 | 400 | [8 empty] | 100 | 100 | [8 empty] | 100 | 100 | [8 empty] | 1000 | 1000 | [6 empty] | 615 | 953.8 | -338.8 | 385 | 46.2 |  | 338.8
(b)Sub-total Capital Component: |  |  |  |  | 6201.22 | 5379.12 |  | 822.1 | [6 empty] | 2951.17 | 475.27 |  | 2475.9 | 0 | [5 empty] | 22313.52 | 12449.52 |  | 9864 | 0 | [5 empty] | 27926.53 | 7733.53 |  | 20193 | 0 | [5 empty] | 13185.75 | 5234.12 |  | 7951.63 | 0 | [5 empty] | 4997.97 | 773.82 |  | 4224.15 | 0 | [5 empty] | 1551.56 | 307.7 |  | 1243.86 | 0 | [5 empty] | 79127.72 | 32353.08 |  | 46774.64 | 0 |  |  |  | 78742.72 | 32306.88 | 46435.84 | 19349.72 | 6789.16 |  | 4659.16 | 7901.4
Total Cost (a+b) : |  |  |  |  | 11890.36 | 6899.33 |  | 1197.72 | 3793.31 | [5 empty] | 3048.86 | 547.12 |  | 2511.5 | 5.79 | [5 empty] | 26000 | 14000 |  | 11100 | 900 | [5 empty] | 30765 | 8846 |  | 20919 | 1000 | [5 empty] | 15816 | 6210 |  | 8606 | 1000 | [5 empty] | 7586.34 | 1656.34 |  | 4930 | 1000 | [5 empty] | 3075.88 | 1042.8 |  | 1830.78 | 202.3 | [5 empty] | 98182.44 | 39201.59 |  | 51095 | 7901.4 |  |  |  | 97797.44 | 39155.39 | 50756.2 | 365 | 175 |  | 190
(c) Physical Contingency ( Lump sum): | [34 empty] | 55 | 10 |  | 45 | [6 empty] | 45 | 15 |  | 30 | [6 empty] | 36 | 16 |  | 20 | [6 empty] | 115 | 100 |  | 15 | [6 empty] | 251 | 141 |  | 110 |  |  |  |  | -134 | 94.8 | -228.8 | 1178.2 | 553.3 |  | 624.9
(d) Price Contingency (Lump sum): | [34 empty] | 180 | 44 |  | 136 | [6 empty] | 139 | 75 |  | 64 | [6 empty] | 125 | 75 |  | 50 | [6 empty] | 460.28 | 370.58 |  | 89.7 | [6 empty] | 904.28 | 564.58 |  | 339.7 |  |  |  |  | 519.28 | 518.38 | 0.9 | 20892.92 | 7517.46 |  | 5474.06 | 7901.4
Grand Total (a+b+c+d) : |  |  |  |  | 11890.36 | 6899.33 |  | 1197.72 | 3793.31 | [5 empty] | 3048.86 | 547.12 |  | 2511.5 | 5.79 | [5 empty] | 26000 | 14000 |  | 11100 | 900 | [5 empty] | 31000 | 8900 |  | 21100 | 1000 | [5 empty] | 16000 | 6300 |  | 8700 | 1000 | [5 empty] | 7747.34 | 1747.34 |  | 5000 | 1000 | [5 empty] | 3651.16 | 1513.38 |  | 1935.48 | 202.3 | [5 empty] | 99337.72 | 39907.17 |  | 51544.7 | 7901.4 |  |  |  | 98952.72 | 39860.97 | 51205.9
-385
-385