## Sheet1
Government of the People’s Republic of Bangladesh
Ministry of Planning
Implementation Monitoring and Evaluation Division
Project Monitoring Form: IMED 03/2003 (Revised) (Page 1 of 4)
(Quarterly Progress Report)
ADP: 2019-2020-, Reporting Quarter: April 2020 to June 2020
A. Quarterly Financial Progress Report
Code
A.1 a) Project Title: “Haor Flood Managemen and
Livelihood Improvement Projec (BWDB part)”
b) Ministry: Ministry of Water Resources
c) Division: Water Resources
d) Agency: Bangladesh Water Development Board
A.2 Quarterly Financial Progress:
Head | Release for the Quarter |  | Expenditure for the Quarter |  |  | Current Year’s Expenditure
| GoB | RPA | GoB | RPA | DPA | GoB | RPA | DPA
Revenue | 245 | 261.69 | 621.77 | 261.69 | 311.37 | 729.92 | 421.6 | 450
Capital | - | 9643.57 | 2351.99 | 9643.57 | - | 2367.47 | 9751.95 | 0
Grand Total | 245 | 9905.26 | 420.21 | 9905.26 | 311.37 | 3097.39 | 10173.55 | 450
Cash Foreign Exchange Spent |  |  | Spent from Own Resources |  |  |  | CD/VAT
|  |  | Cash |  | Kind
- |  |  | - |  | - |  | -
RPA Spent (Cumulative to Date) |  |  | RPA Claimed |  |  |  | RPA Reimbursed
|  |  | Reporting Quarter |  | Cumulative to Date |  | Reporting Quarter | Cumulative to Date
cÖ‡hvR¨ bq |  |  | cÖ‡hvR¨ bq |  | cÖ‡hvR¨ bq |  | cÖ‡hvR¨ bq
‡bvU
1. RPA (c~bfiY‡hvM¨ cÖKí mvnvh¨) N‡i B‡¤úªó, †¯úkvj GKvD›U BZ¨vw` AšÍf~©³ _vK‡e¦
2. ''Spent from Own Resources'' – Gi N‡i ms¯’vi wbR¯^ A_©vqb †_‡K cÖK‡íi Rb¨ e¨q D‡jøL Ki‡Z n‡e¦
3. RPA msµvšÍ wnmve cÖ‡hvR¨ bv n‡j mswkøó N‡i ÒcÖ‡hvR¨ bqÓ wjL‡Z n‡e¦
14701 224080500

## Sheet2
Project Monitoring Form: IMED 03/2003 (Revised) (Page 2 of 4)
(Quarterly Progress Report)
ADP: 2019-2020, Reporting Quarter: April 2020 to June 2020
B. Quarterly Component-wise Progress
Code
B.1 | Project Title: “Haor Flood Managemen and
Livelihood Improvement Projec (BWDB part)”
B.2 | Quarterly Component-wise Progress:
Sl. No | Name of the Component (As per Table E-1 of PP) or (As per Part E (32) of TAPP) | Unit | Cumulative Progress Upto Last June |  |  | Revised Yearly Target |  |  | Progress in Current Quarter |  |  | Current Year's Progress |  |  | Remarks
|  |  | Physical |  | Financial | Physical |  | Financial | Physical |  | Financial | Physical |  | Financial
|  |  | Qtty | % |  | Qtty | % |  | Qtty | % |  | Qtty | %
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
A. | Revenue Component
1 | Allowances | L.S. | L.S. | - | 37.62 | - | - | 14.5 | - | - | 4 | - | - | 14.5
2 | Travel expences | L.S. | L.S. | - | 58.54 | L.S. |  | 15 | L.S. |  | 6.54 |  |  | 14.98
3 | Office rent for PMO |  |  |  | 116.67 |  |  | 34.25 |  |  | 7.69 |  |  | 34.21
4 | Misc. taxes | L.S. | L.S. | 1.2 | 1603.18 | L.S. |  | 179.54 | L.S. |  | 89.73 |  |  | 177.18
5 | Postage, telephone, Internate, Fax, telex etc. | L.S. | L.S. | - | 2.18 | L.S. |  | 0.7 | L.S. |  | 0.31 |  |  | 0.65
6 | Registration Fees (Vehicles) | L.S. | L.S. | - | 11.92 | L.S. |  | 1 | L.S. |  | 0.03 |  |  | 0.17
7 | Water & Elecricity | L.S. | L.S. | - | 9.85 | L.S. |  | 4.7 | L.S. |  | 0.95 |  |  | 3.44
8 | Gas & Fuel and Petrol & Lubricant | L.S. | L.S. | - | 82.11 | L.S. |  | 31 | L.S. |  | 8.48 |  |  | 28.2
9 | Insurance/Bank Charges (incl.Veh.) | L.S. | L.S. | - | 1.16 | L.S. |  | 1 | L.S. |  | 0.5 |  |  | 0.91
10 | Printing & Binding | L.S. | L.S. | - | 34.16 | L.S. |  | 0.5 | L.S. |  | 0.08 |  |  | 0.5
11 | Stationary | L.S. | L.S. | - | 49.91 | L.S. |  | 20 | L.S. |  | 5.55 |  |  | 19.95
12 | Books & periodical |  |  |  | 0.28 |  |  | 0.2 |  |  | 0.17 |  |  | 0.2
13 | Overseas Training |  |  |  | - |  |  | - |  |  | - |  |  | 0
14 | Local Training |  |  | 3 | 2226.33 |  |  | 810 |  |  | 66.67 |  |  | 443.3
15 | Casual labour/Job worker | L.S. | L.S. | - | 10.96 | L.S. |  | 3.5 | L.S. |  | 1.03 |  |  | 3.49
16 | Consumable Stores |  | - |  | 3.74 |  |  | 3 |  |  | 0.54 |  |  | 3
Sl. No | Name of the Component (As per Table E-1 of PP) or (As per Part E (32) of TAPP) | Unit | Cumulative Progress Upto Last June |  |  | Revised Yearly Target |  |  | Progress in Current Quarter |  |  | Current Year's Progress |  |  | Remarks
|  |  | Physical |  | Financial | Physical |  | Financial | Physical |  | Financial | Physical |  | Financial
|  |  | Qtty | % |  | Qtty | % |  | Qtty | % |  | Qtty | %
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
17 | Consultancy | L.S. | L.S. | 3 | 5168.01 | L.S. |  | 700 | L.S. |  | 187.62 |  |  | 450
18 | Honorarium/Fees/ Remuneration | L.S. | L.S. | - | 15.32 | L.S. |  | 7 | L.S. |  | 0.94 |  |  | 3.82
19 | Survey |  |  |  | 85.02 |  |  | 30 |  |  | 23.98 |  |  | 30
20 | Computer Consumables | L.S. | L.S. | - | 20.47 | L.S. |  | 10 | L.S. |  | 3.79 |  |  | 10
21 | Other expenses |  |  | 1.8 | 875.46 |  |  | 300 |  |  | 58.16 |  |  | 299.96
22 | Repair & Maintenance of Vehicles, furniture, computers & other structure | L.S. | L.S. | - | 211.96 | L.S. |  | 84.11 | L.S. |  | 18.98 |  |  | 63.06
| Total Revenue (Sub Total A) : |  |  | 9 | 10624.85 |  |  | 2510 |  |  | 485.74 |  |  | 1601.52
B. | Capital Component
1 | Motor Vehicle | Nos. | Nos. | 1 | 657.12 | Nos. |  | - | Nos. |  | - |  |  | 0
2 | Water Transport | Nos. | Nos. | - | 61.29 |  |  | - |  |  | - |  |  | 0
3 | Machinary & other equipment | Nos. | Nos. | - | 9.74 | Nos. |  | - | Nos. |  | - |  |  | 0
4 | Engineering equipment |  |  |  | 31.8 |  |  | - |  |  | 5 |  |  | 5
5 | Computer & Accessories | Nos. | Nos. | - | 33.63 | Nos. |  | - | Nos. |  | - |  |  | 0
6 | Furniture & fixture and Aircooler | L.S. | L.S. | - | 55.05 | L.S. |  | 4 | L.S. |  | 2.99 |  |  | 2.99
7 | Land acquisition |  |  | 8 | 14323.6 |  |  | 1000 |  |  | 1000 |  |  | 1000
8 | Construction Works |  |  | 36 | 19763.62 |  |  | 16186 |  |  | 7244.32 |  |  | 11111.43
| Total Capital : |  |  | 45 | 34935.85 |  |  | 17195 |  |  | 8252.31 |  | - | 12119.42
| Total: |  |  | 54 | 45560.7 |  | 3 | 19445 |  |  | 8738.05 |  |  | 13720.94
‡bvU t
1. 2 bs Kjv‡g ïaygvÎH mKj A‡½i bvg D‡jøL Ki‡Z n‡e †h mKj A½ ev¯Íevq‡bi Rb¨ eZ©gvb A_© eQ‡i jÿ¨gvÎ w¯’i Kiv n‡q‡Q Ges hv AvBGgBwW 02/2003 (ms‡kvwaZ) dig Gi A.2 ‡Z D‡jøL Kiv n‡q‡Q¦
2. KvwiMwi mnvqZv cÖK‡íi †ÿ‡Î 2 bs Kjv‡g ev¯Íe AvDUcyU †hgbt wi‡cvU©, cÖwkÿY BZ¨vw` wjwce× Ki‡Z n‡e¦
3. cwigvc‡hvM¨ ev¯Íe AMÖMwZ AwR©Z n‡j % ‡`qvi welqwU cÖhvR¨ n‡e bv (Kjvg-5, 8, 11 I 14)¦ Z‡e we‡ePbvaxb mg‡q KvR nIqv m‡Z¡I †h mKj A‡½i ev¯Íe Kv‡Ri djvdj msL¨v/GK‡K cwigvc‡hvM¨ nq bvB, ïaygvÎ †m‡ÿ‡Î % e¨envi Ki‡Z n‡e¦ D³ As‡Mi cy‡iv cÖKíKvjxb mg‡qi Zzjbvq mswkøó mg‡hi AMÖMwZi % w`‡Z n‡e¦ 16 bs Kjv‡g % e¨env‡ii Kvib wjwce× Ki‡Z n‡e¦
4. hw` †Kvb A‡½i †ÿ‡Î ms¯’vi wbR¯^ m¤ú` †_‡K e¨q _v‡K, Zvn‡j Zv Financial Kjv‡g Ab¨vb¨ wnmv‡ei m‡_ †hvM K‡i †`Lv‡Z n‡e¦
14701 224080500

## Sheet3
Project Monitoring Form: IMED 03/2003 (Revised) (Page 3 of 4)
(Quarterly Progress Report)
ADP: 2019-2020-, Reporting Quarter: April 2020 to June 2020
C. Implementation Problems and Suggested Measures
Code
C.1 | Project Title: “Haor Flood Managemen and
Livelihood Improvement Projec (BWDB part)”
C.2 Implementation Problems: Not Applicable
Problem Number | Problem Type | Description of Problem (s)
1. | Approval Process
2. | Procurement
3. | Management
4. | Fund Allocation/Release
5. | Manpower Recruitment
6. | Others (specify)
C.3 Suggested Measures: (In brief and specific)
Problem Number | Measures Suggested
1.
2.
3.
4.
5.
6.
Others
None
C.4 Is the project declared Completed |  |  | Yes | No
Project Director/ |  |  | Head of the Agency/
Authorized Signature |  |  | Authorized Signature
Date: |  |  | Date:
Secretary/Head of the Planning Wing/Branch
Authorized Signature
Date:
14701 224080500
√

## Sheet4
Project Monitoring Form: IMED 03/2003 (Revised) (Page 4 of 4)
(Quarterly Progress Report)
ADP: 2019-2020-, Reporting Quarter: April 2020 to June 2020
D. Contract Implementation Report
(Please fill-in this form for goods and works contract of value above Tk. 200.00 lakh and consultancy contract of value above Tk. 100.00 lakh)
Code
D.1 Project Title: "Haor Flood Managemen and
Livelihood Improvement Projec (BWDB part)"
D.2 Contract Implementation:
Description of contracts (as per tender document) | Contract value | Date of work order/contract agreement | Completion date as per contract | Progress
|  |  |  | Amount paid |  | Physical (%)
Consultancy Services for Management, Design & Supervision and other related Services | JPY :246,048,000 BDT: 7050.40 lakh | 21st April 2015 | 30th June 2022 | BDT: 5618.01 |  | 70
‡bvU t
1¦ ‡Kvb KbUªv± Pjgvb _vKvKvjxb mg‡q cÖwZ †KvqvU©v‡i G Q‡K Z_¨ cÖ`vb Ki‡Z n‡e¦ Z‡e K›Uªv± mgvß nevi ci gvÎ GKeviB Zvi Progress report Ki‡Z n‡e, evievi bq¦
2¦ KbUªv± msµvšÍ wnmve cÖ‡hvR¨ bv n‡j mswkøó N‡i ÒcÖ‡hvR¨ bqÓ wjL‡Z n‡e¦
D.3 Problems/Reasons for Delay in Contract Implementation (if any):
Sl No. | Description
Project Director/ |  |  |  |  | Head of the Agency/
Authorized Signature |  |  |  |  | Authorized Signature
Date: |  |  |  |  | Date:
Secretary/Head of the Planning Wing/Branch
Authorized Signature
Date:
14701 24080500