## Monthly_19_20_GOB
Code | Description | Imed_Code | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
3111302 | Conveyance Allowance | REV_1 | Aug: 4650; Sep: 5000; Oct: 5000; Nov: 5100; Dec: 5000 | 24750 | 0.2475 | 0.5
3111327 | Overtime Allowance | REV_1 | Oct: 0 | 0 | 0 | 0
3111338 | Other Allowance | REV_1 | Oct: 362147; Nov: 122607; Dec: 134261 | 619015 | 6.1902 | 14
3241101 | Travel Expenses (TA & DA for PMO & PIU) | REV_2 | Sep: 91434; Oct: 120270; Nov: 105930; Dec: 135406 | 453040 | 4.5304 | 15
3211129 | Rent-Office : Office Accomodation for PMO (3,500sft) for 8 years | REV_3 | Aug: 570140; Sep: 285070; Oct: 285070; Nov: 285070; Dec: 285370 | 1710720 | 17.1072 | 34.25
3821103 | Misc. Taxes (Income Tax of Consultants, Outsourcing Staff Salary,House rent, Fees for Environmental clearance etc.) | REV_4 | Aug: 852263; Sep: 668538; Oct: 633392; Nov: 175528; Dec: 4307841 | 6637562 | 66.3756 | 359.08
3211119 | Postage | REV_5 | Aug: 1438; Sep: 1725; Oct: 1581; Dec: 5589 | 10333 | 0.10333 | 0.5
3211120 | Telephones/Telegram/Teleprinter | REV_5 | Sep: 6178; Oct: 0 | 6178 | 0.06178 | 0.2
3211117 | Telex/Fax/Internet | REV_5 | Sep: 2190; Oct: 0 | 2190 | 0.0219 | 0.2
3221104 | Registration Fee (Vehicles) | REV_6 | Sep: 0; Oct: 0; Dec: 6085 | 6085 | 0.06085 | 1
3211115 | Water | REV_7 | Aug: 2820; Sep: 6411; Oct: 0; Dec: 16510 | 25741 | 0.25741 | 0.45
3211113 | Electricity | REV_7 | Aug: 37257; Sep: 67934; Oct: 30428; Dec: 49618 | 185237 | 1.8524 | 3.5
3243102 | Gas & Fuel | REV_8 | Sep: 26648; Oct: 13820; Nov: 112742; Dec: 28403 | 181613 | 1.8161 | 6
3243101 | Petrol and Lubricant | REV_8 | Aug: 129500; Sep: 168858; Oct: 118371; Nov: 97513; Dec: 407423 | 921665 | 9.2166 | 20
3221108 | Insurance/Bank Charges (including Vehicles) | REV_9 | Oct: 0 | 0 | 0 | 0.15
3255102 | Printing & Binding | REV_10 | Aug: 14000; Sep: 1404; Oct: 14625; Nov: 11700 | 41729 | 0.41729 | 0.5
3255104 | Stationery, Seals & Stamps | REV_11 | Aug: 49597; Sep: 329458; Oct: 5207; Nov: 333170; Dec: 54432 | 771864 | 7.7186 | 20
3211127 | Books & Periodicals | REV_12 | Aug: 575; Sep: 219; Oct: 1358; Nov: 5588; Dec: 263 | 8003 | 0.08003 | 0.2
3231201 | Overseas Training Course(08 Trainees) & Overseas Study Tour (12 Participants) | REV_13 | Oct: 0 | 0 | 0 | 0
3231201 | Local Training for (a) O&M manual (For BWDB Officials) and (b) Water Management Organization (WMO) | REV_14 | Oct: 77343; Nov: 134031.5; Dec: 7223 | 218597.5 | 2.186 | 196.17
3231201 | Agriculture Promotion Support Sub-project (APSS) : Field Programme, Farmer Training Programme, Field Staff Empowerment Programme, Farm Machinery & Facility Support and Technology Development Programme etc. | REV_14 | Oct: 364148; Nov: 334368; Dec: 507444 | 1205960 | 12.0596 | 677.14
3231201 | Small Scale Income Generation Sub-project (SIGS): Floating Bed Vegetable Culture Scheme, Small-scale Vegetable Production Support Scheme, Fruit Production Support Scheme, Micro Poultry Raising Scheme and Small-scale Mushroom Culture Scheme etc. | REV_14 | Oct: 0; Nov: 60036 | 60036 | 0.60036 | 246.66
3211109 | Casual labour/Job worker | REV_15 | Sep: 36800; Oct: 0; Nov: 334368 | 371168 | 3.7117 | 3.5
3256103 | Consumable Stores | REV_16 | Oct: 0 | 0 | 0 | 3
3257101 | Consultancy : International - 71 M/M National - 324 M/M | REV_17 | Oct: 0 | 0 | 0 | 500
3111332 | a) Honorarium/Fees/Remuneration (for different Committee) | REV_18 | Sep: 69575; Oct: 0; Dec: 57960 | 127535 | 1.2753 | 5
3111332 | b) Interim Evaluation | REV_18 | Oct: 0 | 0 | 0 | 1
3111332 | c) Progress Monitoring | REV_18 | Oct: 0 | 0 | 0 | 1
3257104 | Survey | REV_19 | Oct: 303360 | 303360 | 3.0336 | 50
3255101 | Computer Consumables | REV_20 | Aug: 13365; Sep: 240670; Oct: 316303; Nov: 28470 | 598808 | 5.9881 | 10
3256101 | Other Expenses: Salary of Manpower through Outsourcing | REV_21 | Aug: 3070966; Sep: 2043145; Oct: 2136764; Nov: 464684; Dec: 2170291 | 9885850 | 98.8585 | 300
3258101 | Motor Vehicles | REV_22 | Aug: 8468; Sep: 25598; Oct: 48488; Nov: 16096; Dec: 73812 | 172462 | 1.7246 | 15
3258102 | Furnitures & Fixtures | REV_22 | Oct: 0 | 0 | 0 | 2
3258103 | Computers & office equipments | REV_22 | Oct: 0; Dec: 26357 | 26357 | 0.26357 | 3
3258105 | Machineries & Equipments | REV_22 | Aug: 7642; Sep: 411; Oct: 16500; Nov: 3819; Dec: 17071 | 45443 | 0.45443 | 2
3258107 | Office Building : Repair & Maintenance | REV_22 | Oct: 0 | 0 | 0 | 0
3258106 | Residential Building : Repair & Maintenance | REV_22 | Oct: 0 | 0 | 0 | 5
3258105 | Engineering Equipments | REV_22 | Aug: 5650; Sep: 18886; Oct: 6570 | 31106 | 0.31106 | 2
3258114 | Repair/Replacement of Regulator Gates and other related works(Rehabilitation Haors) | REV_22 | Oct: 0; Nov: 28740; Dec: 378118 | 406858 | 4.0686 | 58.25
3258128 | Water Transport : Repair of Speedboat(s) | REV_22 | Oct: 0 | 0 | 0 | 0.75
3258107 | Others : Repair & Maintenance | REV_22 | Oct: 0 | 0 | 0 | 3
4112101 | Jeep (above 2500 c.c. made by Pragati) -1 No.for Project Director, PMO, Jeep (2200 c.c. to 2500 c.c. made by Pragati) (4 Wheel Drive) -8 Nos. and Double Cabin Pickup-1 No. (1 for DPD, PMO, 1 for 4 EE, PMO, Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1 No., Brahmanbaria 1 No., 1 for Planning Commission & 1 Pickup for Deputy Chief Extension Officer, PMO)= Total 10 Nos. | CAP_1 | Oct: 0 | 0 | 0 | 95.6
4112101 | Motorcycle - 35 Nos. (PMO 2 Nos.,Kishoreganj 11 Nos., Netrokona 6 Nos., Sunamganj 6 Nos., Habiganj 6 Nos.& Brahmanbaria 4 Nos). | CAP_1 | Oct: 0 | 0 | 0
4112102 | Speed Boat with Engine and all accessories (75 hp & 6 Nos.) | CAP_2 | Oct: 0 | 0 | 0
4112316 | Photocopier -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_3 | Oct: 0 | 0 | 0
4112316 | Fax -7 nos (PMO 2 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No). | CAP_3 | Oct: 0 | 0 | 0
4112304 | Survey Equipments (Digital leveling Instrument 5 nos., Total Station 2 nos. & Hand Held GPS 10 Nos) | CAP_4 | Oct: 0 | 0 | 0
4112304 | Networking Equipment- 6 nos (PMO 1 No., Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_4 | Oct: 0 | 0 | 0
4112304 | Engineering Laboratory Equipments for Kishoregonj WD Division | CAP_4 | Oct: 0 | 0 | 0 | 5
4112202 | Desktop Computer- 30 nos. (Project Management Office 9 Nos.,Chief Planninng 3 Nos., Chief Engineer Design 3 Nos., Office of the Joint Chief Planning 2 Nos.,Director Accounts 2 Nos.,Kishoreganj 3 Nos., Netrokona 2 Nos., Sunamganj 2 Nos., Habiganj 2 Nos.& Brahmanbaria 2 Nos.) | CAP_5 | Oct: 0 | 0 | 0
4112202 | Laptop Computer -11 nos (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No) | CAP_5 | Oct: 0 | 0 | 0
4112202 | A3 Combo Printer 2 no ( PMO) | CAP_5 | Oct: 0 | 0 | 0
4112202 | Laser Printer- 11 nos. (PMO 6 Nos.,Kishoreganj 1 No., Netrokona 1 No., Sunamganj 1 No., Habiganj 1No.& Brahmanbaria 1 No.) | CAP_5 | Oct: 0 | 0 | 0
4112314 | Furnitures & Fixtures | CAP_6 | Oct: 0 | 0 | 0
4112303 | Aircooler | CAP_6 | Oct: 0 | 0 | 0 | 4
4141101 | Land Acquisition ( 470 hectare) | CAP_7 | Oct: 0 | 0 | 0 | 2049.42
4111306 | Construction of Irrigation Inlet (New Haors) | CAP_8 | Oct: 0 | 0 | 0 | 490.33
4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | CAP_8 | Oct: 0; Dec: 1548/390.75 | 0 | 0 | 0
4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | CAP_8 | Oct: 0 | 0 | 0 | 8105.58
4111307 | Re-excavation of Khal/River (New Haors) | CAP_8 | Oct: 0 | 0 | 0 | 3956.08
4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | CAP_8 | Oct: 0 | 0 | 0 | 900.73
4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | CAP_8 | Oct: 0 | 0 | 0 | 913.26
4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | CAP_8 | Oct: 0 | 0 | 0 | 657.55
4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | CAP_8 | Oct: 0 | 0 | 0 | 4914.31
4111201 | Rehabilitation of Regulator (New Haors) | CAP_8 | Oct: 0 | 0 | 0 | 0
4111201 | Construction of WMG Office | CAP_8 | Oct: 0 | 0 | 0 | 348.14
4111201 | O&M During Construction | CAP_8 | Oct: 0 | 0 | 0 | 0
XXXXX1 | Physical Contingency | C | [12 empty] | 0 | 0
XXXXX2 | Price Contingency | D | [12 empty] | 0 | 0
Note on L7: hp:Environent()