## Rate
item no | group | Itemcode | Description | unit | quantity | Rate
1 | 1 | 04-180 | Site preparation | Sqm | 5060 | 39.001
2 | 2 | 16-100 | Erection of bamboo profile | Nos | 166 | 370.001
3 | 3 | 16-450 | Ringbundh Construction | Cum | 5016 | 140.001
4 | 4 | 16-220-10 | Earth work by carried Earth in Emb const | Cum | 16969.08 | 300.001
5 | 5 | 16-240-10 | Earth work by Excavator in Emb const 85% MDD | Cum | 16969.08 | 159.001
6 | 6 | 16-510 | Earth work in excavation of foundation trenches | Cum | 4840.65 | 200.001
7 | 7 | 16-180 | Royalty of specified earth taken from private land | Cum | 11432.33 | 16.001
8 | 8 | 16-150 | Extra rate for every additional lead of 15m or part | Cum | 3463.25 | 61.001
9 | 9 | 16-170 | Extra rate for every additional lift of 1.0m or part | Cum | 3463.25 | 32.001
10 | 10 | 40-550-30 | Supplying and laying sand as filter layers FM 1.0 to 1.5 | Cum | 1695.6 | 700.001
11 | 11 | 40-500-40 | Geotextile Filter 3mm | Sqm | 62271.26 | 255.001
12 | 12 | 40-380-20 | 175 Kg Geobags | Nos | 7431 | 500.001
13 | 13 | 40-380-20 | 125 Kg Geobags | Nos | 14137 | 400.001
14 | 14 | 40-530-20 | Pea gravek filter 40mm to 20mm | Cum | 1002.37 | 4572.001
15 | 15 | 40-530-30 | Pea gravek filter 20mm to 5mm | Cum | 1002.37 | 4451.001
16 | 16 | 40-190-15 | C.C. blocks Block Size: 50cmx50cmx50cm | Nos | 5295 | 1800.001
17 | 17 | 40-190-05 | C.C. blocks Block Size: 50cmx50cmx30cm | Nos | 10136 | 1206.001
18 | 18 | 40-190-35 | C.C. blocks Block Size: 40cmx40cmx40cm | Nos | 15224 | 1000.001
19 | 19 | 40-190-40 | C.C. blocks Block Size: 40cmx40cmx40cm | Nos | 59777 | 450.001
20 | 20 | 40-270-10 | Labour charge for CC Block Placing with 200m | Cum | 2154.637 | 1452.001
21 | 21 | 40-270-20 | Labour charge for CC Block Placing with 200m | Cum | 2154.637 | 2275.001
22 | 22 | 28-120-20 | Cment concrete work in leanest mix. 1:3:6 | Cum | 138.24 | 11998.001
23 | 23 | 36-150-10 | Shuttering for Verutcal and Inclined wall | Sqm | 354.71 | 1187.001
24 | 24 | 76-120-10 | Reinforcement 0 to 30mm dia | Kg | 428.02 | 103.001
25 | 25 | 20-100-10 | Single brick flat soling | Sqm | 6 | 467.001
26 | 26 | 28-200-10 | RCC 1:1.5:3 | Cum | 3.71 | 14016.001
27 | 27 | 16-120-10 | Earth work by Manual Labour in Emb const 85% MDD | Cum | 3463.25 | 200.001
28 | 28 | 48-100 | Fine Dressing and Close Turfing | Sqm | 106121.8 | 22.001
29 | 29 | 16-470 | Removing Cross Bundh | Cum | 13012.8 | 115.001
30 | 30 | 16-430-10 | Dredge Earth Carriage by Dump Truck | Cum | 9000 | 40.001
31 | 31 | 31 | Preparetion of mobilization of the site for construction of s | Item | 1 | 467050.001
32 | 32 | 32 | Providing and maintaining adequate portable water supply | Item | 1 | 111148.001
33 | 33 | 33 | Operate, maintain of plant and equipment such as generator | Item | 1 | 110909.001
34 | 34 | 34 | Provide and maintain 1 (one) no. engine boat with boatmen | Days | 120 | 2497.001
35 | 35 | 35 | Mobilize, Strengthen required land based construction equipment s | Item | 1 | 92026.001
36 | 36 | 36 | Demobilization and clean-up of the sit | Item | 1 | 112344.001
37 | 37 | 37 | Environmental Monitoring | Item | 1 | 250000.001
126118543.784
[5 empty] | Mobilization | 1443117.126
14.4312

## Segegation
code | description | unit | Rate | TA_From 695 to 935=240 | TA_From 965 to 1015=50 | TA_From 4500 to 4570=40 | TA_From 35020 to 35100=40 | TB_From 0 to 695=695 | TB_From 1015 to 2180=1165 | TB_From 9200 to 10350=1150 | RS_4600_ibtw_7800=850 | RS_25200_ibtw_36630=3850 | FF_30M_at_950 | FF_15M_at_4520 | FF_15M_at_35050 | Total
|  |  |  | 240 | 50 | 40 | 40 | 695 | 1195 | 1150 | 850 | 3850 | 30 | 15 | 15
|  |  |  | 0.24 | 0.05 | 0.04 | 0.04 | 0.695 | 1.195 | 1.15 | 0.85 | 3.85 | 0.03 | 0.015 | 0.015
|  |  |  | 0.24 | 0.05 | 0.04 | 0.04 | 0.695 | 1.195 | 1.15 | 0.85 | 3.85 | 0.03 | 0.015 | 0.015
04-180 | Site preparation | Sqm | 39.001 | 5060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5060
16-100 | Erection of bamboo profile | Nos | 370.001 | 6 | 2 | 2 | 2 | 14 | 24 | 24 | 17 | 17 | 0 | 0 | 0 | 108
16-450 | Ringbundh Construction | Cum | 140.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052 | 1482 | 1482 | 5016
16-220-10 | Earth work by carried Earth in Emb const | Cum | 300.001 | 3966.09 | 826.265 | 164.8 | 164.8 | 1677.12 | 2811.29 | 2775.09 | 1683 | 7623 | 0 | 0 | 0 | 21691.455
16-240-10 | Earth work by Excavator in Emb const 85% MDD | Cum | 159.001 | 3966.09 | 826.265 | 164.8 | 164.8 | 1677.12 | 2811.29 | 2775.09 | 1683 | 7623 | 0 | 0 | 0 | 21691.455
16-510 | Earth work in excavation of foundation trenches | Cum | 200.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2524.95 | 1192.73 | 1122.98 | 4840.66
16-180 | Royalty of specified earth taken from private land | Cum | 16.001 | 3966.09 | 826.265 | 164.8 | 164.8 | 1677.12 | 2811.29 | 2775.09 | 1683 | 7623 | 1771.25 | 1022.6 | 669.4 | 25154.705
16-160 | Extra rate for every additional lead of 15m or part | Cum | 61.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1771.25 | 1022.6 | 669.4 | 3463.25
16-170 | Extra rate for every additional lift of 1.0m or part | Cum | 32.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1771.25 | 1022.6 | 669.4 | 3463.25
40-550-30 | Supplying and laying sand as filter layers FM 1.0 to 1.5 | Cum | 700.001 | 636 | 132.6 | 67.4 | 67.4 | 0 | 0 | 0 | 0 | 0 | 360.08 | 267.29 | 241.78 | 1772.55
40-500-40 | Geotextile Filter | Sqm | 255.001 | 6936 | 1445 | 770 | 770 | 10800.3 | 18104.1 | 17871 | 0 | 0 | 2456.5 | 1837.97 | 1667.84 | 62658.71
40-380-20 | 175 Kg Geobags | Nos | 500.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4021.08 | 1851.01 | 1558.69 | 7430.78
40-380-30 | 125 Kg Geobags | Nos | 400.001 | 0 | 0 | 0 | 0 | 3225 | 5406 | 5336 | 0 | 0 | 0 | 0 | 0 | 13967
40-530-20 | Pea gravek filter 40mm to 20mm | Cum | 4572.001 | 318 | 66.25 | 38.56 | 38.56 | 0 | 0 | 0 | 0 | 0 | 240.05 | 178.2 | 161.18 | 1040.8
40-530-30 | Pea gravek filter 20mm to 5mm | Cum | 4451.001 | 318 | 66.25 | 38.56 | 38.56 | 0 | 0 | 0 | 0 | 0 | 240.05 | 178.2 | 161.18 | 1040.8
40-190-15 | C.C. blocks Block Size: 50cmx50cmx50cm | Nos | 1800.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2669.5 | 1355.65 | 1270.15 | 5295.3
40-190-05 | C.C. blocks Block Size: 50cmx50cmx30cm | Nos | 1206.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4794.83 | 2950.84 | 2389.85 | 10135.52
40-190-35 | C.C. blocks Block Size: 40cmx40cmx40cm | Nos | 1000.001 | 6000 | 1250 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 3562.5 | 1781.25 | 1781.25 | 16375
40-190-40 | C.C. blocks Block Size: 40cmx40cmx40cm | Nos | 450.001 | 37920 | 7900 | 4040 | 4040 | 0 | 0 | 0 | 0 | 0 | 2655.25 | 3916.85 | 3916.85 | 64388.95
40-270-10 | Labour charge for CC Block Placing with 200m | Cum | 1452.001 | 798.72 | 166.4 | 96.64 | 96.64 | 0 | 0 | 0 | 0 | 0 | 503.13 | 315.05 | 288.67 | 2265.25
40-270-20 | Labour charge for CC Block Placing with 200m | Cum | 2275.001 | 798.72 | 166.4 | 96.64 | 96.64 | 0 | 0 | 0 | 0 | 0 | 503.13 | 315.05 | 288.67 | 2265.25
28-120-20 | Cment concrete work in leanest mix. 1:3:6 | Cum | 11998.001 | 28.8 | 6 | 4.8 | 4.8 | 0 | 0 | 0 | 0 | 0 | 50.44 | 23.44 | 23.44 | 141.72
36-150-10 | Shuttering for Verutcal and Inclined wall | Sqm | 1187.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166.24 | 94.24 | 94.24 | 354.72
76-120-10 | Reinforcement 0 to 30mm dia | Kg | 103.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142.67 | 142.67 | 142.67 | 428.01
20-100-10 | Single brick flat soling | Sqm | 467.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 6
28-200-10 | RCC 1:1.5:3 | Cum | 14016.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 1.24 | 1.24 | 3.72
16-120-10 | Earth work by Manual Labour in Emb const 85% MDD | Cum | 200.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1771.25 | 1022.6 | 669.4 | 3463.25
48-100 | Fine Dressing and Close Turfing | Sqm | 22.001 | 0 | 0 | 0 | 0 | 9202 | 15425 | 15226 | 11722 | 53092 | 0 | 0 | 0 | 104667
16-470 | Removing Cross Bundh | Cum | 115.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1641.6 | 1185.6 | 1185.6 | 4012.8
16-430-10 | Dredge Earth Carriage by Dump Truck | Cum | 40.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 467050.001 | 33553089.3085 | 6949459.1047 | 3906251.209 | 3906251.209 | 5048360.7727 | 8462585.643 | 8353571.5323 | 1063615.788 | 4795314.978 | 24639088.4122 | 15230577.2517 | 13817741.9379
|  |  | 111148.001 | 335.5309 | 69.4946 | 39.0625 | 39.0625 | 50.4836 | 84.6259 | 83.5357 | 10.6362 | 47.9531 | 246.3909 | 152.3058 | 138.1774 | 1297.2591
|  |  | 110909.001 | [12 empty] | 14.4312
|  |  | 2497.001 | [12 empty] | 1311.6902 | 1261.18 | 50.5102
92026.001
112344.001
250000.001
|  |  |  | 335.5309 | 69.4946 | 39.0625 | 39.0625 | 50.4836 | 84.6259 | 83.5357 | 10.6362 | 47.9531 | 246.3909 | 152.3058 | 138.1774
|  |  |  | 335.5309 | 335.53 | 335.53
|  |  |  | 69.4946 | 69.49 | 69.49
|  |  |  | 39.0625 | 39.06 | 39.06
|  |  |  | 39.0625 | 39.06 | 39.06
|  |  |  | 50.4836 | 50.48 | 50.48
|  |  |  | 84.6259 | 84.63 | 84.63
|  |  |  | 83.5357 | 83.54 | 83.54
|  |  |  | 10.6362 | 10.64 | 10.64
|  |  |  | 47.9531 | 47.95 | 47.95
|  |  |  | 246.3909 | 246.39 | 246.39
|  |  |  | 152.3058 | 152.31 | 152.31
|  |  |  | 138.1774 | 138.18 | 138.18

## Earth Work Calculation
code | description | TA_From 695 to 935=240 | TA_From 965 to 1015=50 | TA_From 4500 to 4570=40 | TA_From 35020 to 35100=40 | TB_From 0 to 695=695 | TB_From 1015 to 2180=1165 | TB_From 9200 to 10350=1150 | RS_4600_ibtw_7800=850 | RS_25200_ibtw_36630=3850 | Total
| Total Earth | 7932.17 | 1652.53 | 329.6 | 329.6 | 3354.24 | 5622.57 | 5550.18 | 3366 | 15246 | 43382.89
16-220-10 | Carried Earth | 3966.085 | 826.265 | 164.8 | 164.8 | 1677.12 | 2811.285 | 2775.09 | 1683 | 7623 | 21691.445
16-240-10 | Excavator | 3966.085 | 826.265 | 164.8 | 164.8 | 1677.12 | 2811.285 | 2775.09 | 1683 | 7623 | 21691.445
16-180 | Royalty | 3966.085 | 826.265 | 164.8 | 164.8 | 1677.12 | 2811.285 | 2775.09 | 1683 | 7623 | 21691.445
40-550 | Sand Filter | 636 | 132.6 | 67.4 | 67.4 | 0 | 0 | 0 | 0 | 0 | 903.4
40-500-40 | Geotextile Filter 3mm | 6936 | 1445 | 770 | 770 | 10800.3 | 18104.1 | 17871 | 0 | 0 | 56696.4
40-530-20 | gravel filter 40mm to 20mm | 318 | 66.25 | 38.56 | 38.56 | 0 | 0 | 0 | 0 | 0 | 461.37
40-530-30 | gravel filter 20mm to 5mm | 318 | 66.25 | 38.56 | 38.56 | 0 | 0 | 0 | 0 | 0 | 461.37
40-190-40 | CC Block 40X40X20 | 37920 | 7900 | 4040 | 4040 | 0 | 0 | 0 | 0 | 0 | 53900
40-190-35 | CC Block 30X30X30 | 6000 | 1250 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 9250
| volume | 1597.44 | 332.8 | 193.28 | 193.28 | 0 | 0 | 0 | 0 | 0 | 2316.8
40-270-10 | Labour Charge within 200m | 798.72 | 166.4 | 96.64 | 96.64 | 0 | 0 | 0 | 0 | 0 | 1158.4
40-270-20 | Labour Charge beyond 200m | 798.72 | 166.4 | 96.64 | 96.64 | 0 | 0 | 0 | 0 | 0 | 1158.4
40-380-30 | Geobags 125 kg | 0 | 0 | 0 | 0 | 3225 | 5406 | 5336 | 0 | 0 | 13967
48-100 | Fine Dressing and close turfing | 0 | 0 | 0 | 0 | 9202 | 15425 | 15226 | 11722 | 53092 | 104667
28-120-10 | CC 1:3:6 | 28.8 | 6 | 4.8 | 4.8 | 0 | 0 | 0 | 0 | 0 | 44.4