## Structure_Type
| Items | Initial | Code | Payment_30_06_2020 | DPP_Item
0 | Construction of Irrigation Inlet | IRRI_C | 1 | 22 | Inlet
1 | Rehab Regulator Rehab Haor | REG_R_REHAB | 2 | 0 | Reg_Rehab_Rehab
2 | Regulator | REG_C | 3 | 6503.97 | Reg_CW_Box
3 | Box Drainage Outlet | DROU_C | 4 | 0 | Reg_CW_Box
4 | Causeway | CW_C | 5 | 0 | Reg_CW_Box
5 | Bridge | BRI_C | 6 | 0 | Reg_CW_Box
6 | Khal_River Reexcavation(New Haor) | REX_KH_RIV_NEW | 7 | 2546.54 | Khal_Riv_New
7 | Khal_River Reexcavation(Rehab Haor) | REX_KH_RIV_REHAB | 8 | 51.09 | Khal_Riv_Rehab
8 | Embankment Rehablitation | EMB_R | 9 | 0 | Full_Emb_Rehab
9 | Submersible Embankment Rehabilitation | SEMB_R | 10 | 0 | Sub_Emb_Rehab
10 | Submersible Embankment Construction | SEMB_C | 11 | 5833.04 | Sub_Emb_Const
11 | Rehab Regulator New Haor | REG_R_NEW | 12 | 0 | Reg_Rehab_New
12 | Thrashing Floor Construction | THF_CONS | 14 | 0 | Thr_Fl_Cost
13 | Construction of WMG | WMG_OFF | 15 | 0 | Wmg_Office
14 | M&E GATE Repair | GATE_REP | 16 | 0 | Gate_Repair

## Projection_Info
| Package Name | Component | Unit | Qnty | Cost | Present_Progress | Projected_progress | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code
0 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Resectioning of Embankment along the left bank of the Bashira River inbwt 2.420 to 9.760 | km | 9.42 | 237.21 | 1 | 1 | HOBI/PW-01 | Rehab | 10 | 0 | R-8 | HOBI
1 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | construction of new Embankment along the left bank of bitangal khal inbwt 10.000 to 17.000 | km | 7 | 149.29 | 1 | 1 | HOBI/PW-01 | Rehab | 10 | 0 | R-8 | HOBI
2 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Reexcavation of Bashira River 0.000 to 20.000 | km | 17.4 | 732.6 | 0.8 | 1 | HOBI/PW-01 | Rehab | 8 | 0 | R-8 | HOBI
3 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Reexcavation of Matikatakahl from 0.000 to Km 2.295 | km | 2.925 | 99.9 | 1 | 1 | HOBI/PW-01 | Rehab | 8 | 0 | R-8 | HOBI
4 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Reahblitation of Existing 3-vent Regulator | nos. | 1 | 69.47 | 0 | 1 | HOBI/PW-01 | Rehab | 3 | 0 | R-8 | HOBI
5 | BWDB/Hobi/HFMLIP/PW-01 Bashira River | Construction of 6.00m Islampur causeway | nos. | 1 | 247.53 | 0 | 1 | HOBI/PW-01 | Rehab | 5 | 0 | R-8 | HOBI
6 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Resctioning of Submersible Embankment from 0.000 to 26.000 at Left Bank of Kushiyara | Km | 5.7 | 287.53 | 1 | 1 | HOBI/PW-02 | Rehab | 10 | 0 | R-7 | HOBI
7 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Resctioning of Submersible Embankment from 0.000 to 16.02 at Right Bank of Khoai | Km | 16.02 | 377.59 | 1 | 1 | HOBI/PW-02 | Rehab | 10 | 0 | R-7 | HOBI
8 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Construction of New Embankment from Km 22.850 to 31.210 | Km | 9.42 | 304.03 | 1 | 1 | HOBI/PW-02 | Rehab | 10 | 0 | R-7 | HOBI
9 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Reexcavation of Satmukha Khal from 0.000 to 1.790 km | Km | 1.79 | 53.0475 | 1 | 1 | HOBI/PW-02 | Rehab | 8 | 0 | R-7 | HOBI
10 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Reexcavation of Singer Beel Khal from 0.000 to 2.720 km | Km | 2.72 | 29.975 | 1 | 1 | HOBI/PW-02 | Rehab | 8 | 0 | R-7 | HOBI
11 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Construction of Dairar Khal Causeway 6-m width Causeway | nos. | 1 | 244.2 | 0.95 | 1 | HOBI/PW-02 | Rehab | 5 | 0 | R-7 | HOBI
12 | BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Ikrampur CW-6M | nos. | 1 | 210.95 | 0.1 | 1 | HOBI/PW-02 | 0 | 5 | 0 | R-7 | HOBI
13 | BWDB/Hobi/HFMLIP/PW-04 Mokhar Haor | Submesible Embankment from 31.600 to 81.740 | km | 23.815 | 638.85 | 0.5 | 1 | HOBI/PW-04 | New | 11 | 0 | N-10 | HOBI
14 | BWDB/Hobi/HFMLIP/PW-04 Mokhar Haor | Block road | km | 2 | 507.95 | 0.78 | 1 | HOBI/PW-04 | New | 11 | 0 | N-10 | HOBI
15 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Boranbil khal Regulator (1-vent) | nos. | 1 | 141.3235 | 0 | 0.75 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
16 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Chandakhali khal Regulator(1-vent) | nos. | 1 | 154.0746 | 0 | 0.75 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
17 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Chargaowdair khal Regulator(1-vent) | nos. | 1 | 151.0703 | 0.3 | 1 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
18 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Hao | Chhoto Katari khal Regulator(1-vent) | nos. | 1 | 143.8109 | 0.1 | 0.7 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
19 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Hao | Islampur khal Regulator (1-vent) | nos. | 1 | 155.6933 | 0.8 | 1 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
20 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Hao | Tetter Drepasionkhal Regulator(2-vent) | nos. | 1 | 216.7515 | 0 | 0.7 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
21 | BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Soaybeel khal Regulator (5-vent) | nos. | 1 | 353.8204 | 1 | 1 | HOBI/PW-05 | New | 3 | 0 | N-10 | HOBI
22 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Bibiyana 6.0m Causeway | nos. | 1 | 415.5317 | 1 | 1 | HOBI/PW-06 | New | 5 | 0 | N-10 | HOBI
23 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Old kushiyana 6.0m Causeway | nos. | 1 | 373.3459 | 0.85 | 1 | HOBI/PW-06 | New | 5 | 0 | N-10 | HOBI
24 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Ratna River 4.0m Causeway | nos. | 1 | 143.1604 | 1 | 1 | HOBI/PW-06 | New | 5 | 0 | N-10 | HOBI
25 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Rukway 4.0m Causeway | nos. | 1 | 165.1831 | 0.85 | 1 | HOBI/PW-06 | New | 5 | 0 | N-10 | HOBI
26 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX1 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
27 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX2 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
28 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX3 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
29 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX4 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
30 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX5 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
31 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX6 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
32 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX7 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
33 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX8 | nos. | 1 | 37.0833 | 0.85 | 1 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
34 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX9 | nos. | 1 | 37.0833 | 0.4 | 0.4 | HOBI/PW-06 | New | 4 | 0 | N-10 | HOBI
35 | BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Irrigation Inlet | nos. | 15 | 150.7581 | 0.55 | 1 | HOBI/PW-06 | New | 1 | 0 | N-10 | HOBI
36 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Chargaowdair khal | km | 3.036 | 45.4209 | 1 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
37 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Chotokatari Khal | km | 3.264 | 61.408 | 1 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
38 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Salukadhar Khal | km | 2.428 | 67.6663 | 1 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
39 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Islampur khal | km | 0.634 | 25.7065 | 0 | 0 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
40 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Soyabeel Khal | km | 3.285 | 139.5951 | 1 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
41 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Chatal Beel Khal | km | 5.2176 | 103.126 | 0 | 0 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
42 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Rajendrapur Khal | km | 4.327 | 115.1915 | 0.45 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
43 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Purohogun Khal | km | 2.428 | 65.549 | 1 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
44 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Sutki River | km | 4.5 | 145.977 | 0.57 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
45 | BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Ratna River | km | 7.51 | 137.4972 | 0.53 | 1 | HOBI/PW-07 | New | 7 | 0 | N-10 | HOBI
46 | BWDB/Kish/HFMLIP/ PW-28 | WMG Building | Nos | 6 | 189.48 | 0 | 0.33 | KISH/PW-28/Lot-03 | New | 15 | 0 | N-10 | HOBI

## Package_Name
| sl | Package_No | Payment_30_06_2020
0 | 1 | KISH/PW-01 | 51.09
1 | 2 | KISH/PW-02 | 347.71
2 | 3 | KISH/PW-03 | 625.93
3 | 4 | KISH/PW-04 | 714.69
4 | 5 | KISH/PW-05 | 575.15
5 | 6 | KISH/PW-06 | 837.25
6 | 7 | KISH/PW-07 | 565.07
7 | 8 | KISH/PW-08 | 0
8 | 9 | KISH/PW-09 | 712.33
9 | 10 | KISH/PW-10 | 409.68
10 | 11 | KISH/PW-11 | 522.86
11 | 12 | KISH/PW-12 | 705.59
12 | 13 | KISH/PW-13 | 647.2
13 | 14 | KISH/PW-14 | 806.89
14 | 15 | KISH/PW-15 | 333.94
15 | 16 | KISH/PW-16 | 721.62
16 | 17 | KISH/PW-17 | 1451.95
17 | 18 | KISH/PW-18 | 711.02
18 | 19 | KISH/PW-19 | 331.35
19 | 20 | KISH/PW-20 | 501.12
20 | 21 | KISH/PW-21 | 268.24
21 | 22 | KISH/PW-22 | 281.05
22 | 23 | KISH/PW-23 | 720.33
23 | 24 | KISH/PW-24 | 890.42
24 | 25 | KISH/PW-25 | 749.37
25 | 26 | KISH/PW-26 | 501.12
26 | 27 | KISH/PW-27 | 0
27 | 28 | KISH/PW-28/Lot-01 | 61.6
28 | 29 | KISH/PW-28/Lot-02 | 0
29 | 30 | KISH/PW-28/Lot-03 | 0
30 | 31 | KISH/PW-28/Lot-04 | 74.41
31 | 32 | KISH/PW-29 | 0
32 | 33 | KISH/PW-30 | 0
33 | 34 | KISH/PW-31 | 0
34 | 35 | KISH/PW-32 | 0
35 | 36 | KISH/PW-33 | 0
36 | 37 | KISH/PW-34 | 0
37 | 38 | KISH/PW-35 | 0
38 | 39 | KISH/PW-36 | 0
39 | 40 | KISH/PW-37 | 0
40 | 41 | KISH/PW-38 | 0
41 | 42 | HOBI/PW-01 | 938.57
42 | 43 | HOBI/PW-02 | 1079.52
43 | 44 | HOBI/PW-03 | 0
44 | 45 | HOBI/PW-04 | 655.94
45 | 46 | HOBI/PW-05 | 307.8
46 | 47 | HOBI/PW-06 | 1094.31
47 | 48 | HOBI/PW-07 | 667.67
48 | 49 | NETR/PW-01 | 817.97
49 | 50 | NETR/PW-02 | 475.85
50 | 51 | NETR/PW-03 | 712.73
51 | 52 | NETR/PW-04 | 844.17
52 | 53 | NETR/PW-05 | 635.34
53 | 54 | NETR/PW-06 | 375.82
54 | 55 | NETR/PW-07 | 567.71
55 | 56 | NETR/PW-08 | 134.16
56 | 57 | SUNM/PW-01 | 913.55
57 | 58 | SUNM/PW-02 | 926.3
58 | 59 | SUNM/PW-03 | 511.73
59 | 60 | SUNM/PW-04 | 1521.41
60 | 61 | SUNM/PW-05 | 1061.82
61 | 62 | SUNM/PW-06 | 1268.067
62 | 63 | SUNM/PW-07 | 0

## Value_of_Work_Done
| Package | Structure Code | Component | Unit | Qnty | Cost | Present_Progress | Projected_progress | VDW_30_06_2020 | VDW_30_06_2021 | Work_Done_20_21 | Payment_30_06_2020
13 | HOBI/PW-04 | 11 | Submesible Embankment from 31.600 to 81.740 | km | 23.815 | 638.85 | 0.5 | 1 | 319.425 | 638.85 | 319.425 | 0 | 1
5 | HOBI/PW-01 | 5 | Construction of 6.00m Islampur causeway | nos. | 1 | 247.53 | 0 | 1 | 0 | 247.53 | 247.53 | 0 | 2
12 | HOBI/PW-02 | 5 | Ikrampur CW-6M | nos. | 1 | 210.95 | 0.1 | 1 | 21.095 | 210.95 | 189.855 | 0 | 3
20 | HOBI/PW-05 | 3 | Tetter Drepasionkhal Regulator(2-vent) | nos. | 1 | 216.7515 | 0 | 0.7 | 0 | 151.726 | 151.726 | 0 | 4
2 | HOBI/PW-01 | 8 | Reexcavation of Bashira River 0.000 to 20.000 | km | 17.4 | 732.6 | 0.8 | 1 | 586.08 | 732.6 | 146.52 | 0 | 5
16 | HOBI/PW-05 | 3 | Chandakhali khal Regulator(1-vent) | nos. | 1 | 154.0746 | 0 | 0.75 | 0 | 115.5559 | 115.5559 | 0 | 6
14 | HOBI/PW-04 | 11 | Block road | km | 2 | 507.95 | 0.78 | 1 | 396.201 | 507.95 | 111.749 | 0 | 7
15 | HOBI/PW-05 | 3 | Boranbil khal Regulator (1-vent) | nos. | 1 | 141.3235 | 0 | 0.75 | 0 | 105.9926 | 105.9926 | 0 | 8
17 | HOBI/PW-05 | 3 | Chargaowdair khal Regulator(1-vent) | nos. | 1 | 151.0703 | 0.3 | 1 | 45.3211 | 151.0703 | 105.7492 | 0 | 9 | 1494.1028
18 | HOBI/PW-05 | 3 | Chhoto Katari khal Regulator(1-vent) | nos. | 1 | 143.8109 | 0.1 | 0.7 | 14.3811 | 100.6677 | 86.2866 | 0
4 | HOBI/PW-01 | 3 | Reahblitation of Existing 3-vent Regulator | nos. | 1 | 69.47 | 0 | 1 | 0 | 69.47 | 69.47 | 0
35 | HOBI/PW-06 | 1 | Irrigation Inlet | nos. | 15 | 150.7581 | 0.55 | 1 | 82.917 | 150.7581 | 67.8412 | 0
45 | HOBI/PW-07 | 7 | Ratna River | km | 7.51 | 137.4972 | 0.53 | 1 | 72.8735 | 137.4972 | 64.6237 | 0
42 | HOBI/PW-07 | 7 | Rajendrapur Khal | km | 4.327 | 115.1915 | 0.45 | 1 | 51.8362 | 115.1915 | 63.3553 | 0
44 | HOBI/PW-07 | 7 | Sutki River | km | 4.5 | 145.977 | 0.57 | 1 | 83.2069 | 145.977 | 62.7701 | 0
46 | KISH/PW-28/Lot-03 | 15 | WMG Building | Nos | 6 | 189.48 | 0 | 0.33 | 0 | 62.5284 | 62.5284 | 0
23 | HOBI/PW-06 | 5 | Old kushiyana 6.0m Causeway | nos. | 1 | 373.3459 | 0.85 | 1 | 317.344 | 373.3459 | 56.0019 | 0
19 | HOBI/PW-05 | 3 | Islampur khal Regulator (1-vent) | nos. | 1 | 155.6933 | 0.8 | 1 | 124.5546 | 155.6933 | 31.1387 | 0
25 | HOBI/PW-06 | 5 | Rukway 4.0m Causeway | nos. | 1 | 165.1831 | 0.85 | 1 | 140.4056 | 165.1831 | 24.7775 | 0
11 | HOBI/PW-02 | 5 | Construction of Dairar Khal Causeway 6-m width Causeway | nos. | 1 | 244.2 | 0.95 | 1 | 231.99 | 244.2 | 12.21 | 0
26 | HOBI/PW-06 | 4 | BoX1 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
27 | HOBI/PW-06 | 4 | BoX2 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
28 | HOBI/PW-06 | 4 | BoX3 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
29 | HOBI/PW-06 | 4 | BoX4 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
30 | HOBI/PW-06 | 4 | BoX5 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
31 | HOBI/PW-06 | 4 | BoX6 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
32 | HOBI/PW-06 | 4 | BoX7 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
33 | HOBI/PW-06 | 4 | BoX8 | nos. | 1 | 37.0833 | 0.85 | 1 | 31.5208 | 37.0833 | 5.5625 | 0
0 | HOBI/PW-01 | 10 | Resectioning of Embankment along the left bank of the Bashira River inbwt 2.420 to 9.760 | km | 9.42 | 237.21 | 1 | 1 | 237.21 | 237.21 | 0 | 0
1 | HOBI/PW-01 | 10 | construction of new Embankment along the left bank of bitangal khal inbwt 10.000 to 17.000 | km | 7 | 149.29 | 1 | 1 | 149.29 | 149.29 | 0 | 0
3 | HOBI/PW-01 | 8 | Reexcavation of Matikatakahl from 0.000 to Km 2.295 | km | 2.925 | 99.9 | 1 | 1 | 99.9 | 99.9 | 0 | 0
6 | HOBI/PW-02 | 10 | Resctioning of Submersible Embankment from 0.000 to 26.000 at Left Bank of Kushiyara | Km | 5.7 | 287.53 | 1 | 1 | 287.53 | 287.53 | 0 | 0
7 | HOBI/PW-02 | 10 | Resctioning of Submersible Embankment from 0.000 to 16.02 at Right Bank of Khoai | Km | 16.02 | 377.59 | 1 | 1 | 377.59 | 377.59 | 0 | 0
8 | HOBI/PW-02 | 10 | Construction of New Embankment from Km 22.850 to 31.210 | Km | 9.42 | 304.03 | 1 | 1 | 304.03 | 304.03 | 0 | 0
9 | HOBI/PW-02 | 8 | Reexcavation of Satmukha Khal from 0.000 to 1.790 km | Km | 1.79 | 53.0475 | 1 | 1 | 53.0475 | 53.0475 | 0 | 0
10 | HOBI/PW-02 | 8 | Reexcavation of Singer Beel Khal from 0.000 to 2.720 km | Km | 2.72 | 29.975 | 1 | 1 | 29.975 | 29.975 | 0 | 0
21 | HOBI/PW-05 | 3 | Soaybeel khal Regulator (5-vent) | nos. | 1 | 353.8204 | 1 | 1 | 353.8204 | 353.8204 | 0 | 0
22 | HOBI/PW-06 | 5 | Bibiyana 6.0m Causeway | nos. | 1 | 415.5317 | 1 | 1 | 415.5317 | 415.5317 | 0 | 0
24 | HOBI/PW-06 | 5 | Ratna River 4.0m Causeway | nos. | 1 | 143.1604 | 1 | 1 | 143.1604 | 143.1604 | 0 | 0
34 | HOBI/PW-06 | 4 | BoX9 | nos. | 1 | 37.0833 | 0.4 | 0.4 | 14.8333 | 14.8333 | 0 | 0
36 | HOBI/PW-07 | 7 | Chargaowdair khal | km | 3.036 | 45.4209 | 1 | 1 | 45.4209 | 45.4209 | 0 | 0
37 | HOBI/PW-07 | 7 | Chotokatari Khal | km | 3.264 | 61.408 | 1 | 1 | 61.408 | 61.408 | 0 | 0
38 | HOBI/PW-07 | 7 | Salukadhar Khal | km | 2.428 | 67.6663 | 1 | 1 | 67.6663 | 67.6663 | 0 | 0
39 | HOBI/PW-07 | 7 | Islampur khal | km | 0.634 | 25.7065 | 0 | 0 | 0 | 0 | 0 | 0
40 | HOBI/PW-07 | 7 | Soyabeel Khal | km | 3.285 | 139.5951 | 1 | 1 | 139.5951 | 139.5951 | 0 | 0
41 | HOBI/PW-07 | 7 | Chatal Beel Khal | km | 5.2176 | 103.126 | 0 | 0 | 0 | 0 | 0 | 0
43 | HOBI/PW-07 | 7 | Purohogun Khal | km | 2.428 | 65.549 | 1 | 1 | 65.549 | 65.549 | 0 | 0

## Package_wise_payment
| Package_No | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | KISH/PW-01 | 0 | 0 | 51.09 | -51.09
1 | KISH/PW-02 | 0 | 0 | 347.71 | -347.71
2 | KISH/PW-03 | 0 | 0 | 625.93 | -625.93
3 | KISH/PW-04 | 0 | 0 | 714.69 | -714.69
4 | KISH/PW-05 | 0 | 0 | 575.15 | -575.15
5 | KISH/PW-06 | 0 | 0 | 837.25 | -837.25
6 | KISH/PW-07 | 0 | 0 | 565.07 | -565.07
7 | KISH/PW-08 | 0 | 0 | 0 | 0
8 | KISH/PW-09 | 0 | 0 | 712.33 | -712.33
9 | KISH/PW-10 | 0 | 0 | 409.68 | -409.68
10 | KISH/PW-11 | 0 | 0 | 522.86 | -522.86
11 | KISH/PW-12 | 0 | 0 | 705.59 | -705.59
12 | KISH/PW-13 | 0 | 0 | 647.2 | -647.2
13 | KISH/PW-14 | 0 | 0 | 806.89 | -806.89
14 | KISH/PW-15 | 0 | 0 | 333.94 | -333.94
15 | KISH/PW-16 | 0 | 0 | 721.62 | -721.62
16 | KISH/PW-17 | 0 | 0 | 1451.95 | -1451.95
17 | KISH/PW-18 | 0 | 0 | 711.02 | -711.02
18 | KISH/PW-19 | 0 | 0 | 331.35 | -331.35
19 | KISH/PW-20 | 0 | 0 | 501.12 | -501.12
20 | KISH/PW-21 | 0 | 0 | 268.24 | -268.24
21 | KISH/PW-22 | 0 | 0 | 281.05 | -281.05
22 | KISH/PW-23 | 0 | 0 | 720.33 | -720.33
23 | KISH/PW-24 | 0 | 0 | 890.42 | -890.42
24 | KISH/PW-25 | 0 | 0 | 749.37 | -749.37
25 | KISH/PW-26 | 0 | 0 | 501.12 | -501.12
26 | KISH/PW-27 | 0 | 0 | 0 | 0
27 | KISH/PW-28/Lot-01 | 0 | 0 | 61.6 | -61.6
28 | KISH/PW-28/Lot-02 | 0 | 0 | 0 | 0
29 | KISH/PW-28/Lot-03 | 0 | 62.5284 | 0 | 62.5284
30 | KISH/PW-28/Lot-04 | 0 | 0 | 74.41 | -74.41
31 | KISH/PW-29 | 0 | 0 | 0 | 0
32 | KISH/PW-30 | 0 | 0 | 0 | 0
33 | KISH/PW-31 | 0 | 0 | 0 | 0
34 | KISH/PW-32 | 0 | 0 | 0 | 0
35 | KISH/PW-33 | 0 | 0 | 0 | 0
36 | KISH/PW-34 | 0 | 0 | 0 | 0
37 | KISH/PW-35 | 0 | 0 | 0 | 0
38 | KISH/PW-36 | 0 | 0 | 0 | 0
39 | KISH/PW-37 | 0 | 0 | 0 | 0
40 | KISH/PW-38 | 0 | 0 | 0 | 0
41 | HOBI/PW-01 | 1072.48 | 1536 | 938.57 | 597.43
42 | HOBI/PW-02 | 1305.2575 | 1507.3225 | 1079.52 | 427.8025
43 | HOBI/PW-03 | 0 | 0 | 0 | 0
44 | HOBI/PW-04 | 715.626 | 1146.8 | 655.94 | 490.86
45 | HOBI/PW-05 | 538.0772 | 1134.5263 | 307.8 | 826.7263
46 | HOBI/PW-06 | 1366.3583 | 1559.4788 | 1094.31 | 465.1688
47 | HOBI/PW-07 | 587.556 | 778.3051 | 667.67 | 110.6351
48 | NETR/PW-01 | 0 | 0 | 817.97 | -817.97
49 | NETR/PW-02 | 0 | 0 | 475.85 | -475.85
50 | NETR/PW-03 | 0 | 0 | 712.73 | -712.73
51 | NETR/PW-04 | 0 | 0 | 844.17 | -844.17
52 | NETR/PW-05 | 0 | 0 | 635.34 | -635.34
53 | NETR/PW-06 | 0 | 0 | 375.82 | -375.82
54 | NETR/PW-07 | 0 | 0 | 567.71 | -567.71
55 | NETR/PW-08 | 0 | 0 | 134.16 | -134.16
56 | SUNM/PW-01 | 0 | 0 | 913.55 | -913.55
57 | SUNM/PW-02 | 0 | 0 | 926.3 | -926.3
58 | SUNM/PW-03 | 0 | 0 | 511.73 | -511.73
59 | SUNM/PW-04 | 0 | 0 | 1521.41 | -1521.41
60 | SUNM/PW-05 | 0 | 0 | 1061.82 | -1061.82
61 | SUNM/PW-06 | 0 | 0 | 1268.067 | -1268.067
62 | SUNM/PW-07 | 0 | 0 | 0 | 0

## Structure_Wise_payment
| Items | Code | DPP_Item | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | Construction of Irrigation Inlet | 1 | Inlet | 82.917 | 150.7581 | 22 | 128.7581
1 | Rehab Regulator Rehab Haor | 2 | Reg_Rehab_Rehab | 0 | 0 | 0 | 0
2 | Regulator | 3 | Reg_CW_Box | 538.0772 | 1203.9963 | 6503.97 | -5299.9737
3 | Box Drainage Outlet | 4 | Reg_CW_Box | 266.9996 | 311.4996 | 0 | 311.4996
4 | Causeway | 5 | Reg_CW_Box | 1269.5267 | 1799.9011 | 0 | 1799.9011
5 | Bridge | 6 | Reg_CW_Box | 0 | 0 | 0 | 0
6 | Khal_River Reexcavation(New Haor) | 7 | Khal_Riv_New | 587.556 | 778.3051 | 2546.54 | -1768.2349
7 | Khal_River Reexcavation(Rehab Haor) | 8 | Khal_Riv_Rehab | 769.0025 | 915.5225 | 51.09 | 864.4325
8 | Embankment Rehablitation | 9 | Full_Emb_Rehab | 0 | 0 | 0 | 0
9 | Submersible Embankment Rehabilitation | 10 | Sub_Emb_Rehab | 1355.65 | 1355.65 | 0 | 1355.65
10 | Submersible Embankment Construction | 11 | Sub_Emb_Const | 715.626 | 1146.8 | 5833.04 | -4686.24
11 | Rehab Regulator New Haor | 12 | Reg_Rehab_New | 0 | 0 | 0 | 0
12 | Thrashing Floor Construction | 14 | Thr_Fl_Cost | 0 | 0 | 0 | 0
13 | Construction of WMG | 15 | Wmg_Office | 0 | 62.5284 | 0 | 62.5284
14 | M&E GATE Repair | 16 | Gate_Repair | 0 | 0 | 0 | 0

## DPP_Wise_payment
| DPP_Item | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
0 | Inlet | 82.92 | 150.76 | 22 | 128.76
1 | Reg_Rehab_Rehab | 0 | 0 | 0 | 0
2 | Reg_CW_Box | 2074.6 | 3315.4 | 1478.11 | 1837.29
3 | Khal_Riv_New | 587.56 | 778.31 | 667.67 | 110.64
4 | Khal_Riv_Rehab | 769 | 915.52 | 766.97 | 148.55
5 | Full_Emb_Rehab | 0 | 0 | 0 | 0
6 | Sub_Emb_Rehab | 1355.65 | 1355.65 | 1152.82 | 202.83
7 | Sub_Emb_Const | 715.63 | 1146.8 | 655.94 | 490.86
8 | Reg_Rehab_New | 0 | 0 | 0 | 0
9 | Thr_Fl_Cost | 0 | 0 | 0 | 0
10 | Wmg_Office | 0 | 62.53 | 0 | 62.53
11 | Gate_Repair | 0 | 0 | 0 | 0
|  | 5585.36 | 7724.97 | 4743.51 | 2981.46