## Sheet1
Package | Name | Type | Start | Finish | Length | Vent No | Status | Progress | VWD | Problem
KISH/PW-02 | Construction of 2-vent Bata Khal Regulator at 12.09 km | REGCN | 12.09 | 12.09 | 1 | 2 | OG | 0.32 | 0 | NP
KISH/PW-02 | Diakul Khal from km 1.710 to m 4.690=2.980 | EXKHLN | 1.7 | 4.69 | 2.99 | 0 | OG | 0.22 | 0 | NP
KISH/PW-02 | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | EXKHLN | 0.18 | 4.655 | 4.475 | 0 | OG | 0.02 | 0 | NP
KISH/PW-02 | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | EXKHLN | 0 | 2.225 | 2.225 | 0 | OG | 0.09 | 0 | NP
KISH/PW-02 | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | EXKHLN | 0 | 1.38 | 460 | 0 | OG | 0.89 | 0 | NP
KISH/PW-02 | Bata khal from km, 0.000 to km. 2.790 km | EXKHLN | 0 | 2.79 | 2.79 | None | OG | 0.03 | 0 | NP
KISH/PW-02 | Submersible Embankment from 11.95 to 12.33=0.315 Km | SEMBCN | 11.95 | 12.23 | 0.315 | None | OG | 0.65 | 0 | NP
KISH/PW-03 | Submersible Embankment from 7.366 to 17.749 Part-A | SEMBCN | 7.369 | 17.749 | 10.383 | None | OG | 0.61 | 0 | NP
KISH/PW-03 | Constriction of Kata Khali Khal Regulator 1-V (1.5m x 1.8m ) at km 23.846 (Part-A) | REGCN | 23.85 | 23.85 | 1 | 1 | OG | 0.75 | 0 | NP
KISH/PW-04 | SamarbariKhal Regulator 4-Vent (1.50mx1.80m) at km. 0.78 (Part- C) | REGCN | 0.78 | 0.78 | 1 | 4 | OG | 0.85 | 0 | NP
KISH/PW-04 | Construction of Northern Depression Regulator 1-Vent (1.50mx1.80m) at km. 2.62 (Part- B) | REGCN | 2.62 | 2.62 | 1 | 1 | OG | 0.13 | 0 | NP
KISH/PW-04 | Submersible Embankment from 0.007 to 6.541 Part-B | SEMBCN | 0.007 | 6.541 | 6.534 | None | OG | 0.79 | 0 | NP
KISH/PW-04 | Construction of Southern Depression Regulator 1-Vent (1.50mx1.80m) at km. 6.20 (Part- B) | REGCN | 6.2 | 6.2 | 1 | 1 | OG | 0.36 | 0 | NP
KISH/PW-05 | Construction of Kata Khal Regulator 3-Vent (1.50mx1.80m) at km. 15.30 | REGCN | 15.3 | 15.3 | 1 | 3 | OG | 0.71 | 0 | NP
KISH/PW-05 | Submersible Embankment from 0 to 19.377 Part-C | SEMBCN | 0 | 19.377 | 12.214 | None | OG | 0.73 | 0 | NP
KISH/PW-06 | Construction of Mahindra Khal Regulator (4V-1.5 x 1.80m) at km 12.18. | REGCN | 12.18 | 12.18 | 1 | 4 | OG | 0.23 | 0 | NP
KISH/PW-06 | Samarbari Khal | EXKHLN | 0 | 3.99 | 3.99 | 0 | OG | 0.95 | 0 | NP
KISH/PW-06 | Kurigai Gang | EXRIVN | 0 | 8.38 | 8.38 | 0 | OG | 0.54 | 0 | NP
KISH/PW-06 | Kata Khal | EXKHLN | 0 | 0.6 | 0.6 | 0 | OG | 0.32 | 0 | NP
KISH/PW-06 | Mahinhandra Khal | EXKHLN | 1 | 1.9 | 0.9 | 0 | OG | 0.24 | 0 | NP
KISH/PW-06 | Beri Gang | EXRIVN | 0 | 3.56 | 3.56 | 0 | OG | 0.12 | 0 | NP
KISH/PW-06 | Kata Khali Khal | EXKHLN | 0.2 | 4 | 3.8 | 0 | OG | 0.31 | 0 | NP
KISH/PW-07 | Old Singua River | EXRIVN | 7.3 | 14.4 | 7.1 | 0 | OG | 0.41 | 0 | NP
KISH/PW-07 | Construction of Submersible embnakment In between km. 0.000to km. 56.949) =3.879 km. | SEMBCN | 0 | 56.949 | 3.879 | 0 | OG | 0.1 | 0 | NP
KISH/PW-07 | Karpasha Khal | EXKHLN | 0.1 | 1.615 | 1.515 | 0 | OG | 0.88 | 0 | NP
KISH/PW-07 | Dampara Khal | EXKHLN | 0.04 | 3.6 | 3.56 | 0 | OG | 0.27 | 0 | NP
KISH/PW-07 | Baniajan Khal | EXKHLN | 0.16 | 7.06 | 6.9 | 0 | OG | 0.95 | 0 | NP
KISH/PW-07 | Suti Khal | EXKHLN | 0 | 6.1 | 6.1 | 0 | OG | 0.74 | 0 | NP
KISH/PW-07 | Diga Nadi | EXRIVN | 2.5 | 8.1 | 5.6 | 0 | OG | 0.93 | 0 | NP
KISH/PW-07 | Hajirkhali Khal | EXKHLN | 0.175 | 1.81 | 1.635 | 0 | OG | 0.03 | 0 | NP
KISH/PW-13 | 2-Vent Bera Khal Regulator at Km 4.07 in Naogaon Haor Project | REGCN | 4.07 | 4.07 | 1 | 2 | OG | 0.99 | 0 | NP
KISH/PW-13 | Submersible Embankment from KM 0.00 0to KM 10.000 (Part-A)) | SEMBCN | 0 | 10 | 10 | 0 | OG | 0.91 | 0 | LA
KISH/PW-13 | 3-Vent Pangair Dair Khal Regulator at Km 2.09 in Naogaon Haor Project | REGCN | 2.09 | 2.09 | 1 | 3 | OG | 0.92 | 0 | NP
KISH/PW-14 | 2-Vent Regulator Gokhra at Km 6.04 in Naogaon Haor Project | REGCN | 6.04 | 6.04 | 1 | 2 | OG | 0.95 | 0 | LA
KISH/PW-14 | Submergible Embankment from KM 10.000 to 28.900=16.900 KM (Part-A) | SEMBCN | 10 | 28.9 | 16.9 | 0 | OG | 0.9 | 0 | NP |  | 0.91124
KISH/PW-15 | Submersible Embankment from 0.000 to 9.00-(Part-B) | SEMBCN | 0 | 9 | 9 | 0 | c | 1 | 0 | NP
KISH/PW-15 | 2-Vent Khayer Khal Regulator at Km 5.56 in Naogaon Haor Project | REGCN | 5.56 | 5.56 | 1 | 2 | OG | 0 | 0 | LP | Abandoned
KISH/PW-09 | 2- vent box drainage outlet of Mohorkona of Nunnir haor. | BOXSLCN | 7.74 | 7.74 | 1 | 0 | OG | 0.42 | 0 | NP
KISH/PW-09 | 6.0m Causeway at Samarbari of Nunnir Haor. | CASWCN | 0.78 | 0.78 | 1 | 6 | OG | 0.76 | 0 | NP
KISH/PW-09 | 6m Dampara at km 33.3 in Boro Haor Project | CASWCN | 33.3 | 33.3 | 1 | 6 | OG | 0.09 | 0 | NP
KISH/PW-09 | 4m Karpasha at km 27 in Boro Haor Project | CASWCN | 27 | 27 | 1 | 4 | OG | 0.46 | 0 | NP
KISH/PW-10 | Submersible embankment in between km 0.020 to km 12.400=11.750 | SEMBCN | 0.02 | 12.4 | 11.75 | None | OG | 0.5 | 0 | NP
KISH/PW-10 | 6m Gazipur Causeway at Km 12.34 | CASWCN | 12.34 | 12.34 | 1 | 1 | OG | 0.94 | 0 | NP
KISH/PW-10 | 1-vent 1.50X1.80 Regulator at Jalalpur 22.64 km | REGCN | 22.64 | 22.64 | 1 | 4 | OG | 0.64 | 0 | NP
KISH/PW-11 | 2-Vent Lalpur Khal Regulator at Km16.13 in Noapara Haor Project | REGCN | 16.13 | 16.13 | 1 | 2 | OG | 0.6 | 0 | NP
KISH/PW-11 | Construction of Submersible Embankment in between km 12.400 to km 23.260 | SEMBCN | 12.4 | 23.26 | 10.857 | None | OG | 0.87 | 0 | NP
KISH/PW-16 | Submergible Embankment from KM 9.000 to KM 30.420=14.120 KM (Part-B) | SEMBCN | 9 | 30.42 | 14.12 | 0 | c | 0.95 | 0 | NP | Block Road Not Completed
KISH/PW-16 | 2-Vent Markhali Khal Regulator at Km 33.8 in Naogaon Haor Project | REGCN | 33.8 | 33.8 | 1 | 3 | OG | 0.85 | 0 | LP
KISH/PW-17 | Irrigation Inlet No-50 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-49 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-48 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-47 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-46 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-45 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-44 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-39 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-38 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-37 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-59 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-58 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-60 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-61 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-54 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-57 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-56 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-55 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Box Sluice at Km6.65 in Naogaon Haor Project | BOXSLCN | 6.65 | 6.65 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Box Sluice at Km9.39 in Naogaon Haor Project | BOXSLCN | 9.39 | 9.39 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Box Sluice at Km11.21 in Naogaon Haor Project | BOXSLCN | 11.21 | 11.21 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Box Sluice at Km13.7 in Naogaon Haor Project | BOXSLCN | 13.7 | 13.7 | 1 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Box Sluice at Km18.24 in Naogaon Haor Project | BOXSLCN | 18.24 | 18.24 | 1 | 0 | OG | 0.91 | 0 | LP | 0
KISH/PW-17 | 4-Vent Neora Khal Regulator at Km 44.230 in Naogaon Haor Project | REGCN | 44.15 | 44.15 | 1 | 4 | c | 1 | 0 | NP
KISH/PW-17 | 1-Vent Bagadia Khal Regulator at Km 14.52 in Naogaon Haor Project | REGCN | 14.52 | 14.52 | 1 | 2 | c | 1 | 0 | NP
KISH/PW-17 | Submersible Embankment from 30.420 to 44.200=13.170 KM-(Part-B) | SEMBCN | 30.42 | 44.2 | 13.17 | 0 | c | 1 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-43 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.45 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-42 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.52 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-41 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.23 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-40 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.64 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-53 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.72 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-52 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.24 | 0 | NP
KISH/PW-17 | Irrigation Inlet No-51 in Naogaon Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.15 | 0 | NP
KISH/PW-24 | Submersible Embankment from Km 0.000 to Km 33.520 | SEMBCN | 0 | 33.52 | 19.843 | None | OG | 0.12 | 0 | NP
KISH/PW-12 | 4-Vent Mohorkona Regulator at Km 1.64 in Noapara Haor Project | REGCN | 1.64 | 1.64 | 1 | 4 | OG | 0.84 | 0 | NP
KISH/PW-12 | NabinpurKhal km 4.000 to km 6.800= 2.800 km | EXKHLN | 4 | 6.8 | 2.8 | 0 | OG | 0.67 | 0 | NP
KISH/PW-12 | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km, | EXKHLN | 0.3 | 3.3 | 3 | 0 | OG | 0.44 | 0 | NP
KISH/PW-12 | NaluarKhal km 0.200 to km 0.800 = 0.600 km | EXKHLN | 0.2 | 0.8 | 0.6 | 0 | OG | 0.22 | 0 | NP
KISH/PW-12 | Lalpurkhal km 0.410 to km 4.40 = 3.900 km, | EXKHLN | 0.41 | 4.4 | 3.99 | 0 | OG | 0.42 | 0 | NP
KISH/PW-12 | 3-Vent Naluar Khal Regulator at Km 4.77 in Noapara Haor Project | REGCN | 4.77 | 4.77 | 1 | 3 | OG | 0.15 | 0 | NP
KISH/PW-18 | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM | EXKHLN | 0.495 | 8.405 | 7.91 | 0 | OG | 0.63 | 0 | NP
KISH/PW-18 | MarkhaliKha l from KM 1.01 to KM 4.120=3.11 KM | EXKHLN | 1.01 | 4.12 | 3.11 | 0 | OG | 0.1 | 0 | NP
KISH/PW-18 | KhaiyarKhal 4m causeway at km 24.06 in Naogaon Haor Project | CASWCN | 24.06 | 24.06 | 1 | 4 | OG | 0.02 | 0 | NP
KISH/PW-18 | MarkhaliKhal 6.6 m causeway at km 39.07 in Naogaon Haor Project | CASWCN | 39.07 | 39.07 | 1 | 6 | OG | 0.1 | 0 | NP
KISH/PW-18 | NeoraKhal 4m causeway at km 44.2 in Naogaon Haor Project | CASWCN | 44.2 | 44.2 | 1 | 4 | OG | 0.6 | 0 | NP
KISH/PW-18 | PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM | EXKHLN | 0.08 | 4.36 | 4.28 | 0 | OG | 0.48 | 0 | NP
KISH/PW-18 | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | EXKHLN | 0.52 | 2.03 | 1.51 | 0 | OG | 0.53 | 0 | NP
KISH/PW-18 | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM | EXKHLN | 0.185 | 0.91 | 0.73 | 0 | OG | 0.45 | 0 | NP
KISH/PW-18 | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | EXKHLN | 0.12 | 2.635 | 2.52 | 0 | OG | 0.5 | 0 | NP
KISH/PW-18 | NandirKhal from KM 0.00 to KM 5.985=5.985 | EXKHLN | 0 | 5.985 | 5.99 | 0 | OG | 0.94 | 0 | NP
KISH/PW-18 | DheuhalKhal 4m causeway at km 12.44 in Naogaon Haor Project | CASWCN | 12.44 | 12.44 | 1 | 4 | OG | 0.98 | 0 | NP
KISH/PW-19 | Re-excavation of Atoplal River from KM 0.000 to KM 7.113 | EXRIVN | 0 | 7.113 | 7.11 | 0 | OG | 0.72 | 0 | NP
KISH/PW-19 | Re-excavation of Berachapra River from KM 0.000 to KM 15.820 | EXRIVN | 0 | 15.82 | 15.82 | 0 | OG | 0.69 | 0 | NP
KISH/PW-20 | Construction of 4m Chhitra Khal causeway at km 21.77 in Nunnir Haor Project | CASWCN | 21.77 | 21.77 | 1 | 4 | OG | 0.73 | 0 | NP
KISH/PW-20 | 4m Nabinpur Khal Causeway at Km 23.380 | CASWCN | 23.38 | 23.28 | 1 | 4 | OG | 0.23 | 0 | NP
KISH/PW-20 | 4m Dipjurikhal Causeway at Km 27.000 | CASWCN | 27 | 27 | 1 | None | OG | 0.89 | 0 | NP
KISH/PW-20 | 4m Sudhikhal Causeway at Km 33.300 | CASWCN | 33.3 | 33.3 | 1 | 4 | OG | 0.98 | 0 | NP
KISH/PW-20 | Box Sluice near Nasir at 7.740 of Nunnir Haor Project | BOXSLCN | 7.74 | 7.74 | 1 | 0 | OG | 0.4 | 0 | NP
KISH/PW-20 | Box Sluice Chagaliakhal at Km 10.480 | BOXSLCN | 10.48 | 10.48 | 1 | 0 | OG | 0.24 | 0 | NP
KISH/PW-20 | Boxsluice Singhpurkhal at Km 11.170 in Noapa Haor | BOXSLCN | 11.17 | 11.17 | 1 | 0 | OG | 0.58 | 0 | NP
KISH/PW-20 | Boxsluice Gorucharakhal at Km 10.000 in Noapara Haor | BOXSLCN | 10 | 10 | 1 | 0 | OG | 0.28 | 0 | NP
KISH/PW-20 | Irrigation Inlet No-32 in Noapara Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.9 | 0 | NP
KISH/PW-20 | Irrigation Inlet No-33 in Noapara Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.04 | 0 | NP
KISH/PW-26 | Phulesswari khal (Old) from km 3.250 to km 3.760 = 0.510 km | EXKHLN | 3.25 | 3.76 | 0.51 | 0 | OG | 0.7 | 0 | NP
KISH/PW-26 | Construction of Submersible Embankment in between Km 8.200 to 18.030=0.540 | SEMBCN | 8.2 | 18.03 | 0.54 | 0 | OG | 0.98 | 0 | NP
KISH/PW-26 | Phulesswari khal (New) from km 0.000 to km 4.715 = 4.715 km | EXKHLN | 0 | 4.715 | 4.715 | 0 | OG | 0.92 | 0 | NP
KISH/PW-26 | KalnaKhal from km 14.200 to km 17.200 = 1.140 km | EXKHLN | 14.2 | 17.2 | 1.14 | 0 | OG | 1 | 0 | NP
KISH/PW-26 | Suti Nadi from km 2.200 to km 17.700= 15.500 km | EXRIVN | 2.2 | 17.7 | 15.5 | 0 | OG | 0.88 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-80 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.73 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-79 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.9 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-78 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.86 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-77 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.83 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-76 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.89 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-75 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.43 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-74 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.75 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-73 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.08 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-85 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.71 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-86 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.72 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-72 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.42 | 0 | NP
KISH/PW-25 | Box Sluice at Km24.23 in Dakhshiner Haor Project | BOXSLCN | 24.23 | 24.23 | 1 | 0 | OG | 0.26 | 0 | NP
KISH/PW-25 | 6m causeway at km 12.38 in Dakhshiner Haor Project | CASWCN | 12.38 | 12.38 | 1 | 6 | OG | 0.31 | 0 | NP
KISH/PW-25 | 6m causeway at km 23.46 in Dakhshiner Haor Project | CASWCN | 23.46 | 23.46 | 1 | 6 | OG | 0.37 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-81 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.69 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-82 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.13 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-83 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.08 | 0 | NP
KISH/PW-25 | Irrigation Inlet No-84 in Dakhshiner Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.19 | 0 | NP
KISH/PW-25 | Shankirkhal from km 0.290 to km 8.885 = 8.595 km | EXKHLN | 0.41 | 8.995 | 8.585 | 0 | OG | 0.01 | 0 | NP
KISH/PW-25 | Bantai river from km 0.000 to km 1.650 | EXRIVN | 0 | 1.65 | 1.65 | 0 | OG | 0.27 | 0 | NP
KISH/PW-25 | 5-Vent Regulator at Km 23.19 in Dakhshiner Haor Project | REGCN | 23.19 | 23.19 | 1 | 5 | OG | 0.27 | 0 | NP
KISH/PW-25 | 4m causeway at km 0.02 in Dakhshiner Haor Project | CASWCN | 0.02 | 0.02 | 1 | 4 | OG | 0.74 | 0 | NP
KISH/PW-22 | Irrigation Inlet No-64 in Badla Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.87 | 0 | NP
KISH/PW-22 | Submersible Embankment from 12.059 to 26.998 Total Length 10.463 | SEMBCN | 12.059 | 26.8 | 10.463 | 0 | OG | 0.49 | 0 | NP
KISH/PW-22 | Sajna Khal from km. 0.000 to km. 1.000 | EXKHLN | 0 | 1 | 1 | 0 | OG | 0.23 | 0 | NP
KISH/PW-22 | Chandpur Khal from km. 0.000 to km. 0.700 | EXKHLN | 0 | 0.7 | 0.7 | 0 | OG | 0.69 | 0 | NP
KISH/PW-22 | Baduti Khal from km. 0.000 to km. 1.000 | EXKHLN | 0 | 1 | 1 | 0 | OG | 0.97 | 0 | NP
KISH/PW-22 | Kanala Khal from km. 0.000 to km. 0.584 | EXKHLN | 0 | 0.584 | 0.584 | 0 | OG | 0.21 | 0 | NP
KISH/PW-22 | Kursi Khal from km. 0.000 to km. 2.900 | EXKHLN | 0 | 2.9 | 2.9 | 0 | C | 0.33 | 0 | NP
KISH/PW-22 | Bamuna Khal from km. 0.000 to km. 1.400 | EXKHLN | 0 | 1.4 | 1.4 | 0 | OG | 0.19 | 0 | NP
KISH/PW-22 | Chouganga Khal from km. 1.700 to 1.900 km | EXKHLN | 1.7 | 1.9 | 0.2 | 0 | OG | 0.22 | 0 | NP
KISH/PW-22 | Maora Khal from km. 0.000 to km. 1.700 | EXKHLN | 0 | 1.7 | 1.7 | 0 | OG | 0 | 0 | NP
KISH/PW-22 | Burimara Khal from km. 0.000 to km. 0.439 | EXKHLN | 0 | 0.439 | 0.439 | 0 | OG | 0.28 | 0 | NP
KISH/PW-22 | 4m Kalnakhal causeway at km 7.500 in Badla Haor Project | CASWCN | 7.5 | 7.5 | 1 | 4 | OG | 0.76 | 0 | NP
KISH/PW-22 | Box Sluice at Km19.5 in Badla Haor Project | BOXSLCN | 19.5 | 19.5 | 1 | 0 | OG | 0.35 | 0 | NP
KISH/PW-22 | Box Sluice at Km22.3 in Badla Haor Project | BOXSLCN | 22.3 | 22.3 | 1 | 0 | OG | 0.61 | 0 | NP
KISH/PW-22 | Box Sluice at Km23.6 in Badla Haor Project | BOXSLCN | 23.6 | 23.6 | 1 | 0 | OG | 0.93 | 0 | NP
KISH/PW-22 | Irrigation Inlet No-67 in Badla Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.57 | 0 | NP
KISH/PW-22 | Irrigation Inlet No-63 in Badla Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.95 | 0 | NP
KISH/PW-22 | Irrigation Inlet No-66 in Badla Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.94 | 0 | NP
KISH/PW-22 | Irrigation Inlet No-65 in Badla Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.33 | 0 | NP
KISH/PW-22 | Irrigation Inlet No-62 in Badla Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.77 | 0 | NP
KISH/PW-23 | Irrigation Inlet No-68 in Chatal Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.46 | 0 | NP
KISH/PW-23 | Submersible Embankment from 2.469 to 6.979=4.510 | SEMBCN | 2.469 | 6.979 | 4.51 | 0 | C | 0.71 | 0 | NP
KISH/PW-23 | 2-Vent Mozila Khal Regulator at Km 12.250 in Chatal Haor Project | REGCN | 12.25 | 12.25 | 1 | 2 | OG | 0.84 | 0 | NP
KISH/PW-23 | 2-Vent NoaparakhaliKhal Regulator at Km 5.73 in Chatal Haor Project | REGCN | 5.73 | 5.73 | 1 | 2 | OG | 0.97 | 0 | NP
KISH/PW-23 | Re-excavation of Mozilla Khal from Km 0.000 to 1.775 | EXKHLN | 0 | 1.775 | 1.775 | 0 | OG | 0.54 | 0 | NP
KISH/PW-23 | Re-excavation of Mogar Khal from Km 0.000 to 0.150 | EXKHLN | 0 | 0.15 | 0.15 | 0 | OG | 0.14 | 0 | NP
KISH/PW-23 | Box Sluice Mogarkhal at Km2.74 in Chatal Haor Project | BOXSLCN | 2.74 | 2.74 | 1 | 0 | OG | 0.15 | 0 | NP
KISH/PW-23 | Irrigation Inlet No-71 in Chatal Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.95 | 0 | NP
KISH/PW-23 | Irrigation Inlet No-70 in Chatal Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.62 | 0 | NP
KISH/PW-23 | Irrigation Inlet No-69 in Chatal Haor Project | IRINCN | 0 | 0 | 1 | 0 | OG | 0.45 | 0 | NP
KISH/PW-01 | Ganakkhali khal from km 0.000 to km 5.625=5.625 km | EXRIVN | 0 | 5.625 | 5.625 | 0 | OG | 0.15 | 0 | NP
KISH/PW-01 | Betal Doba from km1.315 to km 3.466 =2.151 km | EXRIVN | 1.315 | 3.446 | 2.151 | 0 | OG | 0.16 | 0 | NP
KISH/PW-01 | Alalia-bahadia Khal from km 1.325 to km 2.545=1.220 km | EXRIVN | 1.325 | 2.545 | 1.22 | 0 | OG | 0.58 | 0 | NP
KISH/PW-01 | katakhali khal from km 0.000 to km 1.550=1.550 km | EXRIVN | 0 | 1.55 | 1.55 | 0 | OG | 0.38 | 0 | NP
KISH/PW-01 | Kali Khal from km 0.00 to km 1.00=1.000 km. | EXRIVR | 0 | 1 | 1 | None | OG | 0.11 | 0 | NP
KISH/PW-21 | Construction of Kursi Khal Regulatior 2-vent 1.50m x 1.80m at km 16.10 | REGCN | 16.1 | 16.1 | 1 | 2 | OG | 0.48 | 0 | NP
KISH/PW-21 | Sub-Mergible Emabankment from km 2.565 to km 12.059=9.494 km | SEMBCN | 2.565 | 12.059 | 9.494 | 0 | OG | 0.23 | 0 | NP
KISH/PW-21 | Construction of Chouganga Khal Regulatior 1-vent 1.50m x 1.80m at km 24.40 | REGCN | 24.4 | 24.4 | 1 | 1 | OG | 0.12 | 0 | NP
KISH/PW-27 | Constration of 1vent (1.80m x 1.50 m) Phulesgwari Regulator at km 8.241 | REGCN | 8.24 | 8.24 | 1 | 1 | OG | 0.65 | 0 | NP
KISH/PW-27 | Constration of 1 vent (1.80m x 1.50 ) kalna regulatior at km 16.170 1 no. | REGCN | 16.17 | 16.17 | 1 | 1 | OG | 0.02 | 0 | NP
KISH/PW-27 | 6m Suti causeway | CASWCN | 17.71 | 17.71 | 1 | 6 | OG | 0.99 | 0 | NP
KISH/PW-27 | 4mchonati causeway | CASWCN | 9.84 | 9.84 | 1 | 4 | OG | 0.18 | 0 | NP
KISH/PW-27 | Drainage box outlet at km | BOXSLCN | 0 | 0 | 1 | 0 | OG | 0.74 | 0 | NP
KISH/PW-27 | Drainage box outlet at km 17.74 | BOXSLCN | 17.74 | 17.74 | 1 | 0 | OG | 0.86 | 0 | NP