## Sheet1
id | Code | Description
57 | 4111306 | Construction of Irrigation Inlet (New Haors) | 4111306_Construction of Irrigation Inlet (New Haors)
58 | 4111307 | Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects) | 4111307_ Re-installation/Construction of Regulator/ Causeway (Rehabilitation Sub-Projects)
59 | 4111307 | Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors) | 4111307_ Installation/Construction of New Regulators/ Causeway/Bridge/Box Drainage Outlet) (New Haors)
60 | 4111307 | Re-excavation of Khal/River (New Haors) | 4111307_ Re-excavation of Khal/River (New Haors)
61 | 4111201 | Re-excavation of Khal/River (Rehabilitation Sub-Projects) | 4111201_ Re-excavation of Khal/River (Rehabilitation Sub-Projects)
62 | 4111201 | Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects) | 4111201_ Rehabilitation of Full Embankment (Resection/ construction) (Rehabilitation Sub-Projects)
63 | 4111201 | Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) | 4111201_ Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects)
64 | 4111201 | Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum) | 4111201_Construction of Submersible Embankment (New Haors) (Earth Volume: 29.98 lakh cum)
65 | 4111201 | Rehabilitation of Regulator (New Haors) | 4111201_ Rehabilitation of Regulator (New Haors)
66 | 4111201 | Construction of WMG Office | 4111201_Construction of WMG Office
67 | 4111201 | O&M During Construction | 4111201_O&M During Construction

## Sheet5
| 7146.032 | 156388 |  |  | Khal | Box
| 2175338.384 | 582066.296 |  |  | 2651098.73 | 3807686.27 | 6458785 |  | Chtra Khal CW | 3058698.583
| 442686.376 | 132743.207 |  |  | 0.41046 | 0.58954 |  |  | Nabinpur Khal CW | 3991659.935
| 25927.941 | 2610.381 |  | GoB | 331387.7 | 475961.3 |  |  | Dipjuri KHal CW | 2816996.163
total | 2651098.733 | 71523.693 |  | RPA | 2319711.03 | 3331724.97 | 5651436 |  | Sudhi Khal CW | 3363880.156
|  | 769684.617 |  |  | 2651098.73 |  |  |  | Box Sluice | 808976.339 | DF | GoB | RPA
|  | 776580.144 | [6 empty] | Sub-Total Structure | 14040211.176 | 0.93161 | 1755026.3105 | 12285185.1049
|  | 2491596.338 | [6 empty] | Irrigation Inlet | 1030629.567 | 0.068386 | 128828.6895 | 901800.8951
|  |  | 2491596.338 | [6 empty] | 15070840.743 |  | 1883855 | 13186986 | 15070841
Kish-22 1st IPC
[9 empty] | Embankment | Khal |  |  | DF | GoB | RPA
[9 empty] | 5478066.24 | 6284471.15 | Embankment | 5478066.24 | 0.45355 | 616282.5073 | 4313977.0978
[10 empty] | 315745.97 | Khal | 6600217.12 | 0.54645 | 742524.4927 | 5197670.9022
[8 empty] | Total | 5478066.24 | 6600217.12 |  |  | 1 | 1358807 | 9511648
[8 empty] | GT |  | 12078283.36
Kish-22 2nd IPC
[9 empty] | Embankment | Khal |  |  | DF | GoB | RPA
[9 empty] | 5478066.24 | 6284471.15 | Embankment | 5478066.24 | 0.45355 | 68476.0357 | 479330.4359
[10 empty] | 315745.97 | Khal | 6600217.12 | 0.54645 | 82502.9643 | 577518.5641
[8 empty] | Total | 5478066.24 | 6600217.12 |  |  | 1 | 150979 | 1056849 | 1207828
[8 empty] | GT |  | 12078283.36
Kis -17 9th RA Bill
[11 empty] | Embankment | 5923319.27
[11 empty] | Block Road | 317931.49
[11 empty] | Total | 6241250.76 |  |  |  | DF | GoB | RPA
[11 empty] | Bagdia Khal Regulator | 1361092.04 |  | Emb | 6241250.76 | 0.33151 | 769465.2938 | 5386258.0511
[11 empty] | Neora Khal Regulator | 0 |  | Reg/Box | 6996164.259 | 0.37161 | 862536.3399 | 6037755.4942
[11 empty] | Pipe Inlet | 5589090.31 |  | Inlet | 5589090.31 | 0.29687 | 689062.3663 | 4823437.4548
[11 empty] | Box Drainage Outlet | 5635072.219 |  |  | 18826505.329 | 1 | 2321064 | 16247451
[11 empty] | Total | 12585254.569
[11 empty] | GT | 18826505.329
[11 empty] | Kish -10 4th RA Bill |  | DF
[11 empty] | EMB | 4734271.736 | 0.52055 | 591783.8037 | 4142488.1874
[11 empty] | Regulator | 4360514.774 | 0.47945 | 545064.1963 | 3815450.8126
[12 empty] | 9094786.51 | 1 | 1136848 | 7957939 | 9094787
[11 empty] | Kish -11 4th RA Bill |  | DF
[11 empty] | EMB | 0 | 0.52055 | 591783.8037 | 4142488.1874
[11 empty] | Regulator | 3214491.54 | 0.47945 | 545064.1963 | 3815450.8126
[13 empty] | 1 | 1136848 | 7957939 | 9094787
[11 empty] | Kish -25 5th RA Bill |  |  |  | DF | GoB | RPA
[11 empty] | Khal | 5702443.78 | Khal | 5702443.78 | 0.4773 | 712805.5214 | 4989638.1727
[11 empty] | Regulator | 6070081.27 | Regulator | 6244931.4 | 0.5227 | 780616.4786 | 5464314.8273
[11 empty] | Mobilization | 174850.13 |  |  | 1 | 1493422 | 10453953
[11 empty] | Regulator | 6244931.4
11947375.18
[11 empty] | Kish -13 5th RA Bill |  |  |  | DF | GoB | RPA
[11 empty] | Emb | 4129593.08 | Khal | 5702443.78 | 0.4773 | 712805.5214 | 4989638.1727
[11 empty] | Regulator |  | Regulator | 6244931.4 | 0.5227 | 780616.4786 | 5464314.8273
[11 empty] | Mobilization | 174850.13 |  |  | 1 | 1493422 | 10453953
[11 empty] | Regulator | 6244931.4
11947375.18

## IPC_Dist
Sl No | IPCNo | Inlet | Reg_Rehab_Rehab | Reg_CW_Box | Khal_Riv_New | Khal_Riv_Rehab | Full_Emb_Rehab | Sub_Emb_Rehab | Sub_Emb_Const | Reg_Rehab_New | Wmg_Office | Gate_Repair | Total | Gob | Rpa | Package No | IPC No | Month
1 | 60/NETR-Gate Replacement final Bill | [10 empty] | 224805 |  | 28740 | 196065 | GT-01 | 1 | 12
2 | 76/NETR-Gate Replacement 1st RA Bill | [10 empty] | 2260946 |  | 237399 | 2023547 | GT-02 | 1 | 12
3 | 84/(SUNM-01)-05 1st RA Bill |  |  | 11767769.7 | [9 empty] | 1548390.75 | 10838735.25 | SUNM-05 | 1 | 12
4 | 92/NETR-Gate Replacement 2nd RA Bill | [10 empty] | 831186 |  | 104719 | 726467 | GT-02 | 2 | 12
5 | 110/NETR-05 1st RA Bill |  |  | 12310799 | [9 empty] | 1538850 | 10771949 | NETR-05 | 1 | 1
6 | 111/KISH-23 1st RA Bill |  |  | 11592350 | [9 empty] | 1449044 | 10143306 | KISH-23 | 1 | 1
7 | 120/NETR-06 4th RA Bill |  |  | 3807686.27 | 2651098.73 | [8 empty] | 807349 | 5651436 | NETR-06 | 4 | 1
8 | 132/(SUNM-01)-06 5th RA Bill |  |  |  | 13531309 | [8 empty] | 1691414 | 11839895 | SUNM-06 | 5 | 1
9 | 131/KISH-20 4th RA Bill | 1030629.59 |  | 14040211.41 | [9 empty] | 1883855 | 13186986 | KISH-20 | 4 | 1
10 | 133/KISH-22 1st RA Bill |  |  |  | 5940195.39 |  |  |  | 4930259.62 |  |  |  |  | 1358807 | 9511648 | KISH-22 | 1 | 1
11 | 138/KISH-22 2nd RA Bill |  |  |  | 660021.52 |  |  |  | 547806.48 |  |  |  |  | 150979 | 1056849 | KISH-22 | 2 | 2
12 | 142/KISH-17 9th RA Bill | 5512499.82 |  | 6900291.83 |  |  |  |  | 6155723.35 |  |  |  |  | 2321064 | 16247451 | KISH-17 | 9 | 2
13 | 144/KISH-10 4th RA Bill |  |  | 4360515.01 |  |  |  |  | 4734271.99 |  |  |  |  | 1136848 | 7957939 | KISH-10 | 4 | 2
14 | 143/KISH-11 5th RA Bill |  |  | 3214492 | [9 empty] | 401812 | 2812680 | KISH-11 | 5 | 2
15 | 152/HOBI-6 7th RA Bill |  |  | 10040694 | [9 empty] | 1255087 | 8785607 | HOBI-06 | 7 | 2
16 | 154/(SUNM-02)-02 2nd RA Bill |  |  | 0 | 12042332 | [8 empty] | 1505304 | 10537128 | SUNM-02 | 2 | 2
17 | 153/KISH-09 5th RA Bill |  |  | 7786053 | [9 empty] | 973257 | 6812796 | KISH-09 | 5 | 2
18 | 155/KISH-25 5th RA Bill |  |  | 6244931.31 | 5702443.69 | [8 empty] | 1493422 | 10453953 | KISH-25 | 5 | 2
19 | 157/KISH-13 5th RA Bill | [7 empty] | 4129593 |  |  |  |  | 516199 | 3613394 | KISH-13 | 5 | 2
20 | 158/KISH-13 6th RA Bill | [7 empty] | 3129025 |  |  |  |  | 391128 | 2737897 | KISH-13 | 6 | 2
21 | 156/SUNM-01 4th RA Bill |  |  | 10121557.06 |  |  |  |  | 9416806.852 |  |  |  |  | 2442296 | 17096068 | SUNM-01 | 4 | 2
22 | 161/KISH-16 9th RA Bill | [7 empty] | 4153902.918 |  |  |  |  | 519238 | 3634665 | KISH-16 | 9 | 2
23 | 160/(SUNM-01)-05 2nd RA Bill |  |  | 31435052 | [9 empty] | 3929382 | 27505670 | SUNM-05 | 2 | 2
24 | 159/KISH-28/Lot-4 1st RA Bill | [9 empty] | 7440653 |  |  | 930082 | 6510571 | KISH-28/Lot-4 | 1 | 2
25 | 161/HOBI-1 5th RA Bill | [7 empty] | 8773275 |  |  |  |  | 1096659 | 7676616 | HOBI-01 | 5 | 3
26 | 172/KISH-12 7th RA Bill |  |  | 967157.27 | 7576934.1 | [8 empty] | 1068011 | 7476080 | KISH-12 | 7 | 3
27 | 175/KISH-23 2nd RA Bill |  |  | 15300148.25 |  |  |  |  | 5002242.94 |  |  |  |  | 2537799 | 17764592 | KISH-23 | 2 | 3
28 | 174/NETR-01 4th RA Bill | [7 empty] | 6272429.75 |  |  |  |  | 784054 | 5488375 | NETR-01 | 4 | 3
29 | 173/NETR-03 4th RA Bill |  |  | 2376584.493 |  |  |  |  | 5851260.367 |  |  |  |  | 1028481 | 7199364 | NETR-03 | 4 | 3
30 | 190/KISH-22 2nd RA Bill |  |  | 3951018.61 | 1303448.12 |  |  |  | 3401350.1 |  |  |  |  | 1081977 | 7573840 | KISH-22 | 2 | 3
31 | 191/KISH-26 6th RA Bill |  |  |  | 5018209.87 | [8 empty] | 627276 | 4390934 | KISH-26 | 6 | 3
32 | 194/(SUNM-01)-06 6th RA Bill |  |  |  | 28440949.88 | [8 empty] | 2930119 | 20510831 | SUNM-06 | 6 | 3
33 | 192/(SUNM-01)-04 4th RA Bill | [7 empty] | 11803695.96 |  |  |  |  | 1475462 | 10328234 | SUNM-04 | 4 | 3
34 | 195/NETR-06 5th RA Bill |  |  | 3678989.383 | 1997998.992 |  |  |  |  | 24430.227 |  |  |  | 712677 | 4988742 | NETR-06 | 5 | 3
35 | 193/KISH-05 5th RA Bill |  |  | 764582 |  |  |  |  | 7622328.7 |  |  |  |  | 1048364 | 7338547 | KISH-05 | 5 | 3
36 | 199/KISH-17 10th RA Bill | 4444197.77 |  | 181114.164 | [9 empty] | 781917 | 5473421 | KISH-17 | 10 | 3
37 | 210/(SUNM-01)-06 6th RA final Bill |  |  |  | 28440949.88 | [8 empty] | 625000 | 4375000 | SUNM-06 | 6 | 3
38 | 209/(SUNM-01)-05 2nd RA Bill |  |  | 31061589.32 | [9 empty] | 3882699 | 27178890 | SUNM-05 | 2 | 3
39 | 213/KISH-23 3rd RA Bill |  |  | 18143506.6 |  |  |  |  | 644634.2 |  |  |  |  | 2348518 | 16439623 | KISH-23 | 3 | 4
40 | 212/(SUNM-02)-02 3rd RA Bill |  |  |  | 35010947 | [8 empty] | 4376368 | 30634579 | SUNM-02 | 3 | 4
41 | 214/KISH-26 7th RA Bill |  |  |  | 9000456.89 | [8 empty] | 1125057 | 7875399 | KISH-26 | 7 | 4
42 | 217/KISH-14 8th RA Bill | [7 empty] | 6195501.836 |  |  |  |  | 774438 | 5421064 | KISH-14 | 8 | 4
43 | 218/KISH-17 11th RA Bill | 2677161.36 |  | 6396151.47 |  |  |  |  | 686638.29 |  |  |  |  | 1181215 | 8268502 | KISH-17 | 11 | 4
44 | 220/KISH-03 8th RA Bill |  |  | 333327.884 |  |  |  |  | 4060359.229 |  |  |  |  | 549211 | 3844476 | KISH-03 | 8 | 4
45 | 216/KISH-16 10th RA Bill | [7 empty] | 2275479 |  |  |  |  | 284435 | 1991044 | KISH-16 | 10 | 4
46 | 219/KISH-9 6th RA Bill |  |  | 8581506.13 | [9 empty] | 1072688 | 7508818 | KISH-09 | 6 | 4
47 | 225/KISH-21 1st RA Bill | [7 empty] | 19139634.74 |  |  |  |  | 2392454 | 16747181 | KISH-21 | 1 | 4
48 | 226/(SUNM-01)-05 3rd RA Bill |  |  | 52195699.36 | [9 empty] | 6524462 | 45671237 | SUNM-05 | 3 | 4
49 | 232/HOBI-2 4th RA Bill |  |  | 14453370.69 |  |  |  |  | 6619216.55 |  |  |  |  | 2571157 | 17998099 | HOBI-02 | 4 | 5
50 | 233/KISH-25 6th RA Bill |  |  |  | 1017606.69 |  |  |  | 5862363.64 |  |  |  |  | 687997 | 4815979 | KISH-25 | 6 | 5
51 | 351/(SUNM-02)-02 4th RA Bill |  |  |  | 30565887.63 | [8 empty] | 3820736 | 26745152 | SUNM-02 | 4 | 5
52 | 248/KISH-01 1st RA Bill |  |  |  |  | 5108675.07 | [7 empty] | 638585 | 4470090 | KISH-01 | 1 | 5
53 | 250/(SUNM-01)-03 3rd RA Bill |  |  | 19919089.84 | [9 empty] | 2489886 | 17429204 | SUNM-03 | 3 | 5
54 | 252/NETR-08 1st RA Bill |  |  | 10607590.28 | [9 empty] | 1325949 | 9281641 | NETR-08 | 1 | 5
55 | 249/(SUNM-01)-04 5th RA Bill | [7 empty] | 21924820 |  |  |  |  | 2740603 | 19184217 | SUNM-04 | 5 | 5
56 | 246/KISH-11 6th RA Bill |  |  | 3582351.46 | [9 empty] | 447794 | 3134557 | KISH-11 | 6 | 5
57 | 247/KISH-10 5th RA Bill |  |  | 3457479.39 |  |  |  |  | 3940433.72 |  |  |  |  | 924739 | 6473174 | KISH-10 | 5 | 5
58 | 245/KISH-6 12th RA Bill |  |  |  | 3785875.06 | [8 empty] | 473234 | 3312641 | KISH-06 | 12 | 5
59 | 243/NETR-03 5th RA Bill | [7 empty] | 10106760.09 |  |  |  |  | 1263345 | 8843415 | NETR-03 | 5 | 5
60 | 242/NETR-02 4th RA Bill |  |  |  |  | 9265078.22 | [7 empty] | 1158135 | 8106943 | NETR-02 | 4 | 5
61 | 241/NETR-01 5th RA Bill | [5 empty] | 1181164.51 | [6 empty] | 1476471 | 10335294 | NETR-01 | 5 | 5
62 | 240/HOBI-5 3rd RA Bill |  |  | 3421028.06 | [9 empty] | 427629 | 2993399 | HOBI-05 | 3 | 5
63 | 244/KISH-23 4th RA Bill |  |  | 10902577.68 |  |  |  |  | 3276311.75 |  |  |  |  | 1772361 | 12406528 | KISH-23 | 4 | 5
64 | 255/NETR-06 6th RA Bill |  |  | 797985.01 | 356391.44 |  |  |  |  | 976050 |  |  |  | 266303.31 | 1864123.18 | NETR-06 | 6 | 6
65 | 256/NETR-04 4th RA Bill |  |  |  |  | 18663800.67 |  | 4842188.09 | [5 empty] | 2938249 | 20567740 | NETR-04 | 4 | 6
66 | 257/KISH-26 8th RA Bill |  |  |  | 9480354.1 |  |  |  | 477480.29 |  |  |  |  | 1244729 | 8713105 | KISH-26 | 8 | 6
67 | 273/KISH-13 7th RA Bill | [7 empty] | 7682708.75 |  |  |  |  | 960339 | 6722370 | KISH-13 | 7 | 6
68 | 347/(SUNM-01)-06 7th RA Bill |  |  |  | 16117256.97 | [8 empty] | 2014657 | 14102600 | SUNM-06 | 7 | 6
69 | 351/KISH-21 2nd RA Bill | [7 empty] | 7683514.47 |  |  |  |  | 960439 | 6723075 | KISH-21 | 2 | 6
70 | 349/(SUNM-01)-04 6th RA Bill | [7 empty] | 14652108 |  |  |  |  | 1831514 | 12820594 | SUNM-04 | 6 | 6
71 | 348/(SUNM-01)-05 4th RA Bill |  |  | 10164437.2 | [9 empty] | 1270555 | 8893882 | SUNM-05 | 4 | 6
72 | 350/(SUNM-02)-01 5th RA Bill |  |  | 9258302.87 | 203113.3 |  |  |  | 544818.16 |  |  |  |  | 1250779 | 8755455 | SUNM-01 | 5 | 6
73 | 352/HOBI-4 5th RA Bill | [7 empty] | 2918327.09 |  |  |  |  | 364791 | 2553536 | HOBI-04 | 5 | 6
74 | 353/HOBI-5 4th RA Bill |  |  | 4065192.31 | [9 empty] | 508149 | 3557043 | HOBI-05 | 4 | 6
75 | 346/KISH-14 9th RA Bill |  |  | 395448 |  |  |  |  | 6835897.89 |  |  |  |  | 799871 | 5599096 | KISH-14 | 9 | 6
76 | 345/KISH-12 8th RA Bill |  |  |  | 7041775.36 |  |  |  | 2173969.32 |  |  |  |  | 1151968 | 8063777 | KISH-12 | 8 | 6
77 | 356/KISH-26 9th RA Final Bill |  |  |  | 1333756.381 |  |  |  | 3138936.3 |  |  |  |  | 559087 | 3913606 | KISH-26 | 9 | 6
78 | 355/HOBI-6 8th RA Bill |  |  |  | 7166150.797 | [8 empty] | 895769 | 6270381 | HOBI-06 | 8 | 6
79 | 344/HOBI-1 6th RA Bill |  |  |  | 841027.357 |  |  |  | 12356769.643 |  |  |  |  | 1649725 | 11548073 | HOBI-01 | 6 | 6
80 | 354/HOBI-2 5th RA Bill |  |  | 5452594.47 |  |  |  |  | 23284588.45 |  |  |  |  | 3592148 | 25145035 | HOBI-02 | 5 | 6
81 | 370/NETR-04 5th RA Bill |  |  |  |  | 6871914.25 |  | 3134579.898 | [5 empty] | 1342829 | 9399803 | NETR-04 | 5 | 6
82 | 378/NETR-05 3rd RA Bill |  |  | 20162366.32 | [9 empty] | 2520296 | 17642070 | NETR-05 | 3 | 6
83 | 369/NETR-08 2nd RA Bill |  |  | 3038478 | [9 empty] | 379810 | 2658668 | NETR-08 | 2 | 6
84 | 371/KISH-28 2nd RA Bill | [9 empty] | 1890979 |  |  | 236372 | 1654607 | KISH-28/Lot-1 | 2 | 6
85 | 361/KISH-20 5th RA Bill |  |  | 11734497.34 | [9 empty] | 1091812 | 7642685 | KISH-20 | 5 | 6
86 | 362/KISH-17 12th RA Bill | 237277.17 |  | 4754324.16 |  |  |  |  | 3536591.639 |  |  |  |  | 1066024 | 7462169 | KISH-17 | 12 | 6
87 | 360/KISH-16 11th RA Bill | [7 empty] | 8566376 |  |  |  |  | 1070797 | 7495579 | KISH-16 | 11 | 6
88 | 357/HOBI-7 5th RA Bill |  |  |  | 21434033 | [8 empty] | 2602548 | 18217838 | HOBI-07 | 5 | 6
89 | 375/KISH-04 6th/final RA Bill |  |  | 3950811.102 |  |  |  |  | 1869271.878 |  |  |  |  | 711031 | 4977219 | KISH-04 | 6 | 6
90 | 377/KISH-13 8th RA Bill |  |  | 3715423 | [9 empty] | 464428 | 3250995 | KISH-13 | 8 | 6
91 | 374/KISH-09 7th RA Bill |  |  | 15319532 | [9 empty] | 1914942 | 13404590 | KISH-09 | 7 | 6
92 | 359/KISH-07 9th RA Bill |  |  |  | 4972139.51 |  |  |  | 112500 |  |  |  |  | 635580 | 4449060 | KISH-07 | 9 | 6
93 | 373/KISH-22 3rd RA Bill | [7 empty] | 7671622.1 |  |  |  |  | 921416 | 6449915 | KISH-22 | 3 | 6
94 | 372/KISH-25 7th RA Bill |  |  | 2004423.12 | 2200388.38 |  |  |  | 27775 |  |  |  |  | 701073 | 4907507 | KISH-25 | 7 | 6
95 | 363/KISH-24 8th/Final RA Bill | [7 empty] | 10277493 |  |  |  |  | 1284687 | 8992806 | KISH-24 | 8 | 6
96 | 358/KISH-06 13th/Final RA Bill |  |  | 1253692.11 | 5035264.49 | [8 empty] | 994457 | 6961196 | KISH-06 | 13 | 6
97 | 364/KISH-02 7th RA Bill |  |  | 1831376.254 | 1360415.54 |  |  |  | 455742.37 |  |  |  |  | 455942 | 3191592 | KISH-02 | 7 | 6
98 | 376/KISH-23 5th RA Bill |  |  | 5389926.93 | 1782400.4 | [8 empty] | 896541 | 6275786 | KISH-23 | 5 | 6
99 | 365/KISH-19 6th RA Bill | [7 empty] | 3499306 |  |  |  |  | 437413 | 3061893 | KISH-19 | 6 | 6
100 | 366/NETR-01 6th RA Bill | [5 empty] | 20826914 | [6 empty] | 2603364 | 18223550 | NETR-01 | 6 | 6
101 | 367/NETR-02 5th RA Bill |  |  |  |  | 3669874 | [7 empty] | 458734 | 3211140 | NETR-02 | 5 | 6
102 | 368/NETR-03 6th RA Bill | [5 empty] | 24327546 | [6 empty] | 3040943 | 21286603 | NETR-03 | 6 | 6

## Sheet3
|  | EMB | Khal
|  | 17644936.1 | 204301.34
|  | -166123.08 | 98414.79
|  | 4900152.1 | 3557905.85
|  | 286245 | 866744.93
|  | 619378.33 | 161285.36
|  | 23284588.45 | 15775.98
|  | 28737182.92 | 14288.02
|  | 5452594.47 | 53423.24
4972139.51
| Khal | Emb
| 875966.733 | 46900.13
| 906433.664 | 2590080.18
| 1782400.397 | 1949709.13
| 7172327.33 | 1366206.83
| 5389926.933 | 739134.85
379009.28
600581.7
7671622.1
358/Kish-06 13th/Final RA Bill | 5035264.49 |  |  | 1253692.11 | 786119.575 | 5502837.025

## Sheet2
372/Kish-25 7th RA Bill | 2004423.12 | 2200388.38 |  |  | 27775 |  | 529073 | 4232587
363/Kish-24 8th/Final RA Bill |  |  |  |  | 10277493 |  | 1284687 | 8992806
358/Kish-06 13th/Final RA Bill |  | 5035264.49 |  |  |  | 1253692.11 | 786119.575 | 5502837.025
364/Kish-02 7th RA Bill |  | 1360415.54 |  |  | 455742.37 | 1831376.254 | 455942 | 3191592
376/Kish-23 5th RA Bill | 5389926.93 | 1782400.4 |  |  |  |  | 896541 | 6275786
365/Kish-19 6th RA Bill |  |  |  |  | 3499306 |  | 437413 | 3061893
366/Netr-01 6th RA Bill |  |  |  | 20826914 |  |  | 2603364 | 18223550
367/Netr-02 5th RA Bill |  |  | 3669874 |  |  |  | 458734 | 3211140
368/Netr-03 6th RA Bill |  |  |  | 24327546 |  |  | 3040943 | 21286603

## Package_wise_cost
PackageNo | IPC1 | IPC2 | IPC3 | IPC4 | IPC5 | IPC6 | IPC7 | IPC8 | IPC9 | IPC10 | IPC11 | IPC12 | IPC13 | IPC14 | IPC15 | IPC16 | IPC17 | IPC18 | IPC19 | IPC20 | Total
KISH-01
KISH-02
KISH-03
KISH-04
KISH-05
KISH-06
KISH-07
KISH-09
KISH-10
KISH-11
KISH-12
KISH-13
KISH-14
KISH-15
KISH-16
KISH-17
KISH-18
KISH-19
KISH-20
KISH-21
KISH-22
KISH-23
KISH-24
KISH-25
KISH-26
KISH-27
KISH-28/Lot-1
KISH-28/Lot-2
KISH-28/Lot-3
KISH-28/Lot-4
HOBI-01
HOBI-02
HOBI-04
HOBI-05
HOBI-06
HOBI-07
HOBI-08
NETR-01
NETR-02
NETR-03
NETR-04
NETR-05
NETR-06
NETR-07
NETR-08
SUNM-01
SUNM-02
SUNM-03
SUNM-04
SUNM-05
SUNM-06
GT-01
GT-02
GT-03

## Monthly_Rpa
PackageNo | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Inlet
Reg_Rehab_Rehab
Reg_CW_Box
Khal_Riv_New
Khal_Riv_Rehab
Full_Emb_Rehab
Sub_Emb_Rehab
Sub_Emb_Const
Reg_Rehab_New
Wmg_Office
Gate_Repair

## Monthly_Gob
PackageNo | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Inlet
Reg_Rehab_Rehab
Reg_CW_Box
Khal_Riv_New
Khal_Riv_Rehab
Full_Emb_Rehab
Sub_Emb_Rehab
Sub_Emb_Const
Reg_Rehab_New
Wmg_Office
Gate_Repair