## HaorCode
Name | Code
Chandpur Haor Sub-Project | N-1
Nunnir Haor Sub-Project | N-2
Boro Haor Sub-Project | N-3
Noapara Haor Sub-Project | N-4
Naogaon Haor Sub-Project | N-5
Badla Haor Sub-Project | N-6
Chatal Haor Sub-Project | N-7
Dakhshiner Haor Sub-Project | N-8
Suniar Haor Sub-Project | N-9
Mokhar Haor Sub-Project | N-10
Ganesh Haor Sub-Project | N-11
Dharmapasha Rui Beel Sub-Project | N-12
Jaliar Haor Sub-Project | N-13
Dhakua Haor Sub-Project | N-14
Alalia-Bahadia Sub-Project | R-1
Modkhola-Bairagir Char Sub-Project | R-2
Ganakkhali Sub-Project | R-3
Boraikhali Khal Sub-Project | R-4
Koirdahla Ratna Sub-Project | R-5
Guingajuri Sub-Project | R-6
Aralia Khal Sub-Project | R-7
Bashira River Re-excavation Sub-Project | R-8
Dampara Water Management Scheme | R-9
Kangsha River Scheme | R-10
Singer Beel Sub-Project | R-11
Khaliajuri FCD Polder-2 | R-12
Khaliajuri FCD Polder-4 | R-13
Chandal Beel Sub-Project | R-14
Satdona Beel Scheme | R-15
All Haor | A-1

## Structure_Type
Items | Initial | Code | Payment_30_06_2020 | DPP_Item
Construction of Irrigation Inlet | IRRI_C | 1 | 291.81 | Inlet
Rehab Regulator Rehab Haor | REG_R_REHAB | 2 | 0 | Reg_Rehab_Rehab
Regulator | REG_C | 3 | 6503.97 | Reg_CW_Box
Box Drainage Outlet | DROU_C | 4 | 0 | Reg_CW_Box
Causeway | CW_C | 5 | 0 | Reg_CW_Box
Bridge | BRI_C | 6 | 0 | Reg_CW_Box
Khal_River Reexcavation(New Haor) | REX_KH_RIV_NEW | 7 | 2546.54 | Khal_Riv_New
Khal_River Reexcavation(Rehab Haor) | REX_KH_RIV_REHAB | 8 | 51.09 | Khal_Riv_Rehab
Embankment Rehablitation | EMB_R | 9 |  | Full_Emb_Rehab
Submersible Embankment Rehabilitation | SEMB_R | 10 |  | Sub_Emb_Rehab
Submersible Embankment Construction | SEMB_C | 11 | 5833.04 | Sub_Emb_Const
Rehab Regulator New Haor | REG_R_NEW | 12 |  | Reg_Rehab_New
Thrashing Floor Construction | THF_CONS | 14 |  | Thr_Fl_Cost
Construction of WMG | WMG_OFF | 15 |  | Wmg_Office
M&E GATE Repair | GATE_REP | 16 |  | Gate_Repair

## Hobiganj
Package Name | Component | Unit | Qnty | Cost | Remarks | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Resectioning of Embankment along the left bank of the Bashira River inbwt 2.420 to 9.760 | km | 7 | 151.385 |  | HOBI/PW-01 | Rehab | 10 |  | R-8 | HOBI
BWDB/Hobi/HFMLIP/PW-01 Bashira River | construction of new Embankment along the left bank of bitangal khal inbwt 10.000 to 17.000 | km | 7 | 151.385 |  | HOBI/PW-01 | Rehab | 10 |  | R-8 | HOBI
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Reexcavation of Bashira River 0.000 to 20.000 | km | 17.4 | 732.6 |  | HOBI/PW-01 | Rehab | 8 |  | R-8 | HOBI
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Reexcavation of Matikatakahl from 0.000 to Km 2.295 | km | 2.925 | 99.9 |  | HOBI/PW-01 | Rehab | 8 |  | R-8 | HOBI
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Construction of 2-vent Regulator | nos. | 1 | 208 |  | HOBI/PW-01 | Rehab | 3 |  | R-8 | HOBI
BWDB/Hobi/HFMLIP/PW-01 Bashira River | Construction of 4.00m causeway | nos. | 1 | 178.13 |  | HOBI/PW-01 | Rehab | 5 |  | R-8 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Resctioning of Submersible Embankment from 0.000 to 26.000 at Left Bank of Kushiyara | Km | 7.23 | 274.56 |  | HOBI/PW-02 | Rehab | 10 |  | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Construction of Retired Embankment in between 0.000 to 26.500 | Km | 6.894 | 225.46 |  | HOBI/PW-02 | Rehab | 10 |  | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Resctioning of Submersible Embankment from 0.000 to 16.02 at Right Bank of Khoai | Km | 16.02 | 318.42 |  | HOBI/PW-02 | Rehab | 10 |  | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Construction of New Embankment from Km 22.850 to 31.210 | Km | 8.36 | 149.54 |  | HOBI/PW-02 | Rehab | 10 |  | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Reexcavation of Kairdhala Khal from 0.000 to 1.6950 km | Km | 1.695 | 132.8661 |  | HOBI/PW-02 | Rehab | 8 |  | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Reexcavation of Satmukha Khal from 0.000 to 1.790 km | Km | 1.79 | 53.0475 |  | HOBI/PW-02 | Rehab | 8 |  | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Reexcavation of Singer Beel Khal from 0.000 to 2.720 km | Km | 2.72 | 29.975 |  | HOBI/PW-02 | Rehab | 8 |  | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-02 Kairdhala | Construction of Causeway 4-m width Causeway | nos. | 1 | 168.38 |  | HOBI/PW-02 | Rehab | 5 |  | R-7 | HOBI
BWDB/Hobi/HFMLIP/PW-04 Mokhar Haor | Submesible Embankment from 31.600 to 81.740 | km | 23.815 | 638.85 |  | HOBI/PW-04 | New | 11 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-04 Mokhar Haor | Block road | km |  | 507.95 |  | HOBI/PW-04 | New | 11 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Boranbil khal Regulator (1-vent) | nos. | 1 | 141.3235 |  | HOBI/PW-05 | New | 3 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Chandakhali khal Regulator(1-vent) | nos. | 1 | 154.0746 |  | HOBI/PW-05 | New | 3 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Chargaowdair khal Regulator(1-vent) | nos. | 1 | 151.0703 |  | HOBI/PW-05 | New | 3 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-05 Mokhar Hao | Chhoto Katari khal Regulator(1-vent) | nos. | 1 | 143.8109 |  | HOBI/PW-05 | New | 3 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-05 Mokhar Hao | Islampur khal Regulator (1-vent) | nos. | 1 | 155.6933 |  | HOBI/PW-05 | New | 3 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-05 Mokhar Hao | Tetter Drepasionkhal Regulator(2-vent) | nos. | 1 | 216.7515 |  | HOBI/PW-05 | New | 3 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-05 Mokhar Haor | Soaybeel khal Regulator (5-vent) | nos. | 1 | 353.8204 |  | HOBI/PW-05 | New | 3 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Bibiyana 6.0m Causeway | nos. | 1 | 415.5317 |  | HOBI/PW-06 | New | 5 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Old kushiyana 6.0m Causeway | nos. | 1 | 373.3459 |  | HOBI/PW-06 | New | 5 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Ratna River 4.0m Causeway | nos. | 1 | 143.1604 |  | HOBI/PW-06 | New | 5 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Rukway 4.0m Causeway | nos. | 1 | 165.1831 |  | HOBI/PW-06 | New | 5 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX1 | nos. | 1 | 37.0833 |  | HOBI/PW-06 | New | 4 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX2 | nos. | 1 | 37.0833 |  | HOBI/PW-06 | New | 4 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX3 | nos. | 1 | 37.0833 |  | HOBI/PW-06 | New | 4 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX4 | nos. | 1 | 37.0833 |  | HOBI/PW-06 | New | 4 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX5 | nos. | 1 | 37.0833 |  | HOBI/PW-06 | New | 4 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX6 | nos. | 1 | 37.0833 |  | HOBI/PW-06 | New | 4 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX7 | nos. | 1 | 37.0833 |  | HOBI/PW-06 | New | 4 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX8 | nos. | 1 | 37.0833 |  | HOBI/PW-06 | New | 4 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | BoX9 | nos. | 1 | 37.0833 |  | HOBI/PW-06 | New | 4 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-06 Mokhar Haor | Irrigation Inlet | nos. | 15 | 150.7581 |  | HOBI/PW-06 | New | 1 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Chargaowdair khal | km | 3.036 | 45.4209 |  | HOBI/PW-07 | New | 7 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Chotokatari Khal | km | 3.264 | 61.408 |  | HOBI/PW-07 | New | 7 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Salukadhar Khal | km | 2.428 | 67.6663 |  | HOBI/PW-07 | New | 7 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Islampur khal | km | 0.634 | 25.7065 |  | HOBI/PW-07 | New | 7 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Soyabeel Khal | km | 3.285 | 139.5951 |  | HOBI/PW-07 | New | 7 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Chatal Beel Khal | km | 5.2176 | 103.126 |  | HOBI/PW-07 | New | 7 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Rajendrapur Khal | km | 4.327 | 115.1915 |  | HOBI/PW-07 | New | 7 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Purohogun Khal | km | 2.428 | 65.549 |  | HOBI/PW-07 | New | 7 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Sutki River | km | 8.03 | 145.977 |  | HOBI/PW-07 | New | 7 |  | N-10 | HOBI
BWDB/Hobi/HFMLIP/PW-07 Mokhar Haor | Ratna River | km | 7.51 | 137.4972 |  | HOBI/PW-07 | New | 7 |  | N-10 | HOBI
7825.8595

## Kishoregnj
Package Name | Component | Unit | Qnty | Cost | Present_Progress | Projected_progress | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code
BWDB/Kish/HFMLIP/ PW-01 | Betal Doba from KM 1.315 to KM 3.466 =2.151 KM | Km | 2.151 | 40.94 | 1 | 1 | KISH/PW-01 | Rehab | 8 |  | R-2 | KISH
BWDB/Kish/HFMLIP/ PW-01 | Alalia-bahadia Khal from KM 1.325 to KM 2.545=1.220 KM | Km | 1.22 | 35.88 | 1 | 1 | KISH/PW-01 | Rehab | 8 |  | R-1 | KISH
BWDB/Kish/HFMLIP/ PW-01 | katakhali khal from KM 0.000 to KM 1.550=1.550 KM | Km | 1.55 | 19.18 | 0 | 1 | KISH/PW-01 | Rehab | 8 |  | R-3 | KISH
BWDB/Kish/HFMLIP/ PW-01 | Ganakkhali Khal from KM 0.000 to KM 5.625=5.625 KM | Km | 5.625 | 309.8 | 0 | 1 | KISH/PW-01 | Rehab | 8 |  | R-3 | KISH
BWDB/Kish/HFMLIP/ PW-01 | kali Khal from KM 0.00 to KM 1.000=1.000 KM | Km | 1 | 45.95 | 0 | 1 | KISH/PW-01 | Rehab | 8 |  | R-3 | KISH
BWDB/Kish/HFMLIP/ PW-01 | Repair & Maintenense Alalia Bahadia Regulator 2 vent | Km | 1 | 44.79 | 0 | 1 | KISH/PW-01 | Rehab | 2 |  | R-1 | KISH
Package No-02 /ChandpurHaor | Regulator 2 vent (1.50m X 1.80m)-1 | Nos | 1 | 155.5114 | 1 | 1 | KISH/PW-02 |  | 3 |  | N-1 | KISH
Package No-02 /ChandpurHaor | R/E. of Diakul Khal from km. 1.710 to km. 4.690 = 2.980 km. | Km | 2.98 | 31.9576 | 1 | 1 | KISH/PW-02 |  | 7 |  | N-2 | KISH
Package No-02 /ChandpurHaor | Manick Khali khal from km. 0.180 to km. 4.655 = 4.475 km | Km | 4.475 | 93.4351 | 1 | 1 | KISH/PW-02 |  | 7 |  | N-3 | KISH
Package No-02 /ChandpurHaor | Bamonkhal from km, 0.00 to km. 2.225 = 2.225 km. | Km | 2.225 | 52.1722 | 1 | 1 | KISH/PW-02 |  | 7 |  | N-4 | KISH
Package No-02 /ChandpurHaor | GoraderKhal from km. 0.00 to km. 0.340 km. & from km. 1.380 = 0.460 km | Km | 0.46 | 16.201 | 1 | 1 | KISH/PW-02 |  | 7 |  | N-5 | KISH
Package No-02 /ChandpurHaor | Bata khal from km, 0.000 to km. 2.790 km | Km | 2.79 | 68.8599 | 1 | 1 | KISH/PW-02 |  | 7 |  | N-6 | KISH
Package No-02 /ChandpurHaor | Construction of Sub-mergible Embankment From km. 11.915 to km 12.230 = 0.315 km | Km | 0.315 | 14.8109 | 1 | 1 | KISH/PW-02 |  | 11 |  | N-7 | KISH
Package No.-03/ Nunnir Haor (Part-A) | Regulator 1 vent (1.50m X 1.80m)-1 at km 23.846 (Part-A) | Nos | 1 | 155.5114 | 1 | 1 | KISH/PW-03 |  | 3 |  | N-2 | KISH
Package No.-03/ Nunnir Haor (Part-A) | Construction of Sub-mergible Embankment at NunnirHaor From km.7.366 to km. 17.749 = 10.383 km,(Part-A), | Km | 10.383 | 247.1255 | 1 | 1 | KISH/PW-03 |  | 11 |  | N-2 | KISH
Package No.-03/ Nunnir Haor (Part-A) | Block Road | Km |  | 286.8206 | 1 | 1 | KISH/PW-03 |  | 11 |  | N-2 | KISH
Package No.-04/ Nunnir Haor (Part B+C) | Northern Depression Regulator 1-Vent (1.50mx1.80m)-1 at km. 2.62 (Part- B) | Nos | 1 | 97.9579 | 1 | 1 | KISH/PW-04 |  | 3 |  | N-2 | KISH
Package No.-04/ Nunnir Haor (Part B+C) | Southern Depression Regulator 1-Vent (1.50mx1.80m)-2 at km. 6.20 (Part- B) | Nos | 1 | 97.9579 | 1 | 1 | KISH/PW-04 |  | 3 |  | N-2 | KISH
Package No.-04/ Nunnir Haor (Part B+C) | Regulator 4-Vent (1.50mx1.80m)-1 at km. 0.78 (Part- C) | Nos | 1 | 257.73 | 1 | 1 | KISH/PW-04 |  | 3 |  | N-2 | KISH
Package No.-04/ Nunnir Haor (Part B+C) | Construction of Sub-Mergible Embankment at Nunnir Haor From km.0.070 to km. 6.541 = 6.471 km(Part-B) | Km | 6.471 | 256.8713 | 1 | 1 | KISH/PW-04 |  | 11 |  | N-2 | KISH
Package No.-05/ NunnirHaor (Part-A& C) | Regulator 3-Vent (1.50mx1.80m)-1 at km. 15.30 | Nos | 1 | 190.22 | 1 | 1 | KISH/PW-05 |  | 3 |  | N-2 | KISH
Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) From km.0.000 to km. 1.697 = 1.697 km | Km | 1.697 | 35.282 | 1 | 1 | KISH/PW-05 |  | 11 |  | N-2 | KISH
Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km. 1.917 to km.2.000 = 0.083 km | Km | 0.083 | 4.0969 | 1 | 1 | KISH/PW-05 |  | 11 |  | N-2 | KISH
Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km 2.487 to km 3.077 =0.590 km | Km | 0.59 | 8.7693 | 0 | 1 | KISH/PW-05 |  | 11 |  | N-2 | KISH
Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km.7.745 to km.15.239 =7.494 km | Km | 7.494 | 156.8227 | 1 | 1 | KISH/PW-05 |  | 11 |  | N-2 | KISH
Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km. 16.881 tokm.18.380 =1.499 km | Km | 1.499 | 28.9482 | 1 | 1 | KISH/PW-05 |  | 11 |  | N-2 | KISH
Package No.-05/ NunnirHaor (Part-A& C) | Construction of Submersible Embankment.(Part-C) from km. 18.526 to km.19.377= 0.851km.= Total =12.214 km.(Part-C). | Km | 0.851 | 17.8983 | 1 | 1 | KISH/PW-05 |  | 11 |  | N-2 | KISH
Package No.-05/ NunnirHaor (Part-A& C) | Block Road | Km | 12.214 | 325.54 | 1 | 1 | KISH/PW-05 |  | 11 |  | N-2 | KISH
Package No.-06/ NunnirHaor (Part-A) | Regulator 4-Vent (1.50mx1.80m)-1 at km 12.18. | Nos | 1 | 227.8819 | 1 | 1 | KISH/PW-06 |  | 3 |  | N-2 | KISH
Package No.-06/ NunnirHaor (Part-A) | Re-excavasion of Khal Katakhali Khal-1 from km 0.00 to km 4.500 | Km | 4 | 41.55 | 1 | 1 | KISH/PW-06 |  | 7 |  | N-2 | KISH
Package No.-06/ NunnirHaor (Part-A) | Samar bari khal-2 form km. 0.20 to km 3.99 | Km | 3.43 | 69.7 | 1 | 1 | KISH/PW-06 |  | 7 |  | N-2 | KISH
Package No.-06/ NunnirHaor (Part-A) | Mahinhandra khal-3 from km 1.00 to km 1.90 | Km | 0.9 | 23.7 | 1 | 1 | KISH/PW-06 |  | 7 |  | N-2 | KISH
Package No.-06/ NunnirHaor (Part-A) | Kata khal-4 from km 0.100 to km 0.600 | Km | 0.5 | 10.04 | 1 | 1 | KISH/PW-06 |  | 7 |  | N-2 | KISH
Package No.-06/ NunnirHaor (Part-A) | Kurigai Gang-5 from km 0.00 to km 8.400 | Km | 7.07 | 356.51 | 1 | 1 | KISH/PW-06 |  | 7 |  | N-2 | KISH
Package No.-06/ NunnirHaor (Part-A) | Beri Gang-6 from km 0.00 to km 3.56 | Km | 3.56 | 120..16 | 1 | 1 | KISH/PW-06 |  | 7 |  | N-2 | KISH
Package No.-07/ Boro Haor | Hazir Khal | Km | 1.73 | 20.5494 | 0 | 0 | KISH/PW-07 |  | 7 |  | N-3 | KISH
Package No.-07/ Boro Haor | Karpasha Khal | Km | 1.615 | 26.0781 | 2.16 | 2.16 | KISH/PW-07 |  | 7 |  | N-3 | KISH
Package No.-07/ Boro Haor | Dampara Khal | Km | 3.6 | 46.8873 | 0.4 | 0.4 | KISH/PW-07 |  | 7 |  | N-3 | KISH
Package No.-07/ Boro Haor | Baniajan | Km | 6.854 | 130.1184 | 1 | 1 | KISH/PW-07 |  | 7 |  | N-3 | KISH
Package No.-07/ Boro Haor | Suti Khal | Km | 6.1 | 120.3313 | 1 | 1 | KISH/PW-07 |  | 7 |  | N-3 | KISH
Package No.-07/ Boro Haor | Digha Nadi | Km | 5.7 | 424.0032 | 0.65 | 1 | KISH/PW-07 |  | 7 |  | N-3 | KISH
Package No.-07/ Boro Haor | Old Singua | Km | 10.86 | 197.6384 | 0 | 0 | KISH/PW-07 |  | 7 |  | N-3 | KISH
Package No.-07/ Boro Haor | Construction of Submersible Embankment. (In between km. 0.000to km. 56.949) =3.879 km. | Km | 3.879 | 35.33 | 0.08 | 0.2 | KISH/PW-07 |  | 11 |  | N-3 | KISH
Package No.-07/ Boro Haor | Block Road | Km |  | 55.74 | 0 | 1 | KISH/PW-07 |  | 11 |  | N-3 | KISH
Package No.PW-09/Kish/ Boro Haor | Causeway 6.0m wide-1 at Dampara | Nos | 1 | 210.83 | 1 | 1 | KISH/PW-09 |  | 5 |  | N-3 | KISH
Package No.PW-09/Kish/ Boro Haor | Causeway 4.0m wide-1 at Karpasha | Nos | 1 | 176.64 | 1 | 1 | KISH/PW-09 |  | 5 |  | N-3 | KISH
Package No.PW-09/Kish/ Boro Haor | Mohorkona Box Outlet | Nos | 1 | 66.64 | 1 | 1 | KISH/PW-09 |  | 4 |  | N-3 | KISH
Package No.PW-09/Kish/ Boro Haor | Causeway 6.0m wide-1 at Samar Bari | Nos | 1 | 241.26 | 1 | 1 | KISH/PW-09 |  | 5 |  | N-3 | KISH
Package No.: PW-10/ Noapara Haor | Causeway 6.0m wide-1 | Nos | 1 | 137.35 | 0 | 0.65 | KISH/PW-10 |  | 3 |  | N-4 | KISH
Package No.: PW-10/ Noapara Haor | Regulator 1-Vent (1.50mx1.80m)-1 at Jalalpur 22.64 km | Nos | 1 | 128.67 | 0.45 | 1 | KISH/PW-10 |  | 3 |  | N-4 | KISH
Package No.: PW-10/ Noapara Haor | Construction of Submergible embankment in between km 0.020 to km 12.400 = 11.750 km | Km | 11.75 | 274.06 | 0.64 | 1 | KISH/PW-10 |  | 11 |  | N-4 | KISH
Package No.: PW-10/ Noapara Haor | Block Road | Km |  | 343.88 | 1 | 1 | KISH/PW-10 |  | 11 |  | N-4 | KISH
Package No.-11/ Noapara Haor | Regulator 2 vent (1.50m x 1.80m)-1 at 16.13 km at over lalpurkhal | Nos | 1 | 274.49 | 0.95 | 1 | KISH/PW-11 |  | 3 |  | N-4 | KISH
Package No.-11/ Noapara Haor | Construction of sub-mergible embankment in between km 12.400 to km 23.260 = 10.860 km | Km | 10.86 | 557.63 | 0.5 | 1 | KISH/PW-11 |  | 11 |  | N-4 | KISH
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Regulator 3 vent (1.50m x 1.80m)-1 at NaluarKhal km 4.77 | Nos | 1 | 253.8935 | 1 | 1 | KISH/PW-12 |  | 3 |  | N-4 | KISH
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Regulator 4 vent (1.50m x 1.80m)*1 at Meharkona km 1.64 | Nos | 1 | 277.0365 | 1 | 1 | KISH/PW-12 |  | 3 |  | N-4 | KISH
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Re-excavation of Lalpurkhal km 0.410 to km 4.40 = 3.900 km | Km | 3.9 | 18.397 | 0 | 0 | KISH/PW-12 |  | 7 |  | N-4 | KISH
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | NaluarKhal km 0.200 to km 0.800 = 0.600 km | Km | 0.6 | 4.398 | 1 | 1 | KISH/PW-12 |  | 7 |  | N-4 | KISH
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | MaherkonaKhal km 0.300 to km 3.300 = 3.00 km | Km | 3 | 99.257 | 1 | 1 | KISH/PW-12 |  | 7 |  | N-4 | KISH
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | NabinpurKhal km 4.000 to km 6.800= 2.800 km | Km | 2.8 | 110.6945 | 1 | 1 | KISH/PW-12 |  | 7 |  | N-4 | KISH
BWDB/ Kish/HFMLIP/PW-12 Noapara Haor | Jalalpurkhal km 0.090 to km 0.457= 0.367 km) Total 10.757 km | Km | 0.367 | 167.984 | 1 | 1 | KISH/PW-12 |  | 7 |  | N-4 | KISH
Package No.-13/ Naogaon Haor (Part-A) | Pangadair Regulator 3-Vent (1.50mx1.80m)-1 at km. 2.09 | Nos | 1 | 232.96 | 0.95 | 1 | KISH/PW-13 |  | 3 |  | N-5 | KISH
Package No.-13/ Naogaon Haor (Part-A) | Bera Khal Regulator 2-Vent (1.50mx1.80m)-1 at km. 4.07 | Nos | 1 | 193 | 0.95 | 1 | KISH/PW-13 |  | 3 |  | N-5 | KISH
Package No.-13/ Naogaon Haor (Part-A) | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 0.00 to KM 10.00=10.00KM | Km | 10 | 576.67 | 0.4 | 1 | KISH/PW-13 |  | 11 |  | N-5 | KISH
Package No.-14/ Naogaon Haor (Part-A) | Regulator 2-Vent (1.50mx1.80m)-1 at km. 6.04 | Nos | 1 | 263.7 | 0.95 | 1 | KISH/PW-14 |  | 3 |  | N-5 | KISH
Package No.-14/ Naogaon Haor (Part-A) | Construction of Submergible Embankment around Naogaon Haor (Part-A) from KM 10.00 to KM 28.90.00=16.90 KM | Km | 16.9 | 485.98 | 0.86 | 1 | KISH/PW-14 |  | 11 |  | N-5 | KISH
Package No.-14/ Naogaon Haor (Part-A) | Block Road | Km | 0.5 | 133.96 | 0 | 1 | KISH/PW-14 |  | 11 |  | N-5 | KISH
Package No.-15/ Naogaon Haor- Part-B | Regulator 2-Vent (1.50mx1.80m)-1 at km. 5.56 | Nos | 1 | 166.9 | 0 | 0 | KISH/PW-15 |  | 3 |  | N-5 | KISH
Package No.-15/ Naogaon Haor- Part-B | Construction of Submergible Embankment around Naogaon Haor (Part-B) from KM 0.000 to KM 9.000=9.000 KM | Km | 9 | 616.92 | 1 | 1 | KISH/PW-15 |  | 11 |  | N-5 | KISH
Package No.-16/ NaogaonHaor-Part-B | Regulator 2-Vent (1.5m x 1.80 m) at km 33.80 (14.120km) | Nos | 1 | 267.88 | 0.85 | 1 | KISH/PW-16 |  | 3 |  | N-5 | KISH
Package No.-16/ NaogaonHaor-Part-B | Submergible Embankment around Naogaon Haor (Part-B) from KM 9.000 to KM 30.420 = 14.120KM | km | 1 | 343.32 | 1 | 1 | KISH/PW-16 |  | 11 |  | N-5 | KISH
Package No.-16/ NaogaonHaor-Part-B | Block Road | Km |  | 167.97 | 1 | 1 | KISH/PW-16 |  | 11 |  | N-5 | KISH
Package No.-17/ Naogaon Haor-Part-B | Regulator 4-Vent (1.50m×1.80m)-1 at KM 44.230 of Naogaon Haor (Part-B) | Nos | 1 | 348.66 | 1 | 1 | KISH/PW-17 |  | 3 |  | N-5 | KISH
Package No.-17/ Naogaon Haor-Part-B | Rehulator 1-Vent (1.50m×1.80m)-1 at KM 14.52 of Naogaon Haor (Part-B) | Nos | 1 | 217.5324 | 1 | 1 | KISH/PW-17 |  | 3 |  | N-5 | KISH
Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-1 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 |  | 4 |  | N-5 | KISH
Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-2 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 |  | 4 |  | N-5 | KISH
Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-3 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 |  | 4 |  | N-5 | KISH
Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-4 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 |  | 4 |  | N-5 | KISH
Package No.-17/ Naogaon Haor-Part-B | Box Drainage Outlet-5 | Nos | 1 | 35.4887 | 1 | 1 | KISH/PW-17 |  | 4 |  | N-5 | KISH
Package No.-17/ Naogaon Haor-Part-B | Submergible Embankment around Naogaon Haor (Part-B) in between KM 30.420 to KM 44.200 =13.170 KM | Km | 1 | 460.54 | 1 | 1 | KISH/PW-17 |  | 11 |  | N-5 | KISH
Package No.-17/ Naogaon Haor-Part-B | Block Road | Km |  | 89.5 | 1 | 1 | KISH/PW-17 |  | 11 |  | N-5
Package No.-17/ Naogaon Haor-Part-B | Irrigation Pipe Inlet-1 | Nos | 25 | 274.47 | 1 | 1 | KISH/PW-17 |  | 1 |  | N-5 | KISH
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 4m wide-1 DheuhalKhal at km 12.44 | Nos | 1 | 159.8606 | 0 | 1 | KISH/PW-18 |  | 5 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 4m wide-2 KhaiyarKhal at km 24.06 | Nos | 1 | 161.4295 | 0.8 | 1 | KISH/PW-18 |  | 5 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 4m wide-3 NeoraKhal at km 44.20 | Nos | 1 | 186.8205 | 1 | 1 | KISH/PW-18 |  | 5 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Causeway 6m wide-1 MarkhaliKhal at km 39.07 | Nos | 1 | 265.5873 | 0.8 | 1 | KISH/PW-18 |  | 5 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Re-Excavation of PangairDairKhal from KM 0.080 to KM 4.360 = 4.280 KM, | Km | 4.28 | 101.2011 |  |  | KISH/PW-18 |  | 7 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | BeraKhal from KM 0.520 to KM 2.030=1.510 KM | Km | 1.51 | 35.7041 | 1 | 1 | KISH/PW-18 |  | 7 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | Gokhrakhal from KM 0.185 to KM 0.910=0.725 KM (Part-A), | Km | 0.725 | 17.1427 | 1 | 1 | KISH/PW-18 |  | 7 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | NeoraKhal from KM 0.120 to KM 2.635=2.515 KM | Km | 2.515 | 59.4674 | 1 | 1 | KISH/PW-18 |  | 7 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | NandirKhal from KM 0.00 to KM 5.985=5.985 KM, | Km | 5.985 | 141.516 | 0 | 1 | KISH/PW-18 |  | 7 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-18 NaogaonHaor (Part A & B) | KhaiyerKhal from KM 0.495 to KM 8.405=7.910 KM and | Km | 7.91 | 187.0328 | 0 | 1 | KISH/PW-18 |  | 7 |  |  | KISH
BWDB/ Kish/HFMLIP/PW-19 Naogaon Haor (Part A) | Re-excavation of Berachapra River (KM 0.00 to KM 15.820=15.820 KM) | Km | 15.82 | 472.9622 | 0.19 | 1 | KISH/PW-19 |  | 7 |  | N-5 | KISH
BWDB/ Kish/HFMLIP/PW-19 Naogaon Haor (Part A) | Atoplal River (KM 0.00 to KM7.11=7.113KM) Total=22.933 | Km | 7.113 | 374.9638 | 0.25 | 1 | KISH/PW-19 |  | 7 |  | N-5 | KISH
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Chitra Khal 4m wide | Nos | 1 | 136.31 | 1 | 1 | KISH/PW-20 | New | 5 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Nabinpur Khal 4m Wide | Nos | 1 | 193.69 | 1 | 1 | KISH/PW-20 | New | 5 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Dipjuri Khal 4m CW | Nos | 1 | 185.03 | 1 | 1 | KISH/PW-20 | New | 5 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Sudhikhal 4m wide CW | Nos | 1 | 136.66 | 1 | 1 | KISH/PW-20 | New | 5 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Chhagalia khal sluice | Nos | 1 | 41.0186 | 1 | 1 | KISH/PW-20 | New | 3 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Near nasir sluice | Nos | 1 | 42.7991 | 1 | 1 | KISH/PW-20 | New | 3 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Shingpur khal sluice | Nos | 1 | 41.9704 | 1 | 1 | KISH/PW-20 | New | 3 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Gharu khal sluice | Nos | 1 | 41.9704 | 0.75 | 1 | KISH/PW-20 | New | 3 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-20 Nunnir, Boro & Noapara Haor | Irrigation Pipe Inlet 600mm dia | Nos | 36 | 334.27 | 0.57 | 0.57 | KISH/PW-20 | New | 1 |  |  | KISH
BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Construction of Kursi Khal Regulator (2-vent, 1.50m x 1.80m) at km 16.10 | Nos | 1 | 321.3991 | 0.48 | 1 | KISH/PW-21 | New | 3 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Construction of Chouganga Khal Regulator (1-vent, 1.50m x 1.80m) at km 24.40 | Nos | 1 | 156.6821 | 0.45 | 1 | KISH/PW-21 | New | 3 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Rehabilitation of 5nos Regulator (2 vent 1.50m x 1.80m- 2nos, 1 vent 1.50m x 1.80m- 3nos) | Nos | 5 | 120.5564 | 0 | 1 | KISH/PW-21 | New | 12 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-21 Badla Haor | Sub-Mergible Embankment From km. 2.565 to km 12.059 = 9.494 km | Km | 9.494 | 329.1074 | 0 | 1 | KISH/PW-21 | New | 11 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Sub-Mergible Embankment inbetween km. 12.059 to km. 26.998 Total Length 10.463 km | Km | 10.463 | 235.9924 | 0.8 | 0.8 | KISH/PW-22 |  | 11 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Re-excavation of Sajna Khal from km. 0.000 to km. 1.000 | Km | 1 | 18.1492 | 0 | 1 | KISH/PW-22 |  | 7 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Chandpur Khal from km. 0.000 to km. 0.700 | Km | 0.7 | 28.0679 | 1 | 1 | KISH/PW-22 |  | 7 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Baduti Khal from km. 0.000 to km. 1.000 | Km | 1 | 5.8814 | 0 | 1 | KISH/PW-22 |  | 7 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Kanala Khal from km. 0.000 to km. 0.584 | Km | 0.584 | 8.1389 | 0 | 1 | KISH/PW-22 |  | 7 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Kursi Khal from km. 0.000 to km. 2.900 | Km | 2.9 | 84.8797 | 0.16 | 1 | KISH/PW-22 |  | 7 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Bamuna Khal from km. 0.000 to km. 1.400 | Km | 1.4 | 11.9047 | 0 | 1 | KISH/PW-22 |  | 7 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Chouganga Khal from km. 1.700 to km. 1.900 | Km | 1.9 | 2.4463 | 0 | 1 | KISH/PW-22 |  | 7 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Maora Khal from km. 0.000 to km. 1.700 | Km | 1.7 | 14.6073 | 1 | 1 | KISH/PW-22 |  | 7 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Burimara Khal from km. 0.000 to km. 0.439 | Km | 0.439 | 4.4592 | 0 | 1 | KISH/PW-22 |  | 7 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Causeway 4.0m wide-1 at km 7.50 of Kanala Khal | Nos | 1 | 195.2169 | 0.15 | 1 | KISH/PW-22 |  | 5 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Box Drainage Outlet 900mm x 900mm-1 | Nos | 1 | 36.662 | 0 | 1 | KISH/PW-22 |  | 4 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Box Drainage Outlet 900mm x 900mm-2 | Nos | 1 | 36.662 | 0 | 1 | KISH/PW-22 |  | 4 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-22 Badla Haor | Box Drainage Outlet 900mm x 900mm-3 | Nos | 1 | 36.662 | 0 | 1 | KISH/PW-22 |  | 4 |  | N-6 | KISH
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Sub-Mergible Embankment From km. 2.469 to km 6.979= 4.51 km | Km | 4.51 | 107.4208 | 0.8 | 1 | KISH/PW-23 | New | 11 |  | N-7 | KISH
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Regulator 2-vent (1.50m x 1.80m)-1 Mozilla Khal | Nos | 1 | 295.5262 | 0.85 | 1 | KISH/PW-23 | New | 3 |  | N-7 | KISH
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Regulator 2-vent (1.50m x 1.80m)-2 Noaparakhali Khal | Nos | 1 | 227.0604 | 0.95 | 1 | KISH/PW-23 | New | 3 |  | N-7 | KISH
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Re-excavation of Khal Mozila Khal from km. 0.000 to km. 1.775 | Km | 1.775 | 28.5772 | 0 | 0.3 | KISH/PW-23 | New | 7 |  | N-7 | KISH
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Mogar Khal from km. 0.000 to km. 0.150 Total Length1.925 km | km | 0.15 | 3.8604 | 1 | 1 | KISH/PW-23 | New | 7 |  | N-7 | KISH
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Box Drainage Outlet (900mm x 900mm)-1 at km. 2.74 | Nos | 1 | 38.9293 | 1 | 1 | KISH/PW-23 | New | 4 |  | N-7 | KISH
BWDB/Kish/HFMLIP/ PW-23 Chatal Haor | Irrigation Pipe Inlet 600mm dia | Nos | 4 | 62.862 | 1 | 1 | KISH/PW-23 | New | 1 |  | N-7 | KISH
Package No.-24/ Dakshiner Haor. | Submergible embankment from km.0.00 to km. 33.520 = 19.843 km | Nos | 19.843 | 1149.1962 | 1 | 1 | KISH/PW-24 | New | 11 |  | N-8 | KISH
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Regulator 5-Vent-1 | Nos | 1 | 405.9371 | 0.65 | 1 | KISH/PW-25 | New | 3 |  | N-8 | KISH
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Re-excavation of Shankirkhal from km 0.290 to km 8.885 = 8.595 km | Nos | 1 | 320.0346 | 0.88 | 0.88 | KISH/PW-25 | New | 7 |  | N-8 | KISH
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Re-excavation of Bantai river from km 0.000 to km 1.650 = 1.650 km) | Km | 1.65 | 54.4035 | 0.36 | 1 | KISH/PW-25 | New | 7 |  | N-8 | KISH
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Joyshiddhi Causeway 6.0m wide-1 | Nos | 1 | 346.4138 | 0 | 0 | KISH/PW-25 | New | 5 |  | N-8 | KISH
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Shankir Khal Causeway 6.0m wide-2 | Nos | 1 | 288.0795 | 0 | 0 | KISH/PW-25 | New | 5 |  | N-8 | KISH
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Shankir Kha Causeway 4.0m wide-1 | Nos | 1 | 189.5297 | 0.65 | 1 | KISH/PW-25 | New | 5 |  | N-8 | KISH
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Box Sluice-1 | Nos | 1 | 41.8221 | 0 | 0 | KISH/PW-25 | New | 4 |  | N-8 | KISH
BWDB/Kish/HFMLIP/ PW-25 Dakshiner Haor | Irrigation Pipe Inlet 600mm dia | Nos | 15 | 118.5673 | 0.86 | 1 | KISH/PW-25 | New | 1 |  | N-8 | KISH
BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | Construction of sub-mergible embankment in between km 8.200 to km 18.030 = 0.540 km | Km | 0.54 | 22.7161 | 0 | 0 | KISH/PW-26 | New | 11 |  | N-9 | KISH
BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | Re-excavation of Khal Phulesswarikhal from km 0.000 to km 3.960 = 3.960 km | Km | 3.96 | 71.5264 | 0 | 0 | KISH/PW-26 | New | 7 |  | N-9 | KISH
BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | GoalkhaliKhal from km 0.500 to km 2.600 = 2.100 km | Km | 2.1 | 12.7224 | 0 | 0 | KISH/PW-26 | New | 7 |  | N-9 | KISH
BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | KalnaKhal from km 0.800 to km 1.940 = 1.140 km | Km | 1.14 | 16.3878 | 0 | 0 | KISH/PW-26 | New | 7 |  | N-9 | KISH
BWDB/Kish/HFMLIP/ PW-26 Sonai Haor | SutiNadi from km 2.200 to km 17.700= 15.500 km) | Km | 15.5 | 367.3183 | 0 | 0 | KISH/PW-26 | New | 7 |  | N-9 | KISH
BWDB/Kish/HFMLIP/ PW-27 | phuleshwari | Nos | 1 | 156.62 | 0 | 1 | KISH/PW-27 | New | 3 |  | N-9 | KISH
BWDB/Kish/HFMLIP/ PW-27 | Kalna | Nos | 1 | 148 | 0 | 1 | KISH/PW-27 | New | 3 |  | N-9 | KISH
BWDB/Kish/HFMLIP/ PW-27 | RCC Box Drainage | Nos | 1 | 41.88 | 0 | 1 | KISH/PW-27 | New | 4 |  | N-9 | KISH
BWDB/Kish/HFMLIP/ PW-27 | Causeway | Nos | 1 | 140.87 | 0 | 1 | KISH/PW-27 | New | 5 |  | N-9 | KISH
BWDB/Kish/HFMLIP/ PW-27 | Causeway & Drainage | Nos | 1 | 407.31 | 0 | 1 | KISH/PW-27 | New | 5 |  | N-9 | KISH

## Projection
Sl No | Package Name | Structue Name | unit | Quanty | Contract Value | STC Code | Bill Paid | Remaining Bill | Value of work done as per 04,March,2020 | Projection | Workstatus | FSE Name | Contractor | Remarks
1 | NETR/PW-01 | Resectioning of Full embankment from 0.000 to 41.771 | Km | 35.828 | 1132.4847 | 9 | 334.51 | 797.9747 | 504.16 | 609.57 | OG | Abul Latif |  | Excavator=3
2 | NETR/PW-01 | Resectioning of Full embankment from 0.911to 11.600 | km | 10.69 | 212.86 | 9 | 94.35 | 118.51 | 59.6 | 97.91 | OG | Abdul Latif |  | Excavator=1
3 | NETR/PW-02 | Dhalia Khal | Km | 7.37 | 68.3113 | 8 | 53.9464 | 14.365 | 0 | 0 | P
4 | NETR/PW-02 | Balai khal | Km | 5.896 | 107.2237 | 8 | 43.1571 | 64.0666 | 0 | 0 | P
5 | NETR/PW-02 | Anda Khal | Km | 7.192 | 215.6843 | 8 | 52.6435 | 163.0409 | 215.684 | 215.684 | C
6 | NETR/PW-02 | Dupikhali Khal part-1 | Km | 3.66 | 106.6825 | 8 | 26.7902 | 79.8923 | 106.683 | 106.683 | C
7 | NETR/PW-02 | Dupikhali Khal part-1 | Km | 5.057 | 112.0192 | 8 | 37.0158 | 75.0033 | 112.019 | 112.019 | C | Munshi
8 | NETR/PW-02 | Dudhkura Khal | Km | 5.4 | 57.6844 | 8 | 39.5265 | 18.1579 | 57.684 | 57.684 | C
9 | NETR/PW-02 | kurikunia Khal | Km | 1.903 | 48.574 | 8 | 13.9294 | 34.6446 | 0 | 0 | P | Munshi
10 | NETR/PW-02 | Dighjan Khal | Km | 4.32 | 102.8289 | 8 | 31.6212 | 71.2077 | 0 | 0 | P | Munshi
11 | NETR/PW-02 | Tutnir Khal | Km | 3.15 | 37.9263 | 8 | 23.0571 | 14.8691 | 0 | 0 | P | Abul Latif
12 | NETR/PW-02 | Kamalpur Khal | Km | 2.98 | 91.9555 | 8 | 21.8128 | 70.1427 | 22.19 | 38.81 | OG | Abul Latif |  | Excavator=1
13 | NETR/PW-03 | Resection of Full embankment in Kangsha River Sheme | km | 20.9 | 450.21 | 9 | 94.537 | 355.673 | 177.08 | 177.08 | P | Abul Latif
14 | NETR/PW-03 | Resection of Submesible Singer Bill | km | 3.56 | 29.21 | 10 | 16.103 | 13.107 | 29.1 | 29.21 | C | Abul Latif
15 | NETR/PW-03 | Reinstllation of 5-vent Regulator Dampara | No | 1 | 389.57 | 2 | 178.46 | 211.11 | 89.23 | 178.46 | OG |  |  | Intense Monitoring Needed for Completion
16 | NETR/PW-04 | Reexcavation of Piyan River from 0.075 to 5.00 | Km | 4.925 | 335.3397 | 8 | 69.1796 | 266.1601 | 33.5 | 33.5 | P |  |  | Dreger=1
17 | NETR/PW-04 | Reexcavation of Nayori Khal from 0.000 to 7.565 | Km | 7.565 | 158.059 | 8 | 106.2627 | 51.7963 | 63.22 | 158.059 | P
18 | NETR/PW-04 | Reexcavation of Feni Khal from 0.000 to 1.903 | Km | 1.903 | 16.0636 | 8 | 26.7307 | -10.6672 | 8.04 | 8.04 | P
19 | NETR/PW-04 | Reexcavation of Jhalokhali from 0.000 to 6.76 | Km | 6.76 | 282.4937 | 8 | 94.9552 | 187.5385 | 282.4937 | 282.4937 | C
20 | NETR/PW-04 | Reexcavation of Putia Khal from 0.000 to 5.235 | Km | 5.235 | 313.3495 | 8 | 73.5341 | 239.8155 | 313.3495 | 313.3495 | C
21 | NETR/PW-04 | Resectioning of Submersible EMB from 44.600 to 48.650 | Km | 3.75 | 154.6148 | 10 | 50.4346 | 104.1802 | 113.38 | 113.38 | P
22 | NETR/PW-04 | Resectioning of Submersible EMB from 42.000 to 43.000 | Km | 1 | 33.674 | 10 | 13.4492 | 20.2248 | 0 | 0 | P | Anil
23 | NETR/PW-04 | Resectioning of Submersible EMB from 22.000 to 25.000 | Km | 3 | 99.547 | 10 | 40.3477 | 59.1993 | 39.79 | 99.47 | OG | Anil
24 | NETR/PW-04 | Resectioning of Submersible EMB from 6.000 to 7.000 | Km | 1 | 38.1199 | 10 | 13.4492 | 24.6707 | 38.12 | 38.12 | C | Anil
25 | NETR/PW-04 | Resectioning of Submersible EMB from 6.000 to 7.000 | Km | 1 | 69.6592 | 10 | 13.4492 | 56.21 | 69.659 | 69.659 | C | 9.75
26 | NETR/PW-05 | Const of Submesible Emb from Km 6.800 to 24.855 | Km | 1 | 57.25 | 3 | 0 | 57.25 | 0 | 0 | P |  |  | This component should be dropped
27 | NETR/PW-05 | Const of 1-Vent Chapri Regulator | Nos | 1 | 242.75 | 3 | 41.0367 | 201.7133 | 60.68 | 242.75 | OG |  |  | Will be completed this year
28 | NETR/PW-05 | Const of 1-Vent Ukra Regulator | Nos | 1 | 286.86 | 3 | 41.0367 | 245.8233 | 143.13 | 286.86 | OG |  |  | Will be completed this year
29 | NETR/PW-05 | Const of 1-Vent Ichamati Regulator | Nos | 1 | 182.66 | 3 | 41.0367 | 141.6233 | 109.6 | 182.66 | OG |  |  | Will be completed this year
30 | NETR/PW-05 |  | Nos | 1 | 419.66 | 3 | 0 | 419.66 | 104.92 | 419.66 | OG |  |  | Indepth Monitoring Required for Completion this year
31 | NETR/PW-06 | Reexcavation of Narsua River from Km 0.000 to 6.225 | Km | 6.226 | 224.4496 | 7 | 133.3476 | 91.102 | 224.45 | 224.45 | C
32 | NETR/PW-06 | Reexcavation of Ukra Khal from Km 0.111 to 2.043 Km | Km | 1.933 | 118.7745 | 7 | 41.4007 | 77.3738 | 35.632 | 35.632 | P |  |  | 70% work is dropped
33 | NETR/PW-06 | Reexcavation of Chapri Khal from Km 0.280 to 2.590 Km | Km | 2.31 | 88.1515 | 7 | 49.4752 | 38.6763 | 52.9 | 52.9 | P |  |  | 60% complete40% dropped
34 | NETR/PW-06 | Reexcavation of Ichamati Khal from Km 0.072 to 1.250 Km | Km | 1.178 | 51.0575 | 7 | 25.2302 | 25.8272 | 15.31 | 15.31 | P |  |  | 30% complete70% dropped
35 | NETR/PW-06 | Reexcavation of Boilara Khal from Km 8.550 to 8.900 Km | Km | 0.35 | 28.0376 | 7 | 7.4962 | 20.5413 | 0 | 0 | P |  |  | Work on held
36 | NETR/PW-06 | Const of BoX drainage ountlet at Bhadera | Nos | 1 | 42.25 | 4 | 19.04 | 23.21 | 29.58 | 42.25 | OG
37 | NETR/PW-06 | Const of BoX drainage ountlet at Moheswar Khal | Nos | 1 | 42.25 | 4 | 19.04 | 23.21 | 29.58 | 42.5 | OG
38 | NETR/PW-06 | Const of Irrigation Inlet | Nos | 2 | 16.92 | 1 | 0 | 16.92 | 0 | 0 | P |  |  | On held
39 | NETR/PW-06 | Rehbilation of existing Regulator | Nos | 1 | 19.43 | 12 | 0 | 19.43 | 0 | 19.43 | OG
40 | NETR/PW-07 | Reexcavation of Kangsha river | Km | 15 | 654.8026 | 7 | 354.81 | 299.9926 | 491.02 | 491.02 | C |  |  | 75% Complete not possible to continue
41 | NETR/PW-07 | Reexcavation of Gumai river | Km | 9 | 238.8741 | 7 | 212.89 | 25.9841 | 179.16 | 179.16 | C |  |  | 75% Complete not possible to continue
Total |  |  |  |  | 7378.3229 |  | 2549.0924 | 4829.2306 | 3810.9442 | 4973.7632

## Netrokona
Package Name | Component | Unit | Qnty | Tendered Value | Billed Amount | Remaining Bill | Value of Work Done | Projection FY19-20 | Bill payable FY 19-20 | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code
BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Resectioning of Full embankment from 0.000 to 41.771 | Km | 35.828 | 1132.4847 | [5 empty] | NETR/PW-01 | Rehab | 9 |  | R-9 | NETR
BWDB/Netra/HFMLIP/PW-01 Dampara & Singer Beel(Re-hab) | Resectioning of Full embankment from 0.911to 11.600 | km | 10.69 | 212.86 | [5 empty] | NETR/PW-01 | Rehab | 9 |  | R-11 | NETR
BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dhalia Khal | Km | 7.37 | 68.3113 | [5 empty] | NETR/PW-02 | Rehab | 8 |  | R-9 | NETR
BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Balai khal | Km | 5.896 | 107.2237 | [5 empty] | NETR/PW-02 | Rehab | 8 |  | R-9 | NETR
BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Anda Khal | Km | 7.192 | 215.6843 | [5 empty] | NETR/PW-02 | Rehab | 8 |  | R-10 | NETR
BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dupikhali Khal part-1 | Km | 3.66 | 106.6825 | [5 empty] | NETR/PW-02 | Rehab | 8 |  | R-10 | NETR
BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dupikhali Khal part-1 | Km | 5.057 | 112.0192 | [5 empty] | NETR/PW-02 | Rehab | 8 |  | R-10 | NETR
BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dudhkura Khal | Km | 5.4 | 57.6844 | [5 empty] | NETR/PW-02 | Rehab | 8 |  | R-10 | NETR
BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | kurikunia Khal | Km | 1.903 | 48.574 | [5 empty] | NETR/PW-02 | Rehab | 8 |  | R-10 | NETR
BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Dighjan Khal | Km | 4.32 | 102.8289 | [5 empty] | NETR/PW-02 | Rehab | 8 |  | R-10 | NETR
BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Tutnir Khal | Km | 3.15 | 37.9263 | [5 empty] | NETR/PW-02 | Rehab | 8 |  | R-11 | NETR
BWDB/Netra/HFMLIP/PW-02 Dampara,Kangsha & Singer Beel(Re-hab) | Kamalpur Khal | Km | 2.98 | 91.9555 | [5 empty] | NETR/PW-02 | Rehab | 8 |  | R-11 | NETR
BWDB/Netra/HFMLIP/PW-03 Dampara,Kangsha & Singer Beel(Re-hab) | Resection of Full embankment in Kangsha River Sheme | km | 20.9 | 450.21 | [5 empty] | NETR/PW-03 | Rehab | 9 |  | R-10 | NETR
BWDB/Netra/HFMLIP/PW-03 Dampara,Kangsha & Singer Beel(Re-hab) | Resection of Submesible Singer Bill | km | 3.56 | 29.21 | [5 empty] | NETR/PW-03 | Rehab | 10 |  | R-11 | NETR
BWDB/Netra/HFMLIP/PW-03 Dampara,Kangsha & Singer Beel(Re-hab) | Reinstllation of 5-vent Regulator Dampara | No | 1 | 389.57 | [5 empty] | NETR/PW-03 | Rehab | 2 |  | R-9 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Piyan River from 0.075 to 5.00 | Km | 4.925 | 335.3397 | [5 empty] | NETR/PW-04 | Rehab | 8 |  | R-12 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Nayori Khal from 0.000 to 7.565 | Km | 7.565 | 158.059 | [5 empty] | NETR/PW-04 | Rehab | 8 |  | R-12 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Feni Khal from 0.000 to 1.903 | Km | 1.903 | 16.0636 | [5 empty] | NETR/PW-04 | Rehab | 8 |  | R-13 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Jhalokhali from 0.000 to 6.76 | Km | 6.76 | 282.4937 | [5 empty] | NETR/PW-04 | Rehab | 8 |  | R-13 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Reexcavation of Putia Khal from 0.000 to 5.235 | Km | 5.235 | 313.3495 | [5 empty] | NETR/PW-04 | Rehab | 8 |  | R-13 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Resectioning of Submersible EMB from 44.600 to 48.650 | Km | 3.75 | 154.6148 | [5 empty] | NETR/PW-04 | Rehab | 10 |  | R-13 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Resectioning of Submersible EMB from 42.000 to 43.000 | Km | 1 | 33.674 | [5 empty] | NETR/PW-04 | Rehab | 10 |  | R-13 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Resectioning of Submersible EMB from 22.000 to 25.000 | Km | 3 | 99.547 | [5 empty] | NETR/PW-04 | Rehab | 10 |  | R-13 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Resectioning of Submersible EMB from 6.000 to 7.000 | Km | 1 | 38.1199 | [5 empty] | NETR/PW-04 | Rehab | 10 |  | R-13 | NETR
BWDB/Netra/HFMLIP/PW-04 Khaliajuri FCD-2 & FCD-4 | Resectioning of Submersible EMB from 6.000 to 7.000 | Km | 1 | 69.6592 | [5 empty] | NETR/PW-04 | Rehab | 10 |  | R-13 | NETR
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of Submesible Emb from Km 6.800 to 24.855 | Km | 3.071 | 57.25 | [5 empty] | NETR/PW-05 | New | 3 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of 1-Vent Chapri Regulator | Nos | 1 | 242.75 | [5 empty] | NETR/PW-05 | New | 3 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of 1-Vent Ukra Regulator | Nos | 1 | 286.86 | [5 empty] | NETR/PW-05 | New | 3 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of 1-Vent Ichamati Regulator | Nos | 1 | 182.66 | [5 empty] | NETR/PW-05 | New | 3 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-05 Ganesh Haor | Const of 4-Vent Ichamati Regulator | Nos | 1 | 419.66 | [5 empty] | NETR/PW-05 | New | 3 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Narsua River from Km 0.000 to 6.225 | Km | 6.226 | 224.4496 | [5 empty] | NETR/PW-06 | New | 7 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Ukra Khal from Km 0.111 to 2.043 Km | Km | 1.933 | 118.7745 | [5 empty] | NETR/PW-06 | New | 7 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Chapri Khal from Km 0.280 to 2.590 Km | Km | 2.31 | 88.1515 | [5 empty] | NETR/PW-06 | New | 7 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Ichamati Khal from Km 0.072 to 1.250 Km | Km | 1.178 | 51.0575 | [5 empty] | NETR/PW-06 | New | 7 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Reexcavation of Boilara Khal from Km 8.550 to 8.900 Km | Km | 0.35 | 28.0376 | [5 empty] | NETR/PW-06 | New | 7 |  | N-11 | NETR
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const of BoX drainage ountlet at Bhadera | Nos | 1 | 42.25 | [5 empty] | NETR/PW-06 | New | 4 |  | N-11
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const of BoX drainage ountlet at Moheswar Khal | Nos | 1 | 42.25 | [5 empty] | NETR/PW-06 | New | 4 |  | N-11
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Const of Irrigation Inlet | Nos | 2 | 16.92 | [5 empty] | NETR/PW-06 | New | 1 |  | N-11
BWDB/Netra/HFMLIP/PW-06 Ganesh Haor | Rehbilation of existing Regulator | Nos | 1 | 19.43 | [5 empty] | NETR/PW-06 | New | 12 |  | N-11
BWDB/Netra/HFMLIP/PW-07 Ganesh Haor | Reexcavation of Kangsha river | Km | 15 | 654.8026 | [5 empty] | NETR/PW-07 | New | 7 |  | N-12
BWDB/Netra/HFMLIP/PW-07 Ganesh Haor | Reexcavation of Gumai river | Km | 9 | 238.8741 | [5 empty] | NETR/PW-07 | New | 7 |  | N-12
7378.3229

## Sunamgonj
Package Name | Component | Unit | Qnty | Cost | Remarks | Package | Haor Type | Structure Code | Earth Volume | Hoar Code | District Code
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Submersible Embankment between km10.600 to 49.426 total 33.849km | km | 33.849 | 867.33 |  | SUNM/PW-01 | New | 11 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Re-Excavation of Dariabaz Khal | km | 1.48 | 18.8287 |  | SUNM/PW-01 | New | 7 |  |  | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Re-Excavation of Juriganga Khal | km | 1.438 | 32.0288 |  | SUNM/PW-01 | New | 7 |  |  | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Re-Excavation of Purukania Khal | km | 1.56 | 41.0489 |  | SUNM/PW-01 | New | 7 |  |  | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Re-Excavation of Muktakhai River | Km | 3.2 | 176.4745 |  | SUNM/PW-01 | New | 7 |  |  | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-1 | Nos | 1 | 45.09 |  | SUNM/PW-01 | New | 4 |  |  | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-2 | Nos | 1 | 45.09 |  | SUNM/PW-01 | New | 4 |  |  | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-3 | Nos | 1 | 45.09 |  | SUNM/PW-01 | New | 4 |  |  | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-4 | Nos | 1 | 45.09 |  | SUNM/PW-01 | New | 4 |  |  | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-5 | Nos | 1 | 45.09 |  | SUNM/PW-01 | New | 4 |  |  | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-6 | Nos | 1 | 45.09 |  | SUNM/PW-01 | New | 4 |  |  | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Box Drainage Outlet-7 | Nos | 1 | 45.09 |  | SUNM/PW-01 | New | 4 |  |  | SUNM
BWDB/Sunam/HFMLIP/PW-01 Dhakua Haor (Division-2) | Irrigation Inlet | Nos | 9 | 10.66 |  | SUNM/PW-01 | New | 1 |  |  | SUNM
BWDB/Sunam/HFMLIP/PW-02 Dhakua Haor (Division-2) | Re-excavation of Piyan River from km 19.000 to km 55.575 total 36.575km | Km | 36.575 | 1193.75 |  | SUNM/PW-02 | New | 7 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | 1 vent (1.50m X 1.80m)-1 | Nos | 1 | 183.3461 |  | SUNM/PW-03 | New | 3 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | 2 vent (1.50m X 1.80m)-1 | Nos | 1 | 308.0018 |  | SUNM/PW-03 | New | 3 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-1 | Nos | 1 | 182.286 |  | SUNM/PW-03 | New | 5 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-2 | Nos | 1 | 182.286 |  | SUNM/PW-03 | New | 5 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-3 | Nos | 1 | 182.286 |  | SUNM/PW-03 | New | 5 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-4 | Nos | 1 | 182.286 |  | SUNM/PW-03 | New | 5 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 4.0m wide-5 | Nos | 1 | 182.286 |  | SUNM/PW-03 | New | 5 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-03 Dhakua Haor (Division-1) | Causeway 6.0m wide-1 | Nos | 1 | 279.3507 |  | SUNM/PW-03 | New | 5 |  | N-14 | SUNM
BWDB/Sunam/HFMLIP/PW-04 Dharmapasha Rui Beel (Division-1) | Construction of Submersible embankment-34.94km | Km | 34.94 | 1564.32 |  | SUNM/PW-04 | New | 11 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Dahar 4vent (1.50m X 1.80m)-1 Regulator | Nos | 1 | 283.3851 |  | SUNM/PW-05 | New | 3 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Deola 2 vent (1.50m X 1.80m)-1 Regulator | Nos | 1 | 267.8703 |  | SUNM/PW-05 | New | 3 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Manani Causeway 6.0m wide-1 | Nos | 1 | 225.81 |  | SUNM/PW-05 | New | 5 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Dahar Causeway 4.0m wide-1 | Nos | 1 | 301.6651 |  | SUNM/PW-05 | New | 5 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Daharagang Causeway 4.0m wide-2 | Nos | 1 | 187.8663 |  | SUNM/PW-05 | New | 5 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-05 Dharmapasha Rui Beel (Division-1) | Chandrasona Causeway 4.0m wide-3 | Nos | 1 | 191.3901 |  | SUNM/PW-05 | New | 5 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Khurma Khal | km | 7.18 | 36.0889 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Udani Khal | km | 3.828 | 54.377 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Deola Khal | km | 1.965 | 70.1082 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Shaitan Khal | km | 13.8 | 565.0549 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Banni Khal2 | km | 2.913 | 36.3507 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Rui Beel Khal | km | 3.414 | 62.7308 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Dahar Gang | km | 6.832 | 176.7629 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Gobra Khal | km | 2.893 | 45.6733 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Banni Khal1 | km | 2.622 | 39.8891 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Dagar Khal | km | 2.665 | 15.5116 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Rajpur Khal | km | 3.595 | 37.8562 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Kolma Khal | km | 2.204 | 17.6969 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Agunia khal | km | 7.611 | 157.1547 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Kakura Khal | km | 1.305 | 32.5728 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Dharam Beel Khal | km | 1.105 | 37.7084 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Bararia Khal | km | 2.11 | 14.6001 |  | SUNM/PW-06 | New | 7 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Const. of Box Drainage Outlet-1 | Nos | 1 | 45.13 |  | SUNM/PW-06 | New | 4 |  | N-12 | SUNM
BWDB/Sunam/HFMLIP/PW-06 Dharmapasha Rui Beel (Division-1) | Irrigation Inlet | Nos | 12 | 131.38 |  | SUNM/PW-06 | New | 1 |  | N-12 | SUNM

## Packages
sl | Package_No | Payment_30_06_2020
1 | KISH/PW-01 | 51.09
2 | KISH/PW-02 | 347.71
3 | KISH/PW-03 | 625.93
4 | KISH/PW-04 | 714.69
5 | KISH/PW-05 | 575.15
6 | KISH/PW-06 | 837.25
7 | KISH/PW-07 | 565.07
8 | KISH/PW-08 | 0
9 | KISH/PW-09 | 712.33
10 | KISH/PW-10 | 409.68
11 | KISH/PW-11 | 522.86
12 | KISH/PW-12 | 705.59
13 | KISH/PW-13 | 647.2
14 | KISH/PW-14 | 806.89
15 | KISH/PW-15 | 333.94
16 | KISH/PW-16 | 721.62
17 | KISH/PW-17 | 1451.95
18 | KISH/PW-18 | 711.02
19 | KISH/PW-19 | 331.35
20 | KISH/PW-20 | 501.12
21 | KISH/PW-21 | 268.24
22 | KISH/PW-22 | 281.05
23 | KISH/PW-23 | 720.33
24 | KISH/PW-24 | 890.42
25 | KISH/PW-25 | 749.37
26 | KISH/PW-26 | 501.12
27 | KISH/PW-27 | 0
28 | KISH/PW-28 | 0
29 | KISH/PW-29 | 0
30 | KISH/PW-30 | 0
31 | KISH/PW-31 | 0
32 | KISH/PW-32 | 0
33 | KISH/PW-33 | 0
34 | KISH/PW-34 | 0
35 | KISH/PW-35 | 0
36 | KISH/PW-36 | 0
37 | KISH/PW-37 | 0
38 | KISH/PW-38 | 0

## Netrokona_Categorical_Projectio
Sl No | Package Name | Structue Name | unit | Quanty | Contract Value | STC Code | Bill Paid | Remaining Bill | Value of work done as per 04,March,2020 | Projection | Workstatus | FSE Name | Contractor | Remarks
1 | NETR/PW-01 | Resectioning of Full embankment from 0.000 to 41.771 | Km | 35.828 | 1132.4847 | 9 | 334.51 | 797.9747 | 504.16 | 609.57 | OG |  |  | Excavator=3
2 | NETR/PW-01 | Resectioning of Full embankment from 0.911to 11.600 | km | 10.69 | 212.86 | 9 | 94.35 | 118.51 | 59.6 | 97.91 | OG |  |  | Excavator=1
5 | NETR/PW-02 | Anda Khal | Km | 7.192 | 215.6843 | 8 | 52.6435 | 163.0409 | 215.684 | 215.684 | C
6 | NETR/PW-02 | Dupikhali Khal part-1 | Km | 3.66 | 106.6825 | 8 | 26.7902 | 79.8923 | 106.683 | 106.683 | C
7 | NETR/PW-02 | Dupikhali Khal part-1 | Km | 5.057 | 112.0192 | 8 | 37.0158 | 75.0033 | 112.019 | 112.019 | C
8 | NETR/PW-02 | Dudhkura Khal | Km | 5.4 | 57.6844 | 8 | 39.5265 | 18.1579 | 57.684 | 57.684 | C
12 | NETR/PW-02 | Kamalpur Khal | Km | 2.98 | 91.9555 | 8 | 21.8128 | 70.1427 | 22.19 | 38.81 | OG |  |  | Excavator=1
3 | NETR/PW-02 | Dhalia Khal | Km | 7.37 | 68.3113 | 8 | 53.9464 | 14.365 | 0 | 0 | P
4 | NETR/PW-02 | Balai khal | Km | 5.896 | 107.2237 | 8 | 43.1571 | 64.0666 | 0 | 0 | P
9 | NETR/PW-02 | kurikunia Khal | Km | 1.903 | 48.574 | 8 | 13.9294 | 34.6446 | 0 | 0 | P
10 | NETR/PW-02 | Dighjan Khal | Km | 4.32 | 102.8289 | 8 | 31.6212 | 71.2077 | 0 | 0 | P
11 | NETR/PW-02 | Tutnir Khal | Km | 3.15 | 37.9263 | 8 | 23.0571 | 14.8691 | 0 | 0 | P
14 | NETR/PW-03 | Resection of Submesible Singer Bill | km | 3.56 | 29.21 | 10 | 16.103 | 13.107 | 29.1 | 29.21 | C
15 | NETR/PW-03 | Reinstllation of 5-vent Regulator Dampara | No | 1 | 389.57 | 2 | 178.46 | 211.11 | 89.23 | 178.46 | OG |  |  | Intense Monitoring Needed for Completion
13 | NETR/PW-03 | Resection of Full embankment in Kangsha River Sheme | km | 20.9 | 450.21 | 9 | 94.537 | 355.673 | 177.08 | 177.08 | P
19 | NETR/PW-04 | Reexcavation of Jhalokhali from 0.000 to 6.76 | Km | 6.76 | 282.4937 | 8 | 94.9552 | 187.5385 | 282.4937 | 282.4937 | C
20 | NETR/PW-04 | Reexcavation of Putia Khal from 0.000 to 5.235 | Km | 5.235 | 313.3495 | 8 | 73.5341 | 239.8155 | 313.3495 | 313.3495 | C
24 | NETR/PW-04 | Resectioning of Submersible EMB from 6.000 to 7.000 | Km | 1 | 38.1199 | 10 | 13.4492 | 24.6707 | 38.12 | 38.12 | C | Anil
25 | NETR/PW-04 | Resectioning of Submersible EMB from 6.000 to 7.000 | Km | 1 | 69.6592 | 10 | 13.4492 | 56.21 | 69.659 | 69.659 | C | 34.895
23 | NETR/PW-04 | Resectioning of Submersible EMB from 22.000 to 25.000 | Km | 3 | 99.547 | 10 | 40.3477 | 59.1993 | 39.79 | 99.47 | OG | Anil
16 | NETR/PW-04 | Reexcavation of Piyan River from 0.075 to 5.00 | Km | 4.925 | 335.3397 | 8 | 69.1796 | 266.1601 | 33.5 | 33.5 | P |  |  | Dreger=1
17 | NETR/PW-04 | Reexcavation of Nayori Khal from 0.000 to 7.565 | Km | 7.565 | 158.059 | 8 | 106.2627 | 51.7963 | 63.22 | 63.22 | P
18 | NETR/PW-04 | Reexcavation of Feni Khal from 0.000 to 1.903 | Km | 1.903 | 16.0636 | 8 | 26.7307 | -10.6672 | 8.04 | 8.04 | P
21 | NETR/PW-04 | Resectioning of Submersible EMB from 44.600 to 48.650 | Km | 3.75 | 154.6148 | 10 | 50.4346 | 104.1802 | 113.38 | 113.38 | P
22 | NETR/PW-04 | Resectioning of Submersible EMB from 42.000 to 43.000 | Km | 1 | 33.674 | 10 | 13.4492 | 20.2248 | 0 | 0 | P | Anil
27 | NETR/PW-05 | Const of 1-Vent Chapri Regulator | Nos | 1 | 242.75 | 3 | 41.0367 | 201.7133 | 60.68 | 242.75 | OG |  |  | Will be completed this year
28 | NETR/PW-05 | Const of 1-Vent Ukra Regulator | Nos | 1 | 286.86 | 3 | 41.0367 | 245.8233 | 143.13 | 286.86 | OG |  |  | Will be completed this year
29 | NETR/PW-05 | Const of 1-Vent Ichamati Regulator | Nos | 1 | 182.66 | 3 | 41.0367 | 141.6233 | 109.6 | 182.66 | OG |  |  | Will be completed this year
30 | NETR/PW-05 |  | Nos | 1 | 419.66 | 3 | 0 | 419.66 | 104.92 | 419.66 | OG |  |  | Indepth Monitoring Required for Completion this year
26 | NETR/PW-05 | Const of Submesible Emb from Km 6.800 to 24.855 | Km | 1 | 57.25 | 3 | 0 | 57.25 | 0 | 0 | P |  |  | This component should be dropped
31 | NETR/PW-06 | Reexcavation of Narsua River from Km 0.000 to 6.225 | Km | 6.226 | 224.4496 | 7 | 133.3476 | 91.102 | 224.45 | 224.45 | C
36 | NETR/PW-06 | Const of BoX drainage ountlet at Bhadera | Nos | 1 | 42.25 | 4 | 19.04 | 23.21 | 29.58 | 42.25 | OG
37 | NETR/PW-06 | Const of BoX drainage ountlet at Moheswar Khal | Nos | 1 | 42.25 | 4 | 19.04 | 23.21 | 29.58 | 42.5 | OG
39 | NETR/PW-06 | Rehbilation of existing Regulator | Nos | 1 | 19.43 | 12 | 0 | 19.43 | 0 | 19.43 | OG
32 | NETR/PW-06 | Reexcavation of Ukra Khal from Km 0.111 to 2.043 Km | Km | 1.933 | 118.7745 | 7 | 41.4007 | 77.3738 | 35.632 | 35.632 | P |  |  | 70% work is dropped
33 | NETR/PW-06 | Reexcavation of Chapri Khal from Km 0.280 to 2.590 Km | Km | 2.31 | 88.1515 | 7 | 49.4752 | 38.6763 | 52.9 | 52.9 | P |  |  | 60% complete40% dropped
34 | NETR/PW-06 | Reexcavation of Ichamati Khal from Km 0.072 to 1.250 Km | Km | 1.178 | 51.0575 | 7 | 25.2302 | 25.8272 | 15.31 | 15.31 | P |  |  | 30% complete70% dropped
35 | NETR/PW-06 | Reexcavation of Boilara Khal from Km 8.550 to 8.900 Km | Km | 0.35 | 28.0376 | 7 | 7.4962 | 20.5413 | 0 | 0 | P |  |  | Work on held
38 | NETR/PW-06 | Const of Irrigation Inlet | Nos | 2 | 16.92 | 1 | 0 | 16.92 | 0 | 0 | P |  |  | On held
40 | NETR/PW-07 | Reexcavation of Kangsha river | Km | 15 | 654.8026 | 7 | 354.81 | 299.9926 | 491.02 | 491.02 | C |  |  | 75% Complete not possible to continue
41 | NETR/PW-07 | Reexcavation of Gumai river | Km | 9 | 238.8741 | 7 | 212.89 | 25.9841 | 179.16 | 179.16 | C |  |  | 75% Complete not possible to continue
Sub-Total |  |  |  |  | 7378.3229 | 294 | 2549.0924 | 4829.2306 | 3810.9442 | 4878.9242
[5 empty] | CV |  | BP | RB | VWD | PVWD | PFM
|  |  |  | NETR/PW-01 | 1345.3447 |  | 428.86 | 916.4847 | 563.76 | 707.48 | 278.62
|  |  |  | NETR/PW-02 | 948.8902 |  | 343.5 | 605.3902 | 514.26 | 530.88 | 187.38
|  |  |  | NETR/PW-03 | 868.99 |  | 289.1 | 579.89 | 295.41 | 384.75 | 95.65
|  |  |  | NETR/PW-04 | 1500.9205 |  | 501.7924 | 999.1281 | 961.5522 | 1021.2322 | 519.4398
|  |  |  | NETR/PW-05 | 1189.18 |  | 123.11 | 1066.07 | 418.33 | 1131.93 | 1008.82
|  |  |  | NETR/PW-06 | 631.3207 |  | 295.03 | 336.2907 | 387.452 | 432.472 | 137.442
|  |  |  | NETR/PW-07 | 893.6768 |  | 567.7 | 325.9768 | 670.18 | 670.18 | 102.48
|  |  |  | Total | 7378.3229 | 0 | 2549.0924 | 4829.2306 | 3810.9442 | 4878.9242 | 2329.8318

## Habiganj_Categorical_Projection
Sl No | Package Name | Structue Name | unit | Quanty | Contract Value | STC Code | Bill Paid | Remaining Bill | Value of work done as per 04,March,2020 | Projection | Workstatus | FSE Name | Contractor | Remarks
1 | HOBI/PW-01 | Resectioning of Embankment along the left bank of the Bashira River inbwt 2.420 to 9.760 | km | 7 | 151.385 | 10 | 40 | 111.385 | 151.385 | 151.385 | C |  |  |  | 1
2 | HOBI/PW-01 | construction of new Embankment along the left bank of bitangal khal inbwt 10.000 to 17.000 | km | 7 | 151.385 | 10 | 40 | 111.385 | 151.385 | 151.385 | C |  |  |  | 1
3 | HOBI/PW-01 | Reexcavation of Bashira River 0.000 to 20.000 | km | 17.4 | 732.6 | 8 | 561.9328 | 170.6672 | 585.24 | 585.24 | P |  |  | C14R3.5 | 1
4 | HOBI/PW-01 | Reexcavation of Matikatakahl from 0.000 to Km 2.295 | km | 2.925 | 99.9 | 8 | 76.6272 | 23.2728 | 99.9 | 99.9 | C |  |  |  | 1
5 | HOBI/PW-01 | Construction of 2-vent Regulator | nos. | 1 | 208 | 3 | 0 | 208 | 318.42 | 318.42 | P |  |  |  | 1
6 | HOBI/PW-01 | Construction of 4.00m causeway | nos. | 1 | 178.13 | 5 | 0 | 178.13 | 149.54 | 149.54 | P |  |  | Dropped as per information from FSE | 1
7 | HOBI/PW-02 | Resctioning of Submersible Embankment from 0.000 to 26.000 at Left Bank of Kushiyara | Km | 7.23 | 274.56 | 10 | 119.6743 | 154.8857 | 274.56 | 274.56 | C |  |  |  | 1
8 | HOBI/PW-02 | Construction of Retired Embankment in between 0.000 to 26.500 | Km | 6.894 | 225.46 | 10 | 98.2728 | 127.1872 | 0 | 0 | P |  |  | Dropped as per information from FSE | 1
9 | HOBI/PW-02 | Resctioning of Submersible Embankment from 0.000 to 16.02 at Right Bank of Khoai | Km | 16.02 | 318.42 | 10 | 138.7919 | 179.6281 | 37.0833 | 37.0833 | C |  |  |  | 1
10 | HOBI/PW-02 | Construction of New Embankment from Km 22.850 to 31.210 | Km | 8.36 | 149.54 | 10 | 65.181 | 84.359 | 149.54 | 149.54 | C |  |  |  | 1
11 | HOBI/PW-02 | Reexcavation of Kairdhala Khal from 0.000 to 1.6950 km | Km | 1.695 | 132.8661 | 8 | 101.264 | 31.6021 | 0 | 0 | P |  |  | Dropped as per information from FSE | 1
12 | HOBI/PW-02 | Reexcavation of Satmukha Khal from 0.000 to 1.790 km | Km | 1.79 | 53.0475 | 8 | 40.4302 | 12.6173 | 53.0475 | 53.0475 | C |  |  |  | 1
13 | HOBI/PW-02 | Reexcavation of Singer Beel Khal from 0.000 to 2.720 km | Km | 2.72 | 29.975 | 8 | 22.8455 | 7.1295 | 29.975 | 29.975 | C |  |  |  | 1
14 | HOBI/PW-02 | Construction of Causeway 4-m width Causeway | nos. | 1 | 168.38 | 5 | 0 | 168.38 | 50.514 | 168.38 | OG |  |  | Possible to complete this FY | 1
36 | HOBI/PW-04 | Submesible Embankment from 31.600 to 81.740 | km | 23.815 | 638.85 | 11 | 349.1504 | 289.6996 | 374.97 | 374.97 | P |  |  | C:13.5 R:10.Remaining Part May Not Be done This FY | 1
37 | HOBI/PW-04 | Block road | km |  | 507.95 | 11 | 277.6096 | 230.3404 | 346.06 | 507.95 |  |  |  | CC Block Manufacturing Complete | 1
15 | HOBI/PW-05 | Boranbil khal Regulator (1-vent) | nos. | 1 | 141.3235 | 3 | 25.0048 | 116.3188 | 0 | 0 | P |  |  | Will not be started this FY | 1
16 | HOBI/PW-05 | Chandakhali khal Regulator(1-vent) | nos. | 1 | 154.0746 | 3 | 27.2608 | 126.8137 | 0 | 0 | P |  |  | Will not be started this FY | 1
17 | HOBI/PW-05 | Chargaowdair khal Regulator(1-vent) | nos. | 1 | 151.0703 | 3 | 26.7293 | 124.341 | 45.32 | 90.64 | OG |  |  | Projected prog 60% | 1
18 | HOBI/PW-05 | Chhoto Katari khal Regulator(1-vent) | nos. | 1 | 143.8109 | 3 | 25.4449 | 118.3661 | 0 | 0 | P |  |  | Will not be started this FY | 1
19 | HOBI/PW-05 | Islampur khal Regulator (1-vent) | nos. | 1 | 155.6933 | 3 | 27.5472 | 128.146 | 93.41 | 155.6933 | OG |  |  | Possible to complete this FY | 1
20 | HOBI/PW-05 | Tetter Drepasionkhal Regulator(2-vent) | nos. | 1 | 216.7515 | 3 | 38.3504 | 178.401 | 130.05 | 216.7515 | OG |  |  | Projected prog 60% | 1
21 | HOBI/PW-05 | Soaybeel khal Regulator (5-vent) | nos. | 1 | 353.8204 | 3 | 62.6024 | 291.218 | 353.8204 | 353.8204 | OG |  |  | Possible to complete this FY | 1
22 | HOBI/PW-06 | Bibiyana 6.0m Causeway | nos. | 1 | 415.5317 | 5 | 292.4601 | 123.0716 | 415.5317 | 415.5317 | C |  |  |  | 1
23 | HOBI/PW-06 | Old kushiyana 6.0m Causeway | nos. | 1 | 373.3459 | 5 | 262.7689 | 110.577 | 336 | 373.3459 | OG |  |  | Block Pitching is going on | 1
24 | HOBI/PW-06 | Ratna River 4.0m Causeway | nos. | 1 | 143.1604 | 5 | 100.7594 | 42.401 | 128.84 | 143.1604 | OG |  |  | Block Pitching is going on | 1
25 | HOBI/PW-06 | Rukway 4.0m Causeway | nos. | 1 | 165.1831 | 5 | 116.2594 | 48.9237 | 115.63 | 165.1831 | OG |  |  | 2nd lift of wing wall going on | 1
26 | HOBI/PW-06 | BoX1 | nos. | 1 | 37.0833 | 4 | 16.1111 | 20.9722 | 37.0833 | 37.0833 | C |  |  |  | 1
27 | HOBI/PW-06 | BoX2 | nos. | 1 | 37.0833 | 4 | 16.1111 | 20.9722 | 37.0833 | 37.0833 | C |  |  |  | 1
28 | HOBI/PW-06 | BoX3 | nos. | 1 | 37.0833 | 4 | 16.1111 | 20.9722 | 37.0833 | 37.0833 | C |  |  |  | 1
29 | HOBI/PW-06 | BoX4 | nos. | 1 | 37.0833 | 4 | 16.1111 | 20.9722 | 37.0833 | 37.0833 | C |  |  |  | 1
30 | HOBI/PW-06 | BoX5 | nos. | 1 | 37.0833 | 4 | 16.1111 | 20.9722 | 37.0833 | 37.0833 | C |  |  |  | 1
31 | HOBI/PW-06 | BoX6 | nos. | 1 | 37.0833 | 4 | 16.1111 | 20.9722 | 37.0833 | 37.0833 | C |  |  |  | 1
32 | HOBI/PW-06 | BoX7 | nos. | 1 | 37.0833 | 4 | 16.1111 | 20.9722 | 37.0833 | 37.0833 | C |  |  |  | 1
33 | HOBI/PW-06 | BoX8 | nos. | 1 | 37.0833 | 4 | 16.1111 | 20.9722 | 37.0833 | 37.0833 | C |  |  |  | 1
34 | HOBI/PW-06 | BoX9 | nos. | 1 | 37.0833 | 4 | 16.1111 | 20.9722 | 37.0833 | 37.0833 | C |  |  |  | 1
35 | HOBI/PW-06 | Irrigation Inlet | nos. | 15 | 150.7581 | 1 | 0 | 150.7581 | 90.5 | 90.5 | P |  |  | C8 | 1
38 | HOBI/PW-07 | Chargaowdair khal | km | 3.036 | 45.4209 | 7 | 33.4774 | 11.9435 | 45.4209 | 45.4209 | C |  |  |  | 1
39 | HOBI/PW-07 | Chotokatari Khal | km | 3.264 | 61.408 | 7 | 45.2607 | 16.1473 | 61.408 | 61.408 | C |  |  |  | 1
40 | HOBI/PW-07 | Salukadhar Khal | km | 2.428 | 67.6663 | 7 | 49.8734 | 17.7929 | 67.6663 | 67.6663 | C |  |  |  | 1
41 | HOBI/PW-07 | Islampur khal | km | 0.634 | 25.7065 | 7 | 18.9469 | 6.7596 | 0 | 0 | P |  |  | Dropped as per information from FSE | 1
42 | HOBI/PW-07 | Soyabeel Khal | km | 3.285 | 139.5951 | 7 | 102.8884 | 36.7067 | 139.5951 | 139.5951 | C |  |  |  | 1
43 | HOBI/PW-07 | Chatal Beel Khal | km | 5.2176 | 103.126 | 7 | 76.0089 | 27.1171 | 0 | 0 | P |  |  | Dropped as per information from FSE | 1
44 | HOBI/PW-07 | Rajendrapur Khal | km | 4.327 | 115.1915 | 7 | 84.9018 | 30.2898 | 115.1915 | 115.1915 | C |  |  |  | 1
45 | HOBI/PW-07 | Purohogun Khal | km | 2.428 | 65.549 | 7 | 48.3128 | 17.2362 | 65.549 | 65.549 | C |  |  |  | 1
46 | HOBI/PW-07 | Sutki River | km | 8.03 | 145.977 | 7 | 0 | 145.977 | 37.35 | 145.977 | OG |  |  |  | 1
47 | HOBI/PW-07 | Ratna River | km | 7.51 | 137.4972 | 7 | 0 | 137.4972 | 26.3 | 137.4972 | OG |  |  |  | 1
[5 empty] | 7825.8595 |  | 3541.6375 | 4284.222 | 5372.9523 | 6168.0567
[5 empty] | CV |  | BP | RB | VWD | PVWD | PE
|  |  |  | HOBI/PW-01 | 1521.4 |  | 718.56 | 802.84 | 1455.87 | 1455.87 | 737.31
|  |  |  | HOBI/PW-02 | 1352.2486 |  | 586.4597 | 765.7889 | 594.7198 | 712.5858 | 126.1261
|  |  |  | HOBI/PW-04 | 1146.8 |  | 626.76 | 520.04 | 721.03 | 882.92 | 256.16
|  |  |  | HOBI/PW-05 | 1316.5445 |  | 232.9399 | 1083.6046 | 622.6004 | 816.9052 | 583.9652
|  |  |  | HOBI/PW-06 | 1581.7287 |  | 917.2476 | 664.4811 | 1420.2512 | 1521.4706 | 604.223
|  |  |  | HOBI/PW-07 | 907.1377 |  | 459.6703 | 447.4673 | 558.4809 | 778.3051 | 318.6348
[5 empty] | 7825.8595 |  | 3541.6375 | 4284.222 | 5372.9523 | 6168.0567 | 2626.4192

## Sunamgonj_Categorical_Projectio
Sl No | Package Name | Structue Name | unit | Quanty | Contract Value | STC Code | Bill Paid | Remaining Bill | Value of work done as per 04,March,2020 | Projection | Workstatus | FSE Name | Contractor | Remarks
2 | SUNM/PW-01 | Re-Excavation of Dariabaz Khal | km | 1.48 | 18.8287 |  | 18.1004 | 0.72836 | 18.829 | 18.829 | C
5 | SUNM/PW-01 | Re-Excavation of Muktakhai River | Km | 3.2 | 176.4745 |  | 169.6479 | 6.8267 | 174.475 | 174.475 | C
6 | SUNM/PW-01 | Box Drainage Outlet-1 | Nos | 1 | 45.09 |  | 0 | 45.09 | 31.563 | 45.09 | OG
7 | SUNM/PW-01 | Box Drainage Outlet-2 | Nos | 1 | 45.09 |  | 0 | 45.09 | 18.036 | 45.09 | OG
8 | SUNM/PW-01 | Box Drainage Outlet-3 | Nos | 1 | 45.09 |  | 0 | 45.09 | 21.512 | 45.09 | OG
9 | SUNM/PW-01 | Box Drainage Outlet-4 | Nos | 1 | 45.09 |  | 0 | 45.09 | 11.27 | 45.09 | OG
1 | SUNM/PW-01 | Submersible Embankment between km10.600 to 49.426 total 33.849km | km | 33.849 | 867.33 |  | 360.11 | 507.22 | 251.11 | 251.11 | P
3 | SUNM/PW-01 | Re-Excavation of Juriganga Khal | km | 1.438 | 32.0288 |  | 30.7898 | 1.239 | 4.456 | 4.456 | P |  |  | C0.2R1.28
4 | SUNM/PW-01 | Re-Excavation of Purukania Khal | km | 1.56 | 41.0489 |  | 39.461 | 1.5879 | 13.16 | 13.16 | P |  |  | C0.5R1.06
10 | SUNM/PW-01 | Box Drainage Outlet-5 | Nos | 1 | 45.09 |  | 0 | 45.09 | 0 | 0 | P
11 | SUNM/PW-01 | Box Drainage Outlet-6 | Nos | 1 | 45.09 |  | 0 | 45.09 | 0 | 0 | P
12 | SUNM/PW-01 | Box Drainage Outlet-7 | Nos | 1 | 45.09 |  | 0 | 45.09 | 0 | 0 | P
13 | SUNM/PW-01 | Irrigation Inlet | Nos | 9 | 10.66 |  | 0 | 10.66 | 0 | 0 | P
14 | SUNM/PW-02 | Re-excavation of Piyan River from km 19.000 to km 55.575 total 36.575km | Km | 36.575 | 1193.75 |  | 150.11 | 1043.64 | 240.8 | 471.53 | OG
15 | SUNM/PW-03 | 1 vent (1.50m X 1.80m)-1 | Nos | 1 | 183.3461 |  | 50.7483 | 132.5978 | 146.77 | 183.3461 | OG
16 | SUNM/PW-03 | 2 vent (1.50m X 1.80m)-1 | Nos | 1 | 308.0018 |  | 85.2517 | 222.7501 | 92.4 | 184.8 | OG
17 | SUNM/PW-03 | Causeway 4.0m wide-1 | Nos | 1 | 182.286 |  | 27.0249 | 155.261 | 109.37 | 182.286 | OG
18 | SUNM/PW-03 | Causeway 4.0m wide-2 | Nos | 1 | 182.286 |  | 27.0249 | 155.261 | 109.37 | 182.286 | OG
19 | SUNM/PW-03 | Causeway 4.0m wide-3 | Nos | 1 | 182.286 |  | 27.0249 | 155.261 | 0 | 0 | P
20 | SUNM/PW-03 | Causeway 4.0m wide-4 | Nos | 1 | 182.286 |  | 27.0249 | 155.261 | 0 | 0 | P
21 | SUNM/PW-03 | Causeway 4.0m wide-5 | Nos | 1 | 182.286 |  | 27.0249 | 155.261 | 0 | 0 | P
22 | SUNM/PW-03 | Causeway 6.0m wide-1 | Nos | 1 | 279.3507 |  | 41.4153 | 237.9354 | 0 | 0 | P
23 | SUNM/PW-04 | Construction of Submersible embankment-34.94km | Km | 34.94 | 1564.32 |  | 1037.6 | 526.72 | 1181.06 | 1334.36 | OG |  |  | 4 Excavator.Increase in Excavator Required
24 | SUNM/PW-05 | Dahar 4vent (1.50m X 1.80m)-1 Regulator | Nos | 1 | 283.3851 |  | 0 | 283.3851 | 141.69 | 285.05 | OG
25 | SUNM/PW-05 | Deola 2 vent (1.50m X 1.80m)-1 Regulator | Nos | 1 | 267.8703 |  | 0 | 267.8703 | 187.51 | 267.87 | OG
26 | SUNM/PW-05 | Manani Causeway 6.0m wide-1 | Nos | 1 | 225.81 |  | 0 | 225.81 | 158.07 | 225.81 | OG
27 | SUNM/PW-05 | Dahar Causeway 4.0m wide-1 | Nos | 1 | 301.6651 |  | 0 | 301.6651 | 90.5 | 301.665 | OG
28 | SUNM/PW-05 | Daharagang Causeway 4.0m wide-2 | Nos | 1 | 187.8663 |  | 0 | 187.8663 | 93.93 | 187.866 | OG
29 | SUNM/PW-05 | Chandrasona Causeway 4.0m wide-3 | Nos | 1 | 191.3901 |  | 0 | 191.3901 | 95.7 | 191.39 | OG
31 | SUNM/PW-06 | Udani Khal | km | 3.828 | 54.377 |  | 31.9665 | 22.4105 | 54.377 | 54.377 | C
32 | SUNM/PW-06 | Deola Khal | km | 1.965 | 70.1082 |  | 41.2144 | 28.8938 | 53.52 | 53.52 | C
34 | SUNM/PW-06 | Banni Khal2 | km | 2.913 | 36.3507 |  | 21.3694 | 14.9813 | 36.3507 | 36.3507 | C
35 | SUNM/PW-06 | Rui Beel Khal | km | 3.414 | 62.7308 |  | 36.8774 | 25.8533 | 62.7308 | 62.7308 | C
37 | SUNM/PW-06 | Gobra Khal | km | 2.893 | 45.6733 |  | 26.8499 | 18.8234 | 45.6733 | 45.6733 | C
38 | SUNM/PW-06 | Banni Khal1 | km | 2.622 | 39.8891 |  | 23.4496 | 16.4396 | 39.8891 | 39.8891 | C
40 | SUNM/PW-06 | Rajpur Khal | km | 3.595 | 37.8562 |  | 22.2545 | 15.6018 | 37.8562 | 37.8562 | C
41 | SUNM/PW-06 | Kolma Khal | km | 2.204 | 17.6969 |  | 10.4034 | 7.2934 | 17.6969 | 17.6969 | C
42 | SUNM/PW-06 | Agunia khal | km | 7.611 | 157.1547 |  | 92.3862 | 64.7685 | 157.1547 | 157.1547 | C
44 | SUNM/PW-06 | Dharam Beel Khal | km | 1.105 | 37.7084 |  | 22.1676 | 15.5408 | 37.7084 | 37.7084 | C
45 | SUNM/PW-06 | Bararia Khal | km | 2.11 | 14.6001 |  | 8.5829 | 6.0172 | 14.6001 | 14.6001 | C
30 | SUNM/PW-06 | Khurma Khal | km | 7.18 | 36.0889 |  | 21.2155 | 14.8734 | 10.07 | 36.089 | OG |  |  | 4 Excavatos
33 | SUNM/PW-06 | Shaitan Khal | km | 13.8 | 565.0549 |  | 332.1778 | 232.8772 | 450.4 | 565.0549 | OG |  |  | 4 Excavatos
36 | SUNM/PW-06 | Dahar Gang | km | 6.832 | 176.7629 |  | 103.9133 | 72.8496 | 26.51 | 176.7629 | OG |  |  | 4 excavator Running.Additional Excavator Required
39 | SUNM/PW-06 | Dagar Khal | km | 2.665 | 15.5116 |  | 9.1188 | 6.3928 | 5.817 | 15.5116 | OG |  |  | 3 Excavatos
43 | SUNM/PW-06 | Kakura Khal | km | 1.305 | 32.5728 |  | 19.1485 | 13.4243 | 0 | 32.573 | OG |  |  | 3 Excavatos
46 | SUNM/PW-06 | Const. of Box Drainage Outlet-1 | Nos | 1 | 45.13 |  | 0 | 45.13 | 0 | 0 | P
47 | SUNM/PW-06 | Irrigation Inlet | Nos | 12 | 131.38 |  | 0 | 131.38 | 0 | 0 | P
Sub-Total |  |  |  |  | 8936.8331 |  | 2941.4546 | 5995.3785 | 4241.9352 | 6024.1978
[5 empty] | CV |  | BP | RB | VWD | PVWD | PFM
|  |  |  | SUNM/PW-01 | 1462.001 |  | 618.109 | 843.892 | 544.411 | 642.39 | 24.281
|  |  |  | SUNM/PW-02 | 1193.75 |  | 150.11 | 1043.64 | 240.8 | 471.53 | 321.42
|  |  |  | SUNM/PW-03 | 1682.1286 |  | 312.5399 | 1369.5886 | 457.91 | 732.7181 | 420.1782
|  |  |  | SUNM/PW-04 | 1564.32 |  | 1037.6 | 526.72 | 1181.06 | 1334.36 | 296.76
|  |  |  | SUNM/PW-05 | 1457.9869 |  | 0 | 1457.9869 | 767.4 | 1459.651 | 1459.651
|  |  |  | SUNM/PW-06 | 1576.6466 |  | 823.0957 | 753.551 | 1050.3542 | 1383.5487 | 560.453
|  |  |  | TOTAL | 8936.8331 |  | 2941.4546 | 5995.3785 | 4241.9352 | 6024.1978 | 3082.7432

## Sheet2
| SUNM/PW-01 | SUNM/PW-02 | SUNM/PW-03 | SUNM/PW-04 | SUNM/PW-05 | SUNM/PW-06
Contract_Value
Value_of_Work_Done
Bill_Paid
Projected_Value
| PACKAGE | CV | BP | RB | VWD | PVWD | PE
| SUNM/PW-01 | 1462.001 | 618.109 | 843.892 | 544.411 | 642.39 | 24.281
| SUNM/PW-02 | 1193.75 | 150.11 | 1043.64 | 240.8 | 471.53 | 321.42
| SUNM/PW-03 | 1682.1286 | 312.5399 | 1369.5886 | 457.91 | 732.7181 | 420.1782
| SUNM/PW-04 | 1564.32 | 1037.6 | 526.72 | 1181.06 | 1334.36 | 296.76
| SUNM/PW-05 | 1457.9869 | 0 | 1457.9869 | 767.4 | 1459.651 | 1459.651
| SUNM/PW-06 | 1576.6466 | 823.0957 | 753.551 | 1050.3542 | 1383.5487 | 560.453
| PACKAGE | CV | BP | RB | VWD | PVWD | PE | PFM
| NETR/PW-01 | 1345.3447 | 428.86 | 916.4847 | 563.76 | 707.48 | 278.62
| NETR/PW-02 | 948.8902 | 343.5 | 605.3902 | 514.26 | 530.88 | 187.38
| NETR/PW-03 | 868.99 | 289.1 | 579.89 | 295.41 | 384.75 | 95.65
| NETR/PW-04 | 1500.9205 | 501.7924 | 999.1281 | 961.5522 | 1021.2322 | 519.4398
| NETR/PW-05 | 1189.18 | 123.11 | 1066.07 | 418.33 | 1131.93 | 1008.82
| NETR/PW-06 | 631.3207 | 295.03 | 336.2907 | 387.452 | 432.472 | 137.442
| NETR/PW-07 | 893.6768 | 567.7 | 325.9768 | 670.18 | 670.18 | 102.48
|  | CV | BP | RB | VWD | PVWD | PE
| HOBI/PW-01 | 1521.4 | 718.56 | 802.84 | 1455.87 | 1455.87 | 737.31
| HOBI/PW-02 | 1352.2486 | 586.4597 | 765.7889 | 594.7198 | 712.5858 | 126.1261
| HOBI/PW-04 | 1146.8 | 626.76 | 520.04 | 721.03 | 882.92 | 256.16
| HOBI/PW-05 | 1316.5445 | 232.9399 | 1083.6046 | 622.6004 | 816.9052 | 583.9652
| HOBI/PW-06 | 1581.7287 | 917.2476 | 664.4811 | 1420.2512 | 1521.4706 | 604.223
| HOBI/PW-07 | 907.1377 | 459.6703 | 447.4673 | 558.4809 | 778.3051 | 318.6348

## DPP_Item
DPP_Item | VWD_30_06_2020 | VWD_30_06_2021 | Payment_30_06_2020 | Payment_30_06_2021
Inlet |  |  | 291.81
Reg_Rehab_Rehab |  |  | 0
Reg_CW_Box |  |  | 6503.97
Khal_Riv_New |  |  | 2546.54
Khal_Riv_Rehab |  |  | 51.09
Full_Emb_Rehab |  |  | 0
Sub_Emb_Rehab |  |  | 0
Sub_Emb_Const |  |  | 5833.04
Reg_Rehab_New |  |  | 0
Thr_Fl_Cost |  |  | 0
Wmg_Office |  |  | 0
Gate_Repair |  |  | 0