## Slide 1: RADP 20-21 CIVIL WORKS
DPP_Item | Kishorgonj | Hobogonj | Netrokona | Sunamgonj | Total
Construction of Irrigation Inlet (New Haors) | 354.62 | 128.76 | 36.54 | 142.04 | 661.96
Re-installation/Construction of Regulator/Causeway (Rehabilitation Sub-Projects) | 44.79 | 0 | 79.2 | 0 | 123.99
Installation/Construction of New Regulators/Causeway/Bridge/Box Drainage Outlet) (New Haors) | 2460.16 | 1788.03 | 1242.58 | 1338.55 | 6829.32
Re-excavation of Khal/River (New Haors) (Earth Volume: 68.97 Lakh cum) | 1210.55 | 110.64 | 273.4 | 545.27 | 2139.86
Re-excavation of Khal/River (Rehabilitation Sub-Projects) (Earth Volume: 28.01 Lakh cum) | 400.66 | 148.55 | 898.45 | 0 | 1447.66
Rehabilitation of Full Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 9.16 lakh cum) | 0 | 0 | 356.96 | 0 | 356.96
Rehabilitation of Submergible Embankment (Resection/construction) (Rehabilitation Sub-Projects) (Earth Volume: 7.43 lakh cum) | 0 | 117.93 | 482.08 | 0 | 600.01
Construction of Submersible Embankment (New Haors) (Earth Volume: 25.68 lakh cum) | 1498.18 | 490.86 | 0 | 314.54 | 2303.58
Rehabilitation of Regulator (New Haors) | 120.56 | 0 | 6.95 | 0 | 127.51
Thershing Floor Construction | 0 | 0 | 0 | 0 | 0
Construction of WMG Office | 0 | 0 | 0 | 0 | 0
Gate_Repair | 0 | 0 | 0 | 0 | 0
Total | 6089.52 | 2784.77 | 3376.16 | 2340.4 | 14590.85

## Slide 2: ITEM WISE DISTRIBUTION OF RADP 20-21 in BDT CRORE FOR WHOLE PROJECT
Chart: 
| INLET | STR_REH_RAHAB_HAOR | REG/CW/BOX | KHAL_RIV_NEW_HAOR | KHAL_RIV_REAHB_HAOR | RESEC_FULL_EMB | RESEC_SUB_EMB | CONS_SUB_EMB | STR_REH_NEW_HAOR | Total
 | 6.62 | 1.24 | 68.29 | 21.4 | 14.48 | 3.57 | 6 | 23.04 | 1.28 | 145.91

## Slide 3: ITEM WISE DISTRIBUTION OF RADP 20-21 in BDT CRORE FOR KISHOREGONJ
Chart: 
| INLET | STR_REH_RAHAB_HAOR | REG/CW/BOX | KHAL_RIV_NEW_HAOR | KHAL_RIV_REAHB_HAOR | RESEC_FULL_EMB | RESEC_SUB_EMB | CONS_SUB_EMB | STR_REH_NEW_HAOR | Total
 | 3.55 | 0.45 | 24.61 | 12.11 | 4 | 0 | 0 | 14.98 | 1.21 | 60.91

## Slide 4: ITEM WISE DISTRIBUTION OF RADP 20-21 in BDT CRORE
Chart: 
| INLET | STR_REH_RAHAB_HAOR | REG/CW/BOX | KHAL_RIV_NEW_HAOR | KHAL_RIV_REAHB_HAOR | RESEC_FULL_EMB | RESEC_SUB_EMB | CONS_SUB_EMB | STR_REH_NEW_HAOR | Total
 | 6.62 | 1.24 | 68.29 | 21.4 | 14.48 | 3.57 | 6 | 23.04 | 1.28 | 145.91

## Slide 5: ITEM WISE DISTRIBUTION OF RADP 20-21 in BDT CRORE
Chart: 
| INLET | STR_REH_RAHAB_HAOR | REG/CW/BOX | KHAL_RIV_NEW_HAOR | KHAL_RIV_REAHB_HAOR | RESEC_FULL_EMB | RESEC_SUB_EMB | CONS_SUB_EMB | STR_REH_NEW_HAOR | Total
 | 6.62 | 1.24 | 68.29 | 21.4 | 14.48 | 3.57 | 6 | 23.04 | 1.28 | 145.91

## Slide 6: ITEM WISE DISTRIBUTION OF RADP 20-21 in BDT CRORE
Chart: 
| INLET | STR_REH_RAHAB_HAOR | REG/CW/BOX | KHAL_RIV_NEW_HAOR | KHAL_RIV_REAHB_HAOR | RESEC_FULL_EMB | RESEC_SUB_EMB | CONS_SUB_EMB | STR_REH_NEW_HAOR | Total
 | 6.62 | 1.24 | 68.29 | 21.4 | 14.48 | 3.57 | 6 | 23.04 | 1.28 | 145.91

## Slide 7: JICA’S APPRECIATION

## Slide 8: WHY DID WE GET APPRECIATION
For Accurate Representation of Flood Situation in the project area(Damage)
For Representation and Explaining in detail of Design of different type of protection work.
For Presentation of Activity plan for civil works next two dry seasons
Progress in agriculture component and plan for next FY
Presentations of civil works monitoring format

## Slide 9: Commitment Made to JICA
Commitments to JICA | Follow ups
1. Inclusion of Type B1 protective work for 200m pilot basis | Consultant had been notified to find suitable reach
2. Quality Monitoring Civil Work Plan | 1. QA format finalized 2. Specification drafted (Needs immediate finalization)
3. Improvement of Embankment Turfing | 1. No standard test could be identified 2. Only visual inspection.

## Slide 10: Commitmenta Made to JICA
Photos of condition after major construction activities shall be taken at a regular intervals, e.g. every 200 m, and added to the report.
In case of Type A:
  Before the construction of protection work
  Before applying 100mm thick sand layer
  After applying 100mm thick sand layer
  After applying Geotextile Filter Cloth
  After applying 100 m thick assorted filter
  After applying CC blocks

## Slide 11: Commitmenta Made to JICA

## Slide 12: Commitmenta Made to JICA
Shaping of embankment crest and slope in design level and in desired compaction.
Selection of turfing source.
Cutting and transporting turf in 250mmx250mmx75mm size.
Planting turf in embankment slope without any gap in staggered formation within February .
Continuous watering upto defects liability period.
Application of fertilizer in proportion N:P:K=16:5:12
Replanting if needed in any defect area.

## Slide 13: Work Program for 2020-21
Chart: BDT Crore
| Inlet | Reg Re-inst | Reg/ CW/BDO | Khal/River (New) | Khal/River (Rehab ) | Full Emb | Subm Emb (Rehab) | Subm Emb (New) | Rehabof Reg | WMG office | Threshing Floor | Gate
Total Target as Per 2nd RDPP | 116 | 5 | 112 | 338 | 109 | 68 | 62 | 263 | 7 | 30 | 5 | 86
Program | 50 | 3 | 30 | 75 | 34 | 7 | 8 | 50 | 4 | 13 | 3 | 19

## Slide 14: Activity Plan for Next TWO Years?

## Slide 15: Progress of Re-excavation of Khal/River (New Haor)

## Slide 16
Progress of Re-excavation of Khal/River (Rehab Haor)

## Slide 17: Progress of Construction of Submersible Embankment (New Haor)

## Slide 18: Year wise Civil Works Expenditure

## Slide 19: Specification What Does It Contain?
How ,when and by whom measurement for Individual work Item will be given.
1.How ,when ,by whom and in what frequency Quality Assurance Tests for Individual work items will be performed.
Schedule of Tests for different work Items.

## Slide 20: Measurement
All the measurement will be carried through Joint Measurement Team (JMT)
Constituting Members | Designation
Concerned Sub-Divisional Engineer | Convener
Concerned SAE/SO. | Member
Concerned Field Inspector. | Member
Representative of the Contractor | Member
Concerned Field Supervision Engineer. | Member Secretary

## Slide 21: Measurement
Work Scope of JMT
Submit Measurement Every 15days in standard format. (Annex-II: Standard Forms for Measurement)
Ensure Quality Control tests performed properly
Submit monthly quality control report for every site/reach/structure..
After Completion prepare a defect liability schedule

## Slide 22: Measurement Format for CC Block

## Slide 23: Measurement Format for RCC Work

## Slide 24: Measurement Format for Reinforcement

## Slide 25: Measurement Format for Earth Work

## Slide 26: Measurement Format for Earth Work

## Slide 27: Measurement Format for General Items Not Covered Above

## Slide 28: Summary of Measurement

## Slide 29: Standard Sampling and Testing for Embankment
Sl | Name of Test | Frequency of Test | Test Method
1 | Atterberg's Limit (Plastic Limit & Liquid Limit) | 1. For each source of fill materials 2. One Sample for each 10,000 Cum of fill material 3. Change in the Characteristics of the material noticed on visual examination. | ASTM D 4318 or Equivalent
2 | Grain Size Distribution | As stated above | ASTM D 422 or Equivalent
3 | Modified Proctor Test | As stated above | ASTM D 1557 & ASSTO T 180 D
4 | Moisture Content | I .For each 5000 cum of fill material 2. As per direction of the Project Manager. | ASTM D 4346 & ASTM D 4944 or V Equivalent
5 | Field Dry Density Test | 1. One Sample for each 1000 sqm of compacted surface in each layer 2. As per direction of the Project Manager. | AAHSTO T191 or Equivalent

## Slide 30: Standard Sampling and Testing for CC Block
Sl | Name of Test | Frequency of Test | Test Method
1 | Cement: Fineness Soundness Initial Setting Time and Final Setting Time Compressive Strength Tensile Strength Unit Weight | For each fresh Consignment arriving at Site For each 100 M. Ton As approved or directed by the Project Manager. | ASTM C786, ASTI C403, ISO 679:2009 or Equivalent
2 | Fine Aggregate (Sand) i) Fineness Modulus | 1(one) Sample for each 350 Cum or part thereof At least 1 Sample in a week As approved or directed by the Project Manager. | ASTM C 33 or Equivalent
3 | Coarse Aggregate (Stone Chips) Gradation Test | 1(one) Sample for each 700 Cum or part thereof At least 1 Sample in a week As approved or directed by the Project Manager. | ASTM C330, AASHTO T-85, BS- 812, ASTM C-535 or Equivalent
4 | Water Suitability of Water for Concrete Mixing | For Each source of Water As approved or directed by the Project Manager. | BS EN BS EN 1008:2002
5 | Concrete Concrete Core Test | Concrete Core Test will be carried out for at least one block for each days casting As approved or directed by the Project Manager. | BS 1881, ASTM C-42 Or similar standard

## Slide 31: Standard Sampling and Testing for Geo Textile
Si | Name of Test | Frequency of Test | Test Method
1 | Geotextile Filter Materials: |  | 
 | i. Opening Size 090 | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | EN ISO 12956
 | Mass per unit area | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | BS EN 965
 | CBR Puncture Resistance | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | EN ISO 12336
 | Tensile Strength (machine direction- MD or cross machine direction-CMD) | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | EN ISO 10319
 | Minimum thickness | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | EN ISO 9863
 | Grab Tensile Strength | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | ASTM D 4632
 | Vertical Permeability under 2Kn/m2 & 200Kn/m2 pressure | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | ASTM D4491
 | viii. Horizontal Permeability under 2Kn/m2 pressure | 1.for each quantity of 10,000 square meter 2.At Least 1 test for Total Requirements in Reach of Work if that is less than 10000 square meter | ASTM D4491